## Sheet3 (hidden)
SUPERVISOR | IGL |  | SUPERVISOR | IGL
Count of WO NO | Column Labels |  |  | Column Labels
Row Labels | CHALLENGER | Grand Total |  | CHALLENGER |  | Total TOTAL ESTIMATED COST (SERVICE ITEMS) | Total BILLED/PARTIALLY BILLED COST
AUDITED | 8 | 8 | Row Labels | TOTAL ESTIMATED COST (SERVICE ITEMS) | BILLED/PARTIALLY BILLED COST
FOR AUDIT | 42 | 42 | AUDITED | 309761.23 | 79479.1 | 309761.23 | 79479.1
NO COC | 18 | 18 | FOR AUDIT | 4834813.37 | 368944.03 | 4834813.37 | 368944.03
PAID | 1 | 1 | NO COC | 1976088.49 |  | 1976088.49
Transferred to DCB (point person for OLDT) | 5 | 5 | PAID | 80751.9 | 84452.5 | 80751.9 | 84452.5
SCHED/ INPRG | 39 | 39 | Transferred to DCB (point person for OLDT) | 169350.32 |  | 169350.32
Grand Total | 113 | 113 | SCHED/ INPRG | 3937935.17 |  | 3937935.17
|  |  | Grand Total | 11308700.48 | 532875.63 | 11308700.48 | 532875.63
|  |  | Row Labels | Sum of TOTAL ESTIMATED COST (SERVICES) | Sum of BILLED / PARTIALLY BILLED COST | Sum of TOTAL ESTIMATED COST (SERVICES) | Sum of BILLED / PARTIALLY BILLED COST
|  |  | AUDITED | 309761.23 | 79479.1 |  |  | 309761.23 | 79479.1
|  |  | FOR AUDIT | 4366131.09 | 368944.03 |  |  | 4366131.09 | 368944.03
|  |  | NO COC | 1784857.56 |  |  |  | 1784857.56
|  |  | ON GOING MATERIAL RETURN | 80751.9 | 35552.91 |  |  | 80751.9 | 35552.91
|  |  | SCHED/ INPRG | 4597848.38 |  | 44676.99 |  | 4642525.37
|  |  | Grand Total | 11139350.16 | 483976.04 | 44676.99 |  | 11184027.15 | 483976.04

## SUPV
ME185130 | JEMUEL PERALTA
ME168168 | CRIS EMMANUEL GUEVARRA | EXT
ME168443 | DEAN CARL BORJAL
ME194579 | IAN PATRICK PEREZ
ME188111 | JUSTINE RAMOS
ME166067 | ISAN CARLO LAZARO | P2006000921',
ME173899 | JUNILO MICHAEL FLORES
ME189046 | REYZON MATIENZO
ME177199 | MARC JOSEPH FERRER
ME155242 | RONILO JR GANGE
#REF!

## Justifications
Applicant facility not ready
Applicant holds execution
Conjuct work order not released / completed
ECQ (Site inaccessible)
Energized on site but insufficient contract amount / No PO (System error)
Energized on site but with back job
Group quarantine (Manpower)
MEP (Meralco Electrification Project)
Materials unavailability
No pole stake
Road access problem
Special LGU permits
Third party concern (Applicant-related compliance)
Third party concern (Other than the applicant)
Typhoon response
With ROW problem
With major design modifications
With minor design modifications
With pole / drainage / digging / manhole / pole attachment issue
With scheduled PAI
With system error issue but completed at site
Value | Scope | Start and End Dates | Required Attachment (inclusive of Start and End dates) | Required Remarks (inclusive of Start and End dates
Applicant holds execution | customer-related | Start Date: WMTRL Date | Communication with CRS/Customer | Notes on customer-related concern/s
|  | End Date: Date of resolution with CRS/Customer |  | Reason/s of applicant holding execution
Third party concern (Applicant-related compliance) | delay caused by parties other than the applicant (eg. LGU, HOA - halts execution due to lack of applicant compliance) | Start Date: Date from CRS/Design/PROW coordination | Communication with CRS/Design/PROW | Notes on third party-related concern/s
|  | End Date: Date of concern resolution |  | Reason/s of delay casued by third party
Third party concern (Other than the applicant) | delay caused by parties other than the applicant (eg. Neighbor, LGU, HOA - halts execution or requests transfer of pole location/guying, etc.) | Start Date: Date from CRS/Design/PROW coordination | Communication with CRS/Design/PROW | Notes on third party-related concern/s
|  | End Date: Date of concern resolution |  | Reason/s of delay casued by third party
With ROW problem | expired or unavailable ROW/permit | Start Date: Date from CRS/Design/PROW coordination | Communication with CRS/Design/PROW | Notes on ROW-related concern/s
|  | End Date: Date of concern resolution |  | Reason/s of ROW problem
Special LGU permits | Permits not common to other LGUs - Contractor’s Tax (Antipolo LGU), Baliwag LGU, ASEANA, BESC Permit Acquisition (BGC) | Start Date: Start date of permit acquisition processing | Communication with concerned party | Notes on permit-related concern/s
|  | End Date: Permit acquisition |  | Reason/s of permit/s problem
No pole stake | applicable only to subdivision developments; not applicable if proof of pole stake is available in EAM | Start Date: WMTRL Date | Communication with concerned party | Notes on pole stake-related concern/s
End Date: Date of concern resolution
Conjuct work order not released/completed | conjuct work order number not released or not yet completed | Start Date: Date of coordination with CRS/Design | Communication with CRS/Design | Notes on conjuct WO details
|  | End Date: Date of concern resolution |  | Reason/s of conjuct WO delay in completion
With minor design modifications | Minor design modifications (no change in design scheme / no additional station/task) | Start Date: Date of coordination with Design | Communication with Design | Notes on design modification details
|  | End Date: Date of concern resolution |  | Reason/s of design modification
With major design modifications | Major design modifications (with changes in design scheme / with additional station/task) | Start Date: Date of coordination with Design | Communication with Design | Notes on design modification details
|  | End Date: Date released to construction after WO reversion |  | Reason/s of design modification
With pole / drainage /digging / manhole / pole attachment issue | Location problem not related to ROW problem and/or Thrird party concern | Start Date: Date from Design/PROW coordination | Communication with Design/PROW | Notes on issues with pole / drainage / digging / manhole / pole attachment
End Date: Date of concern resolution
Energized on site but with back job | actual energization date must be indicated in the WO specs | Start Date: Date energized | Communication with vendor | Notes on back job details
|  | End Date: Date of completion of back job/WO FCOMP/Date of concern resolution | WO details/milestones | Reason/s of back job
Energized on site but insufficient contract amount / No PO (System error) | actual energization date must be indicated in the WO specs | Start Date: Date energized | Communication with PCT/NCOM | Notes on contract insufficiency
|  | End Date: Date of completion of budget amendment/WO FCOMP/Date of concern resolution | WO details/milestones
Materials unavailability | item code and desciption must be indicated in justification | Start Date: Date material unavailability | Communication with Stores/MMO | Notes on materials unavailability
|  | End Date: Date of stock availability |  | List of unavailable items
With scheduled PAI | work request number must be indicated in justification | Start Date: Date from PAI request | PAI details | Notes on PAI details
End Date: Date of PAI execution

## UG-SLEM
|  |  | PROJECTS | F | [5 empty] | F | 2024-01-02 | [11 empty] | PERFORMANCE |  |  |  |  | RED(Above 50Days) |  |  |  |  | NEW KPI (Starting October 2021) |  |  |  | COMPUTATION: FOR FCOMP |  |  |  |  | FOR COMP |  |  | (-5) | 0.75 aspiration | [6 empty] | 0.75 aspiration | REMARKS |  | CERTIFICATE OF COMPLETION |  |  |  | FIELD AUDIT |  | RE-WORK |  |  |  | MATERIAL BALANCING |  | TRANSMITTAL TO METER |  | FOR OLDT DETAILS
Date Received Jacket from P&S | Date Received Awarding of Wo | VIP | WO INITIATOR | WO NO | DESCRIPTION | LOCATION | MUNICIPALITY | AREA OF RESPONSIBILITY | VENDOR REMARKS (free text) | C1 REMARKS (with or without issue) | ASSIGNED | STATUS | SUPERVISOR | C1 CONTRACTOR MANHOUR | TOTAL MANHOURS | APPLIED LOAD | TYPE | TOTAL PLANNED PROJECT COST | TOTAL ESTIMATED COST (SERVICES) | BILLED / PARTIALLY BILLED COST | % BILLED | DATE WMTRL | DATE SCHED | DATE RECEIVED BY VC | ACTUAL DATE COMPLETED ON SITE | DATE FCOMP | DATE COMP | # of days WMTRL TO FCOMP APT Without Exclusion (SPT) | # of days SCHED TO FCOMP | # of days COMP | (0.75) DATE NEEDED FOR WMTRL TO FCOMP | (0.95) DATE NEEDED FOR FCOMP | (50 DAYS) DATE NEEDED FOR WMTRL TO FCOMP | COMPUTED INDEX (WMTRL TO FCOMP) CCTI Without Exclusion | COMPUTED INDEX (COMP) | SPT(M) | SPT(L) | 0.75 DURATION (DAYS) | 0.95 DURATION (DAYS) | TARGET DAYS | SPT(M) for comp | DURATION (DAYS)COMP | TARGET DAYS (COMP) | DATE NEEDED TO COMP | TARGET DATE TO COMP | REASON (FOR EXCLUSION) | FOR CCTI EXCLUSION (Y/N) | ENCODED IN EAM (Y/N) | VALIDATED BY DCSAM (Y/N) | For APT Exclusion (Y/N) | START DATE | DURATION FOR EXCLUSION | END DATE (FOR EXCLUSION) | REMARKS / FOLLOW UP BY | REMARKS 2 | DATE NEEDED TO SUBMIT COC | AGEING SUBMISSION OF COC | DATE COMPLETED (FROM COC) | ACTUAL RECEIVED COC | DATE AUDIT | BY: | W/ BACK JOB | BACKJOB TAGGED IN EAM? RE-WORK | DATE RECEIVED BY CONTRACTOR | DATE CORRECTED | DATE MATERIAL BALANCING | BY | Y/N | EMAILED TO METER | DT CORRECTION METHOD | TLN | WITH POLE REPL? | ACTUAL FIELD STATUS | REMARKS3 | ABF PRINTED BY (FOR AUDIT) | DATE PRINTED OF POLE TAG FABRICATION FORM | POLE / TLN TAGS | Days for Exclusion based on emails to concerned office/PCTs (Due to customer only - APT) | APT with Exclusion | Days for Exclusion based on emails to concerned office/PCTs (All reason - CCTI) | Duration for CCTI with exclusion | CCTI With Exclusion | Meralco/Customer Reason | Issue Remarks | CURRENT CCTI
2023-11-08 | 2023-11-06 |  | CBG | X23083339380 | TANG KUNQUAN | QUIRINO, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | UG WO; with issue on pole location | UG | ECOM | COMP | UG | 139.3524 | 659.83 | 1062 | NEW | 4081533.15 | 132841.45 | 94987.61 | 71.5% | 2023-11-03 14:52 | 2023-11-03 14:52 | 2023-11-06 08:47 |  | 2024-02-06 13:06 | 2024-10-16 10:04 | 94.9264 | 94.9264 | 252.8736 | 2023-11-18 06:24 | 2023-11-25 23:20 | 2023-12-23 14:52 | 4.0344 | 4.5977 | 40 | 20 | 17.6471 | 22.3529 | 14.6471 | 55 | 44 | 39 | 2024-03-21 13:06 | 2024-03-16 13:06 | [8 empty] | PAID |  |  | 1900-01-02 | 2024-02-05 | 2024-03-21 | 2024-09-13 | ECI | N | [5 empty] | Y | [6 empty] | PDZC | 2023-11-08 | C5-0512, 116398, C5-8057, 518496, C5-8058 |  | 94.9264 |  | 94.9264 | 4.0344 |  |  | 28.1221 | 4.5977 |  | REV
2024-01-19 |  |  | CBG | X23083306750 | VITACARE UNIMED HOSPITAL AND MEDICAL CENTER CORP. | DAANG-HARI RD., MOLINO IV, BACOOR | BACOOR CITY | DASMA |  | UG | POWERHOUSE | TECO | UG | 72.5251 | 585.55 | 1700 | NEW | 3336508.33 | 36496.41 |  | 0% | 2024-01-04 14:32 | 2024-01-04 14:32 | 2024-01-05 21:40 |  | 2024-01-23 13:08 | 2025-03-07 16:10 | 18.9417 | 18.9417 | 409.1264 | 2024-01-19 06:04 | 2024-01-26 23:00 | 2024-02-23 14:32 | 0.80502 | 7.4387 | 40 | 20 | 17.6471 | 22.3529 | 14.6471 | 55 | 44 | 39 | 2024-03-07 13:08 | 2024-03-02 13:08 | [8 empty] | NO COC |  |  | 1900-01-02 | [10 empty] | Y | [7 empty] | 2024-01-24 | CR8-5430, CR8-8016, CR8-8016, 182943 |  | 18.9417 |  | 18.9417 | 0.80502 |  |  | 25.4877 | 7.4387 |  | REV
2024-02-28 | 2024-03-05 |  | CBG | X23062134423 | SM DEVELOPMENT CORPORATION, | TOWER C, BLOOM RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARANAQUE | Conjunct with UG, target itayo poste March 6 |  | AVECO | COMP | UG | 115.33 | 507.57 | 1563.3 | NEW | 3001400.48 | 89877.04 |  | 0% | 2024-01-19 15:47 | 2024-01-23 14:39 | 2024-02-29 |  | 2024-04-19 14:27 | 2025-02-06 | 90.9444 | 86.9917 | 292.3979 | 2024-02-03 12:38 | 2024-02-11 06:59 | 2024-03-09 15:47 | 3.8172 | 6.6454 | 26 | 23 | 17.8685 | 22.6335 | 14.8685 | 44 | 35.2 | 30.2 | 2024-05-24 19:15 | 2024-05-19 19:15 | [8 empty] | ON GOING MAT RETURN | FULLY BILLED | 2024-04-22 14:27 | 198.3979 | 2024-04-12 | 2024-11-07 | 2024-12-12 | ECI | N | [5 empty] | Y | [10 empty] | 90.9444 |  | 90.9444 | 3.8172 |  |  | 24.54 | 6.6454 |  | REV
2024-04-01 | 2024-03-25 |  | CBG | X24010270067 | PHINMA PROPERTY HOLDINGS CORPORATION | CHROMIUM, METROTOWNE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | UG supervisor | W/O ISSUE | POWERHOUSE | FCOMP | UG | 45.3098 | 375.5 | 1965.8 | NEW | 3158370.51 | 46889.1 |  | 0% | 2024-03-19 11:09 | 2024-04-01 08:44 | 2024-03-22 |  | 2024-04-16 16:38 |  | 28.2285 | 15.3292 | -45398.6931 | 2024-04-04 05:09 | 2024-04-12 05:09 | 2024-05-08 11:09 | 1.1291 | -1134.9673 | 20 | 28 | 18.75 | 23.75 | 15.75 | 40 | 32 | 27 | 2024-05-18 16:38 | 2024-05-13 16:38 | [8 empty] | NO COC |  | 2024-04-19 16:38 | -108.6931 | [10 empty] | Y | [7 empty] | 2024-04-02 | CU8-1255, 520351, CU8-8053 |  | 28.2285 |  | 28.2285 | 1.1291 |  |  | 20.9941 | PENDING COMP |  | REV
|  |  |  | X24041165129 | LIGHT RAIL MANILA CORPORATION | NINOY AQUINO, STO. NINO, PARANAQUE | PARANAQUE CITY | PARAÑAQUE |  |  | SLEM | FCOMP | SLEM |  | 136.13 |  | NEW |  |  |  | #DIV/0! | 2024-04-26 |  |  |  | 2025-05-23 |  |  |  | -45800 | 2024-05-17 04:58 | 2024-05-26 15:53 | 2024-06-15 | 0 | -1040.9091 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 44 | 35.2 | 30.2 | 2025-06-27 04:48 | 2025-06-22 04:48 | [11 empty] | 45293 | [21 empty] | 0 |  | 0 | 0 |  |  | 15.0985 | PENDING COMP |  | REV
|  |  |  | X24041165310 | LIGHT RAIL MANILA CORPORATION | NINOY AQUINO, STO. NINO, PARANAQUE | PARANAQUE CITY | PARAÑAQUE |  |  | SLEM | FCOMP | SLEM |  | 136.13 |  | NEW |  |  |  | #DIV/0! | 2024-04-26 |  |  |  | 2025-06-03 |  |  |  | -45811 | 2024-05-17 04:58 | 2024-05-26 15:53 | 2024-06-15 | 0 | -1041.1591 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 44 | 35.2 | 30.2 | 2025-07-08 04:48 | 2025-07-03 04:48 | [11 empty] | 45293 | [21 empty] | 0 |  | 0 | 0 |  |  | 15.0985 | PENDING COMP |  | REV
|  |  |  | X24041432658 | LIGHT RAIL MANILA CORPORATION | NINOY AQUINO, STO. NINO, PARANAQUE | PARANAQUE CITY | PARAÑAQUE |  |  | SLEM | FCOMP | SLEM |  | 136.13 |  | NEW |  |  |  | #DIV/0! | 2024-05-08 |  |  |  | 2025-02-28 |  | 296 | 45716 | -45716 | 2024-05-29 04:58 | 2024-06-07 15:53 | 2024-06-27 | 9.1709 | -1039 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 44 | 35.2 | 30.2 | 2025-04-04 04:48 | 2025-03-30 04:48 | [11 empty] | 45293 | [21 empty] | 296 |  | 296 | 9.1709 |  |  | 14.7267 | PENDING COMP |  | REV
2024-05-15 | 2024-05-15 |  | CBG | X24020489831 | SM DEVELOPMENT CORPORATION, | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | UG | 108.1986 | 443.47 | 1021 | NEW | 3240513.08 | 55638.73 |  | 0% | 2024-05-10 15:15 | 2024-05-13 18:44 | 2024-05-15 |  | 2024-07-10 08:16 |  | 60.709 | 57.5639 | -45483.3444 | 2024-05-24 12:53 | 2024-06-01 01:03 | 2024-06-29 15:15 | 2.694 | -909.6669 | 32 | 20 | 16.9014 | 21.4085 | 13.9014 | 50 | 40 | 35 | 2024-08-19 08:16 | 2024-08-14 08:16 | [8 empty] | ON GOING MAT RETURN |  | 2024-07-13 08:16 | 6.6556 | 2024-07-03 | 2024-07-20 | 2024-10-07 | ECI | N | [5 empty] | Y | [7 empty] | 2024-05-16 | CZ8-8066, 520527 |  | 60.709 |  | 60.709 | 2.694 |  |  | 20.9752 | PENDING COMP |  | REV
2024-05-28 | 2024-05-29 |  | BIZ | X24030698480 | BRILLO DEL ESTE DEVELOPMENT CORP. | ADMIN-COMMERCIAL, EASTGLORY CENTER, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | VJC | FCOMP | UG | 37.49 | 600.42 | 6237 | NEW | 4328746.13 | 30189.83 | 14379.55 | 47.63% | 2024-05-13 16:22 | 2024-05-15 17:44 | 2024-05-28 |  | 2024-07-15 14:15 |  | 62.9118 | 60.8549 | -45488.5938 | 2024-05-28 07:54 | 2024-06-05 00:50 | 2024-07-02 16:22 | 2.6738 | -827.0653 | 40 | 20 | 17.6471 | 22.3529 | 14.6471 | 55 | 44 | 39 | 2024-08-28 14:15 | 2024-08-23 14:15 | [8 empty] | NO COC | PARTIALLY BILLED - 7/25/24 JSB | 2024-07-18 14:15 | -198.5938 | [10 empty] | Y | [7 empty] | 2024-05-28 | C5-0154, C5-8080, 520856 |  | 62.9118 |  | 62.9118 | 2.6738 |  |  | 19.9595 | PENDING COMP |  | REV
2024-06-14 | 2024-06-18 |  | CBG | X24010113590 | LAS PINAS GENERAL HOSPITAL AND SATELLITE TRAUMA CE | QUIRINO, PULANGLUPA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  | W/O ISSUE | AVECO | FCOMP | UG | 76.7333 | 563.4 | 1434 | NEW | 3729820.96 | 61791.45 |  | 0% | 2024-05-31 13:07 | 2024-06-14 16:32 | 2024-06-11 |  | 2024-07-08 07:07 |  | 37.75 | 23.6076 | -45481.2965 | 2024-06-15 04:39 | 2024-06-22 21:35 | 2024-07-20 13:07 | 1.6044 | -826.9327 | 40 | 20 | 17.6471 | 22.3529 | 14.6471 | 55 | 44 | 39 | 2024-08-21 07:07 | 2024-08-16 07:07 | [8 empty] | NO COC |  | 2024-07-11 07:07 | -191.2965 | [10 empty] | Y | [7 empty] | 2024-06-17 | CY7-8072, CY7-8073, 519311, CY7-8073 |  | 37.75 |  | 37.75 | 1.6044 |  |  | 19.2002 | PENDING COMP |  | REV
2024-08-13 | 2024-08-08 |  | BIZ | X23114429217 | GOLDSERVE HOLDING COMPANY INC. | MIA, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | pole location issue | W/ ISSUE | VJC | FCOMP | UG | 62.1094 | 224.02 | 44 | NEW | 636513.87 | 49637.68 | 41296.18 | 83.2% | 2024-08-08 17:04 | 2024-08-13 07:19 | 2024-08-16 |  | 2025-03-07 |  | 210.2889 | 205.6951 | -45723 | 2024-08-30 13:55 | 2024-09-09 05:04 | 2024-09-27 17:04 | 6.342 | -993.9783 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 46 | 36.8 | 31.8 | 2025-04-12 19:12 | 2025-04-07 19:12 | [8 empty] | FOR AUDIT | PARTIALLY BILLED - 7/25/24 JSB, PARTIAL 5/21/2025 | 2025-03-22 | 30 | 2025-03-07 | 2025-04-21 | [8 empty] | Y | [7 empty] | 2024-08-14 | B5-8037, B5-0084, B5-8038, B5-5094, B5-00971 |  | 210.2889 |  | 210.2889 | 6.342 |  |  | 11.5389 | PENDING COMP |  | REV
|  |  | CBG | X24062079073 | THE LANDMARK MANILA BAY CORPORATION | ASEANA, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | UG | 147.944 | 563.37 | 5950 | NEW | 5216314.41 | 140962.37 |  | 0% | 2024-10-04 10:25 | 2024-10-04 13:19 |  |  | 2024-10-16 16:14 |  |  |  | -45581.6764 | 2024-10-19 01:57 | 2024-10-26 18:53 | 2024-11-23 10:25 | 0 | -828.7578 | 40 | 20 | 17.6471 | 22.3529 | 14.6471 | 55 | 44 | 39 | 2024-11-29 16:14 | 2024-11-24 16:14 | [8 empty] | NO COC | [24 empty] | 0 |  | 0 | 0 |  |  | 13.85 | PENDING COMP |  | REV
2025-02-06 |  |  | BIZ | X24051566102 | ONE PREMIER AND TWO PREMIER CONDOMINIUM CORP. | TWO PREMIER, ALABANG PREMIER, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | UG | TECO | UG |  | 299 | 3791 | NEW | 3214681.55 |  |  | #DIV/0! | 2024-11-22 | 2024-11-27 |  |  | 2025-01-15 | 2025-06-09 06:19 | 54 | 49 | 145.2632 | 2024-12-05 09:45 | 2024-12-12 18:45 | 2025-01-11 | 2.4686 | 3.1579 | 28 | 20 | 16.4063 | 20.7813 | 13.4063 | 46 | 36.8 | 31.8 | 2025-02-20 19:12 | 2025-02-15 19:12 | [8 empty] | PAID | [21 empty] | N/A |  |  | 54 |  | 54 | 2.4686 |  |  | 12.6773 | 3.1579 |  | REV
| 2025-01-22 | Y | CBG | X24114365991 | IFACE INC. | STA. ANA, SUN VALLEY SUBD, PARANAQUE | PARANAQUE CITY | STA. ROSA |  |  | AVECO | FCOMP | RRG | 31.96 | 366.82 | 994 | NEW | 3141766.43 | 32632.89 |  | 0% | 2025-01-16 16:34 | 2025-01-20 15:01 | 2025-01-21 | 2025-04-04 | 2025-04-04 |  |  |  | -45751 | 2025-02-01 05:44 | 2025-02-09 04:26 | 2025-03-07 16:34 | 0 | -953.1458 | 30 | 23 | 18.5484 | 23.4946 | 15.5484 | 48 | 38.4 | 33.4 | 2025-05-12 09:36 | 2025-05-07 09:36 | [8 empty] | FOR AUDIT |  |  | 45861 | 2025-04-04 | 2025-07-23 | [16 empty] | 2025-07-23 | DZ1-8046 |  | 0 |  | 0 | 0 |  |  | 8.9614 | PENDING COMP |  | REV
2025-02-03 |  |  | BIZ | X25010064382 | ACACIA REALTY CORP. | FINANCE AVE, MADRIGAL BUSINESS PARK, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | UG | FCOMP | UG |  | 32.2 |  | TERMINATION | 102570.5 |  |  | #DIV/0! | 2025-01-25 12:59 | 2025-01-31 14:30 |  |  | 2025-06-19 |  |  |  | -45827 | 2025-02-13 07:34 | 2025-02-22 02:55 | 2025-03-16 12:59 | 0 | -1145.675 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 40 | 32 | 27 | 2025-07-21 | 2025-07-16 | [11 empty] | 45293 | [18 empty] | N/A |  |  | 0 |  | 0 | 0 |  |  | 7.3289 | PENDING COMP |  | NON-REV
2025-02-03 |  |  | HMB | X24124836711 | C-E CONSTRUCTION CORPORATION | PARKWAY, FILINVEST CORPORATE CITY, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | UG | FCOMP | UG |  | 556.32 | 535 | NEW | 3359184.98 |  |  | #DIV/0! | 2025-01-28 17:13 | 2025-02-03 13:06 |  |  | 2025-03-14 |  | 44.2826 | 38.4542 | -45730 | 2025-02-14 11:43 | 2025-02-22 18:15 | 2025-03-19 17:13 | 1.6799 | -831.4545 | 40 | 23 | 19.7708 | 25.043 | 16.7708 | 55 | 44 | 39 | 2025-04-27 | 2025-04-22 | [8 empty] | NO COC | [21 empty] | N/A |  |  | 44.2826 |  | 44.2826 | 1.6799 |  |  | 7.9511 | PENDING COMP |  | REV
2025-03-05 |  |  | CBG | R23935710 | CAVITEX INFRASTRUCTURE CORP., CBG | C5 EXTENSION, MOONWALK, PARANAQUE | PARANAQUE CITY | PARAÑAQUE |  |  | UG | FCOMP | UG |  | 182.95 |  | RELOC | 462215.14 |  |  | #DIV/0! | 2025-02-19 08:46 | 2025-02-25 12:48 | 2025-02-21 |  | 2025-04-11 |  |  |  | -45758 | 2025-03-12 13:44 | 2025-03-22 00:39 | 2025-04-10 08:46 | 0 | -1039.9545 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 44 | 35.2 | 30.2 | 2025-05-16 04:48 | 2025-05-11 04:48 | [11 empty] | 45293 | [18 empty] | N/A |  |  | 0 |  | 0 | 0 |  |  | 5.8233 | PENDING COMP |  | NON-REV
|  |  |  | R21138022 | CAVITEX INFRASTRUCTURE CORP. | STREET, MULTINATIONAL VILL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | UG | SCHED | UG |  | 178.48 |  | RELOC |  |  |  | #DIV/0! | 2022-09-07 | 2022-09-09 |  |  |  |  | -44811 | -44813 | 0 | 2022-09-28 04:58 | 2022-10-07 15:53 | 2022-10-27 | -1388.375 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 44 | 35.2 | 30.2 | 1900-02-03 04:48 | 1900-01-29 04:48 | [11 empty] | 0 | [21 empty] | -44811 |  | -44811 | -1388.375 |  |  | 33.5953 | PENDING COMP |  | NON-REV
|  |  |  | R22006061 | PCA RELOC, Overhead Facilities, N, Y, N, DEPARTMENT OF TRANSPORTATION,, CBG | STREET, EAST SERVICE, SN MARTIN DE PORRES, PARANAQUE | PARANAQUE CITY | PARAÑAQUE |  |  | SLEM | SCHED | SLEM |  | 120.75 |  | RELOC |  |  |  | #DIV/0! | 2023-05-11 | 2023-05-19 |  |  |  |  | -45057 | -45065 | 0 | 2023-06-01 04:58 | 2023-06-10 15:53 | 2023-06-30 | -1395.9968 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 44 | 35.2 | 30.2 | 1900-02-03 04:48 | 1900-01-29 04:48 | [33 empty] | -45057 |  | -45057 | -1395.9968 |  |  | 25.9735 | PENDING COMP |  | NON-REV
N/A | N/A |  | CBG | X24041158243 | PHINMA PROPERTY HOLDINGS CORPORATION | ALUMINUM, METROTOWNE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | UG | SCHED | Jayson Ramores | 174.81 | 174.81 | 1965 | NEW | 2772246.78 |  |  | #DIV/0! | 2025-06-20 10:23 | 2025-06-26 15:27 | N/A |  |  |  | -45828.4324 | -45834.6438 | 0 | 2025-07-03 13:09 | 2025-07-10 20:18 | 2025-08-09 10:23 | -2132.7847 | 0 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45828.4324 | 0 | -45828.4324 | -2132.7847 |  |  | 1.888 | 1.888 | 0 | 27.5676 | REV | 0-3 MONTHS
Formulas:
NEW KPI (Starting October 2021) = [DATE WMTRL]+50
DATE NEEDED TO COMP = [DATE FCOMP]+[FOR COMP]
DATE NEEDED TO COMP = [DATE FCOMP]+[SPT(M) for comp]
TARGET DATE TO COMP = [DATE NEEDED TO COMP]-5
TARGET DATE TO COMP = IFERROR(TODAY()-[DATE FCOMP],"")
CERTIFICATE OF COMPLETION = [DATE FCOMP]+3

## C1
|  |  | PROJECTS |  |  | 0 |  |  |  | F | R | [11 empty] | PERFORMANCE |  |  |  |  | RED(Above 50Days) |  |  |  |  | NEW KPI (Starting October 2021) |  |  |  | COMPUTATION: FOR FCOMP |  |  |  |  | FOR COMP |  |  | (-5) | 0.75 aspiration | [6 empty] | 0.75 aspiration | REMARKS |  | CERTIFICATE OF COMPLETION |  |  |  | FIELD AUDIT |  | RE-WORK |  |  |  | MATERIAL BALANCING |  | TRANSMITTAL TO METER |  | FOR OLDT DETAILS | [12 empty] | 2025-07-31 | MANUAL |  |  |  | 2025-07-18
Date Received Jacket from P&S | Date Received Awarding of Wo | VIP | WO INITIATOR | WO NO | DESCRIPTION | LOCATION | MUNICIPALITY | AREA OF RESPONSIBILITY | VENDOR REMARKS (free text) | C1 REMARKS (with or without issue) | ASSIGNED | STATUS | SUPERVISOR | C1 CONTRACTOR MANHOUR | TOTAL MANHOURS | APPLIED LOAD | TYPE | TOTAL PLANNED PROJECT COST | TOTAL ESTIMATED COST (SERVICES) | BILLED / PARTIALLY BILLED COST | % BILLED | DATE WMTRL | DATE SCHED | DATE RECEIVED BY VC | ACTUAL DATE COMPLETED ON SITE | DATE FCOMP | DATE COMP | # of days WMTRL TO FCOMP APT Without Exclusion (SPT) | # of days SCHED TO FCOMP | # of days COMP | (0.75) DATE NEEDED FOR WMTRL TO FCOMP | (0.95) DATE NEEDED FOR FCOMP | (50 DAYS) DATE NEEDED FOR WMTRL TO FCOMP | COMPUTED INDEX (WMTRL TO FCOMP) CCTI Without Exclusion | COMPUTED INDEX (COMP) | SPT(M) | SPT(L) | 0.75 DURATION (DAYS) | 0.95 DURATION (DAYS) | TARGET DAYS | SPT(M) for comp | DURATION (DAYS)COMP | TARGET DAYS (COMP) | DATE NEEDED TO COMP | AGEING DAYS SINCE FCOMP | REASON (FOR EXCLUSION) | FOR CCTI EXCLUSION (Y/N) | ENCODED IN EAM (Y/N) | VALIDATED BY DCSAM (Y/N) | For APT Exclusion (Y/N) | START DATE | DURATION FOR EXCLUSION | END DATE (FOR EXCLUSION) | REMARKS / FOLLOW UP BY | REMARKS 2 | DATE NEEDED TO SUBMIT COC | AGEING SUBMISSION OF COC | DATE COMPLETED (FROM COC) | ACTUAL RECEIVED COC | DATE AUDIT | BY: | W/ BACK JOB | BACKJOB TAGGED IN EAM? RE-WORK | DATE RECEIVED BY CONTRACTOR | DATE CORRECTED | DATE MATERIAL BALANCING | BY | Y/N | EMAILED TO METER | DT CORRECTION METHOD | TLN | WITH POLE REPL? | ACTUAL FIELD STATUS | REMARKS3 | ABF PRINTED BY (FOR AUDIT) | DATE PRINTED OF POLE TAG FABRICATION FORM | POLE / TLN TAGS | Days for Exclusion based on emails to concerned office/PCTs (Due to customer only - APT) | APT with Exclusion | Days for Exclusion based on emails to concerned office/PCTs (All reason - CCTI) | Duration for CCTI with exclusion | CCTI With Exclusion | E2E for PRDI | CURRENT CCTI (with exclusion) | CURRENT CCTI | FINAL CCTI (LESS THAN FCOMP) | PRDI | Days Ageing (as of cell CJ1) | REV/NON-REV | AGE BRACKET | NTC DATE CREATED | AMOUNT | NTC | DATE RECEIVED BY CONTRACTOR | DATE COMPLETED NTC | RUNNING DAYS | NOV & DEBIT MEMO DATE CREATED | AMOUNT | DATE RECEIVED BY CONTRACTOR | EXT | UPDATED SUPV | SUPV NAME | STATUS 4/4/25 | DIFF (in days) FROM WMTRL TO SCHED - 2025 WOs only | filter | SUPERVISOR FULL NAME
2020-06-18 | N/A |  | MN | P2004004805 | MAINT - 44WU_TLN 051257 LOADSPLIT & Inst Addl 25/50/50KVA on CY8-1276/CY8-1275/CY8-1273 | DIAMOND, BERNABE PH 3 SUBD SAN DIONISIO PARAÑAQUE CITY | PARAÑAQUE CITY | PARAÑAQUE | not feasible; for survey team C1 | W/ ISSUE | OPS | SCHED | Dean Carl Borjal | 139.2078 | #N/A | 0 | OLDT | 560984.1 | 109904.21 |  | 0% | 2020-06-05 16:44 | 2020-06-08 08:50 | 2020-06-15 |  |  |  | -43987.6972 | -43990.3681 | 0 | #N/A | #N/A | 2020-07-25 16:44 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 051257 | Y | With concern | Transferred from Alvin to Jimmy |  |  |  | 0 | -43987.6972 | 0 | -43987.6972 | #N/A | 0 |  | #N/A | #N/A | 0 | 1868.3028 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2004004805', | ME168443 |  |  |  | SCHED | DCB
2020-07-13 | N/A |  | MN | P2006000420 | MAINT 45WG TLN 037283; Split Loading Inst Addl 50KVA & 75KVA on A8-0440&ALB1-3102 | BLOCK 32 PUROK 4 UPPER BICUTAN TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Sept 2023, ayaw magpahukay, for survey wityh design/For survey of C1 Team | W/ ISSUE | VJC | CAN | Jenneth Madrid | 90.9766 | #N/A | 0 | OLDT | 442337.68 | 91388.65 |  | 0% | 2020-07-10 14:12 | 2020-07-13 12:34 | 2020-07-13 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2020-08-29 14:12 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 037283 | Y | For schedule | Transferred from Marc to Jimmy |  |  |  | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2006000420', | ME185284 |  |  |  | CAN | Jenneth Madrid
2020-07-13 | N/A |  | MN | P2006000610 | MAINT - 55GG_TLN 271296 Split Loading Inst Addl 50KVA on A8-0735 | JASMIN PUROK 6C LOWER BICUTAN TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Sept 2023, ayaw magpahukay, for survey wityh design/For survey of C1 Team | W/ ISSUE | VJC | CAN | Jenneth Madrid | 22.1094 | #N/A | 0 | OLDT | 186406.1 | 23237.07 |  | 0% | 2020-07-30 00:50 | 2020-08-05 10:47 | 2020-07-13 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2020-09-18 00:50 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 271296 | Y | For schedule | Transferred from Marc to Jimmy |  |  |  | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2006000610', | ME185284 |  |  |  | CAN | Jenneth Madrid
2020-10-21 | N/A |  | MN | P2006000921 | MAINT- 45WG Load-Split TLN 068256; Inst New 75KVA on DZ1-2057 | ROAD 3 NORTH DAANG HARI BAGONG TANYAG TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | not feasible; for survey team C1; continue digging on Dec 9 | W/ ISSUE | ECOM | FCOMP | Dean Carl Borjal | 40.19 | 40.19 | 0 | OLDT | 185553.84 | 24087.84 |  | 0% | 2020-09-28 14:10 | 2020-09-30 08:04 | 2020-10-16 |  | 2025-03-04 |  | 1617.4097 | 1615.6639 | -45720 | 2020-10-17 08:45 | 2020-10-26 04:06 | 2020-11-17 14:10 | 55.7108 | -762 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-03 | 175 | [8 empty] | NO COC |  | 2025-03-19 | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 068256 | Y | With concern | Transferred from Alvin to Jimmy |  |  |  | 0 | 1617.4097 | 0 | 1617.4097 | 55.7108 | 149 |  | 60.843 | 60.843 | 2.4833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2006000921', | ME168443 |  |  |  | FCOMP | RONILO GANGE JR.
2020-10-20 | N/A |  | MN | P2009000813 | MAINT 424WU Uprate from kVA to 75kVA : [039062¦WA372558¦A5-0334¦QS] | ROSAL STO. NINO STO. NINO PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for field survey by crew | W/O ISSUE | CHALLENGER | INPRG | Isan Carlo Lazaro | 15.752 | #N/A | 0 | OLDT | 160243.02 | 10642.55 |  | 0% | 2020-10-14 16:31 | 2020-10-16 09:09 | 2020-09-29 |  |  |  | -44118.6882 | -44120.3812 | 0 | #N/A | #N/A | 2020-12-03 16:31 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | Transferred to DCB (point person for OLDT) |  | 1900-01-14 | 0 | [10 empty] | N |  | Uprating | TLN 039062 | N | For schedule | Transferred from Alvin to Jimmy |  |  |  | 0 | -44118.6882 | 0 | -44118.6882 | #N/A | 0 |  | #N/A | #N/A | 0 | 1737.3118 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2009000813', | ME166067 |  |  |  | INPRG | DCB
2020-10-29 | N/A |  | MN | P2006000924 | MAINT- 45WG Load-Split TLN 033207; Inst Addl 75KVA on DZ2-2222 | ROAD 1 BAGONG TANYAG BAGONG TANYAG TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | ongoing | W/ ISSUE | POWERHOUSE | INPRG | Jenneth Madrid | 59.228 | #N/A | 0 | OLDT | 293278.03 | 52996.47 |  | 0% | 2020-10-21 17:25 | 2020-10-23 15:47 | 2020-10-29 |  |  |  | -44125.7257 | -44127.6576 | 0 | #N/A | #N/A | 2020-12-10 17:25 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 033207 | Y | For schedule | Transferred from Marc to Jimmy / With picture after |  |  |  | 0 | -44125.7257 | 0 | -44125.7257 | #N/A | 0 |  | #N/A | #N/A | 0 | 1730.2743 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2006000924', | ME185284 |  |  |  | INPRG | Jenneth Madrid
2020-12-03 | N/A |  | MN | P2009000788 | MN_MA, Uprate from 37.5kVA to 75kVA : [452201¦WA200084¦A5-1345¦421WG¦QS] | E. RODRIGUEZ JR. MOONWALK MOONWALK PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing | W/O ISSUE | CHALLENGER | INPRG | Isan Carlo Lazaro | 15.952 | #N/A | 0 | OLDT | 151461.47 | 10764.63 |  | 0% | 2020-11-23 16:42 | 2020-11-25 15:58 | 2020-09-29 |  |  |  | -44158.6958 | -44160.6653 | 0 | #N/A | #N/A | 2021-01-12 16:42 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | Transferred to DCB (point person for OLDT) |  | 1900-01-14 | 0 | [10 empty] | N |  | Uprating | TLN 452201 | N | For schedule | Transferred from Alvin to Jimmy / Based on pics with 75KVA already |  |  |  | 0 | -44158.6958 | 0 | -44158.6958 | #N/A | 0 |  | #N/A | #N/A | 0 | 1697.3042 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2009000788', | ME166067 |  |  |  | INPRG | DCB
2020-12-03 | N/A |  | MN | P2007000208 | MAINT 425WG Load-Split 087388/WA345584/100KVA; Inst Addl 75KVA on A7-1008 | KOURUS CAMELLA HOMES MERVILLE PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing | W/O ISSUE | CHALLENGER | INPRG | Isan Carlo Lazaro | 36.1285 | #N/A | 0 | OLDT | 282791.21 | 104391 |  | 0% | 2020-12-01 16:59 | 2020-12-02 09:52 | 2020-12-03 |  |  |  | -44166.7076 | -44167.4111 | 0 | #N/A | #N/A | 2021-01-20 16:59 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | Transferred to DCB (point person for OLDT) |  | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 087388 | Y | For schedule | Transferred from Alvin to Jimmy |  |  |  | 0 | -44166.7076 | 0 | -44166.7076 | #N/A | 0 |  | #N/A | #N/A | 0 | 1689.2924 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2007000208', | ME166067 |  |  |  | INPRG | DCB
2020-12-15 | N/A |  | MN | P2009000548 | MAINT 55GG Loadsplit [069426¦WA145069¦DZ2-0528¦ Install addl 2-75 kVA on Pole DZ2-0526 | V.P. CRUZ PUROK 5 LOWER BICUTAN TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | ongoing | W/ ISSUE | VJC | CAN | Jenneth Madrid | 50.339 | #N/A | 0 | OLDT | 366502.48 | 38657.97 |  | 0% | 2020-12-09 16:21 | 2020-12-14 13:36 | 2020-12-17 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2021-01-28 16:21 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 069426 | Y | With concern | Transferred from Alvin to Jimmy |  |  |  | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2009000548', | ME185284 |  |  |  | CAN | Jenneth Madrid
2020-12-21 | N/A |  | MN | P2007000394 | MAINT_55GG Load-Split 111627/WA329429/50KVA; Inst Addl 75KVA on C8-5486 | 7TH GHQ VILL SIGNAL VILLAGE TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | ongoing | W/O ISSUE | CHALLENGER | INPRG | Isan Carlo Lazaro | 45.5807 | #N/A | 0 | OLDT | 213069.82 | 36545.79 |  | 0% | 2020-12-14 00:32 | 2020-12-16 12:56 | 2020-12-15 |  |  |  | -44179.0222 | -44181.5389 | 0 | #N/A | #N/A | 2021-02-02 00:32 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | Transferred to DCB (point person for OLDT) |  | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 111627 | N | For schedule | Transferred from Alvin to Jimmy |  |  |  | 0 | -44179.0222 | 0 | -44179.0222 | #N/A | 0 |  | #N/A | #N/A | 0 | 1676.9778 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2007000394', | ME166067 |  |  |  | INPRG | DCB
2021-01-06 | N/A |  | MN | P2009000586 | MN_MA, Loadsplit from kVA to 0 DT (kVA,kVA,kVA,kVA) : [134661¦¦DV1-0012¦56GG¦QS] | PRES. M.L. QUEZON CUPANG CUPANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ongoing | W/ ISSUE | ECOM | PCAN3 | Dean Carl Borjal | 13.072 | #N/A | 0 | OLDT | 169419.8 | 17546.74 |  | 0% | 2020-12-30 20:30 | 2021-01-05 10:32 | 2021-01-25 |  |  |  | -44195.8542 | -44201.4389 | 0 | #N/A | #N/A | 2021-02-18 20:30 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 134661 | Y | For schedule | Transferred from Alvin to Jimmy / (ERV - ECOM) |  |  |  | 0 | -44195.8542 | 0 | -44195.8542 | #N/A | 0 |  | #N/A | #N/A | 0 | 1660.1458 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2009000586', | ME168443 |  |  |  | PCAN3 | DCB
| N/A |  | MN | P2101102759 | MN_MAJOR, Loadsplit 51XD [037203¦WA343521¦CV8-1375¦¦] install addl 1-75kVA @ CV8- 1384 | 5TH GOLDEN GATE SUBD TALON III LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | ongoing | W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 10.482 | #N/A | 0 | OLDT | 137331.68 | 7006.35 |  | 0% | 2021-01-31 21:24 | 2021-02-02 13:35 | 2021-02-02 |  |  |  | -44227.8917 | -44229.566 | 0 | #N/A | #N/A | 2021-03-22 21:24 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | Transferred to DCB (point person for OLDT) |  | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 037203 | N | For schedule | Transferred from Alvin to Jimmy |  |  |  | 0 | -44227.8917 | 0 | -44227.8917 | #N/A | 0 |  | #N/A | #N/A | 0 | 1628.1083 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2101102759', | ME166067 |  |  |  | SCHED | DCB
2021-02-22 | N/A |  | MN | P2101102674 | MN_MAJOR, Loadsplit from 75kVA : [003404¦WA110981¦DR1-0404¦57GG¦] | ESTANISLAO LAKEVIEW HOMES I PUTATAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | change vendor/For Re-assignmnet | W/ ISSUE | OPS | FCOMP | Dean Carl Borjal | 243.12 | 243.12 | 0 | OLDT | 333455.39 | 85386.64 |  | 0% | 2021-02-18 16:40 | 2021-02-19 16:34 | 2021-02-01 |  | 2025-04-13 |  | 1514.3056 | 1513.3097 | -45760 | 2021-03-12 13:31 | 2021-03-22 04:40 | 2021-04-09 16:40 | 45.6695 | -762.6667 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-06-12 | 135 | [8 empty] | NO COC |  | 2025-04-28 | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 003404 | Y | With concern | Transferred from Alvin to Jimmy |  |  |  | 0 | 1514.3056 | 0 | 1514.3056 | 45.6695 | 109 |  | 48.9568 | 48.9568 | 1.8167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2101102674', | ME168443 |  |  |  | FCOMP | DCB
2021-02-24 | N/A |  | MN | P2101102720 | MN_MAJOR, Loadsplit from 100kVA : [069436¦WA368739¦B8-0835¦55GG¦] | MIRANDA ZONE 1 SIGNAL VILLAGE TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | not feasible; for survey team C1 | W/ ISSUE | ECOM | PCAN3 | Dean Carl Borjal | 43.2905 | #N/A | 0 | OLDT | 199593.3 | 32150.01 |  | 0% | 2021-02-19 15:50 | 2021-02-23 15:34 | 2021-02-01 |  |  |  | -44246.6597 | -44250.6486 | 0 | #N/A | #N/A | 2021-04-10 15:50 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 069436 | Y | With concern | Transferred from Alvin to Jimmy |  |  |  | 0 | -44246.6597 | 0 | -44246.6597 | #N/A | 0 |  | #N/A | #N/A | 0 | 1609.3403 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2101102720', | ME168443 |  |  |  | PCAN3 | DCB
2021-02-24 | N/A |  | MN | P2101102682 | MN_MAJOR, Loadsplit from 75kVA : [063873¦WA344251¦DR1-1343¦46WH¦] | BORACAY CAMELLA HOMES ALABANG 4 SUBD POBLACION MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for crew survey; for C1 survey | W/ ISSUE | ECOM | FCOMP | Dean Carl Borjal | 47.38 | 47.38 | 0 | OLDT | 187468.53 | 23355.85 |  | 0% | 2021-02-22 14:11 | 2021-02-23 10:38 | 2021-01-26 |  | 2025-03-04 |  | 1470.409 | 1469.5569 | -45720 | 2021-03-13 08:46 | 2021-03-22 04:07 | 2021-04-13 14:11 | 50.6474 | -762 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-03 | 175 | [8 empty] | NO COC |  | 2025-03-19 | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 063873 | Y | With concern | Transferred from Alvin to Jimmy |  |  |  | 0 | 1470.409 | 0 | 1470.409 | 50.6474 | 149 |  | 55.7796 | 55.7796 | 2.4833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2101102682', | ME168443 |  |  |  | FCOMP | DCB
| N/A |  | MN | 100338058856 | MAINT - 414FIL - Retirement of Idle poles and other facilities pole DU1-2176 | ALABANG-ZAPOTE FILINVEST CORPORATE CITY ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for permit on Feb. 22, 2023; no feed back; permit lapsed (03-08-23); | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 12.8467 | #N/A | 0 | RETIREMENT OF IDLE FACILITES | 12290.71 | 11929.02 |  | 0% | 2021-07-06 00:33 | 2021-07-06 08:49 | 2021-10-04 |  |  |  | -44383.0229 | -44383.3674 | 0 | #N/A | #N/A | 2021-08-25 00:33 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44383.0229 | 0 | -44383.0229 | #N/A | 0 |  | #N/A | #N/A | 0 | 1472.9771 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | '100338058856', | #N/A |  |  |  | #N/A | RONILO GANGE JR.
2021-07-14 | OK |  | BIZ | X21062562359 | NO BIA, INC. | LANGKA, FTI CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for cancellation, 1/11-transferred to other vendors, 2-22 same remarks | W/ ISSUE | VJC | CAN | Jemuel Peralta | 98.17 | #N/A | 0 | TERMINATION | 98826.44 | 80129.87 |  | 0% | 2021-07-07 10:39 | 2021-07-13 | 2021-07-09 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2021-08-26 10:39 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [8 empty] | B8-1847, 662411 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X21062562359', | ME185130 |  |  |  | PCAN | JSP
| N/A |  | MN | 100338058959 | MAINT - 414FIL - Retirement of Idle poles and other facilities pole DU1-2307 & DU1-2308 | MALACCA LANE FILINVEST CORPORATE CITY ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | w/ pole attachments | W/ ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 21.7214 | #N/A | 0 | RETIREMENT OF IDLE FACILITES | 22830.98 | 22427.35 |  | 0% | 2021-07-08 08:49 | 2021-07-13 13:58 | 2021-10-04 |  |  |  | -44385.3674 | -44390.5819 | 0 | #N/A | #N/A | 2021-08-27 08:49 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44385.3674 | 0 | -44385.3674 | #N/A | 0 |  | #N/A | #N/A | 0 | 1470.6326 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | '100338058959', | #N/A |  |  |  | #N/A | RONILO GANGE JR.
| N/A |  | MN | 100338059056 | MAINT - 414FIL - Retirement of Idle poles and other facilities pole DT1-2353 & DT1-2180 | PARKWAY FILINVEST CORPORATE CITY ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for permit on Feb. 22, 2023; no feed back; permit lapsed (03-08-23); | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 26.5574 | #N/A | 0 | RETIREMENT OF IDLE FACILITES | 26074.07 | 25670.44 |  | 0% | 2021-07-27 12:55 | 2021-07-29 09:03 | 2021-10-04 |  |  |  | -44404.5382 | -44406.3771 | 0 | #N/A | #N/A | 2021-09-15 12:55 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [6 empty] | JDZ |  |  | 0 | -44404.5382 | 0 | -44404.5382 | #N/A | 0 |  | #N/A | #N/A | 0 | 1451.4618 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | '100338059056', | #N/A |  |  |  | #N/A | RONILO GANGE JR.
| N/A |  | MN | 100338058517 | MAINT - 414FIL - Retirement of Idle poles & facilities P# DU1-2173,DU1-2282,DU1-2172,NPT | MANDARIN PLEASANT VILL BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | w/ pole attachments | W/ ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 44.54 | #N/A | 0 | RETIREMENT OF IDLE FACILITES | 41109.69 | 40614.53 |  | 0% | 2021-08-06 | 2021-08-09 10:05 | 2021-10-04 |  |  |  | -44414 | -44417.4201 | 0 | #N/A | #N/A | 2021-09-25 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44414 | 0 | -44414 | #N/A | 0 |  | #N/A | #N/A | 0 | 1442 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | '100338058517', | #N/A |  |  |  | #N/A | RONILO GANGE JR.
| N/A |  | MN | 100338058622 | MAINT - 414FIL - Retirement of Idle poles and other facilities pole DU1-0002-T & DU1-2172-B | MANDARIN PLEASANT VILL BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | w/ pole attachments | W/ ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 11.9873 | #N/A | 0 | RETIREMENT OF IDLE FACILITES | 24337.19 | 23777.68 |  | 0% | 2021-08-06 15:51 | 2021-08-09 10:06 | 2021-10-04 |  |  |  | -44414.6604 | -44417.4208 | 0 | #N/A | #N/A | 2021-09-25 15:51 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44414.6604 | 0 | -44414.6604 | #N/A | 0 |  | #N/A | #N/A | 0 | 1441.3396 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | '100338058622', | #N/A |  |  |  | #N/A | RONILO GANGE JR.
2021-09-03 | N/A |  | MN | P2106111928 | MAINT 43XD Loadsplit [037150¦WA196961¦CX7-0436¦¦] Install 1-50kVA DT on pole CX7-0434 | KASOY DO?A MANUELA SUBD PH 4-A PAMPLONA III LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | for confirmation; crew survey of C1 | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 48.4981 | #N/A | 0 | OLDT | 193888.88 | 42701.27 |  | 0% | 2021-08-10 15:55 | 2021-08-13 12:56 | 2021-08-14 |  |  |  | -44418.6632 | -44421.5389 | 0 | #N/A | #N/A | 2021-09-29 15:55 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 037150 | Y | Scheduled | Transferred from Alvin to Jimmy |  |  |  | 0 | -44418.6632 | 0 | -44418.6632 | #N/A | 0 |  | #N/A | #N/A | 0 | 1437.3368 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2106111928', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2021-09-14 | N/A |  | MN | P2007000361 | MAINT Load-Split 086298/WA350686/100KVA; Inst Addl 1-75kVA DT on pole B8-6252 (new pole) | DIRECTO ZONE 2 SIGNAL VILLAGE TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for survey with QI, refer to design | W/ ISSUE | OPS | FCOMP | Dean Carl Borjal | 0 | 9.77 | 0 | OLDT | 195433.93 | 25772.59 |  | 0% | 2021-08-29 23:12 | 2021-09-02 10:30 | 2021-09-15 |  | 2025-03-19 |  | 1297.0333 | 1293.5625 | -45735 | 2021-09-17 17:47 | 2021-09-26 13:08 | 2021-10-18 23:12 | 44.6756 | -762.25 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-18 | 160 | [8 empty] | NO COC |  | 2025-04-03 | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 086298 | Y | Scheduled | Transferred from Alvin to Jimmy / With Installation of new pole |  |  |  | 0 | 1297.0333 | 0 | 1297.0333 | 44.6756 | 134 |  | 49.2911 | 49.2911 | 2.2333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2007000361', | ME168443 |  |  |  | FCOMP | DCB
2021-10-07 | 2021-09-30 |  | HMB | R20784640 | ALLANIQUE REALTY DEVT CORP | L. ALLANIQUE, BARANGAY VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | customer refuse on location of pole digging 5/20/2025 for BC coordiantion on WO cancellation 2/15 re-surveyed 07/17/2024 to install pole in-front of existing and use small aleyarm as support | (R) W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 85.05 | 23.26 | 0 | RELOC | 94979.94 | 33678.6 |  | 0% | 2021-09-24 15:04 | 2021-09-30 | 2021-09-30 |  |  |  | -44463.6278 | -44469 | 0 | 2021-10-13 09:39 | 2021-10-22 05:00 | 2021-11-13 15:04 | -1531.525 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [8 empty] | CY9-0440, CY9-5932 | 0 | -44463.6278 | 0 | -44463.6278 | -1531.525 | 0 |  | 48.4073 | 48.4073 | 0 | 1392.3722 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R20784640', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2021-10-21 | 2021-10-22 | Y | REL | R19617176 | OFFICE OF CONGRESSMAN STRIKE B. REVILLA, | GEN. EMILIO AGUINALDO, PANAPAAN VI, BACOOR | BACOOR CITY | DASMA | Job 3 for SSP/liveline, Job 4 with telco for email to FA, Job 5 for survey live line, Task 10 with issue on hukay, request assistance bacoor, job 7 for PAI sched; | W/ ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 1133.2284 | 1795.22 | 0 | RELOC | 1921072.21 | 821316.27 |  | 0% | 2021-10-06 19:29 | 2021-10-12 | 2021-10-13 |  |  |  | -44475.8118 | -44481 | 0 | 2021-11-02 06:54 | 2021-11-13 03:33 | 2021-11-25 19:29 | -1131.6623 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44475.8118 | 0 | -44475.8118 | -1131.6623 | 0 |  | 35.4489 | 35.4489 | 0 | 1380.1882 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R19617176', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2021-10-21 | 2021-10-20 |  | BIZ | X21083519494 | SEVEN TALL TREES EVENTS, INC. | ASEANA, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for permit re application 2/15 | W/ ISSUE | CHALLENGER | CAN | Jemuel Peralta | 97.66 | #N/A | 0 | TERMINATION | 87040.66 | 73733.14 |  | 0% | 2021-10-13 16:33 | 2021-10-15 | 2021-10-20 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2021-12-02 16:33 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [8 empty] | C4-5094, 126264 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X21083519494', | ME185130 |  |  |  | PCAN | JSP
2023-05-12 | N/A |  | MN | P2106111943 | MAINT 45XD Loadsplit [035879¦WA141444¦CX8-0551¦¦] install 1-75kVA DT on pole CX8-0552 | KYOTO BF HOMES BF HOMES PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | INPRG | Jenneth Madrid | 53.3183 | #N/A | 0 | OLDT | 224779.02 | 49304.03 |  | 0% | 2021-10-15 08:36 | 2021-10-15 12:31 | 2023-02-10 |  |  |  | -44484.3583 | -44484.5215 | 0 | #N/A | #N/A | 2021-12-04 08:36 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [12 empty] | Load-splitting | TLN 035879 | Y | Scheduled | Transferred from Alvin to Jimmy Issued and returned as surplus, for re-sched by MECO crew but re-assign to C1 and assign to powerhouse |  |  |  | 0 | -44484.3583 | 0 | -44484.3583 | #N/A | 0 |  | #N/A | #N/A | 0 | 1371.6417 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2106111943', | ME185284 |  |  |  | INPRG | Jenneth Madrid
2021-11-18 | 2021-10-30 |  | CBG | X21094255140 | BAYPRIME PROPERTIES INC. | ASEANA, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for WO cancellation? DT still in used | FOR CANCELLATION | CHALLENGER | CLOSED-CAN | Isan Carlo Lazaro | 118.9334 | #N/A | 0 | TERMINATION | 139589.22 | 107671.04 |  | 0% | 2021-10-27 14:20 | 2021-10-29 15:15 | 2021-10-30 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2021-12-16 14:20 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [9 empty] | COMP-CAN 6/26/2025 | EXECUTED THRU WO X21094255140 | #VALUE! | #VALUE! | [10 empty] | Y | [8 empty] | C5-5085, C5-5500, C5-5501, 169547 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X21094255140', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2021-12-02 | 2021-11-18 |  | BIZ | R21040226 | YIELDERS TRADING CORPORATION | STA. AGUEDA, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/ ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 97.3259 | 256.04 | 0 | RELOC | 541158.15 | 110955.08 |  | 0% | 2021-11-12 16:42 | 2021-11-18 12:41 | 2021-11-18 |  |  |  | -44512.6958 | -44518.5285 | 0 | 2021-12-04 13:33 | 2021-12-14 04:42 | 2022-01-01 16:42 | -1342.4464 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [8 empty] | B5-1677, B5-5719, B5-0469, 674317, B5-5649, 201042 | 0 | -44512.6958 | 0 | -44512.6958 | -1342.4464 | 0 |  | 40.9044 | 40.9044 | 0 | 1343.3042 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21040226', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2021-12-21 | 2021-11-24 |  | HMB | X21104486609 | JEFFREY SAGUN CHAN | MATTHEW, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for follow up Pque BC, DT location issue, 1/11-customer doesn't want DT in front of house, task 3, neighbor holds execution, DT already installed on site - 2/22 | W/ ISSUE | VJC | PCAN3 | Jenneth Madrid | 26.168 | #N/A | 44 | MODIFICATION | 201770.89 | 30870.26 |  | 0% | 2021-11-18 16:50 | 2021-11-24 | 2021-11-24 |  |  |  | -44518.7014 | -44524 | 0 | #N/A | #N/A | 2022-01-07 16:50 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [8 empty] | CZ8-0312, CZ8-0313, 204233 | 0 | -44518.7014 | 0 | -44518.7014 | #N/A | 0 |  | #N/A | #N/A | 0 | 1337.2986 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X21104486609', | ME185284 |  |  |  | PCAN3 | Jenneth Madrid
2021-12-02 | 2021-12-02 |  | HMB | X21030949643 | ROBERTO DE MESA BUNYI | HENRY IDE, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | HOA ISSUE; HOA holds exection of project; FOR CANCELLATION (superseded by WO X23010211288) | W/ ISSUE | ECOM | PCAN | Ronilo Gange Jr. | 169.1834 | #N/A | 14 | MODIFICATION | 814987.11 | 132587.33 |  | 0% | 2021-11-24 11:52 | 2021-11-29 12:35 | 2021-12-01 |  |  |  | -44524.4944 | -44529.5243 | 0 | #N/A | #N/A | 2022-01-13 11:52 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | ON GOING MAT RETURN |  | 1900-01-14 | 0 | [10 empty] | Y | [8 empty] | CS9-5807, CS9-5808, CS9-5809, 195424, CS9-5812, CS9-5810, CS9-5811 | 0 | -44524.4944 | 0 | -44524.4944 | #N/A | 0 |  | #N/A | #N/A | 0 | 1331.5056 | NON-REV | 10 MONTHS AND ABOVE | 2025-07-01 | 18334.94 | NTC ISSUED | 2025-07-03 |  | 54 |  |  |  | 'X21030949643', | ME155242 |  |  |  | PCAN | RONILO GANGE JR.
2021-12-14 | 2021-12-04 |  | HMB | R19291776 | CITY GOVERNMENT OF BACOOR | GEN. TIRONA, HABAY I, BACOOR | BACOOR CITY | DASMA | pole location issue (02-15-23); +1 POLE TASK 1 | W/ ISSUE | DASMA | SCHED | Karl Ferdinand Ruiz | 261.8848 | 708.58 | 0 | RELOC | 1370048.35 | 323549.72 |  | 0% | 2021-12-01 15:43 | 2021-12-03 | 2021-12-03 |  |  |  | -44531.6549 | -44533 | 0 | 2021-12-26 11:45 | 2022-01-05 21:54 | 2022-01-20 15:43 | -1199.8807 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [8 empty] | CW5-5786, CW5-5786, CW5-5785, CW5-5785, CW5-6392, CW5-6393, CX5-0074-T, CW5-0737, 084258, 016045, CW5-0919, 047121, CW5-5787 | 0 | -44531.6549 | 0 | -44531.6549 | -1199.8807 | 0 |  | 36.034 | 36.034 | 0 | 1324.3451 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R19291776', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2022-03-03 | OK | Y | CBG | R21631238 | CAVITEX INFRASTRUCTURE CORP. | N. ARMSTRONG, MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | awaiting clearance from CAVITEX on completion of project, task 11 modification | W/ ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 382.9296 | 638.83 | 0 | PCA RELOC | 1414835.62 | 433240.12 |  | 0% | 2022-03-01 14:24 | 2022-03-03 12:33 | 2022-03-03 |  | 2025-06-10 |  | 1196.4 | 1194.4771 | -45818 | 2022-03-26 10:26 | 2022-04-05 20:35 | 2022-04-20 14:24 | 32.2363 | -763.6333 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-08-09 | 77 | [8 empty] | NO COC |  | 2025-06-25 | #VALUE! | [10 empty] | Y | [9 empty] | 0 | 1196.4 | 0 | 1196.4 | 32.2363 | 51 |  | 33.6105 | 33.6105 | 0.85 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21631238', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2022-05-16 | N/A |  | REL | P2107115141 | MN_MAJOR (WDESIGN), CONGRESSMAN OFFICE STRIKE B. REVILLA, Relocation Request along Bacoor,Cavite | MOLINO BLVD., BAYANAN, BACOOR | BACOOR CITY | DASMA | ongoing pole installation - with overlapping to P2111120001; for prioritization; for execution on 5th week of March; for execution for the month of May; job 3 done; job 4 hotline works; job 2 hotline works; job 1 PAI remaining site 1 site 2 and site 4 | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 635.52 | 1991.66 | 0 | MN MAJOR | 2185454.33 | 433474.43 |  | 0% | 2022-04-18 18:57 | 2022-05-06 13:44 | 2022-05-05 |  | 2025-04-23 |  | 1100.2104 | 1082.4278 | -45770 | 2022-05-15 06:22 | 2022-05-26 03:01 | 2022-06-07 18:57 | 27.9942 | -762.8333 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-06-22 | 125 | [8 empty] | NO COC |  | 2025-05-08 | #VALUE! | [10 empty] | N | [9 empty] | 0 | 1100.2104 | 0 | 1100.2104 | 27.9942 | 99 |  | 30.5132 | 30.5132 | 1.65 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2107115141', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2022-04-29 | OK | Y | CBG | R21662615 | FOOD TERMINAL, INC. | LANGKA, FTI CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for completion May 2022 | W/O ISSUE | VJC | DPRG-PCR | Raeven De Quiroz | 102.0535 | #N/A | 0 | RELOC | 160444.02 | 92012.91 | 83552.45 | 90.81% | 2022-04-22 07:47 | 2022-04-28 | 2022-04-27 |  |  |  | -44673.3243 | -44679 | 0 | #N/A | #N/A | 2022-06-11 07:47 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | CHECKING OF SERVICE ITEM | WITH BACKJOB , BILLED | 1900-01-14 | 0 | 2022-05-19 | 2022-06-25 | 2022-07-20 | ECI | Y | Y | 2022-07-20 |  |  |  | N | [6 empty] | AZT |  | B8-6279, B8-6280, B8-6281 | 0 | -44673.3243 | 0 | -44673.3243 | #N/A | 0 |  | #N/A | #N/A | 0 | 1182.6757 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21662615', | ME164318 |  |  |  | DPRG-PCR | MBF
2022-04-29 | OK | Y | REL | R20609999 | CAVITEX INFRASTRUCTURE CORP. | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | PENDING MPTS | W/ ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 717.716 | 1361.61 | 0 | RELOC | 1575766.41 | 923509.73 |  | 0% | 2022-04-26 13:29 | 2022-04-29 15:17 | 2022-04-29 |  |  |  | -44677.5618 | -44680.6368 | 0 | 2022-05-23 00:54 | 2022-06-02 21:33 | 2022-06-15 13:29 | -1136.7957 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [6 empty] | PDZC |  |  | 0 | -44677.5618 | 0 | -44677.5618 | -1136.7957 | 0 |  | 30.3155 | 30.3155 | 0 | 1178.4382 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R20609999', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2022-09-01 | 2022-08-24 | Y | HMB | X22052042329 | MARIA IMELDA BUYOC SANDWEG | JOY, DREAMLAND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | with issue, 1/11-with cash bond | W/ ISSUE | VJC | PCAN3 | Jemuel Peralta | 162.5766 | #N/A | 45 | MODIFICATION | 803861.8 | 139773.08 |  | 0% | 2022-08-23 11:15 | 2022-08-31 | 2022-08-31 |  |  |  | -44796.4688 | -44804 | 0 | #N/A | #N/A | 2022-10-12 11:15 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [8 empty] | CX9-0863, 034987, CX9-2040, 212355, CX9-0862, CX9-5935 | 0 | -44796.4688 | 0 | -44796.4688 | #N/A | 0 |  | #N/A | #N/A | 0 | 1059.5312 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22052042329', | ME185130 |  |  |  | PCAN3 | JSP
2022-09-10 | 2022-09-09 |  | CBG | R21631255 | CAVITEX INFRASTRUCTURE CORP., | E. RODRIGUEZ JR. INT, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for completion within September; w/ ROW issue w/ SM; pending MPTS | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 79.6756 | 155.01 | 0 | RELOC | 412145.24 | 84176.76 | 98865.27 | 117.4% | 2022-09-05 15:22 | 2022-09-07 | 2022-09-07 | 2025-01-30 | 2025-01-30 |  | 877.3597 | 876 | -45687 | 2022-09-26 20:20 | 2022-10-06 07:15 | 2022-10-25 15:22 | 27.1832 | -761.45 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | NO COC | PARTIALLY BILLED | 2025-02-14 | #VALUE! | [10 empty] | N | [9 empty] | 0 | 877.3597 | 0 | 877.3597 | 27.1832 | 182 |  | 32.822 | 32.822 | 3.0333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21631255', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2022-09-10 | OK | Y | REL | R21135764 | CAVITEX INFRASTRUCTURE CORP. | MULTINATIONAL VILL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for completion within October; on going digging, tasks 5 and 7(90 ft), 11; asking for assistance w/ MPTS | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 812.4623 | 1110.82 | 0 | RELOC | 2403133.25 | 809631.02 | 175011.86 | 21.62% | 2022-09-07 07:53 | 2022-09-09 | 2022-09-12 | 2025-04-11 | 2025-04-22 |  | 957.6715 | 956 | -45769 | 2022-10-03 19:18 | 2022-10-14 15:57 | 2022-10-27 07:53 | 24.3674 | -762.8167 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC | PARTIALLY BILLED | 2025-05-07 | #VALUE! | [10 empty] | N | [9 empty] | 0 | 957.6715 | 0 | 957.6715 | 24.3674 | 100 |  | 26.9119 | 26.9119 | 1.6667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21135764', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2022-10-18 | 2022-10-13 |  | HMB | X22093866615 | DULCINEA BALCE SANTOS | HAITI, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | joint survey within September 2023/ Pole location issue for Survey 3/20/25- sched for digging ; WO COMPLETED CONJUCT WO (X25041157540) | W/ ISSUE | VJC | SCHED | Jenneth Madrid | 29.89 | 109.96 | 45 | MODIFICATION | 167939.25 | 22082.54 |  | 0% | 2022-10-11 15:39 | 2022-10-14 | 2022-10-13 |  |  |  | -44845.6521 | -44848 | 0 | 2022-11-01 20:37 | 2022-11-11 07:32 | 2022-11-30 15:39 | -1389.4486 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [8 empty] | DY1-5978 | 0 | -44845.6521 | 0 | -44845.6521 | -1389.4486 | 0 |  | 31.7063 | 31.7063 | 0 | 1010.3479 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22093866615', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2022-11-23 | 2022-11-18 | Y | CBG | X22031018462 | GLOBE TELECOM, INC. | BLOCK 13, BERNABE CPD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | with digging issue; w/ ROW issue (03-16-23); for digging (03-23-23); follow up to BC Pole location issue (with drainage) - resolved (with revised plan / new pole location and tapping point - revised last 05/16/2023) 09192023 ROW issue - MIDC and GLOBE has on-going negotiation for the neighbor's concent as per CRS TSE 11242023 ROW issue - waiting for update from Globe for the neighbor's concent as per TSE | W/ ISSUE | AVECO | CAN | Ronilo Gange Jr. | 76.2585 | #N/A | 23 | MODIFICATION | 359981.35 | 63350.41 |  | 0% | 2022-11-16 09:07 | 2022-11-21 | 2022-11-18 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2023-01-05 09:07 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [8 empty] | CY7-2464, CY7-6092, CY7-6085, 204030 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22031018462', | ME155242 |  |  |  | CAN | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2207136641 | RTA MN_ 415FIL Replacement of Wood Pole on DU1-0017 | ILAYA ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 111.413 | #N/A | 0 | RTA | 223165.1 | 121601.58 |  | 0% | 2022-12-02 14:45 | 2023-01-11 10:38 | 2023-01-13 |  |  |  | -44897.6146 | -44937.4431 | 0 | #N/A | #N/A | 2023-01-21 14:45 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44897.6146 | 0 | -44897.6146 | #N/A | 0 |  | #N/A | #N/A | 0 | 958.3854 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2207136641', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141348 | RTA MN - 415FIL - DT1-0065 - Replacement of rotten, hazardous and old standard pole | T. MOLINA ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for crew survey; for C1 survey | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 39.2801 | #N/A | 0 | RTA | 69142.18 | 30610.91 |  | 0% | 2022-12-04 21:37 | 2023-01-11 10:30 | 2023-01-14 |  |  |  | -44899.9007 | -44937.4375 | 0 | #N/A | #N/A | 2023-01-23 21:37 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44899.9007 | 0 | -44899.9007 | #N/A | 0 |  | #N/A | #N/A | 0 | 956.0993 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141348', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141350 | RTA MN - 415FIL - DU1-0445 - Replacement of rotten, hazardous and old standard pole | T. MOLINA ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 40.3024 | #N/A | 0 | RTA | 70118.66 | 31407.59 |  | 0% | 2022-12-05 10:43 | 2023-01-11 10:33 | 2023-01-13 |  |  |  | -44900.4465 | -44937.4396 | 0 | #N/A | #N/A | 2023-01-24 10:43 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44900.4465 | 0 | -44900.4465 | #N/A | 0 |  | #N/A | #N/A | 0 | 955.5535 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141350', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141356 | RTA MN - 415FIL - DT1-0057 - Replacement of rotten, hazardous and old standard pole | ILAYA PUROK 7 ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for crew survey; for C1 survey | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 42.5861 | #N/A | 0 | RTA | 73123.35 | 33187.27 |  | 0% | 2022-12-06 22:36 | 2023-01-11 14:20 | 2023-01-14 |  |  |  | -44901.9417 | -44937.5972 | 0 | #N/A | #N/A | 2023-01-25 22:36 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.9417 | 0 | -44901.9417 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.0583 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141356', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141357 | RTA MN - 415FIL - DU1-0003 - Replacement of rotten, hazardous and old standard pole | ILAYA ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 51.0125 | #N/A | 0 | RTA | 80899.28 | 39753.95 |  | 0% | 2022-12-06 22:38 | 2023-01-11 14:24 | 2023-01-13 |  |  |  | -44901.9431 | -44937.6 | 0 | #N/A | #N/A | 2023-01-25 22:38 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.9431 | 0 | -44901.9431 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.0569 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141357', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141358 | RTA MN - 415FIL - DV1-0001 - Replacement of rotten, hazardous and old standard pole | VINALON PUROK 3 CUPANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 39.2801 | #N/A | 0 | RTA | 69142.18 | 30610.91 |  | 0% | 2022-12-06 22:39 | 2023-01-11 14:29 | 2023-01-13 |  |  |  | -44901.9437 | -44937.6035 | 0 | #N/A | #N/A | 2023-01-25 22:39 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.9437 | 0 | -44901.9437 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.0563 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141358', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141362 | RTA MN - 415FIL - DT1-0050 - Replacement of rotten, hazardous and old standard pole | ILAYA PUROK 7 ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for crew survey; for C1 survey | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 51.0125 | #N/A | 0 | RTA | 80899.28 | 29912.66 |  | 0% | 2022-12-06 22:40 | 2023-01-11 14:19 | 2023-01-14 |  |  |  | -44901.9444 | -44937.5965 | 0 | #N/A | #N/A | 2023-01-25 22:40 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.9444 | 0 | -44901.9444 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.0556 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141362', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141366 | RTA MN - 425FIL - DT1-0140 - Replacement of rotten, hazardous and old standard pole | NATIONAL ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 39.2801 | #N/A | 0 | RTA | 69142.18 | 30610.91 |  | 0% | 2022-12-06 22:41 | 2023-01-12 | 2023-01-13 |  |  |  | -44901.9451 | -44938 | 0 | #N/A | #N/A | 2023-01-25 22:41 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.9451 | 0 | -44901.9451 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.0549 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141366', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141368 | RTA MN - 425FIL - DT1-0264 - Replacement of rotten, hazardous and old standard pole | M. DOLLETON PUROK 1 BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for scheduling, drainage and waterline | W/ ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 39.2801 | #N/A | 0 | RTA | 69142.18 | 30610.91 |  | 0% | 2022-12-06 22:46 | 2023-01-12 | 2023-01-14 |  |  |  | -44901.9486 | -44938 | 0 | #N/A | #N/A | 2023-01-25 22:46 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.9486 | 0 | -44901.9486 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.0514 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141368', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2023-01-12 | N/A |  | MN | P2211141370 | RTA MN - 425FIL - ALB1-1897 - Replacement of rotten, hazardous and old standard pole | HERRERA JR. PUROK 1 BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for scheduling, check pole tag | W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 38.3841 | #N/A | 0 | RTA | 68226.09 | 29912.66 |  | 0% | 2022-12-06 22:48 | 2023-01-12 | 2023-01-14 |  |  |  | -44901.95 | -44938 | 0 | #N/A | #N/A | 2023-01-25 22:48 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44901.95 | 0 | -44901.95 | #N/A | 0 |  | #N/A | #N/A | 0 | 954.05 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141370', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2023-01-12 | N/A |  | MN | P2211141364 | RTA MN - 425FIL - DS1-0169 - Replacement of rotten, hazardous and old standard pole | VIRGO PUROK 1 BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for scheduling | W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 39.2801 | #N/A | 0 | RTA | 69095.41 | 30610.91 |  | 0% | 2022-12-08 23:06 | 2023-01-12 | 2023-01-14 |  |  |  | -44903.9625 | -44938 | 0 | #N/A | #N/A | 2023-01-27 23:06 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44903.9625 | 0 | -44903.9625 | #N/A | 0 |  | #N/A | #N/A | 0 | 952.0375 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141364', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2022-12-16 | OK |  | HMB | R21956925 | MACAGGA DANICA RUTH RABENA | REYVILLE I SUBD, REYVILLE I SUBD, BACOOR | BACOOR CITY | DASMA | current plan cannot be executed due to the lack of space for installing a down guy; contractor cannot execute; for digging on Feb. 21, 2023; w/ customer issue: FOR CANCELLATION | W/ ISSUE | ECOM | PCAN4 | Ronilo Gange Jr. | 13.0041 | #N/A | 0 | RELOC | 37045.87 | 13135.2 |  | 0% | 2022-12-09 | 2022-12-14 | 2022-12-15 |  |  |  | -44904 | -44909 | 0 | #N/A | #N/A | 2023-01-28 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44904 | 0 | -44904 | #N/A | 0 |  | #N/A | #N/A | 0 | 952 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21956925', | ME155242 |  |  |  | PCAN4 | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141365 | RTA MN - 425FIL - NPT(NR DT1-5850) - Replacement of rotten, hazardous and old standard pole | M. DOLLETON PUROK 1 BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for scheduling, check if wood pole | W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 39.2801 | #N/A | 0 | RTA | 69101.47 | 30610.91 |  | 0% | 2022-12-09 14:12 | 2023-01-12 | 2023-01-14 |  |  |  | -44904.5917 | -44938 | 0 | #N/A | #N/A | 2023-01-28 14:12 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44904.5917 | 0 | -44904.5917 | #N/A | 0 |  | #N/A | #N/A | 0 | 951.4083 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141365', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2023-01-12 | N/A |  | MN | P2211141360 | RTA MN - 415FIL - DU1-0119-T - Replacement of rotten, hazardous and old standard pole | NATIONAL ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ongoing | W/O ISSUE | POWERHOUSE | SCHED | Jenneth Madrid | 39.2801 | #N/A | 0 | RTA | 69083.29 | 30610.91 |  | 0% | 2022-12-11 21:57 | 2023-01-11 14:27 | 2023-01-13 |  |  |  | -44906.9146 | -44937.6021 | 0 | #N/A | #N/A | 2023-01-30 21:57 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9146 | 0 | -44906.9146 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0854 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141360', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2023-01-12 | N/A |  | MN | P2211141361 | RTA MN - 415FIL - DU1-0117-T - Replacement of rotten, hazardous and old standard pole | ILAYA ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ongoing | W/O ISSUE | POWERHOUSE | SCHED | Jenneth Madrid | 39.2801 | #N/A | 0 | RTA | 69095.41 | 30610.91 |  | 0% | 2022-12-11 21:58 | 2023-01-11 14:25 | 2023-01-13 |  |  |  | -44906.9153 | -44937.6007 | 0 | #N/A | #N/A | 2023-01-30 21:58 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9153 | 0 | -44906.9153 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0847 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141361', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2023-01-12 | N/A |  | MN | P2211141332 | RTA MN - 415FIL - DU1-5951 - Replacement of rotten, hazardous and old standard pole | MONTILLANO ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ongoing | W/O ISSUE | POWERHOUSE | SCHED | Jenneth Madrid | 54.8623 | #N/A | 0 | RTA | 95850.85 | 42754.09 |  | 0% | 2022-12-11 22:22 | 2023-01-11 10:35 | 2023-01-13 |  |  |  | -44906.9319 | -44937.441 | 0 | #N/A | #N/A | 2023-01-30 22:22 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9319 | 0 | -44906.9319 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0681 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141332', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2023-01-12 | N/A |  | MN | P2211141351 | RTA MN - 415FIL - DU1-0686 - Replacement of rotten, hazardous and old standard pole | PNR CUPANG CUPANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ongoing | W/O ISSUE | POWERHOUSE | SCHED | Jenneth Madrid | 47.4984 | #N/A | 0 | RTA | 77366.97 | 37015.41 |  | 0% | 2022-12-11 22:24 | 2023-01-11 14:28 | 2023-01-13 |  |  |  | -44906.9333 | -44937.6028 | 0 | #N/A | #N/A | 2023-01-30 22:24 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9333 | 0 | -44906.9333 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0667 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141351', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2023-01-12 | N/A |  | MN | P2211141353 | RTA MN - 415FIL - DT1-0061 - Replacement of rotten, hazardous and old standard pole | MENDIOLA PUROK 1 ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for crew survey; for C1 survey | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 39.2801 | #N/A | 0 | RTA | 69142.18 | 30610.91 |  | 0% | 2022-12-11 22:24 | 2023-01-11 14:21 | 2023-01-14 |  |  |  | -44906.9333 | -44937.5979 | 0 | #N/A | #N/A | 2023-01-30 22:24 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9333 | 0 | -44906.9333 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0667 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141353', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141343 | RTA MN - 415FIL - ALB1-1353 - Replacement of rotten, hazardous and old standard pole | CAPT. IGNACIO MABOLO I MABOLO I BACOOR CAVITE | BACOOR CITY | DASMA | ongoing | W/O ISSUE | POWERHOUSE | SCHED | Jenneth Madrid | 38.3841 | #N/A | 0 | RTA | 68226.09 | 29912.66 |  | 0% | 2022-12-11 22:27 | 2023-01-11 14:19 | 2023-01-13 |  |  |  | -44906.9354 | -44937.5965 | 0 | #N/A | #N/A | 2023-01-30 22:27 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9354 | 0 | -44906.9354 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0646 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141343', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2023-01-12 | N/A |  | MN | P2211141342 | RTA MN - 415FIL - DT2-2199 - Replacement of rotten, hazardous and old standard pole | SAN GUILLERMO BAYANAN BAYANAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | digging done, schedule only at night | W/O ISSUE | CHALLENGER | INPRG | Isan Carlo Lazaro | 51.0125 | #N/A | 0 | RTA | 80899.28 | 39753.95 |  | 0% | 2022-12-11 22:28 | 2023-01-11 14:23 | 2023-01-14 |  |  |  | -44906.9361 | -44937.5993 | 0 | #N/A | #N/A | 2023-01-30 22:28 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9361 | 0 | -44906.9361 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0639 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141342', | ME166067 |  |  |  | INPRG | Isan Carlo Lazaro
2023-01-12 | N/A |  | MN | P2211141340 | RTA MN - 415FIL - DT1-0301 - Replacement of rotten, hazardous and old standard pole | SAN GUILLERMO PUTATAN PUTATAN MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 38.3841 | #N/A | 0 | RTA | 68226.09 | 29912.66 |  | 0% | 2022-12-11 23:10 | 2023-01-11 14:22 | 2023-01-13 |  |  |  | -44906.9653 | -44937.5986 | 0 | #N/A | #N/A | 2023-01-30 23:10 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9653 | 0 | -44906.9653 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0347 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141340', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-12 | N/A |  | MN | P2211141328 | RTA MN - 425FIL/415FIL - DS1-5305 - Replacement of rotten, hazardous and old standard pole | NATIONAL ALABANG ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for scheduling | W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 39.2801 | #N/A | 0 | RTA | 67679.29 | 30610.91 |  | 0% | 2022-12-11 23:20 | 2023-01-12 | 2023-01-14 |  |  |  | -44906.9722 | -44938 | 0 | #N/A | #N/A | 2023-01-30 23:20 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9722 | 0 | -44906.9722 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0278 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141328', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2023-01-12 | N/A |  | MN | P2211141377 | RTA MN 425FIL - NPT (DR1-0242) Replacement of rotten, hazardous and old standard pole | P. DIAZ POBLACION POBLACION MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | contact person needed from BC; for checking w/ PnS | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 39.2801 | #N/A | 0 | RTA | 69101.47 | 30610.91 |  | 0% | 2022-12-11 23:27 | 2023-01-12 | 2023-01-13 |  |  |  | -44906.9771 | -44938 | 0 | #N/A | #N/A | 2023-01-30 23:27 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [9 empty] | 0 | -44906.9771 | 0 | -44906.9771 | #N/A | 0 |  | #N/A | #N/A | 0 | 949.0229 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2211141377', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-01-03 | 2022-12-27 |  | BIZ | X22125127907 | MEGAWIDE CONSTRUCTION CORPORATION | ALABANG-ZAPOTE, PAMPLONA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | for execution on March 7, 2023; for execution on March 30, 2023; for execution on April 28, 2023 | W/O ISSUE | AVECO | PCAN | Ronilo Gange Jr. | 112.4467 | #N/A | 0 | TERMINATION | 139047.8 | 104815.37 |  | 0% | 2022-12-21 12:42 | 2022-12-29 | 2022-12-27 |  |  |  | -44916.5292 | -44924 | 0 | #N/A | #N/A | 2023-02-09 12:42 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [8 empty] | CX7-5836, CX7-5837, 171617 | 0 | -44916.5292 | 0 | -44916.5292 | #N/A | 0 |  | #N/A | #N/A | 0 | 939.4708 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22125127907', | ME155242 |  |  |  | PCAN | RONILO GANGE JR.
2023-02-15 | N/A |  | MN | P2301143548 | PQUE 43WU Loadsplit [035817¦WA359894¦CW9-0271¦Install 1-75kVA DT on pole CW9-0211 W/POLE | ADELITA CHIOCO BF HOMES BF HOMES PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | with customer opposition sa bunot tayong poste 0419 | W/ ISSUE | OPS | INPRG | Dean Carl Borjal | 84.0239 | #N/A | 0 | OLDT | 310484.15 | 76106.73 |  | 0% | 2023-02-01 10:09 | 2023-02-15 12:24 | 2023-02-03 |  |  |  | -44958.4229 | -44972.5167 | 0 | #N/A | #N/A | 2023-03-23 10:09 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N |  | Load-splitting | TLN 035817 | Y | For schedule |  |  |  | CW9-0211, 035817 | 0 | -44958.4229 | 0 | -44958.4229 | #N/A | 0 |  | #N/A | #N/A | 0 | 897.5771 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2301143548', | ME168443 |  |  |  | INPRG | DCB
2023-02-15 | N/A |  | MN | P2301143554 | PQUE 415FIL Loadsplit [419127¦WA196183¦DT2-2061¦Install additional 1-50kVA DT on pole DT2-2060 | 3RD L & B CPD 2 ALABANG MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | with execution issue; accessibility; for survey c/o C1 | W/ ISSUE | AVECO | TECO | Dean Carl Borjal | 45.82 | 45.82 | 0 | OLDT | 161415.96 | 10396.61 |  | 0% | 2023-02-01 10:11 | 2023-02-15 12:25 | 2023-02-06 |  | 2025-01-15 | 2025-05-31 17:06 | 713.5757 | 699.4826 | 136.7125 | 2023-02-20 04:46 | 2023-03-01 00:07 | 2023-03-23 10:11 | 24.5787 | 2.2785 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-16 | 223 | [8 empty] | PAID | NO COC | 2025-01-30 | #VALUE! | [10 empty] | N |  | Load-splitting | TLN 419127 | N | For schedule |  |  |  | DT2-2060, 419127 | 0 | 713.5757 | 0 | 713.5757 | 24.5787 | 197 |  | 31.3643 | 31.3643 | 3.2833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2301143554', | ME168443 |  |  |  | FCOMP | RONILO GANGE JR.
2023-03-15 | OK | Y | CBG | R21631694 | CAVITEX INFRASTRUCTURE CORP., | KAINGIN, STO. NIÑO, PARAÑAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing (03-16-23); c/o MPTS | W/ ISSUE | ECOM | INPRG | Ronilo Gange Jr. | 1059.1652 | 1865.53 | 0 | RELOC | 3525946.4 | 1241706.01 |  | 0% | 2023-03-07 | 2023-03-08 | 2023-03-14 |  |  |  | -44992 | -44993 | 0 | 2023-04-02 11:25 | 2023-04-13 08:04 | 2023-04-26 | -1144.7964 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [17 empty] | PDZC |  |  | 0 | -44992 | 0 | -44992 | -1144.7964 | 0 |  | 22.3148 | 22.3148 | 0 | 864 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21631694', | ME155242 |  |  |  | INPRG | RONILO GANGE JR.
2023-04-11 | 2023-04-04 |  | CBG | R22344695 | ALVEO LAND CORPORATION | MADRIGAL BUSINESS PARK, ALABANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for PAI and for schedule after Dapulang Project | W/O ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 205.7057 | 656.97 | 0 | RELOC | 4408402.49 | 328357.79 |  | 0% | 2023-03-27 | 2023-04-04 14:16 | 2023-04-12 |  | 2025-01-28 |  | 673 | 664.4056 | -45685 | 2023-04-20 20:02 | 2023-05-01 06:11 | 2023-05-16 | 18.1336 | -761.4167 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-03-29 | 210 | [8 empty] | FOR AUDIT |  | 2025-02-12 | #VALUE! | 2025-03-27 | [9 empty] | N | [7 empty] | 2023-04-11 | CU9-5930, CU9-5931, CU9-5932, CU9-8002, CU9-8003, CU9-1748 | 0 | 673 | 0 | 673 | 18.1336 | 184 |  | 23.0914 | 23.0914 | 3.0667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R22344695', | ME155242 |  |  |  | FCOMP | Erika Mae Orlina
|  |  | HMB | X22104175107 | MARK KENNETH VITUG FLORES | MAPLE DRIVE, MENLO PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | PCAN3 | Ronilo Gange Jr. | 260.1375 | #N/A | 48 | NEW | 262732.62 | 1235620.51 |  | 0% | 2023-04-03 17:27 | 2023-04-05 14:53 |  |  |  |  | -45019.7271 | 0 | 0 | 2025-04-20 23:19 | 2025-04-30 04:43 | 2025-05-20 15:02 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45019.7271 | 0 | -45019.7271 | #N/A | 0 |  | #N/A | #N/A | 0 | 836.2729 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 | [8 empty] | #N/A | Jenneth Madrid
2023-05-04 | 2023-05-04 |  | HMB | X22104473949 | CELEDONIA C. UTANES | KYOTO COR JERUSALEM ST., BF HOMES, PARAÑAQUE | PARAÑAQUE CITY | PARAÑAQUE | Digging Prob. | W/ ISSUE | POWERHOUSE | SCHED | Isan Carlo Lazaro | 64.7485 | 243.45 | 80 | MODIFICATION | 495372.18 | 67653.48 |  | 0% | 2023-04-27 | 2023-05-03 | 2023-05-03 |  |  |  | -45043 | -45049 | 0 | 2023-05-17 23:02 | 2023-05-27 08:23 | 2023-06-16 | -1409.9595 | 0 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-05-06 | CX8-0460, CX8-8074, CX8-0459, 514959, CX8-0547, CX8-8075 | 0 | -45043 | 0 | -45043 | -1409.9595 | 0 |  | 25.8559 | 25.8559 | 0 | 813 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22104473949', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2023-08-16 | 2023-08-14 |  | CBG | X23072866920 | GLOBE TELECOM, INC. | STA. INES, SAN ANTONIO VALLEY 6, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | As per contractor, nakausap nila yung HOA, may i-sesettle pa daw si Globe sakanila. Bukod po dito, nakausap din ng contractor yung tapat ng pagtatayuan ng poste, ayaw rin nito pumayag. 3/16/24 - Already installed pole on 3/13/24, installed DT on 3/15/24; Pending energization of Globe due to issue with HOA | W/ ISSUE | ECOM | PCAN | Ronilo Gange Jr. | 59.1616 | #N/A | 23 | MODIFICATION | 363942.06 | 71262.06 |  | 0% | 2023-08-10 10:40 | 2023-08-15 | 2023-08-12 |  |  |  | -45148.4444 | -45153 | 0 | #N/A | #N/A | 2023-09-29 10:40 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | CANCELLED | Awaiting reply kay Monica, for confirmation ng issue | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-08-17 | CX8-0211, CX8-8131, 518095, CY9-0203 | 0 | -45148.4444 | 0 | -45148.4444 | #N/A | 0 |  | #N/A | #N/A | 0 | 707.5556 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23072866920', | ME155242 |  |  |  | PCAN | RONILO GANGE JR.
2023-09-12 | 2023-08-31 | Y | HMB | R22633190 | CANDIE CHUA CO. | BLK 8, PALM COAST MARINA, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For Sched September 26, 2023 survey/digging; pole location issue Update as of October 28. Issue on HOA and Customer not yet conduct meeting to resolve the issue | W/ ISSUE | ECOM | INPRG | Ronilo Gange Jr. | 85.5844 | 185.89 | 0 | RELOC | 258760.27 | 91241.75 |  | 0% | 2023-08-31 12:27 | 2023-09-05 | 2023-09-05 |  |  |  | -45169.5188 | -45174 | 0 | 2023-09-21 17:25 | 2023-10-01 04:20 | 2023-10-20 12:27 | -1399.483 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-09-12 | B4-2049, 113551, B4-8013, B4-5058, B4-2048 | 0 | -45169.5188 | 0 | -45169.5188 | -1399.483 | 0 |  | 21.672 | 21.672 | 0 | 686.4812 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R22633190', | ME155242 |  |  |  | INPRG | Jenneth Madrid
2023-09-28 | N/A |  | CBG | P2210140139 | ECP-SR:, ASEANA ,DEVT OF 115KV-34.5KV GIS SS Station Service | BELLE, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | pole staking 10/13/2023, 02/07/2024 -With revision and for approval of ASEANA 3/26/24: Approved design by ABPEA -to request for another joint survey and pole staking -VJCto secure and pay for permit after the approval of revised plan 6/6/24 - for payment of permit c/o VJC 7/11/24 - VJCpaid permit 7/15/24 - ABPEA released working permit & gate pass permit FOR ENERGIZATION WITH CONJ. WO FROM C2 | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 334.68 | 445.08 | 68 | ECP | 1162251.69 | 245180.25 |  | 0% | 2023-09-12 11:37 | 2023-09-26 | 2023-09-25 |  | 2025-01-18 |  | 493.516 | 480 | -45675 | 2023-10-04 12:21 | 2023-10-14 04:33 | 2023-11-01 11:37 | 14.7873 | -761.25 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-03-19 | 220 | [8 empty] | NO COC |  | 2025-02-02 | #VALUE! | [10 empty] | Y | [7 empty] | 2023-09-29 | C5-5609, C5-8032, C5-8033, C5-8034, C5-8035, C5-8001, 514027 | 0 | 493.516 | 0 | 493.516 | 14.7873 | 194 |  | 20.6002 | 20.6002 | 3.2333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2210140139', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2023-09-29 | 2023-09-27 |  | HMB | X23072873118 | JOSEPH T. CHUA | NARRA, LAKEVIEW HOMES I, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | HOA claiming that they owned the property not by LGU (on-going return of surplus materials) FOR CANCELLATION | FOR CANCELLATION | ECOM | PCAN3 | Ronilo Gange Jr. | 262.9633 | #N/A | 86 | NEW | 1509543.73 | 257509.03 |  | 0% | 2023-09-26 09:10 | 2023-09-29 | 2023-09-27 |  |  |  | -45195.3819 | -45198 | 0 | #N/A | #N/A | 2023-11-15 09:10 | #N/A | 0 | #N/A | 34 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | ON GOING MAT RETURN |  | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-10-02 | DR1-1524, ALB1-1297, ALB1-1939, DS1-8036, DS1-8037, DS1-8038, 518136, DS1-8039, DR1-1109, DS1-8040 | 0 | -45195.3819 | 0 | -45195.3819 | #N/A | 0 |  | #N/A | #N/A | 0 | 660.6181 | REV | 10 MONTHS AND ABOVE | 2025-07-01 | 92555.66 | NTC ISSUED | 2025-07-03 |  | 54 |  |  |  | 'X23072873118', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2023-10-05 | 2023-09-29 |  | HMB | X22114887149 | ZENAIDA M. CELESTINO | DOÑA INES, ALABANG HILLS SUBD PH 2, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | pole location issue for referral to BC | W/ ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 114.9014 | 196.41 | 104 | MODIFICATION | 506248.25 | 120772.87 |  | 0% | 2023-09-27 08:17 | 2023-10-02 13:29 | 2023-09-29 |  |  |  | -45196.3451 | -45201.5618 | 0 | 2023-10-16 18:59 | 2023-10-25 18:39 | 2023-11-16 08:17 | -1510.1663 | 0 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-10-07 | DV1-0203, 801837, DV1-0204, 515089, DV1-0205 | 0 | -45196.3451 | 0 | -45196.3451 | -1510.1663 | 0 |  | 22.4757 | 22.4757 | 0 | 659.6549 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22114887149', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-11-08 | 2023-11-06 |  | BIZ | X23104085941 | D.L. CERVANTES CONSTRUCTION CORPORATION | ARIA, STA. CECILIA VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | For Schedule | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 8.47 | 13.49 | 0 | TERMINATION | 24652.39 | 10512.77 |  | 0% | 2023-10-29 13:00 | 2023-11-03 15:26 | 2023-11-04 |  | 2025-07-05 |  | 614.4583 | 609.3569 | -45843 | 2023-11-17 07:35 | 2023-11-26 02:56 | 2023-12-18 13:00 | 21.1647 | -764.05 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-03 | 52 | [8 empty] | NO COC |  | 2025-07-20 | #VALUE! | [10 empty] | Y | [7 empty] | N/A | CW7-1298, 197239 | 0 | 614.4583 | 0 | 614.4583 | 21.1647 | 26 |  | 22.0602 | 22.0602 | 0.43333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23104085941', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-11-08 | 2023-11-06 |  | HMB | X23031072544 | MA. FIDES CARLA OASAN TALADUA | BLOCK 8, AVIDA SETTINGS CAVITE PH2, BACOOR | BACOOR CITY | DASMA | Hold by Developer due to need Meralco coordination | W/ ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 83.9154 | 182.27 | 40 | MODIFICATION | 391985.28 | 87441.34 |  | 0% | 2023-10-31 08:45 | 2023-11-03 15:27 | 2023-11-04 |  |  |  | -45230.3646 | -45233.6438 | 0 | 2023-11-21 13:43 | 2023-12-01 00:38 | 2023-12-20 08:45 | -1401.3681 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-11-08 | CP7-5251, 127774, 516578, CP7-5278 | 0 | -45230.3646 | 0 | -45230.3646 | -1401.3681 | 0 |  | 19.7868 | 19.7868 | 0 | 625.6354 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23031072544', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-11-22 | 2023-11-21 |  | HMB | X23093558896 | HELENE ASHLEY RAZO VERA CRUZ | CAVITE, ALABANG HILLS SUBD PH 3, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for digging | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 149.0427 | 214.27 | 36 | MODIFICATION | 563779.23 | 139601.22 |  | 0% | 2023-11-17 09:44 | 2023-11-20 16:22 | 2023-11-18 |  |  |  | -45247.4056 | -45250.6819 | 0 | 2023-12-09 06:35 | 2023-12-18 21:44 | 2024-01-06 09:44 | -1364.6043 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-11-24 | DV1-0420, DV1-0450, DV1-8002, DV1-8003, 516687, DV1-0448 | 0 | -45247.4056 | 0 | -45247.4056 | -1364.6043 | 0 |  | 18.7465 | 18.7465 | 0 | 608.5944 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23093558896', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-11-29 | 2023-11-30 |  | HMB | X22114818590 | NILO F OMILLO | TOURMALINE, LAS PINAS RYL EST1, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | for digging | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 219.0052 | 611.36 | 98.8 | MODIFICATION | 1122491.9 | 246798.79 |  | 0% | 2023-11-22 16:45 | 2023-11-28 07:32 | 2023-11-23 |  |  |  | -45252.6979 | -45258.3139 | 0 | 2023-12-16 09:35 | 2023-12-26 12:29 | 2024-01-11 16:45 | -1271.0684 | 0 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-11-29 | CX7-1183, CX7-1184, CX7-1218, CX7-8039, CX7-8040, CX7-1266, 515051, CX7-1267, CU8-5016 | 0 | -45252.6979 | 0 | -45252.6979 | -1271.0684 | 0 |  | 17.3108 | 17.3108 | 0 | 603.3021 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22114818590', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2023-11-29 | 2023-12-02 |  | HMB | X23010135604 | DANILO CASPE SEPTIMO | P.D.A., SITIO BAGONG SILANG, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Permit issue 01/30/2024 -BC emailed that they had a meeting last time with Muntinlupa LGU & Paranaque LGU that they will secure a work permit first to them before we re-execute the project. 3/27/2024 ROW team set a joint survey and meeting as requested by Muntinlupa LGU to settle the issue 4/23/2024 C1 email BC requesting for update 07/8/2024 -still not settle the dispute as per ROW (HOA complain to BC for the completion of loadside by CBM before the start of execution) (on-going return of surplus materials) FOR CANCELLATION | FOR CANCELLATION | AVECO | PCAN3 | Ronilo Gange Jr. | 233.566 | #N/A | 135 | NEW | 1402828.43 | 265062.37 | 19989 | 7.541% | 2023-11-23 16:24 | 2023-11-28 | 2023-11-24 |  |  |  | -45253.6833 | -45258 | 0 | #N/A | #N/A | 2024-01-12 16:24 | #N/A | 0 | #N/A | 32 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-11-29 | DW1-5973, DW1-5975, DW1-8004, DW1-8005, DW1-8006, DW1-8007, DW1-8008, 515490 | 0 | -45253.6833 | 0 | -45253.6833 | #N/A | 0 |  | #N/A | #N/A | 0 | 602.3167 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23010135604', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2023-11-29 | 2023-12-02 |  | HMB | X23010135483 | ELENA SALAZAR BOÑAGA | P.D.A., SITIO BAGONG SILANG, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Permit issue 01/30/2024 -BC emailed that they had a meeting last time with Muntinlupa LGU & Paranaque LGU that they will secure a work permit first to them before we re-execute the project. 3/27/2024 ROW team set a joint survey and meeting as requested by Muntinlupa LGU to settle the issue 4/23/2024 C1 email BC requesting for update 07/8/2024 -still not settle the dispute as per ROW (HOA complain to BC for the completion of loadside by CBM before the start of execution) (on-going return of surplus materials) FOR CANCELLATION | FOR CANCELLATION | AVECO | PCAN3 | Ronilo Gange Jr. | 75.6316 | #N/A | 135 | NEW | 580669.84 | 99954.07 |  | 0% | 2023-11-23 16:26 | 2023-11-28 | 2023-11-24 |  |  |  | -45253.6847 | -45258 | 0 | #N/A | #N/A | 2024-01-12 16:26 | #N/A | 0 | #N/A | 32 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-11-29 | DW1-8003, 515471 | 0 | -45253.6847 | 0 | -45253.6847 | #N/A | 0 |  | #N/A | #N/A | 0 | 602.3153 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23010135483', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2023-12-01 | 2023-12-05 |  | CBG | X22114994258 | MAYNILAD WATER SERVICES, INC. | SAN GUILLERMO, BAYANAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | superseded by 2024 work order (on-going return of surplus materials) FOR CANCELLATION | FOR CANCELLATION | ECOM | PCAN3 | Ronilo Gange Jr. | 165.0101 | #N/A | 105 | NEW | 1535683.94 | 293927.24 |  | 0% | 2023-11-29 16:05 | 2023-12-01 | 2023-11-30 |  |  |  | -45259.6701 | -45261 | 0 | #N/A | #N/A | 2024-01-18 16:05 | #N/A | 0 | #N/A | 32 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2023-12-02 | DT1-0028, DT1-5722, DT1-0493, DT1-0030-Z, DT2-0174, DT2-0031, DT2-0032, DT2-0033, DT1-0570, DT1-0038, DT1-0039, DT1-0040, DT1-0571, DT2-8001, DT1-0041, DT1-2203, DT1-2202, DT1-0043, DT1-2023, DT1-2024, DT1-2025, DT1-0242, 515166, DT2-8002, DT1-5026, DT1-0575, DT2-5044 | 0 | -45259.6701 | 0 | -45259.6701 | #N/A | 0 |  | #N/A | #N/A | 0 | 596.3299 | REV | 10 MONTHS AND ABOVE | 2025-04-08 | 57684.62 | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22114994258', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2024-02-14 | 2024-02-14 |  | CBG | X24010236211 | INTERNATIONAL CONTAINER TERMINAL SERVICES, INC. | ROAD 4, PAGCOR ENTERTAINMENT CITY, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | On going Retirement | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 446.5173 | 772.82 | 0 | TERMINATION | 759683.83 | 347971.02 |  | 0% | 2024-02-02 14:21 | 2024-02-05 09:24 | 2024-02-06 |  | 2025-04-02 |  | 424.4021 | 421.6083 | -45749 | 2024-02-27 10:23 | 2024-03-08 20:32 | 2024-03-23 14:21 | 11.4353 | -762.4833 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-06-01 | 146 | [8 empty] | NO COC |  | 2025-04-17 | #VALUE! | [10 empty] | Y | [7 empty] | N/A |  | 0 | 424.4021 | 0 | 424.4021 | 11.4353 | 120 |  | 14.6686 | 14.6686 | 2 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010236211', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-03-06 | 2024-03-13 |  | HMB | R22927252 | CARPIO, SEVILLA FESTEJO, HMB | STA. MARTA, SAN ANTONIO VALLEY 14, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For sched of PAI | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 135.6456 | 162.6 | 0 | RELOC | 265042.16 | 96238.57 |  | 0% | 2024-02-28 16:01 | 2024-03-06 12:27 | 2024-03-05 |  | 2025-04-16 |  | 412.3326 | 405.4812 | -45763 | 2024-03-20 20:59 | 2024-03-30 07:54 | 2024-04-18 16:01 | 12.7753 | -762.7167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-06-15 | 132 | [8 empty] | NO COC |  | 2025-05-01 | #VALUE! | [10 empty] | N | [7 empty] | 2024-03-07 | CX8-1077, CX8-1078 | 0 | 412.3326 | 0 | 412.3326 | 12.7753 | 106 |  | 16.0595 | 16.0595 | 1.7667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R22927252', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-03-14 | 2024-03-21 |  | HMB | X24020456466 | CHRISTIAN ARTABAN M. PALINES | DON P. REYES, VICTORIA HOMES-RUBY PARK SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 2.58 | 5.93 | 32 | MODIFICATION | 25334.32 | 4621.16 |  | 0% | 2024-03-07 09:46 | 2024-03-12 08:20 | 2024-03-13 |  |  |  | -45358.4069 | -45363.3472 | 0 | 2024-03-26 04:21 | 2024-04-03 23:42 | 2024-04-26 09:46 | -1562.3451 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | N/A | CP8-0183, 212993 | 0 | -45358.4069 | 0 | -45358.4069 | -1562.3451 | 0 |  | 17.5871 | 17.5871 | 0 | 497.5931 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020456466', | ME155242 |  |  |  | SCHED | JSP
2024-03-14 | 2024-03-21 |  | BIZ | X23093634405 | JESUS, THE GOOD SHEPHERD CHURCH OF MUNTINLUPA, INC | NATIONAL, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For cancellation, superseded by X24041439619 | W/ ISSUE | CHALLENGER | CAN | Jemuel Peralta | 32.1528 | #N/A | 276 | NEW | 816333.08 | 64325.35 |  | 0% | 2024-03-08 09:36 | 2024-03-14 13:50 | 2024-03-13 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-04-27 09:36 | #VALUE! | #VALUE! | #N/A | 30 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-03-19 | DR1-8028, 518761 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23093634405', | ME185130 |  |  |  | CAN | RONILO GANGE JR.
2024-03-14 | 2024-03-21 |  | HMB | X24010064526 | ARLEEN MARIA Z BORROMEO | ZARATOGA LOOP, ALABANG 400 VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 9/19/24 Issue on Water Pipes 9/30/24 Joint Survey with BC Vendor and Customer | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 138.4457 | 191.82 | 44 | MODIFICATION | 803564.77 | 149134.16 | 32572.24 | 21.84% | 2024-03-11 15:28 | 2024-03-14 14:54 | 2024-03-13 | 2025-02-15 | 2025-02-15 |  | 340.3556 | 337.3792 | -45703 | 2024-04-01 20:26 | 2024-04-11 07:21 | 2024-04-30 15:28 | 10.5452 | -761.7167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-04-16 | 192 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-03-02 | -17 | 2025-05-15 | 2025-02-13 | [8 empty] | Y | 2025-02-18 | [6 empty] | 2024-03-19 | DV1-1179, DV1-1180, DV1-8032, 520068, DV1-8033 | 0 | 340.3556 | 0 | 340.3556 | 10.5452 | 166 |  | 15.6884 | 15.6884 | 2.7667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010064526', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-03-22 | 2024-03-21 |  | HMB | X23030848776 | GRACE ZAPATA CRUZ | BELMONT, ALABANG 400 VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 37.29 | 115.57 | 50.5 | MODIFICATION | 315523.45 | 29058.46 |  | 0% | 2024-03-15 08:38 | 2024-03-21 15:02 | 2024-03-19 |  |  |  | -45366.3597 | -45372.6264 | 0 | 2024-04-05 13:36 | 2024-04-15 00:31 | 2024-05-04 08:38 | -1405.5817 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-03-22 | DV1-8017, 516321 | 0 | -45366.3597 | 0 | -45366.3597 | -1405.5817 | 0 |  | 15.5733 | 15.5733 | 0 | 489.6403 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23030848776', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-04-05 | 2024-04-08 |  | CBG | R23110243 | FILINVEST LAND INC., | EAST SERVICE, ALABANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 9/24/24 Hold by Security for request of Permit 10/19/24 Pole Erection Completed | W/O ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 212.6 | 492.26 | 0 | RELOC | 809307.31 | 165680.53 | 101375.61 | 61.19% | 2024-03-27 12:49 | 2024-04-01 10:03 | 2024-04-04 |  | 2025-04-16 08:35 |  | 384.8236 | 379.9389 | -45763.3576 | 2024-04-19 13:24 | 2024-04-29 11:57 | 2024-05-16 12:49 | 11.0904 | -762.7226 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 2025-06-15 08:35 | 131.6424 | [8 empty] | NO COC | PARTIALLY BILLED | 2025-05-01 08:35 | #VALUE! | [10 empty] | N | [7 empty] | 2024-04-05 | DU1-8004, DU1-8005, DU1-2105, DU1-8030 | 0 | 384.8236 | 0 | 384.8236 | 11.0904 | 105.6424 |  | 14.135 | 14.135 | 1.7607 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23110243', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-04-03 | N/A |  | MN | P2403166300 | C1 414ARS 2024 PLANNED Replacement of bare primary conductor (undersized) A8-0103- A8-5058 | CUCUMBER FTI CPD WESTERN BICUTAN TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | For schedule of PAI | W/O ISSUE | VJC | SCHED | Jenneth Madrid | 39.66 | 39.66 | 0 | SUPPLEMENTAL MN FOR PCA | 68971.82 | 30909.43 |  | 0% | 2024-03-30 23:01 | 2024-04-02 10:48 | 2024-04-04 |  |  |  | -45381.959 | -45384.45 | 0 | 2024-04-18 17:36 | 2024-04-27 12:57 | 2024-05-19 23:01 | -1563.1564 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45381.959 | 0 | -45381.959 | -1563.1564 | 0 |  | 16.7759 | 16.7759 | 0 | 474.041 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2403166300', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-04-11 | 2024-04-08 |  | HMB | X24010230692 | RONALDO RICARDO RAYMUNDO BENITEZ | SUSANA HTS, SUSANA HTS SUBD VILL 1, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | Hindi pdn po kasi mafcomp gawa ng wala po location tag yung DT | W/O ISSUE | ECOM | INPRG | Ronilo Gange Jr. | 14.0928 | 41.21 | 80 | MODIFICATION | 240093.51 | 32138.44 |  | 0% | 2024-04-06 10:19 | 2024-04-11 14:47 | 2024-04-06 |  |  |  | -45388.4299 | -45393.616 | 0 | 2024-04-24 12:06 | 2024-05-03 02:59 | 2024-05-26 10:19 | -1615.2941 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | 2024-05-30 | [6 empty] | 2024-04-11 | DP1-0294, 211620 | 0 | -45388.4299 | 0 | -45388.4299 | -1615.2941 | 0 |  | 17.1026 | 17.1026 | 0 | 467.5701 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010230692', | ME155242 |  |  |  | INPRG | Jenneth Madrid
2024-04-17 | 2024-04-24 |  | HMB | X23093808497 | CITY GOVERNMENT OF PARAÑAQUE | COL. E. DE LEON, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For Request of Brgy Permit; waiting for conj. WO (?) | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 110.2066 | 261.72 | 105 | MODIFICATION | 857138.67 | 132136.13 |  | 0% | 2024-04-11 16:50 | 2024-04-17 14:01 | 2024-04-16 |  | 2025-05-31 |  | 414.2986 | 408.416 | -45808 | 2024-05-01 17:10 | 2024-05-10 20:27 | 2024-05-31 16:50 | 13.5017 | -763.4667 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | FOR AUDIT |  | 2025-06-15 | 15 | 2025-05-31 | 2025-06-30 | [8 empty] | Y | 2025-05-10 | [6 empty] | 2024-04-21 | A5-0123, A5-0152, A5-0119, A5-0117, A5-0115, A5-5608, A5-0346, A5-0434, A5-0168, A5-0113, 168709 | 0 | 414.2986 | 0 | 414.2986 | 13.5017 | 61 |  | 15.4896 | 15.4896 | 1.0167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23093808497', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-04-22 | 2024-04-24 |  | HMB | R22608679 | ODIAMAR FRANCES DE CASTRO | MADRID, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 37.03 | 180.6 | 0 | RELOC | 164134.21 | 28855.37 |  | 0% | 2024-04-15 15:47 | 2024-04-22 12:21 | 2024-04-17 |  | 2025-01-10 |  | 269.3424 | 262.4854 | -45667 | 2024-05-06 20:45 | 2024-05-16 07:40 | 2024-06-04 15:47 | 8.345 | -761.1167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-03-11 | 228 | [8 empty] | FOR AUDIT |  | 2025-01-25 | 21 | 2025-01-09 | 2025-02-15 | [8 empty] | N | [7 empty] | 2024-04-24 | CS7-0551 | 0 | 269.3424 | 0 | 269.3424 | 8.345 | 202 |  | 14.6036 | 14.6036 | 3.3667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R22608679', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-04-22 | 2024-04-24 |  | CBG | X24020411401 | JOLLIBEE FOODS CORPORATION | AGUIRRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 5/18/24 Cancelllation of Execution as per Customer Request 6/11/24 Actual Cancellation was on site dun Affected Customer Hold its Execution | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 139.95 | 139.95 | 0 | MODIFICATION | 248790.03 | 109086.2 |  | 0% | 2024-04-16 08:54 | 2024-04-22 10:39 | 2024-04-17 |  | 2024-12-13 |  | 240.6292 | 234.5563 | -45639 | 2024-05-07 13:52 | 2024-05-17 00:47 | 2024-06-05 08:54 | 7.4554 | -760.65 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-02-11 | 256 | [8 empty] | FOR AUDIT |  | 2024-12-28 | 107 | 2025-04-22 | 2025-04-14 | [8 empty] | Y | [7 empty] | N/A | CW9-0551, 376715 | 0 | 240.6292 | 0 | 240.6292 | 7.4554 | 230 |  | 14.5815 | 14.5815 | 3.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020411401', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-05-13 | 2024-05-13 |  | BIZ | X23114600974 | BP WATERWORKS, INC. | PASONG BUAYA II, PASONG BUAYA II, IMUS | IMUS CITY | DASMA | related to X23114600949 PAI Aug 22 night for cancellation all materials and activity transferred to mother wo | W/O ISSUE | AVECO | PCAN | Ronilo Gange Jr. | 48.4283 | #N/A | 61 | NEW | 381605.65 | 38620.57 |  | 0% | 2024-05-09 15:24 | 2024-05-10 16:07 | 2024-05-13 |  |  |  | -45421.6417 | -45422.6715 | 0 | #N/A | #N/A | 2024-06-28 15:24 | #N/A | 0 | #N/A | 34 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2024-05-14 |  | 0 | -45421.6417 | 0 | -45421.6417 | #N/A | 0 |  | #N/A | #N/A | 0 | 434.3583 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23114600974', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2024-05-22 | 2024-05-20 |  | HMB | R23109971 | DOMINGO ALVIN LUY | COUNTRY, COUNTRY HOMES, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 34.9061 | 34.91 | 0 | RELOC | 72927.67 | 28109.38 |  | 0% | 2024-05-14 15:01 | 2024-05-17 14:08 | 2024-05-20 |  |  |  | -45426.6257 | -45429.5889 | 0 | 2024-06-02 09:36 | 2024-06-11 04:57 | 2024-07-03 15:01 | -1564.6949 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [7 empty] | N/A | DS1-2355 | 0 | -45426.6257 | 0 | -45426.6257 | -1564.6949 | 0 |  | 15.2373 | 15.2373 | 0 | 429.3743 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23109971', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-05-30 | 2024-05-24 |  | HMB | X24030775968 | JOEBETH R DE CASTRO | SUNFLOWER, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Actual Completion on Site (11/13/24) | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 117.5764 | 117.58 | 52 | MODIFICATION | 366253.75 | 86522.71 |  | 0% | 2024-05-21 12:56 | 2024-05-24 09:26 | 2024-05-24 |  |  |  | -45433.5389 | -45436.3931 | 0 | 2024-06-10 21:13 | 2024-06-20 02:37 | 2024-07-10 12:56 | -1459.6295 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-05-31 | CV8-0954, CV8-0954, 520939, CV8-0955 | 0 | -45433.5389 | 0 | -45433.5389 | -1459.6295 | 0 |  | 13.9899 | 13.9899 | 0 | 422.4611 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030775968', | ME155242 |  |  |  | SCHED | Isan Carlo Lazaro
2024-06-04 | 2024-06-18 |  | HMB | R23158337 | CROWN ASIA PROPERTIES, INC., | BLOCK 10, PONTICELLI GARDENS 2, BACOOR | BACOOR CITY | DASMA | waiting sched | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 16.6 | 16.6 | 0 | RELOC | 27199.3 | 13366.58 |  | 0% | 2024-05-22 17:15 | 2024-05-24 12:40 | 2024-06-10 |  | 2025-03-27 08:34 |  | 308.6382 | 306.8292 | -45743.3569 | 2024-06-10 11:50 | 2024-06-19 07:11 | 2024-07-11 17:15 | 10.6309 | -762.3893 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-26 08:34 | 151.6431 | [8 empty] | FOR AUDIT |  | 2025-04-11 08:34 | 2.6431 | 2025-03-27 | 2025-04-14 | [8 empty] | Y | [7 empty] | N/A | 151360 | 0 | 308.6382 | 0 | 308.6382 | 10.6309 | 125.6431 |  | 14.9586 | 14.9586 | 2.0941 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23158337', | ME166067 |  |  |  | FCOMP | RONILO GANGE JR.
2024-06-05 | 2024-06-03 |  | HMB | X24010242749 | JUDD MARQUEZ TE SEE | CUENCA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 71.4526 | 168.6 | 80 | MODIFICATION | 440474.35 | 72754.82 |  | 0% | 2024-05-28 10:33 | 2024-06-04 13:51 | 2024-05-30 |  | 2024-12-13 |  | 198.5604 | 191.4229 | -45639 | 2024-06-17 18:50 | 2024-06-27 00:14 | 2024-07-17 10:33 | 6.3791 | -760.65 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-02-11 | 256 | [8 empty] | NO COC |  | 2024-12-28 | #VALUE! | [10 empty] | Y | 2024-08-21 | [6 empty] | 2024-06-07 | CU9-1248, CU9-1247, 520342, CU9-1246 | 0 | 198.5604 | 0 | 198.5604 | 6.3791 | 230 |  | 13.7682 | 13.7682 | 3.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010242749', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
| 2024-06-04 |  | HMB | R23165909 | OREZA EDGARDO CHUA | V.P. CRUZ, PUROK 5, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | For coordination with metering; FOR RETIREMENT WITH FOREIGN ATTACHMET (CCTV) | W/O ISSUE | VJC | SCHED | Jenneth Madrid | 20.1265 | 30.03 | 0 | RELOC | 42896.3 | 24179.61 |  | 0% | 2024-05-29 14:13 | 2024-06-04 08:34 | 2024-05-31 |  |  |  | -45441.5924 | -45447.3569 | 0 | 2024-06-17 08:48 | 2024-06-26 04:09 | 2024-07-18 14:13 | -1565.2104 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [7 empty] | N/A | A8-0771 | 0 | -45441.5924 | 0 | -45441.5924 | -1565.2104 | 0 |  | 14.7218 | 14.7218 | 0 | 414.4076 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23165909', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-06-06 | 2024-06-03 |  | CBG | X24051549285 | DITO TELECOMMUNITY CORPORATION | BLOCK 1, AGUAHAN VILLAGE, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 6/17/2024 Encountered problem on pole location during digging (with waterline) Customer to re-route the line up to June 29, 2024 (customer reported that completed last July 6, 2024) 07/10/2024 Schedule of pole digging on July 11, 2024 07/15/2024 Digging completed Power interruption on July 17, 2024 07/16/2024 Cancelled PAI - hold by HOA, DITO to seek clearance and approval from HOA 08/01/2024 With on-going negotiation c/o DITO as per CRS 09/18/2024 CRS email that there will be a meeting with DITO and TBICAI on Sept 20, 2024 to secure work permit 10/01/2024 TBICAI approved schedule of pole digging on Oct 5 and 6, interruption on Oct 11, 2024 10/30/24 Request by Miguel De Guzma of CBG to cancel WO and Recreate ane WO | W/ ISSUE | ECOM | PCAN3 | Ronilo Gange Jr. | 60.3481 | #N/A | 31 | NEW | 1083160.62 | 74063.42 |  | 0% | 2024-05-30 09:53 | 2024-06-05 13:46 | 2024-05-30 |  |  |  | -45442.4118 | -45448.5736 | 0 | #N/A | #N/A | 2024-07-19 09:53 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-06-07 | DZ2-0507, 206703, DZ2-2249, DZ2-0153, 206703 | 0 | -45442.4118 | 0 | -45442.4118 | #N/A | 0 |  | #N/A | #N/A | 0 | 413.5882 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051549285', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2024-06-20 | 2024-06-18 |  | BIZ | R22573760 | KANE INDUSTRIAL CORP, | NIOG III, NIOG III, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 178.4244 | 336.15 | 0 | RELOC | 514955.42 | 143681.57 |  | 0% | 2024-05-31 16:43 | 2024-06-06 08:50 | 2024-06-03 | 2025-04-03 | 2025-04-04 |  | 307.3035 | 301.6319 | -45751 | 2024-06-23 04:02 | 2024-07-02 23:03 | 2024-07-20 16:43 | 9.0484 | -762.5167 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-06-03 | 144 | [8 empty] | NO COC |  | 2025-04-19 | #VALUE! | [10 empty] | N | [7 empty] | 2024-06-24 | CW6-2017, CW6-6093, CW6-8019, CW6-6092, CW6-8020, CW6-6090, CW6-1545 | 0 | 307.3035 | 0 | 307.3035 | 9.0484 | 118 |  | 12.5228 | 12.5228 | 1.9667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R22573760', | ME155242 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-06-20 | 2024-06-04 | Y | BIZ | X24010310203 | HSL - BRAILLE COLLEGE, INC., | DURIAN, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 7/11/24 - Joint Survey; resolved pole location but need additional phase/leg; only one phase is existing - pending release of conjunctive project | (R) W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 193.1311 | 206.16 | 136 | MODIFICATION | 846143.09 | 155556.72 |  | 0% | 2024-06-03 17:23 | 2024-06-07 09:31 | 2024-06-04 |  | 2025-03-31 10:02 |  | 300.6937 | 297.0215 | -45747.4181 | 2024-06-23 17:43 | 2024-07-02 21:00 | 2024-07-23 17:23 | 9.7994 | -762.457 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 2025-05-30 10:02 | 147.5819 | [8 empty] | MATERIAL BALANCING |  | 2025-04-15 10:02 | 0.58194 | 2025-03-31 | 2025-04-16 | [8 empty] | Y | 2025-04-02 | [6 empty] | 2024-06-24 | B8-5104, B8-5156, B8-5105, 520522, B8-6347 | 0 | 300.6937 | 0 | 300.6937 | 9.7994 | 121.5819 |  | 13.7617 | 13.7617 | 2.0264 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010310203', | ME166067 |  |  |  | FCOMP | Jenneth Madrid
2024-07-03 | 2024-06-26 |  | HMB | X24052001012 | VILLA LIGHT NEIGHBORHOOD ASSOCIATION INC. | BLOCK 10, VILLA LIGHT SUBD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Cancel/create new WO extension of facilities (18spans) -for joint survey target aug2024 For creation of new WO; design not applicable) re-survey on 9/17/2024 | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 736.3592 | #N/A | 225 | NEW | 4930562.97 | 592973.37 |  | 0% | 2024-06-20 22:04 | 2024-06-27 09:12 | 2024-06-26 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-08-09 22:04 | #VALUE! | #VALUE! | #N/A | 30 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [8 empty] | B8-6311, 122357, B8-5575, ALB1-1211, B8-6313, B8-6312, B8-6314, B8-6315, B8-5320, B8-6321, 212060, B8-6323, B8-6324, B8-6325, B8-6326, B8-6327, B8-6328, B8-6329, B8-6330, B8-6331, B8-6316, 212061, B86332, B8-6333, B8-6334, B8-6335, B8-6336, B8-6337, B8-6338, 512298 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24052001012', | ME185284 |  |  |  | CLOSED-CAN | RONILO GANGE JR.
2024-07-17 | 2024-06-28 |  | HMB | X24051821503 | CITY GOVERNMENT OF TAGUIG | SOUTH DAANG HARI, PUROK 10, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 61.6973 | 139.98 | 20 | MODIFICATION | 369106.47 | 49683.3 |  | 0% | 2024-06-25 10:18 | 2024-06-28 14:13 | 2024-06-27 |  |  |  | -45468.4292 | -45471.5924 | 0 | 2024-07-16 15:16 | 2024-07-26 02:11 | 2024-08-14 10:18 | -1408.7441 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-07-18 | DY2-8043, 086919 | 0 | -45468.4292 | 0 | -45468.4292 | -1408.7441 | 0 |  | 12.4108 | 12.4108 | 0 | 387.5708 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051821503', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-07-12 | 2024-07-12 |  | HMB | X24030740806 | REGIDOR HOOD OFRIN | MAIN, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Digging Prob. | W/ ISSUE | POWERHOUSE | INPRG | Isan Carlo Lazaro | 68.4635 | 147.7 | 45 | MODIFICATION | 389891.68 | 55131.92 |  | 0% | 2024-07-10 16:33 | 2024-07-12 12:37 | 2024-07-12 |  |  |  | -45483.6896 | -45485.5257 | 0 | 2024-07-31 21:31 | 2024-08-10 08:26 | 2024-08-29 16:33 | -1409.2169 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-07-12 | A6-0040, 520913 | 0 | -45483.6896 | 0 | -45483.6896 | -1409.2169 | 0 |  | 11.938 | 11.938 | 0 | 372.3104 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030740806', | ME185284 |  |  |  | INPRG | JSP
2024-07-16 | 2024-07-15 |  | HMB | X24062342140 | JOAN ANTONIO QUIMPO | BLOCK 19, ENLISTED PERSONNEL VIL 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | drainge issue; for creation of new WO due to major deisgn modif | W/ ISSUE | CHALLENGER | CAN | Jemuel Peralta | 356.4132 | #N/A | 28 | NEW | 1426938.62 | 287011.09 |  | 0% | 2024-07-11 08:38 | 2024-07-15 14:45 | 2024-07-12 |  | CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-08-30 08:38 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [20 empty] | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062342140', | ME185130 |  |  |  | CAN | RONILO GANGE JR.
2024-07-16 | 2024-07-16 |  | HMB | X24062236601 | LEIGH ANGELI ADARNA ANCHETA | MA. LOURDES ATIENZA, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | On Going 10/14/24 | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 358.343 | 358.34 | 41.5 | MODIFICATION | 1396868.56 | 288566.21 | 50215.24 | 17.4% | 2024-07-11 14:52 | 2024-07-15 14:44 | 2024-07-12 |  | 2025-01-30 |  | 202.3806 | 198.3861 | -45687 | 2024-08-03 02:11 | 2024-08-12 21:12 | 2024-08-30 14:52 | 5.959 | -761.45 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-14 | 36 | 2025-04-25 | 2025-03-22 | [8 empty] | Y | 2025-02-19 | [8 empty] | 0 | 202.3806 | 0 | 202.3806 | 5.959 | 182 |  | 11.3179 | 11.3179 | 3.0333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062236601', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-07-29 | 2024-07-26 |  | CBG | X24051926078 | DITO TELECOMMUNITY CORPORATION | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | SSP and meter (08/16/2024) - cancelled due to refusal on digging of pole location 8/15/24 - For public consultation/consent of residents c/o DITO (Option 1 - As designed), For redesign (Option 2) 8/22/24 - For revision of design (Option 2) | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 112.0971 | #N/A | 31 | NEW | 650720.06 | 90269.18 |  | 0% | 2024-07-23 15:44 | 2024-07-26 13:13 | 2024-07-26 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-09-11 15:44 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-07-29 | B7-0676, B7-8108, 522135, B7-0187, B7-8109, 198114 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051926078', | ME185284 |  |  |  | CLOSED-CAN | Jenneth Madrid
2024-08-03 | 2024-07-26 |  | HMB | X24041183168 | ZENAIDA IGNACIO REYES | DIMASALANG, HAGONOY, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | pole location issue; coordinated with DJJ | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 85.9905 | 15.9 | 2 | MODIFICATION | 199611.03 | 69245.76 |  | 0% | 2024-07-24 14:44 | 2024-07-30 14:28 | 2024-07-26 |  | 2025-03-17 |  | 235.3861 | 229.3972 | -45733 | 2024-08-12 09:19 | 2024-08-21 04:40 | 2024-09-12 14:44 | 8.1077 | -762.2167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-16 | 162 | [8 empty] | FOR AUDIT |  | 2025-04-01 | 14 | 2025-03-17 | 2025-04-15 | [8 empty] | Y | [7 empty] | 2024-08-06 | B8-8074, B9-0058, B9-5158, B9-5189, B8-0012 | 0 | 235.3861 | 0 | 235.3861 | 8.1077 | 136 |  | 12.7922 | 12.7922 | 2.2667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041183168', | ME185284 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-08-03 | 2024-07-31 |  | HMB | X24051525654 | FERHN RUBIA BALATUCAN | GARNET, PARANAQUE GREEN HEIGHTS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For scheduling | W/ ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 187.8665 | 266.15 | 42 | MODIFICATION | 564043.26 | 119793.67 |  | 0% | 2024-07-28 00:31 | 2024-08-01 14:26 | 2024-07-30 |  |  |  | -45501.0215 | -45505.6014 | 0 | 2024-08-18 21:22 | 2024-08-28 12:31 | 2024-09-16 00:31 | -1372.253 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-08-06 | CY9-0494, 035976, CY9-0495, CY9-8040, 521718, CY9-0496, CY9-0642 | 0 | -45501.0215 | 0 | -45501.0215 | -1372.253 | 0 |  | 11.0978 | 11.0978 | 0 | 354.9785 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051525654', | ME166067 |  |  |  | SCHED | RONILO GANGE JR.
2024-08-06 | 2024-08-07 |  | HMB | X24072779669 | MA FATIMA FESTIN PERDIDO | TALIM, TIERRA NUEVA SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For Update |  | AVECO | SCHED | Ronilo Gange Jr. | 53.587 | 131.87 | 130.2 | MODIFICATION | 406130.01 | 42774.69 |  | 0% | 2024-08-01 14:27 | 2024-08-05 14:40 | 2024-08-07 |  |  |  | -45505.6021 | -45509.6111 | 0 | 2024-08-21 01:09 | 2024-08-30 00:49 | 2024-09-20 14:27 | -1520.4997 | 0 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | 2025-06-05 | [6 empty] | 2024-08-06 | CV9-8008, 515260 | 0 | -45505.6021 | 0 | -45505.6021 | -1520.4997 | 0 |  | 12.1424 | 12.1424 | 0 | 350.3979 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072779669', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-08-05 | 2024-08-03 |  | CBG | X24073004063 | RODOLFO C ADRIAS | MOLINO BLVD, MOLINO II, BACOOR | BACOOR CITY | DASMA | For Update |  | AVECO | FCOMP | Ronilo Gange Jr. | 16.38 | 16.38 | 0 | TERMINATION | 24865.03 | 13198.45 |  | 0% | 2024-08-01 15:29 | 2024-08-03 09:45 | 2024-08-03 |  | 2024-12-13 |  | 133.3549 | 131.5938 | -45639 | 2024-08-20 10:04 | 2024-08-29 05:25 | 2024-09-20 15:29 | 4.5933 | -760.65 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-02-11 | 256 | [8 empty] | NO COC |  | 2024-12-28 | #VALUE! | [10 empty] | Y | [7 empty] | N/A |  | 0 | 133.3549 | 0 | 133.3549 | 4.5933 | 230 |  | 12.5156 | 12.5156 | 3.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24073004063', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-08-09 | 2024-08-15 |  | HMB | X24062436826 | DIANE VALERIE ZIGA GARCIA | MA. CRISTINA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For Update |  | AVECO | FCOMP | Ronilo Gange Jr. | 335.6618 | 727.07 | 82.4 | MODIFICATION | 1355923.61 | 269947.83 |  | 0% | 2024-08-05 13:26 | 2024-08-08 09:46 | 2024-08-08 |  | 2025-05-27 06:14 |  | 294.7 | 291.8528 | -45804.2597 | 2024-08-29 06:16 | 2024-09-08 09:10 | 2024-09-24 13:26 | 8.2776 | -763.4043 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 52 | 2025-07-26 06:14 | 90.7403 | [8 empty] | NO COC |  | 2025-06-11 06:14 | #VALUE! | [10 empty] | Y | 2025-05-22 | [6 empty] | 2024-08-10 | CT9-0228, CT9-8069, CT9-8068, CT9-8070, CT9-0230, CT9-8071, CT9-8072, CT9-0077, 522617 | 0 | 294.7 | 0 | 294.7 | 8.2776 | 64.7403 |  | 10.096 | 10.096 | 1.079 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062436826', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-08-09 | 2024-08-05 |  | HMB | X24051525908 | SUZIE CHEN TAN | HEMLOCK, MGV PHASE 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | WAITING FOR SCHED OF PAI (waiting to release conj. Planned MN WO follow up approval of endorsement letter to HOA pres thru BC | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 66.6099 | 103.45 | 68 | MODIFICATION | 319649.19 | 53639.2 |  | 0% | 2024-08-05 15:55 | 2024-08-08 09:58 | 2024-08-08 |  | 2025-04-16 |  | 253.3368 | 250.5847 | -45763 | 2024-08-26 00:12 | 2024-09-04 05:36 | 2024-09-24 15:55 | 8.1389 | -762.7167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-06-15 | 132 | [8 empty] | FOR AUDIT |  | 2025-05-01 | 60 | 2025-04-16 | 2025-06-30 | [8 empty] | Y | 2025-04-16 | [6 empty] | 2024-08-10 | DY1-0078, DY1-0079, 521753, DY1-0077 | 0 | 253.3368 | 0 | 253.3368 | 8.1389 | 106 |  | 11.5443 | 11.5443 | 1.7667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051525908', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-08-13 | 2024-08-07 |  | CBG | X24072565971 | DITO TELECOMMUNITY CORPORATION | DOÑA SOLEDAD, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for cancellation due to third party refusal, pending surplus return of materials | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 96.6433 | #N/A | 22 | NEW | 632652.96 | 77832.37 |  | 0% | 2024-08-07 09:01 | 2024-08-12 07:32 | 2024-08-16 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-09-26 09:01 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | N/A | DZ1-2587, 107768 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072565971', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-08-13 | 2024-08-08 |  | HMB | X23114603408 | GILBERT CLAIRE O REALICA | APO, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 92.7618 | 92.76 | 100 | MODIFICATION | 448826.37 | 74723.06 | 56897.91 | 76.15% | 2024-08-08 13:08 | 2024-08-13 07:44 | 2024-08-14 | 2025-02-11 | 2025-02-11 |  | 186.4528 | 181.6778 | -45699 | 2024-08-27 20:21 | 2024-09-05 19:04 | 2024-09-27 13:08 | 6.2707 | -761.65 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | MATERIAL BALANCING | PARTIALLY BILLED | 2025-02-26 | #VALUE! |  |  | 2025-05-30 | ECI | Y | [5 empty] | Y | 2025-02-11 | [6 empty] | 2024-08-14 | DT1-8041, 519768 | 0 | 186.4528 | 0 | 186.4528 | 6.2707 | 170 |  | 11.9881 | 11.9881 | 2.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23114603408', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-08-13 | 2024-08-18 |  | HMB | X24051519918 | STO. CRISTO PROPERTIES & HOLDINGS CORP. | PASCUAL, PARANAQUE GREEN HEIGHTS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | With customer opposition on DT pole; With new released work order X24093771340; to transfer all materials and SI to X24093771340 for cancellation | FOR CANCELLATION | CHALLENGER | SCHED | Isan Carlo Lazaro | 58.3675 | 139.17 | 114 | NEW | 434654.9 | 47026.09 |  | 0% | 2024-08-08 16:55 | 2024-08-13 09:16 | 2024-08-12 |  |  |  | -45512.7049 | -45517.3861 | 0 | 2024-08-28 03:37 | 2024-09-06 03:17 | 2024-09-27 16:55 | -1520.737 | 0 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-08-14 | CY9-1108, CY9-8039, 521704 | 0 | -45512.7049 | 0 | -45512.7049 | -1520.737 | 0 |  | 11.9051 | 11.9051 | 0 | 343.2951 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051519918', | ME166067 |  |  |  | PCAN3 | Jenneth Madrid
2024-08-13 | 2024-08-08 |  | BIZ | X23114429361 | GOLDSERVE HOLDING COMPANY INC. | MIA, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | conjunct to UG wo X23114429217; for sched of digging | W/ ISSUE | VJC | FCOMP | Jenneth Madrid | 11.8408 | 11.84 | 16 | NEW | 132843.69 | 9535.1 |  | 0% | 2024-08-08 17:05 | 2024-08-13 07:33 | 2024-08-16 |  | 2025-03-05 |  | 208.2882 | 203.6854 | -45721 | 2024-08-27 11:40 | 2024-09-05 07:01 | 2024-09-27 17:05 | 7.1744 | -762.0167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-04 | 174 | [8 empty] | FOR AUDIT |  | 2025-03-20 | 32 | 2025-03-07 | 2025-04-21 | [8 empty] | Y | 2025-04-07 | [6 empty] | 2024-08-14 | B5-8038, 519608 | 0 | 208.2882 | 0 | 208.2882 | 7.1744 | 148 |  | 12.2721 | 12.2721 | 2.4667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23114429361', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-08-15 | 2024-08-22 |  | BIZ | R23075417 | CONGBALAY, SIMPLICIO C, | N. LOPEZ, LOPEZ VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Completed | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 81.4201 | 159.7 | 0 | RELOC | 237016.01 | 65565.56 |  | 0% | 2024-08-12 14:52 | 2024-08-15 13:43 | 2024-08-14 |  | 2025-04-07 |  | 237.3806 | 234.4285 | -45754 | 2024-09-02 19:50 | 2024-09-12 06:45 | 2024-10-01 14:52 | 7.3547 | -762.5667 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-06-06 | 141 | [8 empty] | NO COC |  | 2025-04-22 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-08-15 | CY9-8035, 362095 | 0 | 237.3806 | 0 | 237.3806 | 7.3547 | 115 |  | 10.9178 | 10.9178 | 1.9167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23075417', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-08-21 | 2024-08-22 | Y | HMB | R23354122 | MANAHAN, MELANIE V., | SAPLUNGAN, MEADOWOOD EXEC. VILLAGE PHASE 3B, BACOOR | BACOOR CITY | DASMA | Hold Execution as per BC Mam Grace Alarcon due wrong polcaation as per developer | W/ ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 21.84 | 85.64 | 0 | RELOC | 114511.06 | 17587.5 |  | 0% | 2024-08-14 09:32 | 2024-08-20 08:32 | 2024-08-20 |  | 2025-05-22 |  | 280.6028 | 274.6444 | -45799 | 2024-09-03 11:35 | 2024-09-12 15:20 | 2024-10-03 09:32 | 9.1162 | -763.3167 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [10 empty] | N | [7 empty] | 2024-08-24 | CV6-8051, CV6-6382 | 0 | 280.6028 | 0 | 280.6028 | 9.1162 | 70 |  | 11.3904 | 11.3904 | 1.1667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23354122', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-09-16 | OK |  | CBG | R23208322 | SM DEVELOPMENT CORPORATION | BLDG 10, FIELD RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For resched of PAI (initially sched last 9/17/2024) due to customer's request to relocate involved pole to another location | W/ ISSUE | VJC | FCOMP | Jenneth Madrid | 142.475 | 220.76 | 0 | RELOC | 371967.81 | 114354.6 |  | 0% | 2024-08-19 16:42 | 2024-08-22 13:21 | 2024-08-22 |  | 2025-02-22 |  | 186.3042 | 183.4437 | -45710 | 2024-09-10 13:33 | 2024-09-20 04:42 | 2024-10-08 16:42 | 5.6187 | -761.8333 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-04-23 | 185 | [8 empty] | NO COC |  | 2025-03-09 | #VALUE! | [10 empty] | N | [8 empty] | CZ8-5093, CZ8-5094 | 0 | 186.3042 | 0 | 186.3042 | 5.6187 | 159 |  | 10.4139 | 10.4139 | 2.65 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23208322', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-08-26 | 2024-09-09 |  | HMB | X24072536492 | CITY GOV'T OF LAS PIÑAS | BF CARNIBAL PARK, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 14.8103 | 14.81 | 32 | MODIFICATION | 143928.54 | 11926.44 |  | 0% | 2024-08-20 13:46 | 2024-08-22 14:06 | 2024-08-24 |  | 2025-01-06 |  | 138.4264 | 136.4125 | -45663 | 2024-09-08 08:21 | 2024-09-17 03:42 | 2024-10-09 13:46 | 4.768 | -761.05 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-07 | 232 | [8 empty] | NO COC |  | 2025-01-21 | #VALUE! | [10 empty] | Y | 2024-12-17 | [6 empty] | 2024-08-26 | CV7-0697, 522656 | 0 | 138.4264 | 0 | 138.4264 | 4.768 | 206 |  | 11.8636 | 11.8636 | 3.4333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072536492', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-08-28 | 2024-08-21 |  | BIZ | X24051932778 | KEN VANN JOSPEH K REYES | ALABANG-ZAPOTE, TALON I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  | W/O ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 49.2716 | 84.25 | 68 | NEW | 401921.51 | 39677.16 | 33772.88 | 85.12% | 2024-08-21 15:11 | 2024-08-27 10:45 | 2024-08-28 | 2025-03-08 | 2025-03-08 |  | 198.3674 | 192.5521 | -45724 | 2024-09-09 22:24 | 2024-09-18 21:07 | 2024-10-10 15:11 | 6.6714 | -762.0667 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-07 | 171 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-03-23 | -68 | 2025-01-23 | 2025-01-14 | [8 empty] | Y | 2025-03-11 | [6 empty] | 2024-09-05 | CV8-8058, 522145 | 0 | 198.3674 | 0 | 198.3674 | 6.6714 | 145 |  | 11.548 | 11.548 | 2.4167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051932778', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-02 | OK |  | HMB | R23165916 | POKAAN ALIREZA LUMBAYA | JOLO, MAHARLIKA VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for sched of pole erection | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 27.2133 | 104.1 | 0 | RELOC | 137707.32 | 21914.3 |  | 0% | 2024-08-22 14:43 | 2024-08-30 13:30 | 2024-08-27 | 2025-03-17 | 2025-03-17 |  | 206.3868 | 198.4375 | -45733 | 2024-09-12 19:41 | 2024-09-22 06:36 | 2024-10-11 14:43 | 6.3945 | -762.2167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-05-16 | 162 | [8 empty] | FOR AUDIT |  | 2025-04-01 | 108 | 2025-03-17 | 2025-07-18 | [8 empty] | N | [7 empty] | 2024-09-05 | A8-0212, A8-1517 | 0 | 206.3868 | 0 | 206.3868 | 6.3945 | 136 |  | 10.6081 | 10.6081 | 2.2667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23165916', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-08-30 | 2024-08-22 | Y | HMB | R22419641 | ONOFRE, CORAZON VILLA, | GLORIA DIAZ, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | For Schedule PAI :sadang:done digging and pole erection | Drainage Diversion | ECOM | FCOMP | Ronilo Gange Jr. | 153.4688 | 236.63 | 0 | RELOC | 418004.67 | 123585.18 |  | 0% | 2024-08-22 14:49 | 2024-08-30 13:25 | 2024-08-28 | 2025-07-31 | 2025-07-31 |  | 342.3826 | 334.441 | -45869 | 2024-09-13 11:40 | 2024-09-23 02:49 | 2024-10-11 14:49 | 10.3258 | -764.4833 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-09-29 | 26 | [8 empty] | FOR AUDIT |  | 2025-08-15 | 0 | 2025-08-01 | 2025-08-15 | [8 empty] | N | [7 empty] | 2024-09-05 | CW7-0175, CW7-0174, CW7-0173 | 0 | 342.3826 | 0 | 342.3826 | 10.3258 | 0 |  | 10.3258 | 10.3258 | 0 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R22419641', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-09-05 | 2024-08-28 |  | REL | P2407173485 | RELOCATION OF POLE AFFECTED BY ROAD WIDENING PROJECT IN TRAMO, ALIMA, BACOOR | ALIMA I ALIMA I ALIMA I BACOOR CAVITE | BACOOR CITY | DASMA | Actual Completion on Site (10/29/24) | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 2347.6291 | 3657.11 | 0 | RELOC | 3380199.52 | 1302517.39 |  | 0% | 2024-08-28 07:59 | 2024-09-03 06:44 | 2024-09-04 |  | 2024-12-13 |  | 106.6674 | 100.7194 | -45639 | 2024-09-23 19:24 | 2024-10-04 16:03 | 2024-10-17 07:59 | 2.7141 | -760.65 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-02-11 | 256 | [8 empty] | NO COC |  | 2024-12-28 | #VALUE! | [10 empty] | N | [7 empty] | 2024-09-05 | CX5-2078, CX5-0353, CX5-8009, CX5-8009, CX5-0024, CX5-8010, CX5-0025, CX5-8011, CX5-0356, CX5-8012, CX5-8012, CX5-8013, CX5-0358, CX5-8014, 044767, CX5-0028 | 0 | 106.6674 | 0 | 106.6674 | 2.7141 | 230 |  | 8.5663 | 8.5663 | 3.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2407173485', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-09 | 2024-08-30 |  | HMB | X23104092125 | PHILIP SIGFRID ALFARO FORTUN | SAN AGUSTIN, SUSANA HTS SUBD VILL 6, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | Pole location issue,sadang:Kabit bahay na foreigner, ayaw mag pahukay…Need Po muna makipag sangguni ni sir rommel sa engr on site dun, pra sa hukay, kakain dun sa lot mismo ni owner mag huhukay, hndi na sa boundary lot, pra hndi na mkapag reklamu SI bisaya boss, Hindi boss vic, pero na resolve na ngayon Yan, Pina usod ng konti hukay pra mkaiwas lng dyn sa tubo | W/ ISSUE | ECOM | CLOSED-CAN | Ronilo Gange Jr. | 96.3175 | #N/A | 80 | NEW | 402375.37 | 77586.83 |  | 0% | 2024-08-30 14:29 | 2024-09-06 12:53 | 2024-09-04 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-10-19 14:29 | #VALUE! | #VALUE! | #N/A | 34 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-09-12 | DQ1-0437, DQ1-8004, DQ1-2066, DQ1-2067, 516118, DQ1-5020 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23104092125', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2024-09-06 | 2024-08-30 |  | HMB | X24052000319 | CITY GOVERNMENT OF TAGUIG | MAULENG CREEK , LOWER BICUTAN , TAGUIG | TAGUIG CITY | PARAÑAQUE | On Going Digging | W/O ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 713.3285 | 713.33 | 45 | NEW | 2734702.55 | 572539.79 | 92159.04 | 16.1% | 2024-08-30 15:54 | 2024-09-06 12:30 | 2025-01-20 | 2025-03-10 | 2025-03-05 |  | 186.3375 | 179.4792 | -45721 | 2024-09-24 11:56 | 2024-10-04 22:05 | 2024-10-19 15:54 | 5.0208 | -762.0167 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-05-04 | 174 | [8 empty] | ON GOING MAT RETURN | PARTIALLY BILLED | 2025-03-20 | -10 | 2025-04-25 | 2025-03-10 | 2025-07-15 | RCL | Y |  |  |  | 2025-08-06 | NVP | Y | [7 empty] | 2025-01-20 | DZ2-8070, DZ2-8071, DZ2-8072, DZ2-8073, DZ2-8074, DZ2-8075, DZ2-8076, DZ2-8077, DZ2-8078, DZ2-8079, TLN-522415,DZ2-8080,DZ2-8081,DZ2-8082,DZ2-8083 | 0 | 186.3375 | 0 | 186.3375 | 5.0208 | 148 |  | 9.0085 | 9.0085 | 2.4667 |  | REV |  | 2025-08-06 | 263774.28 | NTC ISSUED | 2025-08-14 |  | 12 |  |  |  | 'X24052000319', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-06 | 2024-08-30 | Y | HMB | X24052000269 | CITY GOVERNMENT OF TAGUIG | MAULING CREEK, PUROK 6D, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | On Going Execution | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 831.7975 | 2323.61 | 45 | NEW | 3487719.57 | 668695.04 |  | 0% | 2024-08-30 16:13 | 2024-09-06 12:33 | 2024-09-04 |  | 2025-05-09 |  | 251.3243 | 244.4771 | -45786 | 2024-09-26 03:38 | 2024-10-07 00:17 | 2024-10-19 16:13 | 6.3948 | -763.1 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-07-08 | 109 | [8 empty] | NO COC |  | 2025-05-24 | #VALUE! | [10 empty] | Y | 2025-05-27 | [6 empty] | 2024-09-07 | DZ2-8082, DZ2-8083, DZ2-8088, DZ2-8089, DZ2-8090, DZ2-8091, DZ2-8092, DZ2-8093, DZ2-8094, DZ2-8095, DZ2-8096, DZ2-8097, DZ2-8098, DZ2-8099, DZ2-8100, DZ2-8106, DZ2-8107, DZ2-8108, DZ2-8109, DZ2-8110, 522536, DZ2-8111 | 0 | 251.3243 | 0 | 251.3243 | 6.3948 | 83 |  | 8.5067 | 8.5067 | 1.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24052000269', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-09-13 | 2024-09-07 |  | CBG | X24041115574 | DITO TELECOMMUNITY CORPORATION | GULAMAN, STO. NINO, TAGUIG CITY | PARAÑAQUE CITY | PARAÑAQUE | 3rd party refusal; for survey on 10/29 with design, PROW, and BC | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 106.5369 | #N/A | 20 | NEW | 364183.84 | 85791.63 |  | 0% | 2024-09-02 10:05 | 2024-09-09 13:15 | 2024-09-07 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-10-22 10:05 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-09-13 | B7-0935, B7-0934, 521368, B7-8099, B7-8100 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041115574', | ME185284 |  |  |  | CLOSED-CAN | Jenneth Madrid
2024-09-10 | 2024-09-07 |  | HMB | R23301679 | JAVIER, ROSALINA | GENESIS, VILLANUEVA SUBD, BACOOR | BACOOR CITY | DASMA | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 16.9341 | 16.93 | 0 | RELOC | 30613.7 | 13636.79 |  | 0% | 2024-09-03 09:42 | 2024-09-09 13:24 | 2024-09-07 |  |  |  | -45538.4042 | -45544.5583 | 0 | 2024-09-22 04:17 | 2024-09-30 23:38 | 2024-10-23 09:42 | -1568.545 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-09-12 | CV5-0683, 212309 | 0 | -45538.4042 | 0 | -45538.4042 | -1568.545 | 0 |  | 11.3872 | 11.3872 | 0 | 317.5958 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23301679', | ME155242 |  |  |  | SCHED | Isan Carlo Lazaro
2024-09-13 | 2024-09-07 |  | HMB | X24062117779 | CITY GOVERNMENT OF PARAÑAQUE | BENIGNO AQUINO SR., BF HOMES, PARANAQUE | MUNTINLUPA CITY | PARAÑAQUE | For scheduling | W/ ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 64.6842 | 64.68 | 44 | MODIFICATION | 375766.47 | 52088.52 |  | 0% | 2024-09-06 06:45 | 2024-09-12 15:04 | 2024-09-07 |  | 2025-04-04 |  | 209.7188 | 203.3722 | -45751 | 2024-09-26 08:48 | 2024-10-05 12:33 | 2024-10-26 06:45 | 6.8133 | -762.5167 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-06-03 | 144 | [8 empty] | FOR AUDIT |  | 2025-04-19 | 20 | 2025-04-14 | 2025-05-09 | [8 empty] | Y | [7 empty] | 2024-09-13 | CY8-8037, 522308 | 0 | 209.7188 | 0 | 209.7188 | 6.8133 | 118 |  | 10.6469 | 10.6469 | 1.9667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062117779', | ME166067 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-16 | 2024-09-12 |  | HMB | R23563800 | WOODRIDGE PROPERTIES, INC., | BLOCK 4, DANAROSE RESIDENCES, BACOOR | LAS PIÑAS CITY | PARAÑAQUE | sadang:Ito Po ay Thursday morning nka sched, pero nag aantay pdin ako ng response kung okey Kay subdivision na gumawa ng gabi mas mapapaaga execution |  | ECOM | FCOMP | Ronilo Gange Jr. | 16.93 | 16.93 | 0 | RELOC | 117785.94 | 13633.28 |  | 0% | 2024-09-06 14:39 | 2024-09-12 15:08 | 2024-09-12 |  | 2025-04-30 |  | 235.3896 | 229.3694 | -45777 | 2024-09-25 09:14 | 2024-10-04 04:35 | 2024-10-26 14:39 | 8.1079 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | FOR AUDIT |  | 2025-05-15 | 12 | 2025-04-29 | 2025-05-27 | [8 empty] | N | [7 empty] | 2024-09-17 | CS7-8097 | 0 | 235.3896 | 0 | 235.3896 | 8.1079 | 92 |  | 11.2768 | 11.2768 | 1.5333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23563800', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-09-16 | 2024-09-12 |  | HMB | X24072759958 | CITY GOVERNMENT OF TAGUIG | PRES. QUIRINO EXT, ZONE 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for sched of digging / request for drainage diversion | W/ ISSUE | VJC | FCOMP | Jenneth Madrid | 534.4512 | 1078.79 | 23 | NEW | 2000088.16 | 429627.22 | 93509.88 | 21.77% | 2024-09-10 09:30 | 2024-09-13 13:54 | 2024-09-11 | 2025-05-31 | 2025-05-31 |  | 262.6043 | 259.4208 | -45808 | 2024-10-06 20:55 | 2024-10-17 17:34 | 2024-10-30 09:30 | 6.6818 | -763.4667 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | FOR AUDIT |  | 2025-06-15 | 43 | 2025-05-31 | 2025-07-28 | [8 empty] | Y | 2025-05-29 | [6 empty] | 2024-09-17 | A8-1197, A8-8086, A8-8087, A8-8088, A8-8089, A8-8090, A8-8091, A8-8092, A8-8093, A8-8094, 522932, A8-1189 | 0 | 262.6043 | 0 | 262.6043 | 6.6818 | 61 |  | 8.2339 | 8.2339 | 1.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072759958', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-09-20 | 2024-09-18 | Y | BIZ | X24072692499 | HSL - BRAILLE COLLEGE, INC., | DURIAN, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | pole location / with existing drainage | W/ ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 550.2171 | 550.22 | 136 | MODIFICATION | 2501537.66 | 443077.47 |  | 0% | 2024-09-11 10:50 | 2024-09-16 14:35 | 2024-09-13 |  | 2025-03-31 10:12 |  | 200.9738 | 195.8174 | -45747.425 | 2024-10-03 23:36 | 2024-10-13 19:00 | 2024-10-31 10:50 | 5.9036 | -762.4571 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 2025-05-30 10:12 | 147.575 | [8 empty] | ON GOING MAT RETURN |  | 2025-04-15 10:12 | 0.575 | 2025-03-31 | 2025-04-16 | 2025-06-16 | AGD | Y | Y |  |  | 2025-06-25 | NVP | N | [7 empty] | 2024-09-21 | B8-0477, B8-8115, B8-8116, B8-8117, B8-5547, B8-5546, B8-1271, B8-1272, B8-8118, B8-1273, B8-8119, B8-1274,B8-1278, B8-8120, B8-1276, B8-8121, B8-5104, B8-0428, B8-1277 | 0 | 200.9738 | 0 | 200.9738 | 5.9036 | 121.575 |  | 9.4749 | 9.4749 | 2.0262 |  | NON-REV |  | 2025-06-25 | 334982.87 | NTC ISSUED | 2025-06-25 |  | 62 | 2025-07-09 | 86751.01 | 2025-07-15 | 'X24072692499', | ME166067 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-24 | 2024-09-17 |  | HMB | X24030736106 | ALFRED REYES FRANCIA | BLOCK 29, SOLVIENTO VILLAS PH 3, BACOOR | BACOOR CITY | DASMA | On Going Execution SOLVIENTO VILLAS Projects | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 262.641 | 307.04 | 4.5 | NEW | 840479.63 | 211499.83 |  | 0% | 2024-09-11 16:55 | 2024-09-16 14:18 | 2024-09-13 |  | 2025-01-10 |  | 120.2954 | 115.4042 | -45667 | 2024-10-04 04:14 | 2024-10-13 23:15 | 2024-10-31 16:55 | 3.542 | -761.1167 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-03-11 | 228 | [8 empty] | NO COC |  | 2025-01-25 | #VALUE! | [10 empty] | Y | 2025-01-10 | [6 empty] | 2024-09-24 | CT6-8001, CT6-8018, 518990, CT6-8019, 520898, CT6-8029, CT6-8030, CT6-6202, CT6-8022, CT6-6201, CT6-8020, CT6-8021 | 0 | 120.2954 | 0 | 120.2954 | 3.542 | 202 |  | 9.4898 | 9.4898 | 3.3667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030736106', | ME155242 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-09-24 | 2024-09-17 |  | HMB | X24030736254 | NEW PACIFIC RESOURCES MANAGEME | BLOCK 36, SOLVIENTO VILLAS PH 3, BACOOR | BACOOR CITY | DASMA | On Going Execution SOLVIENTO VILLAS Projects | W/O ISSUE | AVECO | TECO | Ronilo Gange Jr. | 954.8506 | 1314.55 | 295.5 | NEW | 3368500.83 | 768924.13 | 808259.64 | 105.1% | 2024-09-11 22:25 | 2024-09-16 14:27 | 2024-09-13 | 2025-01-10 | 2025-01-10 | 2025-06-30 13:15 | 120.0662 | 115.3979 | 171.5521 | 2024-10-04 12:03 | 2024-10-14 07:41 | 2024-10-31 22:25 | 3.5219 | 2.8592 | 50 | 30 | 25.5682 | 32.3864 | 22.5682 | 60 | 57 | 52 | 2025-03-11 | 228 | [8 empty] | PAID |  | 2025-01-25 | 10 | 2025-01-10 | 2025-02-04 | 2025-06-06 | AGD |  |  |  |  | 2025-06-19 | NVP | Y | 2025-01-10 | [6 empty] | 2024-09-24 | DV1-0639, DV1-8038, DV1-8039, DV1-8040, 521480, DV1-0813 | 0 | 120.0662 | 0 | 120.0662 | 3.5219 | 202 |  | 9.4473 | 9.4473 | 3.3667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030736254', | ME155242 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-10-17 | 2024-09-17 |  | BIZ | X24072590693 | HARD DISCOUNT PHILIPPINES, INC. | HOLY FAMILY AVE, HOLY FAMILY VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | waiting for schedule, crew diverted to NAIA | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 34.987 | 34.99 | 19 | NEW | 278461.54 | 28174.13 |  | 0% | 2024-09-12 14:51 | 2024-09-17 14:44 | 2024-09-17 |  | 2025-01-24 |  | 133.3812 | 128.3861 | -45681 | 2024-10-01 09:26 | 2024-10-10 04:47 | 2024-11-01 14:51 | 4.5942 | -761.35 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-25 | 214 | [8 empty] | ON GOING MAT RETURN |  | 2025-02-08 | 41 | 2025-01-24 | 2025-03-21 | 2025-05-21 | ECI | Y |  |  |  | 2025-06-10 | NVP | Y | 2025-01-23 | [6 empty] | 2024-10-17 | DZ2-8112, 522696 | 0 | 133.3812 | 0 | 133.3812 | 4.5942 | 188 |  | 11.0698 | 11.0698 | 3.1333 |  | REV |  | 2025-06-10 | 1219.25 | NTC ISSUED | 2025-06-10 |  | 77 | 2025-07-09 | 1219.25 | 2025-07-15 | 'X24072590693', | ME166067 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-25 | 2024-09-20 |  | BIZ | X24030695765 | MITHCAH BIBLE BAPTIST CHURCH INC. | ST. CECILLE, FATIMA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | pole location issue | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 66.9831 | 66.98 | 30 | NEW | 390162.58 | 53940.12 | 18124.07 | 33.6% | 2024-09-16 17:13 | 2024-09-20 14:20 | 2024-09-20 |  | 2025-01-24 |  | 129.2827 | 125.4028 | -45681 | 2024-10-06 19:16 | 2024-10-15 23:01 | 2024-11-05 17:13 | 4.2001 | -761.35 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-03-25 | 214 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-08 | 6 | 2025-01-23 | 2025-02-14 | [8 empty] | Y | 2025-01-23 | [6 empty] | 2024-09-28 | CY7-5947, CY7-5948, CY7-8077, 520597 | 0 | 129.2827 | 0 | 129.2827 | 4.2001 | 188 |  | 10.3079 | 10.3079 | 3.1333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030695765', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-09-25 | 2024-09-19 |  | HMB | R23158435 | CROWN ASIA PROPERTIES, INC., HMB | BLOCK 4, PONTICELLI, BACOOR | BACOOR CITY | DASMA | For Update Truss Guy Ony |  | AVECO | SCHED | Ronilo Gange Jr. | 18.31 | 18.31 | 0 | RELOC | 41797.83 | 14748.76 |  | 0% | 2024-09-18 15:29 | 2024-09-24 12:53 | 2024-09-19 |  |  |  | -45553.6454 | -45559.5368 | 0 | 2024-10-07 10:04 | 2024-10-16 05:25 | 2024-11-07 15:29 | -1569.07 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [7 empty] | N/A | CR8-2143 | 0 | -45553.6454 | 0 | -45553.6454 | -1569.07 | 0 |  | 10.8622 | 10.8622 | 0 | 302.3546 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23158435', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-09-20 | 2024-09-19 |  | HMB | X24093584870 | ZENAIDA IGNACIO REYES | DIMASALANG, HAGONOY, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | EMC frame only - for sched | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 15.46 | 15.46 | 0 | MODIFICATION | 45965.21 | 12449.52 |  | 0% | 2024-09-18 15:30 | 2024-09-20 14:09 | 2024-09-19 | 2025-03-17 | 2025-03-17 |  | 179.3542 | 177.4104 | -45733 | 2024-10-07 10:05 | 2024-10-16 05:26 | 2024-11-07 15:30 | 6.1778 | -762.2167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-16 | 162 | [8 empty] | FOR AUDIT |  | 2025-04-01 | 14 | 2025-03-17 | 2025-04-15 | [8 empty] | N | [7 empty] | N/A | B9-5158 | 0 | 179.3542 | 0 | 179.3542 | 6.1778 | 136 |  | 10.8622 | 10.8622 | 2.2667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093584870', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-09-30 | 2024-09-20 | Y | HMB | X24020641632 | HENRY LAO LIM | BUKIDNON, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | FOLLOW UP FROM ATTY KIM HENARES | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 224.0142 | 224.01 | 169 | NEW | 1042085.27 | 180394.18 |  | 0% | 2024-09-18 16:38 | 2024-09-24 14:23 | 2024-09-20 | 2025-01-20 | 2025-01-20 |  | 123.3073 | 117.4007 | -45677 | 2024-10-08 16:57 | 2024-10-17 20:15 | 2024-11-07 16:38 | 4.0185 | -761.2833 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 2025-03-21 | 218 | [8 empty] | FOR AUDIT |  | 2025-02-04 | 174 | 2025-01-20 | 2025-07-28 | [8 empty] | Y | 2025-01-17 | [6 empty] | 2024-10-02 | B4-0105, B4-0048, 023934, B4-5290, B4-0049, 168691, B4-0050, B4-0051, 520810 | 0 | 123.3073 | 0 | 123.3073 | 4.0185 | 192 |  | 10.2756 | 10.2756 | 3.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020641632', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-10-04 | 2024-10-02 |  | HMB | R23563727 | RICHFIELD PROPERTIES, INC., | BLOCK 15, LOTUS VILLAGE, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 56.42 | 56.42 | 0 | RELOC | 258338.31 | 45433.69 |  | 0% | 2024-09-24 16:05 | 2024-09-30 13:11 | 2024-09-28 |  | 2025-03-19 |  | 175.3299 | 169.4507 | -45735 | 2024-10-14 18:08 | 2024-10-23 21:53 | 2024-11-13 16:05 | 5.6961 | -762.25 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-05-18 | 160 | [8 empty] | NO COC |  | 2025-04-03 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-10-05 | CT6-8036, CT6-8037 | 0 | 175.3299 | 0 | 175.3299 | 5.6961 | 134 |  | 10.0495 | 10.0495 | 2.2333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23563727', | ME185284 |  |  |  | FCOMP | SRO
2024-10-02 | 2024-10-04 |  | BIZ | X24010101554 | TOBIE INTERNATIONAL INC. | EXODUS, BF HOMES MARTINVILLE SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 45.448 | 45.45 | 75 | MODIFICATION | 367791.66 | 36606.23 |  | 0% | 2024-09-24 19:44 | 2024-09-30 13:02 | 2024-10-01 |  | 2025-04-26 |  | 213.1775 | 207.4569 | -45773 | 2024-10-12 21:32 | 2024-10-21 12:24 | 2024-11-13 19:44 | 7.5866 | -762.8833 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-06-25 | 122 | [8 empty] | FOR AUDIT |  |  | 45806 | 2025-04-26 | 2025-05-29 | [8 empty] | Y | 2025-04-24 | [6 empty] | N/A | N/A | 0 | 213.1775 | 0 | 213.1775 | 7.5866 | 96 |  | 11.0031 | 11.0031 | 1.6 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010101554', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-10-02 | 2024-09-27 |  | HMB | X24083108742 | GLENDA G ADEFUIN | BLOCK 2, PATIO HOMES SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | with 3rd party opposition from Posadas HOA | W/ ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 76.9169 | 76.92 | 54 | NEW | 407351.66 | 61939.52 |  | 0% | 2024-09-25 12:12 | 2024-09-30 13:21 | 2024-09-27 |  | 2025-02-15 |  | 142.4919 | 137.4437 | -45703 | 2024-10-14 19:24 | 2024-10-23 18:08 | 2024-11-14 12:12 | 4.7922 | -761.7167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-04-16 | 192 | [8 empty] | FOR AUDIT |  | 2025-03-02 | 1 | 2025-02-15 | 2025-03-03 | [8 empty] | Y | 2025-02-12 | [6 empty] | 2024-10-02 | DX1-0243, DX2-8003, 515059 | 0 | 142.4919 | 0 | 142.4919 | 4.7922 | 166 |  | 10.3751 | 10.3751 | 2.7667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083108742', | ME166067 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-10-02 | 2024-10-04 |  | BIZ | X24083130651 | CLS GRILL AND RESTAURANTS, INC. | AGUIRRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | STA. ROSA | SCHED | Jasper Bastasa | 84.1077 | 104.39 | 45 | NEW | 377002.44 | 67729.74 |  | 0% | 2024-09-25 15:33 | 2024-09-30 13:18 | 2024-10-01 |  |  |  | -45560.648 | -45565.5542 | 0 | 2024-10-16 20:31 | 2024-10-26 07:27 | 2024-11-14 15:33 | -1411.6013 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2024-10-02 | CW9-8050, 149595, CW9-8050 | 0 | -45560.648 | 0 | -45560.648 | -1411.6013 | 0 |  | 9.5536 | 9.5536 | 0 | 295.352 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083130651', | ME184184 |  |  |  | SCHED | Jenneth Madrid
2024-10-02 | 2024-10-02 | Y | HMB | X22125062389 | SONNY L LAGON | ACACIA, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for completion 2nd week of Nov | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 428.8492 | 49.95 | 200 | NEW | 1862458.44 | 345375.27 |  | 0% | 2024-09-26 11:26 | 2024-10-01 09:31 | 2024-09-28 |  | 2025-01-10 |  | 105.5236 | 100.6035 | -45667 | 2024-10-13 19:34 | 2024-10-22 05:44 | 2024-11-15 11:26 | 3.8912 | -761.1167 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-03-11 | 228 | [8 empty] | NO COC |  | 2025-01-25 | #VALUE! | [10 empty] | Y | [8 empty] | CZ9-2124, PLDT-6512, CZ8-8003, CZ8-6100, CZ8-5441, CZ8-5460, CZ8-5472, CZ8-5474, CZ8-8004, CZ8-2165, 515259, CY8-8003, CY8-8004, CZ8-8045, CZ8-8046 | 0 | 105.5236 | 0 | 105.5236 | 3.8912 | 202 |  | 11.3399 | 11.3399 | 3.3667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22125062389', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-10-04 | 2024-10-02 |  | HMB | R23563729 | RICHFIELD PROPERTIES, INC., HMB | BLOCK 9, LOTUS VILLAGE, BACOOR | BACOOR CITY | DASMA | For Update Truss Guy Ony |  | AVECO | FCOMP | Ronilo Gange Jr. | 19.1421 | 19.14 | 0 | RELOC | 42050.26 | 15414.9 |  | 0% | 2024-09-27 08:35 | 2024-10-03 10:58 | 2024-09-28 |  | 2024-12-13 |  | 76.6426 | 70.5431 | -45639 | 2024-10-16 03:09 | 2024-10-24 22:31 | 2024-11-16 08:35 | 2.6399 | -760.65 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-02-11 | 256 | [8 empty] | NO COC |  | 2024-12-28 | #VALUE! | [10 empty] | N | [7 empty] | N/A | CT6-5288 | 0 | 76.6426 | 0 | 76.6426 | 2.6399 | 230 |  | 10.5621 | 10.5621 | 3.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23563729', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-10-09 | 2024-10-02 |  | HMB | X24062428692 | GREENLAND NEW LOWER BICUTAN NEIGHBORHOOD ASSOCIATI | RANGER, PUROK 1A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | drainage diversion before pole erection | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 125.6533 | #N/A | 60 | NEW | 656201.56 | 101185.84 |  | 0% | 2024-09-30 14:58 | 2024-10-04 12:24 | 2024-10-02 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-11-19 14:58 | #VALUE! | #VALUE! | #N/A | 34 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-10-11 | B8-1554, B8-8153, B8-8154, B8-8155, 522623 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062428692', | ME185284 |  |  |  | CLOSED-CAN | RONILO GANGE JR.
2024-10-09 | 2024-10-05 |  | CBG | X24083439704 | DITO TELECOMMUNITY CORPORATION | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 3rd party refusal; for survey on 10/29 with design, PROW, and BC | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 82.5018 | #N/A | 31 | NEW | 346178.09 | 66436.77 |  | 0% | 2024-10-02 07:46 | 2024-10-04 14:18 | 2024-10-05 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-11-21 07:46 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-10-11 | B7-8108, 198114, B7-0676, 522135 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083439704', | ME185284 |  |  |  | CLOSED-CAN | RONILO GANGE JR.
2024-10-08 | 2024-10-03 |  | CBG | X24051828444 | DITO TELECOMMUNITY CORPORATION | STA. MONICA, DON GALO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Problem with R/Way . Not feasible due to large culvert on the location of transformer pole (task 4) | W/ ISSUE | ECOM | CLOSED-CAN | Ronilo Gange Jr. | 127.3669 | #N/A | 31 | NEW | 1895538.6 | 102565.86 |  | 0% | 2024-10-02 08:35 | 2024-10-04 14:16 | 2024-10-05 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-11-21 08:35 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-10-11 | 036237, A5-0077, A5-0076, 204738, A5-0075 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051828444', | ME155242 |  |  |  | PCAN3 | RONILO GANGE JR.
2024-10-08 | 2024-10-07 |  | HMB | X24072733160 | BRGY. MARCELO GREEN | MARCELO, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For Update | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 13.71 | 13.71 | 35 | MODIFICATION | 47460.27 | 11040.3 |  | 0% | 2024-10-02 16:59 | 2024-10-04 14:20 | 2024-10-05 |  |  |  | -45567.7076 | -45569.5972 | 0 | 2024-10-21 11:34 | 2024-10-30 06:55 | 2024-11-21 16:59 | -1569.5544 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | N/A | 124828 | 0 | -45567.7076 | 0 | -45567.7076 | -1569.5544 | 0 |  | 10.3778 | 10.3778 | 0 | 288.2924 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072733160', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-10-08 | 2024-10-03 |  | HMB | X24072577420 | HERMENEGILDO DENAGA SARANILLO | SUMAKWEL, BARANGAY VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 55.9995 | 134.28 | 93.715 | MODIFICATION | 407370.66 | 45119.54 |  | 0% | 2024-10-02 16:59 | 2024-10-07 10:34 | 2024-10-05 |  | 2025-06-03 |  | 243.2924 | 238.5597 | -45811 | 2024-10-23 01:16 | 2024-11-01 06:40 | 2024-11-21 16:59 | 7.8162 | -763.5167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-02 | 84 | [8 empty] | FOR AUDIT |  | 2025-06-18 | 0 | 2025-06-03 | 2025-06-18 | [8 empty] | Y | [7 empty] | 2024-10-11 | CY9-0379, CY9-8047, 522864, CY9-0486, CY9-0485 | 0 | 243.2924 | 0 | 243.2924 | 7.8162 | 58 |  | 9.6795 | 9.6795 | 0.96667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072577420', | ME155242 |  |  |  | SCHED | Isan Carlo Lazaro
2024-10-09 | 2024-10-05 |  | HMB | X24083159101 | CHONA RODRIGUEZ GAN | DOÑA AURORA, TAHANAN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Customer refuse location of digging. for design revision, unable to execute proposed location due to aesthetic and drainage location. | W/ ISSUE | CHALLENGER | PCAN3 | Isan Carlo Lazaro | 91.2262 | 169.51 | 42 | MODIFICATION | 426527.55 | 73462.54 |  | 0% | 2024-10-03 16:53 | 2024-10-08 12:45 | 2024-10-05 |  |  |  | -45568.7037 | -45573.5312 | 0 | 2024-10-24 21:51 | 2024-11-03 08:47 | 2024-11-22 16:53 | -1411.8509 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-10-11 | CW9-0510, 034731, DW1-8039, 523347 | 0 | -45568.7037 | 0 | -45568.7037 | -1411.8509 | 0 |  | 9.3041 | 9.3041 | 0 | 287.2963 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083159101', | ME166067 |  |  |  | SCHED | Jenneth Madrid
2024-10-15 | 2024-10-18 |  | BIZ | X24093584209 | BRILLO DEL ESTE DEVELOPMENT CORP. | PRES. M. ROXAS, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 53.13 | 53.13 | 0 | TERMINATION | 45790.87 | 42792.34 |  | 0% | 2024-10-07 16:15 | 2024-10-14 09:11 | 2024-10-09 |  | 2025-04-03 |  | 177.3229 | 170.6174 | -45750 | 2024-10-27 18:18 | 2024-11-05 22:03 | 2024-11-26 16:15 | 5.7609 | -762.5 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-06-02 | 145 | [8 empty] | NO COC |  | 2025-04-18 | #VALUE! | [10 empty] | Y | [7 empty] | N/A | C5-0530 | 0 | 177.3229 | 0 | 177.3229 | 5.7609 | 119 |  | 9.6269 | 9.6269 | 1.9833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093584209', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-10-15 | 2024-10-19 |  | HMB | X23072646097 | CATHERINE C DIAMANTE | BUSUANGA, TIERRA NUEVA SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 55.649 | 133.93 | 102.5 | MODIFICATION | 380806.27 | 44837.23 |  | 0% | 2024-10-08 17:56 | 2024-10-14 09:29 | 2024-10-11 |  |  |  | -45573.7473 | -45579.3951 | 0 | 2024-10-28 04:38 | 2024-11-06 04:18 | 2024-11-27 17:56 | -1522.7767 | 0 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-10-17 | CV9-0669, CV9-2383, CV9-8022, 517944, CV9-0622 | 0 | -45573.7473 | 0 | -45573.7473 | -1522.7767 | 0 |  | 9.8654 | 9.8654 | 0 | 282.2527 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23072646097', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-10-21 | 2024-10-19 |  | CBG | X24020411873 | IGLESIA NI CRISTO | P. BURGOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | pole location issue | W/ ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 80.56 | 237.12 | 14 | MODIFICATION | 478556.27 | 64873.27 |  | 0% | 2024-10-09 15:40 | 2024-10-14 09:57 | 2024-10-11 |  | 2025-04-02 |  | 174.3472 | 169.5854 | -45749 | 2024-10-31 12:31 | 2024-11-10 03:40 | 2024-11-28 15:40 | 5.2581 | -762.4833 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-06-01 | 146 | [8 empty] | NO COC |  | 2025-04-17 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-10-21 | A5-1343, A5-8027, A5-8028, 520519, A4-0033 | 0 | 174.3472 | 0 | 174.3472 | 5.2581 | 120 |  | 8.8771 | 8.8771 | 2 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020411873', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-10-15 | 2024-10-17 |  | CBG | X24093725127 | LIGHT RAIL MANILA CORPORATION | NINOY AQUINO, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing coordination of SLEM & design team re location of RCLR; with email | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 74.3279 | 288.97 | 4999 | NEW | 900581.01 | 59854.94 |  | 0% | 2024-10-09 16:02 | 2024-10-14 13:32 | 2024-10-11 |  | 2025-03-17 |  | 158.3319 | 153.4361 | -45733 | 2024-10-23 01:47 | 2024-10-30 10:47 | 2024-11-28 16:02 | 7.238 | -762.2167 | 28 | 20 | 16.4063 | 20.7813 | 13.4063 | 60 | 57 | 52 | 2025-05-16 | 162 | [8 empty] | NO COC |  | 2025-04-01 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-10-17 | A5-5544, A5-5530, 198155, A5-1071, 521395, A5-1070, A5-8015, A5-8016, A5-8017 | 0 | 158.3319 | 0 | 158.3319 | 7.238 | 136 |  | 13.4552 | 13.4552 | 2.2667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093725127', | ME185284 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-10-23 | 2024-10-19 |  | HMB | X24072854711 | ROBERTO BALASBAS DIMAYUGA | SAN NICOLAS, SAN MARTIN VILL-4TH ESTATE, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | STA. ROSA | SCHED | Jasper Bastasa | 176.4356 | 411.28 | 69 | NEW | 789203.25 | 142079.61 |  | 0% | 2024-10-10 09:46 | 2024-10-17 12:30 | 2024-10-16 |  |  |  | -45575.4067 | -45582.5208 | 0 | 2024-11-01 10:30 | 2024-11-11 02:42 | 2024-11-29 09:46 | -1365.5866 | 0 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-10-24 | CX9-0868, DX1-8089, DX1-8090, DX1-8091, 523134, CX9-08762 | 0 | -45575.4067 | 0 | -45575.4067 | -1365.5866 | 0 |  | 8.797 | 8.797 | 0 | 280.5933 | REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072854711', | ME184184 |  |  |  | SCHED | Jenneth Madrid
2024-10-28 | 2024-10-19 | Y | HMB | X24083444242 | JEIKA PROPERTIES CORPORATION | BLOCK 6, KATHLEEN PLACE 5 SUBD, BACOOR | BACOOR CITY | DASMA | for scheduling | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 1773.3821 | 1716.66 | 348 | NEW | 8506182.51 | 1428065.65 |  | 0% | 2024-10-10 10:11 | 2024-10-17 12:32 | 2024-10-16 |  | 2025-02-06 |  | 118.5757 | 111.4778 | -45694 | 2024-10-31 14:50 | 2024-11-10 01:40 | 2024-11-29 10:11 | 3.6758 | -761.5667 | 50 | 28 | 24.1935 | 30.6452 | 21.1935 | 60 | 57 | 52 | 2025-04-07 | 201 | [8 empty] | ON GOING MAT RETURN |  | 2025-02-21 | 20 | 2025-02-06 | 2025-03-13 | 2025-05-21 | AGD/RM |  |  |  |  | 2025-06-03 | NVP | Y | 2025-02-14 | [6 empty] | 2024-11-05 | CT8-8001, CT8-0653, CT8-8026, CT8-8027, CT8-8028, CT8-8029, 522240, CT8-8030, CT8-8031, 522241, CT8-8032, CT8-8033, CT8-8034, 522242, CT8-8035, CT8-8040, CT8-8045, CT8-8049, CT8-8036, 522244, 522246, 522247, CT8-8037, CT8-8041, CT8-8046, CT8-8050, CT8-8054, CT8-8038, CT8-8042, CT8-8047, CT8-8051, CT8-8055, 522243, 522245, 522248, CT8-8053, CT8-8060, CT8-8039, CT8-8043, CT8-8044, CT8-8048, CT8-8052, CT8-5057, CT8-8059, CT8-8061 | 0 | 118.5757 | 0 | 118.5757 | 3.6758 | 175 |  | 9.1008 | 9.1008 | 2.9167 |  | REV |  | 2025-06-04 | 259923.86 | NTC ISSUED | 2025-06-04 |  | 83 |  |  |  | 'X24083444242', | ME166067 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-10-30 | 2024-10-18 |  | HMB | R23445427 | ARCEO, ELIZABETH | BLOCK 1, LA CHARINA SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | Done pole erection retirement nalang po ng poste |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 35.9652 | 112.85 | 0 | RELOC | 155380.98 | 28961.94 |  | 0% | 2024-10-11 15:15 | 2024-10-17 12:59 | 2024-10-16 |  |  |  | -45576.6357 | -45582.541 | 0 | 2024-11-01 20:13 | 2024-11-11 07:09 | 2024-11-30 15:15 | -1412.0966 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [7 empty] | 2024-11-05 | DS1-8072 | 0 | -45576.6357 | 0 | -45576.6357 | -1412.0966 | 0 |  | 9.0583 | 9.0583 | 0 | 279.3643 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23445427', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-10-22 | 2024-10-19 |  | HMB | X24072928092 | GAY ANNETTE LIM ANG | ORMOC, ALABANG HILLS SUBD PH 2, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 10.35 | 10.35 | 54 | MODIFICATION | 37965.19 | 8334.57 |  | 0% | 2024-10-11 15:40 | 2024-10-17 13:00 | 2024-10-16 |  | 2025-01-14 |  | 94.347 | 88.4583 | -45671 | 2024-10-29 17:27 | 2024-11-07 08:20 | 2024-11-30 15:40 | 3.3576 | -761.1833 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-03-15 | 224 | [8 empty] | NO COC |  | 2025-01-29 | #VALUE! | [10 empty] | Y | 2025-01-13 | [6 empty] | N/A | DV1-0339, 054468 | 0 | 94.347 | 0 | 94.347 | 3.3576 | 198 |  | 10.4041 | 10.4041 | 3.3 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072928092', | ME155242 |  |  |  | FCOMP | SRO
2024-10-21 | 2024-10-19 |  | CBG | X24062492521 | DOMINIC CONSTRUCTION, INC. | DR. A. SANTOS, SN ANTONIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For scheduling | W/O ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 8.93 | 8.93 | 0 | TERMINATION | 18594.84 | 7191.18 |  | 0% | 2024-10-11 15:44 | 2024-10-17 12:52 | 2024-10-16 |  |  |  | -45576.6554 | -45582.5361 | 0 | 2024-10-30 10:19 | 2024-11-08 05:40 | 2024-11-30 15:44 | -1569.8626 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | N/A | DX1-8058 | 0 | -45576.6554 | 0 | -45576.6554 | -1569.8626 | 0 |  | 10.0696 | 10.0696 | 0 | 279.3446 | NON-REV | 10 MONTHS AND ABOVE |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062492521', | ME166067 |  |  |  | SCHED | Jenneth Madrid
2024-11-04 | 2024-10-21 |  | BIZ | X24093698934 | BLOOMINGDALE ENTERPRISES INC | ALABANG-ZAPOTE, TALON I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | TECO | Jenneth Madrid | 2.198 | 2.2 | 0 | TERMINATION | 16595.27 | 1769.95 |  | 0% | 2024-10-14 13:44 | 2024-10-18 14:53 | 2024-10-21 |  | 2025-02-28 | 2025-07-25 | 136.428 | 132.3799 | 147 | 2024-11-02 08:19 | 2024-11-11 03:40 | 2024-12-03 13:44 | 4.6992 | 2.45 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-29 | 179 | [8 empty] | PAID |  | 2025-03-15 | -12 | 2024-10-28 | 2025-03-03 | [8 empty] | Y | [7 empty] | N/A | CW8-8003 | 0 | 136.428 | 0 | 136.428 | 4.6992 | 153 |  | 9.9692 | 9.9692 | 2.55 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093698934', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-10-30 | 2024-10-21 |  | CBG | X24093787030 | CONVERGE INFORMATION AND COMMUNICATIONS TECHNOLOGY | LAPU-LAPU, PUROK 5, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | with ROW concern; near mosque / brgy. Refusal -FOR CREATION OF NEW WORK ORDER | W/ ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 47.5327 | #N/A | 11 | NEW | 806019.23 | 38276.89 |  | 0% | 2024-10-15 15:03 | 2024-10-18 14:55 | 2024-10-21 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2024-12-04 15:03 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-11-05 | A8-0139, 518094, A8-8060 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093787030', | ME185284 |  |  |  | CLOSED-CAN | Jenneth Madrid
2024-11-05 | 2024-10-21 |  | CBG | X24103888835 | MAKATI DEVELOPMENT CORPORATION | EAST UNION, ARCA SOUTH, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | remaining terminal pole for retirement due to exisiting spun cable (with coordination to UG team) | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 116.3974 | 249.8 | 0 | TERMINATION | 248970.42 | 93739.94 | 75757.59 | 80.82% | 2024-10-16 16:46 | 2024-10-21 15:12 | 2024-10-21 |  | 2025-01-31 |  | 106.3014 | 101.3667 | -45688 | 2024-11-07 13:37 | 2024-11-17 04:46 | 2024-12-05 16:46 | 3.2059 | -761.4667 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | CHECKING OF SERVICE ITEM | PARTIALLY BILLED | 2025-02-15 | 6 | 2025-01-31 | 2025-02-21 | 2025-04-22 | ECI | Y |  |  |  | 2025-06-09 | NVP | Y | [8 empty] | B8-6318, B8-6319 | 0 | 106.3014 | 0 | 106.3014 | 3.2059 | 181 |  | 8.6646 | 8.6646 | 3.0167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103888835', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-10-28 | 2024-10-23 |  | BIZ | X24093549347 | CROWN OF KING SOLOMON ACADEMY INC. | 6TH, SALINAS I, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 384.3897 | 384.39 | 38 | NEW | 1792274.22 | 309541.14 |  | 0% | 2024-10-18 14:46 | 2024-10-23 10:16 | 2024-10-23 |  | 2025-02-14 |  | 118.3847 | 113.5722 | -45702 | 2024-11-10 02:05 | 2024-11-19 21:06 | 2024-12-07 14:46 | 3.4858 | -761.7 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-04-15 | 193 | [8 empty] | NO COC |  | 2025-03-01 | #VALUE! | [10 empty] | Y | 2025-02-11 | [6 empty] | 2024-11-05 | CV5-1041, CV5-8046, CV5-8048, CV5-8049, CV5-8050, CV5-8051, CV5-8052, CV5-8053, CV5-8054, 522689, CV5-8055 | 0 | 118.3847 | 0 | 118.3847 | 3.4858 | 167 |  | 8.403 | 8.403 | 2.7833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093549347', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-10-28 | 2024-10-24 |  | CBG | X24062101038 | GLOBE TELECOM, INC. | TIMBANG, MAMBOG III, BACOOR | BACOOR CITY | DASMA | Digging completed Cancel energization scheduled 11/27/2024 due to ROW/HOA concerns. On-going negotiation with customer and CRS. | W/ ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 100.9782 | 102.03 | 20 | NEW | 353455.45 | 81315.74 |  | 0% | 2024-10-18 15:32 | 2024-10-23 10:20 | 2024-10-24 |  | 2025-03-24 |  | 156.3528 | 151.5694 | -45740 | 2024-11-08 20:30 | 2024-11-18 07:25 | 2024-12-07 15:32 | 4.8443 | -762.3333 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-05-23 | 155 | [8 empty] | NO COC | WITH AUDIT | 2025-04-08 | #VALUE! |  |  | 2025-06-23 | AGD | [6 empty] | Y | [7 empty] | 2024-10-29 | CT6-3403, 394411, CT6-3402, 522343 | 0 | 156.3528 | 0 | 156.3528 | 4.8443 | 129 |  | 8.8411 | 8.8411 | 2.15 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062101038', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-11-07 | 2024-10-29 |  | CBG | X24072868110 | DITO TELECOMMUNITY CORPORATION | 3RD AVE, HEN HEADQUARTER SUPPRT GRP, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | pole erection on Feb. 3rd week (3rd shift) | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 133.7749 | 1550.97 | 22 | NEW | 1544526.93 | 107725.88 | 39828.8 | 36.97% | 2024-10-21 14:09 | 2024-10-28 14:49 | 2024-10-29 | 2025-03-23 | 2025-03-23 |  | 152.4104 | 145.3826 | -45739 | 2024-11-17 01:34 | 2024-11-27 22:13 | 2024-12-10 14:09 | 3.878 | -762.3167 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-05-22 | 156 | [8 empty] | FOR AUDIT |  | 2025-04-07 | 112 | 2025-03-23 | 2025-07-28 | [8 empty] | Y | 2025-03-19 | [6 empty] | 2024-11-09 | C8-5578, C8-5579, C8-5580, 198586 | 0 | 152.4104 | 0 | 152.4104 | 3.878 | 130 |  | 7.1858 | 7.1858 | 2.1667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072868110', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-04 | 2024-10-29 |  | HMB | X24051688503 | ALEXANDER EVAN O. UY | JOHN, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 107.8165 | 186.1 | 80 | MODIFICATION | 494977.65 | 86091.88 |  | 0% | 2024-10-21 15:53 | 2024-10-28 14:51 | 2024-10-29 |  | 2025-05-31 |  | 221.3382 | 214.3812 | -45808 | 2024-11-11 00:10 | 2024-11-20 05:34 | 2024-12-10 15:53 | 7.1109 | -763.4667 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | FOR AUDIT |  | 2025-06-15 | -8 | 2025-06-24 | 2025-06-07 |  | BAYSIDE | [6 empty] | Y | [7 empty] | 2024-11-05 | CZ8-0155, 521943, CZ8-8082, CZ8-0170, CZ8-2001, CZ8-0169 | 0 | 221.3382 | 0 | 221.3382 | 7.1109 | 61 |  | 9.0706 | 9.0706 | 1.0167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051688503', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-11-06 | 2024-10-29 |  | HMB | X24051728852 | JENNY ROMANO BRAMBILLA | STAFFORD, MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 53.196 | 131.48 | 40 | MODIFICATION | 308653.92 | 42837.37 |  | 0% | 2024-10-21 15:55 | 2024-10-28 14:56 | 2024-10-29 |  |  |  | -45586.6632 | -45593.6222 | 0 | 2024-11-11 20:53 | 2024-11-21 07:48 | 2024-12-10 15:55 | -1412.4073 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-06 | A6-8028, 521931 | 0 | -45586.6632 | 0 | -45586.6632 | -1412.4073 | 0 |  | 8.7476 | 8.7476 | 0 | 269.3368 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051728852', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-11-06 | 2024-10-29 |  | HMB | X24051726352 | ELIZA BLANCHE SANTOS ALAY-AY | JOHN GLEN JR., MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 147.1257 | 147.13 | 42 | MODIFICATION | 357616.2 | 86985.66 |  | 0% | 2024-10-21 15:58 | 2024-11-06 09:31 | 2024-10-29 |  |  |  | -45586.6653 | -45602.3965 | 0 | 2024-11-11 20:56 | 2024-11-21 07:51 | 2024-12-10 15:58 | -1412.4074 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-06 | A5-8030, 521895 | 0 | -45586.6653 | 0 | -45586.6653 | -1412.4074 | 0 |  | 8.7476 | 8.7476 | 0 | 269.3347 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051726352', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-11-06 | 2024-10-29 | Y | HMB | X24073033797 | CELSO T DIMARUCUT | DOÑA CONCHA CRUZ, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | VIP, PRESIDENT & CEO OF ROXAS HOLDING. MVP GROUP |  | POWERHOUSE | FCOMP | Jenneth Madrid | 47.4355 | 47.44 | 80 | MODIFICATION | 392547.56 | 38222.75 |  | 0% | 2024-10-22 17:03 | 2024-10-28 15:06 | 2024-10-28 |  | 2025-01-11 |  | 80.2896 | 74.3708 | -45668 | 2024-11-09 18:50 | 2024-11-18 09:43 | 2024-12-11 17:03 | 2.8574 | -761.1333 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-03-12 | 227 | [8 empty] | NO COC |  | 2025-01-26 | #VALUE! | [10 empty] | Y | 2025-01-14 | [6 empty] | 2024-11-07 | CV9-8039, 523206 | 0 | 80.2896 | 0 | 80.2896 | 2.8574 | 201 |  | 10.0106 | 10.0106 | 3.35 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24073033797', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-13 | 2024-10-29 |  | BIZ | X24041458580 | PATIO ALGADA EVENTS PLACE AND LEISURE INC. | DE CASTRO, DE CASTRO I SUBD, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 48.755 | 48.76 | 52 | NEW | 392158.12 | 39261.15 |  | 0% | 2024-10-22 17:09 | 2024-10-28 15:03 | 2024-10-28 |  | 2025-02-18 |  | 118.2854 | 112.3729 | -45706 | 2024-11-09 18:56 | 2024-11-18 09:49 | 2024-12-11 17:09 | 4.2096 | -761.7667 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-19 | 189 | [8 empty] | FOR AUDIT |  | 2025-03-05 | 114 | 2025-02-13 | 2025-06-27 | [8 empty] | Y | [7 empty] | 2024-11-15 | CW6-8058, 518370 | 0 | 118.2854 | 0 | 118.2854 | 4.2096 | 163 |  | 10.0105 | 10.0105 | 2.7167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041458580', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-07 | 2024-10-29 |  | BIZ | X24083434936 | MAXIPRINTS INC. | 1ST, TAGUIG BAGUMBAYAN INDL ASS INC, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | verify if need TBCAI permit | W/O ISSUE | VJC | TECO | Jenneth Madrid | 183.2653 | 183.47 | 220 | MODIFICATION | 980297.45 | 147707.78 | 147879.63 | 100.1% | 2024-10-22 17:14 | 2024-10-28 15:09 | 2024-10-29 | 2024-11-10 | 2025-02-22 | 2025-05-30 08:00 | 122.2819 | 116.3688 | 97.3333 | 2024-11-10 05:25 | 2024-11-18 23:03 | 2024-12-11 17:14 | 4.2642 | 1.6222 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-04-23 | 185 | [8 empty] | PAID | FULLY BILLED | 2025-03-09 | -6 | 2025-02-22 | 2025-03-03 | 2025-04-01 | AGD | Y | Y |  |  | 2025-04-02 | NVP | Y | 2024-11-08 | [6 empty] | 2024-11-09 | DY1-0538 | 0 | 122.2819 | 0 | 122.2819 | 4.2642 | 159 |  | 9.8088 | 9.8088 | 2.65 |  | NON-REV |  |  |  | NTC ISSUED |  |  | 0 |  |  |  | 'X24083434936', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-11 | 2024-10-29 |  | BIZ | X24083317606 | HARD DISCOUNT PHILIPPINES, INC. | M.L. QUEZON, PUROK 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | ongoing digging 11/4/2024 | W/O ISSUE | VJC | COMP | Jenneth Madrid | 36.277 | 114.56 | 19 | NEW | 279802.61 | 29212.9 |  | 0% | 2024-10-22 17:23 | 2024-10-28 15:08 | 2024-10-29 | 2025-03-23 | 2025-03-23 | 2025-08-19 | 151.2757 | 145.3694 | 149 | 2024-11-12 22:21 | 2024-11-22 09:16 | 2024-12-11 17:23 | 4.687 | 2.4833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-05-22 | 156 | [8 empty] | PAID |  | 2025-04-07 | 23 | 2025-05-23 | 2025-04-30 | [6 empty] | 2025-08-12 | NVP | Y | 2025-03-19 | [6 empty] | 2024-11-12 | A8-8097, 523471 | 0 | 151.2757 | 0 | 151.2757 | 4.687 | 130 |  | 8.7147 | 8.7147 | 2.1667 |  | REV |  | 2025-08-12 | 2166.6 | NTC ISSUED | 2025-08-15 |  | 11 |  |  |  | 'X24083317606', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-08 | 2024-10-29 |  | HMB | X23083229143 | JUSTIN PHILIP POLISTICO SARABIA | ALITAGTAG, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 95.9462 | 174.23 | 126 | MODIFICATION | 476184.66 | 76910.28 |  | 0% | 2024-10-23 14:57 | 2024-10-30 14:54 | 2024-10-29 |  | 2025-06-07 |  | 226.3771 | 219.3792 | -45815 | 2024-11-12 01:39 | 2024-11-21 01:19 | 2024-12-12 14:57 | 7.564 | -763.5833 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-08-06 | 80 | [8 empty] | NO COC |  | 2025-06-22 | #VALUE! | [10 empty] | Y | 2025-06-04 | [6 empty] | 2024-11-09 | CS8-0058, 518428, CS8-8033, CS8-0055 | 0 | 226.3771 | 0 | 226.3771 | 7.564 | 54 |  | 9.3684 | 9.3684 | 0.9 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23083229143', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2025-02-27 |  |  | HMB | X24093485934 | MARLON WILLIAMS MARCELINO CASTILLO | ORMOC, ALABANG HILLS SUBD PH 2, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 47.977 | 47.98 | 80 | MODIFICATION | 330669.54 | 38658.8 |  | 0% | 2024-10-28 14:02 | 2024-11-05 14:33 | 2024-11-05 |  | 2025-04-30 |  | 183.4156 | 175.3938 | -45777 | 2024-11-15 15:49 | 2024-11-24 06:41 | 2024-12-17 14:02 | 6.5274 | -762.95 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-04-22 | [6 empty] | 2025-02-27 | DV1-8073,TLN-523664 | 0 | 183.4156 | 0 | 183.4156 | 6.5274 | 92 |  | 9.8016 | 9.8016 | 1.5333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093485934', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-11-05 |  |  | BIZ | X24093762742 | ALSTOM TRANSPORT CONSTRUCTION PHILIPPINES, INC. | NINOY AQUINO, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 35.5434 | 19.38 | 0 | TERMINATION | 44003.21 | 28630.27 |  | 0% | 2024-10-28 16:07 | 2024-11-05 12:24 | 2024-11-05 | 2025-02-01 | 2025-02-01 |  | 95.3286 | 87.4833 | -45689 | 2024-11-16 10:42 | 2024-11-25 06:03 | 2024-12-17 16:07 | 3.2835 | -761.4833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-02 | 206 | [8 empty] | FOR AUDIT |  | 2025-02-16 | 152 | 2025-02-01 | 2025-07-18 | [8 empty] | Y | [7 empty] | N/A | A5-8018 | 0 | 95.3286 | 0 | 95.3286 | 3.2835 | 180 |  | 9.4835 | 9.4835 | 3 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093762742', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-05 |  |  | BIZ | X24093763605 | ALSTOM TRANSPORT CONSTRUCTION PHILIPPINES, INC. | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 18.05 | 18.05 | 0 | TERMINATION | 23857.72 | 14543.28 |  | 0% | 2024-10-28 16:07 | 2024-11-05 12:23 | 2024-11-05 |  |  |  | -45593.6715 | -45601.516 | 0 | 2024-11-16 10:42 | 2024-11-25 06:03 | 2024-12-17 16:07 | -1570.4487 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | N/A | CZ8-8021 | 0 | -45593.6715 | 0 | -45593.6715 | -1570.4487 | 0 |  | 9.4835 | 9.4835 | 0 | 262.3285 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093763605', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-11-08 |  |  | CBG | X24062104789 | GLOBE TELECOM, INC. | DON P. REYES, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | for completion on Nov 27. 2024 | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 90.8975 | 90.9 | 23 | NEW | 356034.6 | 72820.36 |  | 0% | 2024-10-29 10:31 | 2024-11-05 12:32 | 2024-11-05 |  | 2025-01-31 |  | 93.5621 | 86.4778 | -45688 | 2024-11-18 12:34 | 2024-11-27 16:18 | 2024-12-18 10:31 | 3.0396 | -761.4667 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | NO COC |  | 2025-02-15 | #VALUE! | [10 empty] | Y | 2025-01-31 | [6 empty] | 2024-11-09 | CP9-0126, CP9-8013, 522274 | 0 | 93.5621 | 0 | 93.5621 | 3.0396 | 181 |  | 8.92 | 8.92 | 3.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062104789', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-05 |  |  | CBG | X24051588113 | ASEANA BUSINESS PARK ESTATE ASSOCIATION, INC. | ASEANA, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | COMPLETED ONSITE WO OF (AVECO) |  | VJC | SCHED | Jenneth Madrid | 32.8803 | 32.88 | 28 | MODIFICATION | 212227.5 | 26100.1 |  | 0% | 2024-10-31 15:41 | 2024-11-05 12:27 | 2024-11-05 |  |  |  | -45596.6535 | -45601.5188 | 0 | 2024-11-19 10:16 | 2024-11-28 05:37 | 2024-12-20 15:41 | -1570.5514 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | 2025-06-11 | [6 empty] | N/A | C4-2042, 187555 | 0 | -45596.6535 | 0 | -45596.6535 | -1570.5514 | 0 |  | 9.3808 | 9.3808 | 0 | 259.3465 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051588113', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2024-12-11 |  |  | HMB | X24072577424 | ARTHUR NOLASCO IRASUSTA | R. MAGSAYSAY, FILINVEST SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 21.55 | 21.55 | 48 | MODIFICATION | 61552.23 | 17353.63 |  | 0% | 2024-10-31 16:17 | 2024-11-05 13:10 | 2024-11-05 |  | 2025-03-18 |  | 137.3215 | 132.4514 | -45734 | 2024-11-19 10:52 | 2024-11-28 06:13 | 2024-12-20 16:17 | 4.73 | -762.2333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-17 | 161 | [8 empty] | FOR AUDIT |  | 2025-04-02 | -12 | 23-Nov-24 | 2025-03-21 | [8 empty] | Y | [7 empty] | N/A |  | 0 | 137.3215 | 0 | 137.3215 | 4.73 | 135 |  | 9.38 | 9.38 | 2.25 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072577424', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-11 |  |  | HMB | X24072732976 | LUCKY ROCKY CHUA SY | STA. MARIA, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done: digging and poel erect | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 109.024 | 111.67 | 44 | NEW | 364950.15 | 87791.66 | 41380.28 | 47.13% | 2024-10-31 16:19 | 2024-11-05 13:12 | 2024-11-05 |  | 2025-01-08 |  | 68.3201 | 63.45 | -45665 | 2024-11-21 21:17 | 2024-12-01 08:12 | 2024-12-20 16:19 | 2.1168 | -761.0833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-03-09 | 230 | [8 empty] | MATERIAL BALANCING | PARTIALLY BILLED | 2025-01-23 | -12 | 2024-12-19 | 2025-01-11 | 2025-02-17 | ECI | Y |  |  |  | 2025-04-11 | NVP | [8 empty] | 2024-12-19 | CY9-1711,087421,CY9-8051,523877,CY9-8052 | 0 | 68.3201 | 0 | 68.3201 | 2.1168 | 204 |  | 8.4373 | 8.4373 | 3.4 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072732976', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-11-05 |  |  | CBG | X24041323481 | ASEANA BUSINESS PARK ESTATE ASSOCIATION, INC. | PRES. DIOSDADO MACAPAGAL, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 70.0173 | 70.02 | 17 | MODIFICATION | 464521.19 | 56399.27 |  | 0% | 2024-10-31 16:19 | 2024-11-05 12:26 | 2024-11-05 | 2025-06-14 | 2025-06-14 08:05 |  | 225.6569 | 220.8187 | -45822.3368 | 2024-11-20 18:22 | 2024-11-29 22:07 | 2024-12-20 16:19 | 7.3311 | -763.7056 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-08-13 08:05 | 72.6632 | [8 empty] | FOR AUDIT |  | 2025-06-29 08:05 | 38.6632 | 2025-06-14 | 2025-08-07 | [8 empty] | Y | 2025-06-11 | [6 empty] | N/A | C5-5620, 106501 | 0 | 225.6569 | 0 | 225.6569 | 7.3311 | 46.6632 |  | 8.8471 | 8.8471 | 0.77772 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041323481', | ME185284 |  |  |  | COMP | Jenneth Madrid
2024-11-16 |  | Y | HMB | X24083323243 | NICOLE TRINIDAD LOTILLA | DAFFODIL, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | with follow up from Raul Reyes of Corp Com |  | AVECO | FCOMP | Ronilo Gange Jr. | 196.5603 | 431.23 | 42.36 | MODIFICATION | 807326.91 | 158286.09 |  | 0% | 2024-11-04 15:21 | 2024-11-11 14:56 | 2024-11-06 | 2025-03-03 | 2025-03-05 |  | 120.3604 | 113.3778 | -45721 | 2024-11-27 15:56 | 2024-12-07 14:29 | 2024-12-24 15:21 | 3.4687 | -762.0167 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 2025-05-04 | 174 | [8 empty] | NO COC |  | 2025-03-20 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-11-20 | CU8-8098, CU8-8099, CU8-8100, 523464, CU8-0497 | 0 | 120.3604 | 0 | 120.3604 | 3.4687 | 148 |  | 7.734 | 7.734 | 2.4667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083323243', | ME155242 |  |  |  | FCOMP | SRO
2024-11-21 |  |  | BIZ | X24104022999 | DAHN BERGER PHILS. CONSTRUCTION CORPORATION | DOÑA SOLEDAD, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | re-assigned fromPH |  | VJC | TECO | Jenneth Madrid | 176.7701 | 206.73 | 0 | TERMINATION | 140893 | 142356.57 |  | 0% | 2024-11-05 17:04 | 2024-11-11 14:25 | 2024-11-06 | 2025-01-31 | 2025-01-31 | 2025-05-12 14:09 | 86.2889 | 80.3993 | 101.5896 | 2024-11-27 13:55 | 2024-12-07 05:04 | 2024-12-25 17:04 | 2.6024 | 1.6932 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | PAID |  | 2025-02-15 | 6 | 2025-01-31 | 2025-02-21 | 2025-04-08 | AGD | N |  |  |  | 2025-04-16 | NVP | Y | [7 empty] | N/A | DZ1-2624 | 0 | 86.2889 | 0 | 86.2889 | 2.6024 | 181 |  | 8.0611 | 8.0611 | 3.0167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104022999', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-19 |  |  | HMB | X24072831387 | IRMA S AQUINO | ARTHUR, HAPAY CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | sadang:Need ng joint survey dto sir, pra mag lagay ng staka, ayaw mag pahukay ng mga tao dun.. halos lahat | W/O ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 525.7387 | 1689.85 | 75 | NEW | 2473616.36 | 423365.47 |  | 0% | 2024-11-06 07:24 | 2024-11-11 14:45 | 2024-11-06 |  |  |  | -45602.3083 | -45607.6146 | 0 | 2024-12-01 12:23 | 2024-12-12 00:55 | 2024-12-26 07:24 | -1212.4849 | 0 | 50 | 34 | 28.208 | 35.7301 | 25.208 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-20 | DY2-5295, DY2-8055, 523126, DY2-8056, DY2-5057, DY2-8058, 523128, DY2-8059, DY2-8060, DY2-8061, DY2-8062, DY2-8063, DY2-8064, DY2-8065, DY2-8066, DY2-8068, DY2-6067, DY2-8069,DY2-8070 | 0 | -45602.3083 | 0 | -45602.3083 | -1212.4849 | 0 |  | 7.0909 | 7.0909 | 0 | 253.6917 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072831387', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-11-18 | N/A |  | HMB | X24051821123 | CITY GOVERNMENT OF TAGUIG | C-5, WESTERN BICUTAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for sched of digging | W/O ISSUE | VJC | SCHED | Jasper Bastasa | 130.0921 | 260.49 | 27 | NEW | 584047.02 | 104760.12 |  | 0% | 2024-11-06 08:25 | 2024-11-11 14:34 | 2024-11-06 |  |  |  | -45602.3507 | -45607.6069 | 0 | 2024-11-28 05:16 | 2024-12-07 20:25 | 2024-12-26 08:25 | -1375.309 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | assigned to ALEGRE BUILDERS (SRO) |  | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-20 | C8-5453, C8-8106, C8-8107, 522204 | 0 | -45602.3507 | 0 | -45602.3507 | -1375.309 | 0 |  | 8.0418 | 8.0418 | 0 | 253.6493 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051821123', | ME184184 |  |  |  | SCHED | Jenneth Madrid
2024-11-14 |  |  | BIZ | X24072635271 | JOIE MEDINA GAWARAN | LOURDES CPD, LOURDES CPD, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 91.2898 | 91.29 | 28 | NEW | 428865.23 | 73513.49 |  | 0% | 2024-11-07 14:20 | 2024-11-13 14:45 | 2024-11-12 |  | 2025-02-07 |  | 91.4025 | 85.3854 | -45695 | 2024-11-27 16:23 | 2024-12-06 20:08 | 2024-12-27 14:20 | 2.9695 | -761.5833 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | NO COC |  | 2025-02-22 | #VALUE! | [10 empty] | Y | 2025-02-06 | [6 empty] | 2024-11-15 | CV7-8090, 522895 | 0 | 91.4025 | 0 | 91.4025 | 2.9695 | 174 |  | 8.6224 | 8.6224 | 2.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072635271', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-14 |  |  | CBG | X23030972347 | DITO TELECOMMUNITY CORPORATION | ADELFA, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | emailed UAM for sabayan operation on pole replacement | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 57.0283 | 57.03 | 31 | NEW | 1048692.28 | 45923.59 |  | 0% | 2024-11-08 12:23 | 2024-11-13 14:50 | 2024-11-12 |  | 2025-06-04 |  | 207.4839 | 202.3819 | -45812 | 2024-11-28 14:26 | 2024-12-07 18:11 | 2024-12-28 12:23 | 6.7407 | -763.5333 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-08-03 | 83 | [8 empty] | NO COC |  | 2025-06-19 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-11-15 | CZ7-0108, 516509, CZ7-0283, CZ7-2108 | 0 | 207.4839 | 0 | 207.4839 | 6.7407 | 57 |  | 8.5925 | 8.5925 | 0.95 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23030972347', | ME185284 |  |  |  | SCHED | Jenneth Madrid
2024-11-16 |  |  | HMB | X24010234099 | LORENZO ENRIQUEZ GUERRERO | LIPA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For scheduling | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 43.8903 | 43.89 | 90 | MODIFICATION | 272805.41 | 35367.83 |  | 0% | 2024-11-08 12:25 | 2024-11-13 14:59 | 2024-11-13 |  | 2025-03-27 08:33 |  | 138.8387 | 133.7319 | -45743.3562 | 2024-11-26 14:12 | 2024-12-05 05:05 | 2024-12-28 12:25 | 4.941 | -762.3893 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-05-26 08:33 | 151.6438 | [8 empty] | FOR AUDIT |  | 2025-04-11 08:33 | 2.6438 | 2025-03-27 | 2025-04-14 | [8 empty] | Y | 2025-03-25 | [6 empty] | N/A | CS9-5212, 159523 | 0 | 138.8387 | 0 | 138.8387 | 4.941 | 125.6438 |  | 9.4125 | 9.4125 | 2.0941 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010234099', | ME166067 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-14 |  | Y | HMB | X24083277607 | JONATHAN KEE AGABIN | SAMAR, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | FOLLOW UP FROM ATTY KIM HENARES | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 81.7376 | 160.02 | 80 | NEW | 454689.41 | 65090.91 |  | 0% | 2024-11-08 16:13 | 2024-11-13 14:55 | 2024-11-12 |  | 2025-01-14 |  | 66.324 | 61.3785 | -45671 | 2024-11-29 00:30 | 2024-12-08 05:55 | 2024-12-28 16:13 | 2.1308 | -761.1833 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-03-15 | 224 | [8 empty] | NO COC |  | 2025-01-29 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-11-15 | B4-5388, B4-8030, 523440, PLDT-7784 | 0 | 66.324 | 0 | 66.324 | 2.1308 | 198 |  | 8.4919 | 8.4919 | 3.3 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083277607', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-16 |  | Y | HMB | X24072802372 | JOSE MARTIN GRUBA NOEL | QUINTIN PAREDES, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | VIP, OWNER IS RET. GENERAL MANNY IDQUIVAL | For Schedule of Digging 1/8/2024 | ECOM | FCOMP | Ronilo Gange Jr. | 119.9787 | 120.71 | 86 | MODIFICATION | 588535.37 | 96616.31 | 26531.14 | 27.46% | 2024-11-08 16:14 | 2024-11-13 14:53 | 2024-11-21 | 2025-01-10 | 2025-01-11 |  | 63.3237 | 58.3799 | -45668 | 2024-11-29 00:31 | 2024-12-08 05:55 | 2024-12-28 16:14 | 2.0344 | -761.1333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-03-12 | 227 | [8 empty] | MATERIAL BALANCING | PARTIALLY BILLED | 2025-01-26 | -4 | 2025-01-10 | 2025-01-22 | 2025-02-06 | ECI | Y |  |  |  | 2025-02-07 | NVP | Y | 2025-01-09 | [6 empty] | 2024-11-20 | CW9-0663, DW1-8037, 523044, DW1-8038 | 0 | 63.3237 | 0 | 63.3237 | 2.0344 | 201 |  | 8.4918 | 8.4918 | 3.35 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072802372', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-11-14 |  |  | BIZ | X24093693382 | ASIA STRUCTURAL DEVELOPER CORP, | PACIFIC, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | TECO | Ronilo Gange Jr. | 144.9767 | 144.98 | 0 | TERMINATION | 118408.73 | 116746.06 | 93645.38 | 80.21% | 2024-11-08 16:21 | 2024-11-13 14:51 | 2024-11-21 |  | 2025-01-20 | 2025-06-12 14:43 | 72.3185 | 67.3812 | 143.6132 | 2024-11-29 21:19 | 2024-12-09 08:15 | 2024-12-28 16:21 | 2.2406 | 2.3936 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-03-21 | 218 | [8 empty] | PAID |  | 2025-02-04 | #VALUE! |  |  | 2025-05-12 | ECI | N |  |  |  | 2025-06-11 | NVP | Y | [7 empty] | N/A |  | 0 | 72.3185 | 0 | 72.3185 | 2.2406 | 192 |  | 8.1894 | 8.1894 | 3.2 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093693382', | ME155242 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-11-22 |  |  | BIZ | X24103897542 | RAICON DEVELOPMENT CORPORATION | QUIRINO, PULANGLUPA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 48.0167 | 48.02 | 0 | TERMINATION | 58204.17 | 38674.73 |  | 0% | 2024-11-08 16:51 | 2024-11-13 14:43 | 2024-11-12 |  | 2025-04-22 |  | 164.2978 | 159.3868 | -45769 | 2024-11-27 11:26 | 2024-12-06 06:47 | 2024-12-28 16:51 | 5.6591 | -762.8167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [10 empty] | Y | [7 empty] | N/A | CY6-0769 | 0 | 164.2978 | 0 | 164.2978 | 5.6591 | 100 |  | 9.1036 | 9.1036 | 1.6667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103897542', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-18 |  |  | CBG | X24051787930 | DITO TELECOMMUNITY CORPORATION | BLOCK 46, PINAGSAMA PH 2 VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 96.6585 | 93.66 | 22 | NEW | 1090877.69 | 77836.89 |  | 0% | 2024-11-11 15:11 | 2024-11-17 18:14 | 2024-11-15 | 2025-05-06 | 2025-05-06 14:31 |  | 175.9722 | 169.8451 | -45783.6049 | 2024-12-01 17:14 | 2024-12-10 20:59 | 2024-12-31 15:11 | 5.717 | -763.0601 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-07-05 14:31 | 111.3951 | [8 empty] | FOR AUDIT |  | 2025-05-21 14:31 | 51.3951 | 2025-05-06 | 2025-07-12 | [8 empty] | Y | 2025-05-05 | [6 empty] | 2024-11-20 | C8-1139, 212145, C8-1141, C8-0637 | 0 | 175.9722 | 0 | 175.9722 | 5.717 | 85.3951 |  | 8.4913 | 8.4913 | 1.4233 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051787930', | ME166067 |  |  |  | SCHED | SRO
2024-11-18 |  |  | CBG | X24072841870 | DITO TELECOMMUNITY CORPORATION | KALANTAS, PUROK 7, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Digging locations with drainage. For drainage diversion | W/ ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 338.404 | 1933.01 | 31 | NEW | 2161081.48 | 272131.35 |  | 0% | 2024-11-11 15:18 | 2024-11-17 18:18 | 2025-01-23 |  |  |  | -45607.6375 | -45613.7625 | 0 | 2024-12-08 02:43 | 2024-12-18 23:22 | 2024-12-31 15:18 | -1160.461 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-20 | B7-0938, B7-8118, B7-0949, B7-8119, B7-8120, B7-0947, B7-8121, 523080, B7-0946 | 0 | -45607.6375 | 0 | -45607.6375 | -1160.461 | 0 |  | 6.6502 | 6.6502 | 0 | 248.3625 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072841870', | ME166067 |  |  |  | SCHED | Isan Carlo Lazaro
2024-11-21 |  |  | HMB | X24083444240 | WOODRIDGE PROPERTIES INC. | BLOCK 5, DANAROSE RESIDENCES, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | STA. ROSA | FCOMP | Jasper Bastasa | 269.6164 | 269.62 | 32 | NEW | 1088892.82 | 217116.56 |  | 0% | 2024-11-11 16:04 | 2024-11-17 18:11 | 2024-11-14 |  | 2025-05-31 |  | 200.3306 | 194.2424 | -45808 | 2024-12-03 12:55 | 2024-12-13 04:04 | 2024-12-31 16:04 | 6.0417 | -763.4667 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | assigned to ACEC (SRO) |  | 2025-06-15 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-11-27 | CT7-5300, CS7-5491, CS7-8098, 522047, CS7-8105, CT7-5298, CS7-8104, CS7-8106, CS7-8107, CS7-8097, CT7-5295 | 0 | 200.3306 | 0 | 200.3306 | 6.0417 | 61 |  | 7.8814 | 7.8814 | 1.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083444240', | ME184184 |  |  |  | SCHED | Jenneth Madrid
2024-11-19 |  |  | CBG | X24114362991 | MAKATI DEVELOPMENT CORPORATION, | RAMBUTAN, FTI CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 165.6074 | 141.68 | 0 | TERMINATION | 135321.43 | 133359.74 |  | 0% | 2024-11-11 16:12 | 2024-11-17 18:16 | 2024-11-15 |  | 2025-01-31 |  | 80.325 | 74.2389 | -45688 | 2024-12-02 21:10 | 2024-12-12 08:05 | 2024-12-31 16:12 | 2.4887 | -761.4667 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | CHECKING OF SERVICE ITEM |  | 2025-02-15 | 6 | 2024-11-21 | 2025-02-21 | 2025-04-23 | ECI | N |  |  |  | 2025-06-09 | NVP | Y | 2024-11-20 | [6 empty] | N/A | B7-0169 | 0 | 80.325 | 0 | 80.325 | 2.4887 | 181 |  | 8.0966 | 8.0966 | 3.0167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114362991', | ME185284 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-11-22 |  |  | CBG | X24062084382 | AMAIA LAND CORP. | ISABELA, AMAIA STEPS SUCAT, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | customer holds execution; incorrect location of project | W/ ISSUE | AVECO | TECO | Ronilo Gange Jr. | 264.7906 | 465.25 | 97 | NEW | 2640728.35 | 213253.55 |  | 0% | 2024-11-12 14:26 | 2024-11-20 09:27 | 2024-11-14 |  | 2025-01-31 | 2025-06-24 | 79.3986 | 71.6062 | 144 | 2024-12-04 15:10 | 2024-12-14 07:22 | 2025-01-01 14:26 | 2.379 | 2.4 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-04-01 | 207 | [7 empty] | 2025-01-31 | PAID |  | 2025-02-15 | -15 | 2025-05-06 | 2025-01-31 | 2025-06-16 | ECI | Y |  | 2025-06-17 | 2025-06-17 | 2025-06-20 | NVP | Y | [7 empty] | 2024-11-27 | CX9-5827, CX9-8034, 522222, CX9-8035 | 0 | 79.3986 | 0 | 79.3986 | 2.379 | 181 |  | 7.8024 | 7.8024 | 3.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062084382', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-11-22 |  |  | HMB | R23605089 | CHAN JULIE TANG, | NORTH LUZON, PHILAMLIFE VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | CLOSED-CAN | Ronilo Gange Jr. | 144.1848 | #N/A | 0 | RELOC | 345112.37 | 116117.1 |  | 0% | 2024-11-12 16:32 | 2024-11-20 09:31 | 2024-11-21 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2025-01-01 16:32 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | 2024-11-27 | CW7-1170, CW7-8078, 350025, CV6-0063 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23605089', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-12-11 |  |  | CBG | R19938231 | DEPARTMENT OF TRANSPORTATION | LAGUERTA, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 123.4648 | 123.46 | 0 | RELOC | 248190.54 | 99425.59 |  | 0% | 2024-11-12 17:08 | 2024-11-20 09:57 | 2024-11-15 |  |  |  | -45608.7139 | -45616.4146 | 0 | 2024-12-03 22:06 | 2024-12-13 09:01 | 2025-01-01 17:08 | -1413.0905 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | DR1-5135,DR2-5696,DR1-0552,DR25697,DR1-0046 | 0 | -45608.7139 | 0 | -45608.7139 | -1413.0905 | 0 |  | 8.0644 | 8.0644 | 0 | 247.2861 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R19938231', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-11-22 |  |  | CBG | X24051847714 | DITO TELECOMMUNITY CORPORATION | BLOCK 5, ENLISTED PERSONNEL VIL 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | with pole location issue; request for joint survey | W/O ISSUE | VJC | DCOMP | Jenneth Madrid | 143.6218 | #N/A | 31 | NEW | 754908.68 | 115655.3 |  | 0% | 2024-11-14 14:38 | 2024-11-20 06:49 | 2024-11-21 |  |  |  | -45610.61 | -45616.284 | 0 | #N/A | #N/A | 2025-01-03 14:38 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-27 | C8-0532, C8-8044, 517915 | 0 | -45610.61 | 0 | -45610.61 | #N/A | 0 |  | #N/A | #N/A | 0 | 245.39 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051847714', | ME185284 |  |  |  | DCOMP | Jenneth Madrid
2024-11-22 |  | Y | HMB | R23611939 | DPWH DEO LAS PINAS-MUNTI, | MARCOS ALVAREZ, TALON V, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Done pole erection retirement nalang po ng poste hindi po maretire ang poste kasi may gumagawa po ng kalsada |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 80.4941 | 158.78 | 0 | RELOC | 246953.97 | 64820.26 |  | 0% | 2024-11-14 16:10 | 2024-11-20 10:02 | 2024-11-20 |  |  |  | -45610.6734 | -45616.4181 | 0 | 2024-12-05 21:08 | 2024-12-15 08:03 | 2025-01-03 16:10 | -1413.1512 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-27 | CU8-8102 | 0 | -45610.6734 | 0 | -45610.6734 | -1413.1512 | 0 |  | 8.0037 | 8.0037 | 0 | 245.3266 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23611939', | ME185284 |  |  |  | SCHED | Isan Carlo Lazaro
2024-11-27 |  | Y | HMB | X23020656225 | JENNIFER AUSTRIA BARZAGA | LAUAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | SSP Dec 26 | W/O ISSUE | CHALLENGER | FCOMP | Jemuel Peralta | 421.59 | 813 | 127.5 | NEW | 1822047.68 | 338008.24 |  | 0% | 2024-11-15 | 2024-11-25 | 2024-12-05 |  | 2025-01-02 |  | 48 | 38 | -45659 | 2024-12-08 | 2024-12-18 | 2025-01-04 | 1.41 | -830.17 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 39 | 2025-03-03 | 236 | [8 empty] | ON GOING MAT RETURN |  | 2025-01-17 | 28 | 2025-01-02 | 2025-02-14 | 2025-05-12 | RAC |  |  |  |  | 2025-07-25 | NVP | Y | [7 empty] | 2024-11-28 | CU9-2353, CU9-8009, CU9-0017, CU9-8010, CU9-0760, CU9-0761, CU9-0492, CU9-8011, 516197, CU9-0491 | 0 | 48 | 0 | 48 | 1.41 | 210 |  | 7.5787 | 7.5787 | 3.5 |  | REV |  | 2025-07-25 | 188724.53 | NTC ISSUED | 2025-07-28 |  | 29 |  |  |  | 'X23020656225', | ME185130 |  |  |  | FCOMP | JSP
2024-11-27 |  |  | HMB | X24093771340 | STO. CRISTO PROPERTIES & HOLDINGS CORP. | PASCUAL, PARANAQUE GREEN HEIGHTS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | TO TRANSFER ALL ISSUED MATERIALS FROM X24051519918 and transfer all SI | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 18.878 | 77.25 | 114 | NEW | 42608.01 | 15202.2 |  | 0% | 2024-11-15 15:38 | 2024-11-25 15:05 | 2024-11-21 |  | 2025-02-05 |  | 81.349 | 71.3715 | -45693 | 2024-12-04 03:07 | 2024-12-12 20:34 | 2025-01-04 15:38 | 2.8406 | -761.55 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-04-06 | 202 | [8 empty] | FOR AUDIT |  | 2025-02-20 | 25 | 2025-03-05 | 2025-03-17 | [8 empty] | Y | 2025-02-03 | [6 empty] | N/A | CY9-1108, CY9-8039 | 0 | 81.349 | 0 | 81.349 | 2.8406 | 176 |  | 8.9862 | 8.9862 | 2.9333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093771340', | ME166067 |  |  |  | FCOMP | Jenneth Madrid
2025-05-22 | 2025-05-14 |  | CBG | X24062083547 | DITO TELECOMMUNITY CORPORATION | M.L. QUEZON, PUROK 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | New design released 5/8/2025 | W/ ISSUE | CHALLENGER | INPRG | Isan Carlo Lazaro | 40.2713 | 998.11 | 22 | NEW | 270682.98 | 32429.44 |  | 0% | 2024-11-18 | 2025-05-12 10:16 | 2025-05-13 |  |  |  | -45614 | -45789.4278 | 0 | 2024-12-12 20:02 | 2024-12-23 06:11 | 2025-01-07 | -1229.0439 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-05-22 | DY2-8053, TLN-522520 | 0 | -45614 | 0 | -45614 | -1229.0439 | 0 |  | 6.8708 | 6.8708 | 0 | 242 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062083547', | ME166067 |  |  |  | DCOMP | Jenneth Madrid
2024-11-27 |  |  | HMB | X24093681665 | DANIELA MARIE ORCINE NAPILI | BLOCK 2, BAMBOO BREEZE RESIDENCES, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 10.98 | 13.95 | 1.5 | NEW | 31712.56 | 8842.15 |  | 0% | 2024-11-18 11:01 | 2024-11-26 10:54 | 2024-11-20 |  | 2025-03-20 |  | 121.5409 | 113.5458 | -45736 | 2024-12-07 05:36 | 2024-12-16 00:57 | 2025-01-07 11:01 | 4.1864 | -762.2667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-19 | 159 | [8 empty] | NO COC |  | 2025-04-04 | #VALUE! | [10 empty] | Y | [7 empty] | N/A | CU5-6018, CU6-2053 | 0 | 121.5409 | 0 | 121.5409 | 4.1864 | 133 |  | 8.7675 | 8.7675 | 2.2167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093681665', | ME155242 |  |  |  | FCOMP | Isan Carlo Lazaro
2024-11-27 |  |  | BIZ | X24072541358 | WILHOME DEVELOPMENT INC. | MOLINO ROAD, MOLINO III, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | POWERHOUSE | TECO | Jenneth Madrid | 93.062 | 88.72 | 120 | NEW | 833293.59 | 74940.47 | 107086.83 | 142.9% | 2024-11-18 14:12 | 2024-11-26 10:55 | 2024-11-20 | 2025-01-07 | 2025-01-09 | 2025-05-26 16:06 | 51.4085 | 43.5451 | 137.6708 | 2024-12-07 01:41 | 2024-12-15 19:09 | 2025-01-07 14:12 | 1.7951 | 2.2945 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-03-10 | 229 | [8 empty] | PAID |  | 2025-01-24 | 25 | 2025-01-07 | 2025-02-18 | 2025-04-29 | AGD | N |  | 2025-05-14 |  | 2025-05-13 | NVP | Y | 2025-01-07 | [6 empty] | 2024-11-27 | CS7-8119, 522705 | 0 | 51.4085 | 0 | 51.4085 | 1.7951 | 203 |  | 8.8836 | 8.8836 | 3.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072541358', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-02 |  |  | HMB | X24093502622 | GINA BAGASIN ECLIPSE | KALAYAAN VILL/BALAGBAG, KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 3.4 | 3.4 | 1.5 | RECONTRACT OF SERVICE | 25036.83 | 2739.2 |  | 0% | 2024-11-19 09:52 | 2024-11-28 07:57 | 2024-11-27 |  | 2025-02-11 |  | 83.5886 | 74.6687 | -45699 | 2024-12-08 04:27 | 2024-12-16 23:49 | 2025-01-08 09:52 | 2.8792 | -761.65 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | FOR AUDIT |  | 2025-02-26 | -6 | 2025-02-11 | 2025-02-20 | [16 empty] | N/A |  | 0 | 83.5886 | 0 | 83.5886 | 2.8792 | 170 |  | 8.7347 | 8.7347 | 2.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093502622', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-28 |  |  | BIZ | X24103919469 | NOR BARQUILLA CUBERO | GARNET, SEVERINA DIAMOND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 83.1652 | 83.17 | 66 | NEW | 372611.01 | 66970.92 |  | 0% | 2024-11-19 17:58 | 2024-11-27 10:01 | 2024-11-27 |  | 2025-01-27 |  | 68.2516 | 60.5826 | -45684 | 2024-12-09 01:10 | 2024-12-17 23:54 | 2025-01-08 17:58 | 2.2954 | -761.4 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-03-28 | 211 | [8 empty] | NO COC |  | 2025-02-11 | #VALUE! | [10 empty] | Y | 2025-01-23 | [6 empty] | 2024-11-28 | DX1-5182, DX1-8096, 526080 | 0 | 68.2516 | 0 | 68.2516 | 2.2954 | 185 |  | 8.5173 | 8.5173 | 3.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103919469', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-02 |  |  | CBG | X24103880983 | GLOBE TELECOM, INC. | BUHAY NA TUBIG, MOLINO III, BACOOR | BACOOR CITY | DASMA | SSP Feb 1, 2025 | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 26.1465 | 26.15 | 23 | NEW | 206737.88 | 21055.08 |  | 0% | 2024-11-20 10:02 | 2024-11-28 08:10 | 2024-11-28 |  | 2025-01-31 |  | 71.5821 | 63.6597 | -45688 | 2024-12-09 04:37 | 2024-12-17 23:58 | 2025-01-09 10:02 | 2.4656 | -761.4667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | NO COC |  | 2025-02-15 | #VALUE! | [10 empty] | Y | 2025-01-30 | [6 empty] | N/A | TLN-197564 | 0 | 71.5821 | 0 | 71.5821 | 2.4656 | 181 |  | 8.7 | 8.7 | 3.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103880983', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-12-02 |  |  | CBG | X23093531555 | EDOTCO TOWERS, INC. | PROGRESSIVE, PROGRESSIVE VILLAGE 15, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 36.0138 | 36.01 | 23 | MODIFICATION | 219117.43 | 29025.16 |  | 0% | 2024-11-20 10:11 | 2024-11-28 08:08 | 2024-11-28 |  | 2025-01-30 |  | 70.5754 | 62.6611 | -45687 | 2024-12-09 04:46 | 2024-12-18 00:08 | 2025-01-09 10:11 | 2.4309 | -761.45 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | NO COC |  | 2025-02-14 | #VALUE! | [18 empty] | 2024-12-23 | TLN-870204 | 0 | 70.5754 | 0 | 70.5754 | 2.4309 | 182 |  | 8.6998 | 8.6998 | 3.0333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23093531555', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-11-28 |  |  | HMB | X24104029330 | NOEMI A SUMINISTRADO | MILLARES, PUROK 4B, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | SSP 1/10 |  | VJC | CLOSED-CAN | Jenneth Madrid | 19.5603 | #N/A | 15 | NEW | 187691.5 | 15751.46 |  | 0% | 2024-11-20 10:38 | 2024-11-28 07:59 | 2024-11-27 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2025-01-09 10:38 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | Y | [7 empty] | N/A | A8-5396, 193411, A8-1155 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104029330', | ME185284 |  |  |  | COMP-CAN | Jenneth Madrid
2024-12-02 |  |  | HMB | X24104113256 | MA. VICTORIA DE LUNA DUQUE | OSORIO COMPOUND, SITIO DE ASIS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 61.1395 | 61.14 | 31.5 | NEW | 318987.77 | 49234.13 |  | 0% | 2024-11-20 16:49 | 2024-11-28 08:01 | 2024-11-27 |  | 2025-01-09 |  | 49.2996 | 41.666 | -45666 | 2024-12-10 18:52 | 2024-12-19 22:36 | 2025-01-09 16:49 | 1.6016 | -761.1 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-03-10 | 229 | [8 empty] | NO COC |  | 2025-01-24 | #VALUE! | [18 empty] | 2024-12-21 | DZI-0289,DZI-8040,TLN-526312 | 0 | 49.2996 | 0 | 49.2996 | 1.6016 | 203 |  | 8.1967 | 8.1967 | 3.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104113256', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-28 |  |  | CBG | X24114479034 | MAKATI DEVELOPMENT CORPORATION | NEXUS, ARCA SOUTH, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 196.5066 | 195.12 | 0 | TERMINATION | 157531.83 | 158282.26 |  | 0% | 2024-11-21 09:08 | 2024-11-27 14:21 | 2024-11-27 | 2025-02-01 | 2025-02-01 |  | 71.6196 | 65.4021 | -45689 | 2024-12-12 14:06 | 2024-12-22 01:01 | 2025-01-10 09:08 | 2.219 | -761.4833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-04-02 | 206 | [8 empty] | FOR AUDIT |  | 2025-02-16 | 152 | 2025-02-01 | 2025-07-18 | [8 empty] | Y | 2024-11-27 | [6 empty] | N/A | B8-6208 | 0 | 71.6196 | 0 | 71.6196 | 2.219 | 180 |  | 7.7959 | 7.7959 | 3 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114479034', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-28 |  |  | HMB | X24093707345 | CITY GOVERNMENT OF TAGUIG | MAGSAYSAY, ZONE 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | need to complete conjunct ECProject | W/ ISSUE | VJC | CLOSE | Jenneth Madrid | 83.8543 | 89.29 | 157 | NEW | 715296.24 | 67525.75 | 72249.91 | 107% | 2024-11-21 12:51 | 2024-11-28 08:13 | 2024-11-27 |  | 2025-01-26 | 2025-04-30 | 65.4645 | 58.6576 | 94 | 2024-12-10 00:20 | 2024-12-18 17:48 | 2025-01-10 12:51 | 2.2859 | 1.5667 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-03-27 | 212 | [8 empty] | PAID | PAID | 2025-02-10 | 25 | 2025-01-26 | 2025-03-07 | 2025-04-01 | AGD | Y |  |  |  | 2025-04-02 | NVP | Y | 2025-01-22 | [6 empty] | 2024-11-28 | B8-0701, 523895 | 0 | 65.4645 | 0 | 65.4645 | 2.2859 | 186 |  | 8.7808 | 8.7808 | 3.1 |  | REV |  |  |  | NTC ISSUED |  |  | 0 |  |  |  | 'X24093707345', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-28 | N/A |  | HMB | X24083141279 | VILLA FER-FLOR STA. TERESA NEIGHBORHOOD ASSN. INC | BLOCK 2, VILLA FER FLOR SUBDIVISION, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | STA. ROSA | SCHED | Frinz Raelmer Catindig | 226.0445 | 683.94 | 30 | NEW | 1063185.59 | 182029.11 |  | 0% | 2024-11-21 13:52 | 2024-11-28 08:15 | 2024-11-28 |  |  |  | -45617.5774 | -45624.3438 | 0 | 2024-12-16 09:54 | 2024-12-26 20:03 | 2025-01-10 13:52 | -1229.1403 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-28 | DY2-8080, DY2-8081, DY2-8082, 523344, DY2-8083, DY2-8089, DY2-8090, DY2-8103, DY2-8086, DY2-8091 | 0 | -45617.5774 | 0 | -45617.5774 | -1229.1403 | 0 |  | 6.7744 | 6.7744 | 0 | 238.4226 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083141279', | ME188584 |  |  |  | SCHED | Jenneth Madrid
2024-11-28 | N/A |  | HMB | X24093488253 | VILLA FER-FLOR STA. TERESA NEIGHBORHOOD ASSN. INC | BLOCK 1, VILLA FER FLOR SUBDIVISION, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | STA. ROSA | SCHED | Frinz Raelmer Catindig | 225.3589 | 756.33 | 22.5 | NEW | 1106973.1 | 181099.46 |  | 0% | 2024-11-21 13:53 | 2024-11-28 08:17 | 2024-11-28 |  |  |  | -45617.5785 | -45624.3451 | 0 | 2024-12-16 09:55 | 2024-12-26 20:04 | 2025-01-10 13:53 | -1229.1403 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-28 | DY2-8077, DY2-8078, 523689, DY2-8094, DY2-8095, DY2-8096, DY2-8097, DY2-8098, DY2-8099, DY2-8100 | 0 | -45617.5785 | 0 | -45617.5785 | -1229.1403 | 0 |  | 6.7744 | 6.7744 | 0 | 238.4215 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093488253', | ME188584 |  |  |  | SCHED | Jenneth Madrid
2024-11-28 | N/A |  | HMB | X24083140896 | VILLA FER-FLOR STA. TERESA NEIGHBORHOOD ASSN. INC | BLOCK 1, VILLA FER FLOR SUBDIVISION, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | STA. ROSA | SCHED | Troy Mazaredo | 498.1623 | 1497.63 | 22.5 | NEW | 2213932.19 | 401159.44 |  | 0% | 2024-11-22 10:45 | 2024-11-28 08:21 | 2024-11-28 |  |  |  | -45618.4479 | -45624.3479 | 0 | 2024-12-18 22:10 | 2024-12-29 18:49 | 2025-01-11 10:45 | -1160.7361 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-11-28 | DY2-5309, DY2-5310, DY2-8075, DY2-8076, DY2-8077, DY2-8078, DY2-8080, DY2-8081, DY2-8084, DY2-8085, TLN-523342, DY2-8086, DY2-8087, DY2-8088, DY2-8101, DY2-8102 | 0 | -45618.4479 | 0 | -45618.4479 | -1160.7361 | 0 |  | 6.3752 | 6.3752 | 0 | 237.5521 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083140896', | ME192555 |  |  |  | SCHED | Jenneth Madrid
2024-11-28 |  |  | BIZ | X24073004630 | PHILIPPINE SEVEN CORPORATION | UMALI, POBLACION, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 45.667 | 45.67 | 44 | NEW | 381529.43 | 36774.45 | 18714.58 | 50.89% | 2024-11-22 10:58 | 2024-11-27 10:06 | 2024-11-27 |  | 2025-01-06 |  | 44.5434 | 39.5792 | -45663 | 2024-12-11 05:32 | 2024-12-20 00:54 | 2025-01-11 10:58 | 1.5343 | -761.05 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-07 | 232 | [8 empty] | FOR AUDIT |  | 2025-01-21 | 99 | 2025-01-04 | 2025-04-30 | [8 empty] | Y | [7 empty] | 2024-11-28 | DR2-8020, 523167 | 0 | 44.5434 | 0 | 44.5434 | 1.5343 | 206 |  | 8.6298 | 8.6298 | 3.4333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24073004630', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-11-29 |  |  | HMB | X24104049812 | RACHEL RIVERA BACALLA | ILANG-ILANG, DON JUAN BAYVIEW SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 50.0617 | 50.06 | 70 | NEW | 363185.56 | 40313.42 |  | 0% | 2024-11-22 12:54 | 2024-11-28 08:33 | 2024-11-27 |  | 2025-02-07 |  | 76.4623 | 70.6438 | -45695 | 2024-12-10 14:41 | 2024-12-19 05:34 | 2025-01-11 12:54 | 2.7212 | -761.5833 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | FOR AUDIT |  | 2025-02-22 | 125 | 2025-02-03 | 2025-06-27 | [8 empty] | Y | 2025-02-04 | [6 empty] | 2024-11-29 | DX1-0290, 523391, DX2-8015 | 0 | 76.4623 | 0 | 76.4623 | 2.7212 | 174 |  | 8.9135 | 8.9135 | 2.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104049812', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-02 |  | Y | BIZ | X24020649090 | MICHAEL CHRISTIAN R. PICHEL | M.L. QUEZON, PUROK 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Completed, for re-trigger of PO and route to FCOMP |  | VJC | TECO | Jenneth Madrid | 68.0405 | 339.78 | 49 | NEW | 525931.28 | 54791.3 | 138590.65 | 252.9% | 2024-11-22 15:22 | 2024-11-28 08:28 | 2024-11-27 | 2025-01-12 | 2025-01-12 | 2025-08-11 10:41 | 50.3599 | 44.6472 | 211.4451 | 2024-12-15 02:41 | 2024-12-24 21:42 | 2025-01-11 15:22 | 1.4828 | 3.5241 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-03-13 | 226 | [8 empty] | PAID | FULLY BILLED | 2025-01-27 | 93 | 2025-01-12 | 2025-04-30 | 2025-07-01 | ECI | Y |  |  |  | 2025-07-04 | NVP | [8 empty] | 2024-12-19 | 520809,DY2-8042 | 0 | 50.3599 | 0 | 50.3599 | 1.4828 | 200 |  | 7.3717 | 7.3717 | 3.3333 |  | REV |  | 2025-07-14 | 24103.2 | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020649090', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-02 |  | Y | BIZ | X24062171822 | M.H. BURTON REPAIR SERVICES, INC. | BLOCK 5, MAGDIWANG SUBD, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 240.5183 | 240.52 | 120 | NEW | 1126618.35 | 193724.47 |  | 0% | 2024-11-22 15:24 | 2024-11-28 08:31 | 2024-11-27 |  | 2025-03-26 |  | 123.3585 | 117.6451 | -45742 | 2024-12-12 15:44 | 2024-12-21 19:01 | 2025-01-11 15:24 | 4.0202 | -762.3667 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 2025-05-25 | 153 | [8 empty] | NO COC |  | 2025-04-10 | #VALUE! | [10 empty] | Y | 2025-03-05 | [6 empty] | 2024-12-23 | CT7-2306,CT7-8090,CT7-2218,CT7-8091,CT7-8092,TLN-434054 | 0 | 123.3585 | 0 | 123.3585 | 4.0202 | 127 |  | 8.159 | 8.159 | 2.1167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062171822', | ME185284 |  |  |  | FCOMP | SRO
2024-11-28 |  |  | BIZ | X24114483448 | MILLENIUM ERECTORS CORPORATION | ALABANG-ZAPOTE, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 35.07 | 35.07 | 0 | TERMINATION | 36680.51 | 28249.06 |  | 0% | 2024-11-22 15:38 | 2024-11-27 10:08 | 2024-11-27 |  | 2025-03-19 |  | 116.3487 | 111.5778 | -45735 | 2024-12-11 10:13 | 2024-12-20 05:34 | 2025-01-11 15:38 | 4.0076 | -762.25 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-18 | 160 | [8 empty] | NO COC |  | 2025-04-03 | #VALUE! | [10 empty] | Y | 2025-01-14 | [6 empty] | N/A | CV9-5929 | 0 | 116.3487 | 0 | 116.3487 | 4.0076 | 134 |  | 8.6231 | 8.6231 | 2.2333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114483448', | ME185284 |  |  |  | FCOMP | SRO
2024-12-02 |  |  | HMB | X24072816217 | JERICK MARTIN C. FELIZARDO | PALO-ALTO SUBD, PALO-ALTO SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 73.3844 | 151.67 | 16.5 | NEW | 409734.62 | 58717.23 |  | 0% | 2024-11-22 18:56 | 2024-11-28 08:35 | 2024-11-28 |  | 2025-04-14 |  | 142.2109 | 136.6424 | -45761 | 2024-12-13 23:54 | 2024-12-23 10:50 | 2025-01-11 18:56 | 4.4061 | -762.6833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-06-13 | 134 | [8 empty] | NO COC |  | 2025-04-29 | #VALUE! | [10 empty] | Y | 2025-04-11 | [6 empty] | 2024-12-19 | CW5-8034,047134,CW5-0290 | 0 | 142.2109 | 0 | 142.2109 | 4.4061 | 108 |  | 7.7523 | 7.7523 | 1.8 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072816217', | ME155242 |  |  |  | FCOMP | SRO
2024-12-02 |  |  | HMB | X24051781334 | MARIA NATALIA ORIG PALMA | BELMONT, ALABANG 400 VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 56.18 | 134.46 | 106 | MODIFICATION | 386016.72 | 45264.51 |  | 0% | 2024-11-25 08:38 | 2024-11-29 12:45 | 2024-11-27 |  | 2025-08-01 07:23 |  | 248.9482 | 244.7764 | -45870.3076 | 2024-12-14 19:20 | 2024-12-23 18:59 | 2025-01-14 08:38 | 8.3182 | -764.5051 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-09-30 07:23 | 24.6924 | [8 empty] | NO COC | AUDITED | 2025-08-16 07:23 | #VALUE! |  |  | 2025-08-13 | RLM | [6 empty] | Y | 2025-07-23 | [6 empty] | 2024-12-23 | DV1-0795,DV1-8050,TLN-521987, | 0 | 248.9482 | 0 | 248.9482 | 8.3182 | -1.3076 |  | 8.2745 | 8.2745 | -0.021794 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051781334', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-02 |  |  | HMB | R23701790 | DAGUMANPAN, CORNELIA A. | STA. MARIA, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 9.1265 | 9.13 | 0 | RELOC | 20018.21 | 7349.37 |  | 0% | 2024-11-25 16:26 | 2024-11-29 12:41 | 2024-11-29 |  | 2024-12-20 |  | 24.315 | 20.4715 | -45646 | 2024-12-14 11:01 | 2024-12-23 06:23 | 2025-01-14 16:26 | 0.83752 | -760.7667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-02-18 | 249 | [8 empty] | NO COC |  | 2025-01-04 | #VALUE! | [18 empty] | N/A | CY9-8052 | 0 | 24.315 | 0 | 24.315 | 0.83752 | 223 |  | 8.5186 | 8.5186 | 3.7167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23701790', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-02 |  |  | HMB | X24072851053 | DIOSA BELLE SANTILLANOSA CRUCERO | BLOCK 27, PUROK 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 9.8995 | 9.9 | 1.5 | NEW | 28231.84 | 7971.81 |  | 0% | 2024-11-25 17:25 | 2024-11-29 12:51 | 2024-11-27 |  | 2025-03-08 |  | 102.2745 | 98.4646 | -45724 | 2024-12-14 11:59 | 2024-12-23 07:21 | 2025-01-14 17:25 | 3.5228 | -762.0667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-07 | 171 | [8 empty] | FOR AUDIT |  | 2025-03-23 | 99 | 2025-03-08 | 2025-06-30 | [16 empty] | N/A | A7-0928 | 0 | 102.2745 | 0 | 102.2745 | 3.5228 | 145 |  | 8.5172 | 8.5172 | 2.4167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072851053', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-10 |  |  | HMB | X24114538494 | JOHN PAULE RODRIGUEZ | TINDALO, UNITED PQUE PH 2 SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 99.131 | 177.41 | 85 | MODIFICATION | 232274.33 | 79450.9 |  | 0% | 2024-11-26 17:07 | 2024-11-29 12:55 | 2024-11-29 |  |  |  | -45622.7133 | -45625.5382 | 0 | 2024-12-17 01:24 | 2024-12-26 06:49 | 2025-01-15 17:07 | -1465.7071 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-12-10 | A7-0442, A7-8058, ALB1-3261, 520470, A7-0426 | 0 | -45622.7133 | 0 | -45622.7133 | -1465.7071 | 0 |  | 7.9124 | 7.9124 | 0 | 233.2867 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114538494', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-05 |  |  | HMB | X24093766777 | ESMAIL FAIDAH BARODI | DON PEDRO, GARCIA HEIGHTS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 168.6255 | 471.59 | 51 | MODIFICATION | 881252.87 | 135412.87 |  | 0% | 2024-11-26 17:08 | 2024-11-29 13:05 | 2024-12-03 |  | 2025-06-13 |  | 198.2864 | 195.4549 | -45821 | 2024-12-18 17:52 | 2024-12-28 10:04 | 2025-01-15 17:08 | 5.9413 | -763.6833 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-08-12 | 74 | [8 empty] | NO COC |  | 2025-06-28 | #VALUE! | [10 empty] | Y | 2025-06-26 | [6 empty] | 2024-12-10 | CX9-0820, DX1-8095, DX1-8097, DX1-8098, DX1-8092, 523988 | 0 | 198.2864 | 0 | 198.2864 | 5.9413 | 48 |  | 7.3795 | 7.3795 | 0.8 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093766777', | ME185284 |  |  |  | INPRG | RONILO GANGE JR.
2024-12-02 |  |  | HMB | X24072854687 | MALILIN O. RICSENIA | BLOCK 12, BETTER LIVING ANX31 SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | TECO | Jenneth Madrid | 47.7807 | 48.49 | 4.6 | NEW | 176013.59 | 38476.96 | 24449.62 | 63.54% | 2024-11-26 17:08 | 2024-11-29 12:57 | 2024-12-03 |  | 2025-02-14 | 2025-06-28 | 79.2859 | 76.4604 | 134 | 2024-12-15 11:43 | 2024-12-24 07:04 | 2025-01-15 17:08 | 2.731 | 2.2333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-15 | 193 | [8 empty] | PAID | WITH BACKJOB | 2025-03-01 | 2 | 2025-02-14 | 2025-03-03 | 2025-04-08 | AGD | Y |  |  |  | 2025-06-09 | NVP | Y | 2025-02-14 | [6 empty] | 2024-12-19 | DY1-1530,DY1-1530,DY1-5916 | 0 | 79.2859 | 0 | 79.2859 | 2.731 | 167 |  | 8.4832 | 8.4832 | 2.7833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072854687', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2025-02-27 |  |  | HMB | X24104023531 | LOWELL L. YU | NARRA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 88.4315 | 88.43 | 156 | MODIFICATION | 528318.36 | 71228.03 |  | 0% | 2024-11-27 10:23 | 2024-12-04 09:17 | 2024-11-29 |  | 2025-02-08 |  | 72.5671 | 65.6132 | -45696 | 2024-12-15 21:53 | 2024-12-24 15:20 | 2025-01-16 10:23 | 2.5339 | -761.6 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-04-09 | 199 | [8 empty] | NO COC |  | 2025-02-23 | #VALUE! | [18 empty] | N/A |  | 0 | 72.5671 | 0 | 72.5671 | 2.5339 | 173 |  | 8.5748 | 8.5748 | 2.8833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104023531', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-04 |  |  | BIZ | X24104037169 | CHRISTIAN BIBLE BAPTIST CHURCH AND MINISTRIES OF S | IMPEX CPD, IMPEX CPD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 14.3403 | 14.34 | 21 | MODIFICATION | 144365.55 | 11170.37 |  | 0% | 2024-11-27 13:58 | 2024-12-04 09:38 | 2024-11-29 |  | 2025-04-28 |  | 151.4183 | 144.5986 | -45775 | 2024-12-16 08:32 | 2024-12-25 03:54 | 2025-01-16 13:58 | 5.2155 | -762.9167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-27 | 120 | [8 empty] | NO COC |  | 2025-05-13 | #VALUE! | [18 empty] | 2024-12-19 | CW8-5091,526220 | 0 | 151.4183 | 0 | 151.4183 | 5.2155 | 94 |  | 8.4533 | 8.4533 | 1.5667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104037169', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-12-10 |  |  | HMB | X24114393200 | MACRO GOLDEN STAR CORP, | ALABANG-ZAPOTE, PAMPLONA II, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 21.4403 | 21.44 | 4.9 | RECONTRACT OF SERVICE | 142345.36 | 17273.42 |  | 0% | 2024-11-27 14:00 | 2024-12-04 09:22 | 2024-11-29 |  | 2025-02-08 |  | 72.417 | 65.6097 | -45696 | 2024-12-16 08:34 | 2024-12-25 03:56 | 2025-01-16 14:00 | 2.4944 | -761.6 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-09 | 199 | [8 empty] | NO COC |  | 2025-02-23 | #VALUE! | [10 empty] | Y | 2024-12-06 | [6 empty] | 2024-12-10 | CW7-2221, 104426 | 0 | 72.417 | 0 | 72.417 | 2.4944 | 173 |  | 8.4533 | 8.4533 | 2.8833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114393200', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-12-12 |  |  | CBG | X24030891625 | DITO TELECOMMUNITY CORPORATION | AMPARO, POBLACION, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For completion Jan 31, 2025 | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 110.9425 | 1094.61 | 20 | NEW | 1144190.62 | 89339.7 |  | 0% | 2024-11-27 18:15 | 2024-12-04 09:14 | 2024-11-29 |  | 2025-01-31 |  | 64.2392 | 57.6153 | -45688 | 2024-12-24 05:41 | 2025-01-04 02:20 | 2025-01-16 18:15 | 1.6345 | -761.4667 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | NO COC |  | 2025-02-15 | #VALUE! | [10 empty] | Y | 2025-01-30 | [6 empty] | 2024-12-19 | 195632,DR2-5748,DR2-5749,212278 | 0 | 64.2392 | 0 | 64.2392 | 1.6345 | 181 |  | 6.24 | 6.24 | 3.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030891625', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-12-10 |  |  | HMB | X24051731952 | TARASH B. BERMUDEZ | MONIQUE, VILLA CRISTINA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 70.4238 | 39.19 | 3 | NEW | 324422.71 | 42905.86 |  | 0% | 2024-11-29 09:37 | 2024-12-05 10:08 | 2024-12-04 |  | 2025-05-02 |  | 153.5993 | 147.5778 | -45779 | 2024-12-18 04:12 | 2024-12-26 23:33 | 2025-01-18 09:37 | 5.2906 | -762.9833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-01 | 116 | [8 empty] | NO COC |  | 2025-05-17 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-12-10 | CW7-8053, CW7-2005, 522055 | 0 | 153.5993 | 0 | 153.5993 | 5.2906 | 90 |  | 8.3906 | 8.3906 | 1.5 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051731952', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-05 |  | Y | HMB | X24093863040 | AIRA NAVARRO JUBILADO | A. MABINI, TUAZON SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Pending problem with R/Way |  | AVECO | FCOMP | Ronilo Gange Jr. | 113.706 | 347.15 | 20 | NEW | 622295.41 | 91565.09 |  | 0% | 2024-11-29 09:41 | 2024-12-04 09:44 | 2024-12-03 |  | 2025-06-24 |  | 206.5965 | 201.5944 | -45832 | 2024-12-21 21:00 | 2024-12-31 16:01 | 2025-01-18 09:41 | 6.0831 | -763.8667 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-08-23 | 63 | [8 empty] | NO COC |  | 2025-07-09 | #VALUE! | [10 empty] | Y | 2025-06-20 | [6 empty] | 2024-12-10 | CX6-2484, CX6-8132, CX6-8133, 526058, CX6-0061, CX6-8134 | 0 | 206.5965 | 0 | 206.5965 | 6.0831 | 37 |  | 7.1726 | 7.1726 | 0.61667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093863040', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-10 |  |  | CBG | X24114645553 | BGST PRIME DEVELOPMENT CORP. | COASTAL RD, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 599.0932 | 1539.4 | 1528 | NEW | 1597363.95 | 482059.02 |  | 0% | 2024-11-29 14:03 | 2024-12-06 14:40 | 2024-12-13 |  | 2025-01-30 |  | 61.4145 | 54.3889 | -45687 | 2024-12-14 21:05 | 2024-12-22 18:09 | 2025-01-18 14:03 | 2.518 | -761.45 | 50 | 20 | 18.2927 | 23.1707 | 15.2927 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | ON GOING MAT RETURN |  | 2025-02-14 | -15 | 2025-04-22 | 2025-01-30 | 2025-07-18 | AGD | Y |  |  |  | 2025-08-01 | NVP | [8 empty] | 2024-12-23 | CZ7-0528,CZ7-8032,CZ7-8033,CZ7-8034,CZ7-8035,CZ7-8036,CZ7-8037,CZ7-8038,CZ7-8039,CZ7-8040,CZ7-8041,CZ7-8042,CZ7-0475 | 0 | 61.4145 | 0 | 61.4145 | 2.518 | 182 |  | 9.98 | 9.98 | 3.0333 |  | REV |  | 2025-08-04 | 112663.22 | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114645553', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2025-02-27 |  |  | HMB | X24093852320 | ALEXANDRA MARIE PAMINTUAN CRUZ | ST. BERNADETTE, SAN JOSE SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | STA. ROSA | FCOMP | Jasper Bastasa | 222.7607 | 456.21 | 80 | NEW | 899400.28 | 178653.51 |  | 0% | 2024-12-02 08:43 | 2024-12-09 15:26 | 2024-12-17 |  | 2025-06-17 08:00 |  | 196.9704 | 189.6903 | -45825.3333 | 2024-12-24 09:27 | 2025-01-03 01:39 | 2025-01-21 08:43 | 5.9019 | -763.7556 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-08-16 08:00 | 69.6667 | [8 empty] | NO COC |  | 2025-07-02 08:00 | #VALUE! | [18 empty] | 2024-02-27 | CU9-0314,DV1-8077,DV1-8078,DV1-8079,TLN-523975 | 0 | 196.9704 | 0 | 196.9704 | 5.9019 | 43.6667 |  | 7.2103 | 7.2103 | 0.72778 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093852320', | ME184184 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-04 |  |  | CBG | X24114645437 | SM DEVELOPMENT CORPORATION, | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | conj. to reloc WO R23208322 |  | VJC | CLOSED-CAN | Jenneth Madrid | 32.5667 | #N/A | 0 | NEW | 144072.26 | 26225.13 |  | 0% | 2024-12-02 15:31 | 2024-12-04 10:15 | 2024-12-17 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2025-01-21 15:31 | #VALUE! | #VALUE! | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [10 empty] | N | [7 empty] | N/A | CZ8-8102 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114645437', | ME185284 |  |  |  | CLOSED-CAN | Jenneth Madrid
2024-12-10 |  |  | CBG | X23124692592 | BGST PRIME DEVELOPMENT CORP. | COASTAL RD, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 49.3391 | 158.78 | 1528 | NEW | 760153.47 | 38066.29 |  | 0% | 2024-12-02 15:32 | 2024-12-06 14:42 | 2024-12-13 |  | 2025-01-30 |  | 58.3527 | 54.3875 | -45687 | 2024-12-15 18:19 | 2024-12-23 01:27 | 2025-01-21 15:32 | 2.7156 | -761.45 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | NO COC |  | 2025-02-14 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-12-10 | CZ7-0475, 515959 | 0 | 58.3527 | 0 | 58.3527 | 2.7156 | 182 |  | 11.1856 | 11.1856 | 3.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23124692592', | ME155242 |  |  |  | FCOMP | SRO
2024-12-10 |  |  | HMB | X24041187690 | CITY GOV'T OF LAS PINAS | S. TOLENTINO, GATCHALIAN SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 38.7024 | 139.91 | 47 | MODIFICATION | 202593.53 | 31166.05 |  | 0% | 2024-12-02 16:20 | 2024-12-09 15:30 | 2024-12-11 |  | 2025-04-22 |  | 140.3196 | 133.3542 | -45769 | 2024-12-23 21:18 | 2025-01-02 08:13 | 2025-01-21 16:20 | 4.3475 | -762.8167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [10 empty] | Y | 2025-04-04 | [6 empty] | 2024-12-10 | CY8-8034, CY8-8035, 521456, CY7-0020 | 0 | 140.3196 | 0 | 140.3196 | 4.3475 | 100 |  | 7.4458 | 7.4458 | 1.6667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041187690', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-10 |  |  | HMB | X24114420508 | HERMINIO VALERIO | BANABA, CAMELLA SPV CENTRAL PH 2, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 47.6533 | 47.65 | 4 | MODIFICATION | 227444.85 | 38373.64 |  | 0% | 2024-12-02 16:24 | 2024-12-09 15:15 | 2024-12-10 |  |  |  | -45628.6831 | -45635.6354 | 0 | 2024-12-21 10:58 | 2024-12-30 06:20 | 2025-01-21 16:24 | -1571.6546 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-12-10 | CS7-0681, 193090, CS7-0689, CS7-0688, CS7-0687, CS7-0686 | 0 | -45628.6831 | 0 | -45628.6831 | -1571.6546 | 0 |  | 8.2776 | 8.2776 | 0 | 227.3169 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114420508', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-12-12 |  |  | BIZ | X24104112560 | METRO STONERICH CORPORATION, | INDOCHINA LANE, FILINVEST CORPORATE CITY, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 54.72 | 54.72 | 0 | TERMINATION | 49996.03 | 44193.54 |  | 0% | 2024-12-02 16:41 | 2024-12-09 15:29 | 2024-12-17 |  | 2025-02-04 |  | 63.3046 | 56.3549 | -45692 | 2024-12-22 18:44 | 2024-12-31 22:29 | 2025-01-21 16:41 | 2.0566 | -761.5333 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-05 | 203 | [8 empty] | FOR AUDIT |  | 2025-02-19 | 2 | 2025-02-04 | 2025-02-21 | [8 empty] | Y | [7 empty] | N/A |  | 0 | 63.3046 | 0 | 63.3046 | 2.0566 | 177 |  | 7.807 | 7.807 | 2.95 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104112560', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-13 |  |  | HMB | R23806071 | EL GRANDE DEVELOPMENT CORPORATION,, HMB | BAGTIKAN, BF EL GRANDE, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 44.7327 | 120.41 | 0 | RELOC | 157460.57 | 36022.34 |  | 0% | 2024-12-03 15:15 | 2024-12-10 09:03 | 2024-12-16 |  |  |  | -45629.6354 | -45636.3771 | 0 | 2024-12-24 20:13 | 2025-01-03 07:08 | 2025-01-22 15:15 | -1413.7387 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [8 empty] | CU7-2198, CU7-8052 | 0 | -45629.6354 | 0 | -45629.6354 | -1413.7387 | 0 |  | 7.4162 | 7.4162 | 0 | 226.3646 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23806071', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-11 |  |  | HMB | X24062164559 | EDWARD VINCENT SANTOS DAUIGOY | BLOCK 6, TOP MAN VILLAGE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 220.036 | 611.45 | 25.7 | MODIFICATION | 1029760.65 | 175680.33 |  | 0% | 2024-12-03 15:57 | 2024-12-10 09:01 | 2024-12-16 |  |  |  | -45629.6646 | -45636.3757 | 0 | 2024-12-28 11:59 | 2025-01-07 22:08 | 2025-01-22 15:57 | -1229.466 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2024-12-16 | CW8-2008, CW8-8026, CW8-8027, CW8-8028, CW8-8044, CW8-8029, 522385, CW8-2007 | 0 | -45629.6646 | 0 | -45629.6646 | -1229.466 | 0 |  | 6.4488 | 6.4488 | 0 | 226.3354 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062164559', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2025-02-27 |  |  | HMB | X24104312412 | SEVRANDO OLAES LAPUZ | BLOCK 6, MAGDIWANG SUBD, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 58.044 | 58.04 | 73.4 | NEW | 495870.33 | 46765.49 |  | 0% | 2024-12-04 09:18 | 2024-12-09 15:28 | 2024-12-17 |  | 2025-04-04 |  | 120.6125 | 115.3556 | -45751 | 2024-12-23 16:31 | 2025-01-01 15:14 | 2025-01-23 09:18 | 4.0564 | -762.5167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-06-03 | 144 | [8 empty] | NO COC |  | 2025-04-19 | #VALUE! | [10 empty] | Y | 2025-03-31 | [6 empty] | 2024-02-27 | CT7-8139,TLN-526439 | 0 | 120.6125 | 0 | 120.6125 | 4.0564 | 118 |  | 8.0249 | 8.0249 | 1.9667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104312412', | ME184184 |  |  |  | FCOMP | Jenneth Madrid
2024-12-12 |  |  | BIZ | X24093767977 | BIGBANG REALTY AND DEVELOPMENT CORPORATION | ANIBAN I, ANIBAN I, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 341.1727 | 341.17 | 624 | NEW | 2236672.58 | 274874.86 | 100960.52 | 36.73% | 2024-12-04 17:05 | 2024-12-10 09:04 | 2024-12-17 |  | 2025-01-06 |  | 32.2882 | 26.6222 | -45663 | 2024-12-20 06:15 | 2024-12-28 04:57 | 2025-01-23 17:05 | 1.3056 | -761.05 | 30 | 23 | 18.5484 | 23.4946 | 15.5484 | 60 | 57 | 52 | 2025-03-07 | 232 | [8 empty] | FOR AUDIT |  | 2025-01-21 | 63 | 2025-01-07 | 2025-03-25 | [8 empty] | Y | [7 empty] | 2024-12-16 | CX6-1466, 518626, CX6-8027, CX6-8043 | 0 | 32.2882 | 0 | 32.2882 | 1.3056 | 206 |  | 9.6351 | 9.6351 | 3.4333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093767977', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-16 |  |  | HMB | X24083392619 | RONILO LANSANG DAVID | LAPU-LAPU, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | completed 1/12/2025 |  | ECOM | FCOMP | Ronilo Gange Jr. | 144.56 | 145.04 | 69 | NEW | 655324.42 | 116411.06 | 32061.14 | 27.54% | 2024-12-04 17:24 | 2024-12-10 09:05 | 2024-12-17 |  | 2025-01-15 |  | 41.275 | 35.6215 | -45672 | 2024-12-25 01:41 | 2025-01-03 07:05 | 2025-01-23 17:24 | 1.326 | -761.2 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-03-16 | 223 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-01-30 | -8 | 2025-01-12 | 2025-01-22 | [8 empty] | Y | [7 empty] | 2024-12-16 | C5-0076, C5-8177, ALB1-2896, C5-8178, 523569, C5-0077, C5-0040 | 0 | 41.275 | 0 | 41.275 | 1.326 | 197 |  | 7.655 | 7.655 | 3.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083392619', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-11 |  |  | BIZ | X24020533373 | GRUPPO SACHIN & SACHIN CO. | SAN VICTORES, SEACOM CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | TECO | Jenneth Madrid | 17.4303 | 21.38 | 23 | NEW | 178449.2 | 14036.19 | 9864.61 | 70.28% | 2024-12-04 17:37 | 2024-12-10 09:00 | 2024-12-17 | 2025-01-11 | 2025-01-11 | 2025-05-20 10:53 | 37.266 | 31.625 | 129.4535 | 2024-12-23 12:12 | 2025-01-01 07:33 | 2025-01-23 17:37 | 1.2836 | 2.1576 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-12 | 227 | [8 empty] | PAID | FULLY BILLED | 2025-01-26 | 36 | 2025-01-11 | 2025-03-03 | 2025-03-27 | AGD | Y |  |  |  | 2025-04-10 | NVP | Y | [7 empty] | N/A | DX1-1148, 087077 | 0 | 37.266 | 0 | 37.266 | 1.2836 | 201 |  | 8.2069 | 8.2069 | 3.35 |  | REV |  |  |  | NTC ISSUED |  |  | 0 |  |  |  | 'X24020533373', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-13 |  |  | CBG | X24083423327 | NATIONAL RESEARCH COUNCIL OF THE PHILIPPINES | GEN. SANTOS, UPPER BICUTAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 43.93 | 43.93 | 0 | MODIFICATION | 100355.03 | 35399.87 |  | 0% | 2024-12-05 12:41 | 2024-12-12 10:46 | 2024-12-17 |  | 2025-01-18 |  | 43.4715 | 36.5514 | -45675 | 2024-12-24 07:16 | 2025-01-02 02:37 | 2025-01-24 12:41 | 1.4974 | -761.25 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-19 | 220 | [8 empty] | ON GOING MAT RETURN |  | 2025-02-02 | 78 | 2025-01-18 | 2025-04-21 | [6 empty] | 2025-08-12 | NVP | Y | 2025-01-17 | [6 empty] | N/A | DZ1-0632, 035245 | 0 | 43.4715 | 0 | 43.4715 | 1.4974 | 194 |  | 8.1796 | 8.1796 | 3.2333 |  | NON-REV |  | 2025-08-12 | 19630.58 | NTC ISSUED | 2025-08-15 |  | 11 |  |  |  | 'X24083423327', | ME185284 |  |  |  | FCOMP | RONILO GANGE JR.
2024-12-20 |  |  | HMB | X24114379540 | DHAN JERICO MIKE M. DELOS SANTOS | BLOCK 11, VISTA VERDE SOUTH PH I, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | TECO | Ronilo Gange Jr. | 24.1333 | 24.13 | 48 | MODIFICATION | 207326.18 | 19433.91 | 22138.38 | 113.9% | 2024-12-05 14:12 | 2024-12-12 09:54 | 2024-12-17 | 2025-02-08 | 2025-02-08 | 2025-08-06 21:43 | 64.4083 | 57.5875 | 179.9049 | 2024-12-24 08:47 | 2025-01-02 04:08 | 2025-01-24 14:12 | 2.2185 | 2.9984 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-09 | 199 | [8 empty] | PAID |  | 2025-02-23 | -16 | 2024-12-28 | 2025-02-07 | 2025-07-01 | AGD | N |  |  |  | 2025-07-09 | NVP | [8 empty] | 2024-12-20 | CU6-6516,TLN-526581 | 0 | 64.4083 | 0 | 64.4083 | 2.2185 | 173 |  | 8.1774 | 8.1774 | 2.8833 |  | NON-REV |  | 2025-07-10 | 4159.74 | NTC ISSUED | 2025-07-10 |  | 47 |  |  |  | 'X24114379540', | ME155242 |  |  |  | FCOMP | RONILO GANGE JR.
2025-02-27 |  |  | HMB | X24093702490 | BARANGAY MOLINO VI | EVERLASTING, SOLDIER'S HILLS 4 PH II, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 73.845 | 152.13 | 20 | NEW | 367358.69 | 59466.29 |  | 0% | 2024-12-05 16:09 | 2024-12-12 09:56 | 2024-12-16 |  | 2025-02-07 |  | 63.3271 | 56.5861 | -45695 | 2024-12-26 21:07 | 2025-01-05 08:02 | 2025-01-24 16:09 | 1.9621 | -761.5833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | NO COC |  | 2025-02-22 | #VALUE! | [10 empty] | Y | 2025-02-06 | [6 empty] | 2025-02-27 | CT7-8117,TLN-523915 | 0 | 63.3271 | 0 | 63.3271 | 1.9621 | 174 |  | 7.3531 | 7.3531 | 2.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093702490', | ME155242 |  |  |  | FCOMP | Jenneth Madrid
2024-12-13 |  | Y | HMB | X24093725089 | RUBEN LEYVA TERRADO | PILAR, ST. JOSEPH SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 167.3971 | 167.4 | 131.5 | NEW | 833252.11 | 134801.61 |  | 0% | 2024-12-06 12:56 | 2024-12-12 10:48 | 2024-12-17 |  | 2025-01-11 |  | 35.4611 | 29.55 | -45668 | 2024-12-25 23:38 | 2025-01-03 23:18 | 2025-01-25 12:56 | 1.1849 | -761.1333 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-03-12 | 227 | [8 empty] | NO COC |  | 2025-01-26 | #VALUE! | [10 empty] | Y | 2025-01-10 | [6 empty] | 2024-12-16 | CX8-0536, CV9-8058, CX8-0537, CV9-8059, CV9-8060, 523891, CV9-2409-S | 0 | 35.4611 | 0 | 35.4611 | 1.1849 | 201 |  | 7.901 | 7.901 | 3.35 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093725089', | ME185284 |  |  |  | FCOMP | Jenneth Madrid
2024-12-23 |  |  | HMB | X24041001641 | FILINVEST LAND, INC. | BLOCK 2, PRINCETON HEIGHTS PH 3, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 222.4466 | 611.06 | 43.69 | NEW | 1006242.08 | 179131.86 |  | 0% | 2024-12-06 15:29 | 2024-12-12 10:49 | 2024-12-17 |  | 2025-05-31 |  | 175.3549 | 169.5493 | -45808 | 2024-12-31 11:31 | 2025-01-10 21:40 | 2025-01-25 15:29 | 4.7248 | -763.4667 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | NO COC |  | 2025-06-15 | #VALUE! | [10 empty] | Y | 2025-06-25 | [6 empty] | 2024-12-23 | CV6-6330,CV6-8035,CV6-8036,CV6-8037,CV6-8038,TLN-521175,CV6-8039 | 0 | 175.3549 | 0 | 175.3549 | 4.7248 | 61 |  | 6.3685 | 6.3685 | 1.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041001641', | ME155242 |  |  |  | SCHED | Jenneth Madrid
2024-12-15 |  |  | HMB | X24062388683 | MARC MEDALLA O'CONNOR | ARAGONA, CITADELLA EXEC VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 4.2367 | 342.89 | 40.1 | MODIFICATION | 63407.7 | 3411.92 |  | 0% | 2024-12-09 15:08 | 2025-01-20 15:00 | 2024-12-17 |  | 2025-05-29 14:47 |  | 170.9854 | 128.991 | -45806.616 | 2025-01-01 02:27 | 2025-01-10 21:28 | 2025-01-28 15:08 | 5.0346 | -763.4436 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-07-28 14:47 | 88.384 | System Error | Y | Y |  |  | 2024-12-20 | 18 | 2025-01-07 | NO COC |  | 2025-06-13 14:47 | #VALUE! | [10 empty] | Y | 2025-05-29 | [6 empty] | 2024-02-27 | CX8-8154,CX8-8155,CX8-8156,CX8-8157,CX8-8158,CX8-8092,TLN-522627 | 0 | 170.9854 | 18 | 152.9854 | 4.5046 | 62.384 |  | 6.8714 | 6.8714 | 1.0397 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062388683', | ME185284 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-19 |  |  | BIZ | X24104277409 | COMGLASCO AGUILA GLASS CORP. | MANALAC, BAGONG TANYAG, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 60.2846 | 143.57 | 63 | NEW | 525751.37 | 52572.05 |  | 0% | 2024-12-10 09:20 | 2024-12-16 14:19 | 2024-12-19 | 2025-01-11 | 2025-01-11 |  | 31.6109 | 25.4035 | -45668 | 2024-12-30 17:37 | 2025-01-08 23:02 | 2025-01-29 09:20 | 1.0156 | -761.1333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-03-12 | 227 | [8 empty] | FOR AUDIT |  | 2025-01-26 | 173 | 2025-01-11 | 2025-07-18 | [16 empty] | 2024-12-19 | DZ2-8122,526339 | 0 | 31.6109 | 0 | 31.6109 | 1.0156 | 201 |  | 7.473 | 7.473 | 3.35 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104277409', | ME185284 |  |  |  | #N/A | RONILO GANGE JR.
2024-12-23 | 2024-12-21 |  | CBG | X24114628777 | HOUSEHOLD DEVELOPMENT CORPORATION | BARCELONA, BRIA FLATS LAS PIÑAS, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  | W/O ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 99.8407 | 99.84 | 0 | TERMINATION | 89332.4 | 80399.21 |  | 0% | 2024-12-10 09:24 | 2024-12-16 14:18 | 2024-12-17 |  |  |  | -45636.3917 | -45642.5958 | 0 | 2024-12-30 11:27 | 2025-01-08 15:12 | 2025-01-29 09:24 | -1482.6316 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45636.3917 | 0 | -45636.3917 | -1482.6316 | 0 |  | 7.557 | 7.557 | 0 | 219.6083 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114628777', | ME155242 |  |  |  | SCHED | RONILO GANGE JR.
2024-12-16 |  |  | CBG | X24114608975 | LIGHT RAIL MANILA CORPORATION | NINOY AQUINO, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | VJC | FCOMP | Jayson Ramores | 41.7111 | 133.03 | 4999 | NEW | 810419.94 | 33589.2 |  | 0% | 2024-12-10 09:38 | 2024-12-17 15:06 | 2024-12-17 |  | 2025-03-10 |  | 89.5983 | 82.3708 | -45726 | 2024-12-23 12:25 | 2024-12-30 19:33 | 2025-01-29 09:38 | 4.1698 | -762.1 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 2025-05-09 | 169 | [8 empty] | NO COC |  | 2025-03-25 | #VALUE! | [10 empty] | Y | [7 empty] | N/A | A5-5544, A5-5530, A5-1070, A5-8015, A5-8016, A5-8018 | 0 | 89.5983 | 0 | 89.5983 | 4.1698 | 143 |  | 10.8248 | 10.8248 | 2.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114608975', | ME171160 |  |  |  | #N/A | RONILO GANGE JR.
2025-02-27 |  |  | CBG | X24114608824 | DITO TELECOMMUNITY CORPORATION | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | emailed request for drainage diversion last Feb. 7 (no update yet) | W/ ISSUE | VJC | FCOMP | Jenneth Madrid | 80.9276 | 456.41 | 31 | NEW | 644480.07 | 65169.08 |  | 0% | 2024-12-10 10:10 | 2024-12-16 14:17 | 2024-12-16 |  | 2025-04-12 |  | 122.5764 | 116.4049 | -45759 | 2025-01-02 10:45 | 2025-01-12 09:18 | 2025-01-29 10:10 | 3.5326 | -762.65 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 2025-06-11 | 136 | [8 empty] | NO COC |  | 2025-04-27 | #VALUE! | [10 empty] | Y | 2025-04-21 | [6 empty] | 2024-12-27 | B7-8108,TLN-522135 | 0 | 122.5764 | 0 | 122.5764 | 3.5326 | 110 |  | 6.7027 | 6.7027 | 1.8333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114608824', | ME185284 |  |  |  | #N/A | RONILO GANGE JR.
2024-12-19 |  |  | HMB | X24093530616 | SPRINGTOWN DEVELOPMENT CORPORATION | SUSANA, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | Waiting for RTPI Schedule |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 72.2079 | 72.21 | 0 | MODIFICATION | 73744.25 | 58147.16 |  | 0% | 2024-12-10 11:58 | 2024-12-16 14:20 | 2024-12-17 | 2025-05-25 | 2025-04-25 |  | 135.5012 | 129.4028 | -45772 | 2024-12-30 14:01 | 2025-01-08 17:46 | 2025-01-29 11:58 | 4.4022 | -762.8667 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-06-24 | 123 | [8 empty] | FOR AUDIT |  | 2025-05-10 | 5 | 2025-04-25 10:48 | 2025-05-15 | [8 empty] | Y | [7 empty] | N/A |  | 0 | 135.5012 | 0 | 135.5012 | 4.4022 | 97 |  | 7.5535 | 7.5535 | 1.6167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093530616', | ME166067 |  |  |  |  | RONILO GANGE JR.
2024-12-16 |  |  | BIZ | X24104064373 | MA. CECILIA FLORES MAGAT | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 52.0785 | 52.08 | 80 | NEW | 393602.3 | 41961.69 |  | 0% | 2024-12-10 15:43 | 2024-12-16 14:08 | 2024-12-17 |  | 2025-03-17 |  | 96.3453 | 90.4111 | -45733 | 2024-12-29 22:55 | 2025-01-07 21:39 | 2025-01-29 15:43 | 3.2403 | -762.2167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-16 | 162 | [8 empty] | NO COC |  | 2025-04-01 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-12-16 | CZ8-8053, CZ8-8101, 526286 | 0 | 96.3453 | 0 | 96.3453 | 3.2403 | 136 |  | 7.8142 | 7.8142 | 2.2667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104064373', | ME185284 |  |  |  |  | RONILO GANGE JR.
2025-01-23 |  |  | CBG | X24103986359 | DITO TELECOMMUNITY CORPORATION | QUEEN OF DIAMOND, QUEEN'S ROW AREA A SUBD, BACOOR | BACOOR CITY | DASMA |  | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 288.6292 | 288.63 | 22 | NEW | 1649653.47 | 231671.38 |  | 0% | 2024-12-10 15:59 | 2024-12-16 14:16 | 2024-12-17 | 2025-01-24 | 2025-01-30 |  | 50.3342 | 44.4056 | -45687 | 2025-01-01 12:49 | 2025-01-11 03:59 | 2025-01-29 15:59 | 1.518 | -761.45 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | FOR AUDIT |  | 2025-02-14 | 167 | 2025-01-24 | 2025-07-31 | [16 empty] | 2025-01-23 | CS7-8136,CS7-8138,TLN-201851,CS7-8139,TLN-082385 | 0 | 50.3342 | 0 | 50.3342 | 1.518 | 182 |  | 7.0069 | 7.0069 | 3.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103986359', | ME185284 |  |  |  |  | RONILO GANGE JR.
2024-12-23 |  |  | BIZ | X24114379635 | CITYLAND DEVELOPMENT CORPORATION | ALABANG-ZAPOTE, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 29.505 | 29.51 | 139 | NEW | 810419.94 | 23759.63 |  | 0% | 2024-12-11 12:23 | 2024-12-18 09:46 | 2024-12-17 |  | 2025-01-20 |  | 39.484 | 32.5931 | -45677 | 2024-12-28 20:31 | 2025-01-06 06:41 | 2025-01-30 12:23 | 1.456 | -761.2833 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-03-21 | 218 | [8 empty] | NO COC |  | 2025-02-04 | #VALUE! | [10 empty] | Y | 2025-01-14 | [6 empty] | N/A | TLN-055640 | 0 | 39.484 | 0 | 39.484 | 1.456 | 192 |  | 8.536 | 8.536 | 3.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114379635', | ME185284 |  |  |  |  | RONILO GANGE JR.
2024-12-16 | 2024-12-27 |  | BIZ | X24051975891 | FANG LIN OASIS CORPORATION | QUIRINO, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | ECOM | TECO | Ronilo Gange Jr. | 144.6317 | 144.63 | 247 | NEW | 975572.44 | 116492.84 | 56036.87 | 48.1% | 2024-12-11 13:23 | 2024-12-16 14:12 | 2024-12-17 | 2025-02-06 | 2025-02-06 | 2025-07-17 20:48 | 56.4424 | 51.4083 | 161.8667 | 2024-12-30 01:34 | 2025-01-07 19:12 | 2025-01-30 13:23 | 1.9682 | 2.6978 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-04-07 | 201 | [8 empty] | PAID |  | 2025-02-21 | 14 | 2025-02-06 | 2025-03-07 | 2025-06-12 | ECI | Y |  |  |  | 2025-07-09 | NVP | Y | 2025-02-05 | [6 empty] | 2024-12-16 | C5-0273, 522214, C5-8087 | 0 | 56.4424 | 0 | 56.4424 | 1.9682 | 175 |  | 8.0708 | 8.0708 | 2.9167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051975891', | ME155242 |  |  |  |  | RONILO GANGE JR.
2024-12-16 | 2024-12-21 | Y | BIZ | X24103956559 | LILY REAL ESTATE DEVELOPMENT CORPORATION | QUIRINO, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 187.6016 | 228.97 | 395 | NEW | 1391926.53 | 151199.6 |  | 0% | 2024-12-11 13:24 | 2024-12-16 14:14 | 2024-12-17 | 2025-04-04 | 2025-04-04 |  | 113.4418 | 108.4069 | -45751 | 2024-12-29 13:24 | 2025-01-07 03:48 | 2025-01-30 13:24 | 4.0515 | -762.5167 | 28 | 28 | 21 | 26.6 | 18 | 60 | 57 | 52 | 2025-06-03 | 144 | [8 empty] | NO COC |  | 2025-04-19 | #VALUE! | [10 empty] | Y | 2025-04-22 | [6 empty] | 2024-12-16 | C5-8144, C5-8145, 526083 | 0 | 113.4418 | 0 | 113.4418 | 4.0515 | 118 |  | 8.2658 | 8.2658 | 1.9667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103956559', | ME155242 |  |  |  |  | RONILO GANGE JR.
2024-12-19 |  |  | HMB | X24073016208 | KISE GAYLE RAMOS TANG | COUNTRY CLUB, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | waiting for schedule | W/O ISSUE | CHALLENGER | TECO | Jemuel Peralta | 283.2732 | 273.21 | 890.5 | NEW | 1564214.32 | 227012.78 | 219336.99 | 96.62% | 2024-12-11 14:23 | 2024-12-18 09:53 | 2024-12-17 |  | 2025-01-09 | 2025-06-12 | 28.401 | 21.5882 | 154 | 2024-12-26 19:49 | 2025-01-03 16:28 | 2025-01-30 14:23 | 1.1687 | 2.5667 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 2025-03-10 | 229 | [8 empty] | PAID |  | 2025-01-24 | 25 | 2025-01-09 | 2025-02-18 | 2025-05-12 | RAC |  |  |  |  | 2025-05-24 | NVP | Y | 2025-01-08 | [6 empty] | 2024-12-19 | CS9-0022,523221,CS9-8031,CS9-8078 | 0 | 28.401 | 0 | 28.401 | 1.1687 | 203 |  | 9.5219 | 9.5219 | 3.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24073016208', | ME185130 |  |  |  |  | RONILO GANGE JR.
2024-12-15 |  | Y | BIZ | X24104044893 | SONAK HOLDINGS CORPORATION | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 55.05 | 55.05 | 177 | NEW | 141821.41 | 44330.4 | 4026.35 | 9.083% | 2024-12-11 14:30 | 2024-12-13 09:47 | 2024-12-16 | 2025-03-19 | 2025-03-19 09:27 |  | 97.7899 | 95.9861 | -45735.3938 | 2024-12-30 01:59 | 2025-01-07 19:27 | 2025-01-30 14:30 | 3.4147 | -762.2566 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-05-18 09:27 | 159.6062 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-04-03 09:27 | 40.6062 | 2025-03-18 | 2025-05-14 | [8 empty] | Y | 2025-03-17 | [6 empty] | N/A | 262402 | 0 | 97.7899 | 0 | 97.7899 | 3.4147 | 133.6062 |  | 8.08 | 8.08 | 2.2268 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104044893', | ME155242 |  |  |  |  | Isan Carlo Lazaro
2024-12-16 |  |  | HMB | X23104201686 | MINGHAI SU | MATTHEW, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | waiting for schedule | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 52.731 | 52.73 | 63 | NEW | 428089.39 | 42462.88 |  | 0% | 2024-12-11 15:40 | 2024-12-16 14:11 | 2024-12-17 |  | 2025-02-24 |  | 74.3474 | 69.409 | -45712 | 2024-12-30 22:52 | 2025-01-08 21:36 | 2025-01-30 15:40 | 2.5004 | -761.8667 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-04-25 | 183 | [8 empty] | ON GOING MAT RETURN |  | 2025-03-11 | 2 | 2025-02-24 | 2025-03-13 | 2025-03-25 | AGD | N |  |  |  | 2025-06-10 | NVP | Y | 2025-02-21 | [6 empty] | 2024-12-16 | CZ8-8052, 519369 | 0 | 74.3474 | 0 | 74.3474 | 2.5004 | 157 |  | 7.7806 | 7.7806 | 2.6167 |  | REV |  | 2025-06-10 | 4001.31 | NTC ISSUED | 2025-06-10 |  | 77 | 2025-07-09 | 4001.31 | 2025-07-15 | 'X23104201686', | ME166067 |  |  |  |  | JSP
2024-12-16 | 2024-12-21 |  | HMB | X24051797098 | ERIC CHAN KE | MASBATE LOOP, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 64.907 | 152.37 | 117 | MODIFICATION | 410179.91 | 51914.54 |  | 0% | 2024-12-11 15:40 | 2024-12-16 14:10 | 2024-12-17 |  | 2025-05-22 |  | 161.3471 | 156.4097 | -45799 | 2024-12-31 02:23 | 2025-01-09 02:02 | 2025-01-30 15:40 | 5.3912 | -763.3167 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [10 empty] | Y | [7 empty] | 2024-12-16 | B4-8024, 522052 | 0 | 161.3471 | 0 | 161.3471 | 5.3912 | 70 |  | 7.7301 | 7.7301 | 1.1667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051797098', | ME155242 |  |  |  |  | Isan Carlo Lazaro
2024-12-19 |  |  | HMB | X24114498829 | VILLA LIGHT NEIGHBORHOOD ASSOCIATION INC. | BLOCK 10, VILLA LIGHT SUBD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  | W/O ISSUE | VJC | CLOSED-CAN | Jenneth Madrid | 394.3216 | #N/A | 225 | NEW | 2711379.35 | 317538.48 |  | 0% | 2024-12-11 16:03 | 2024-12-18 09:49 | 2024-12-17 |  | CLOSED-CAN |  | #VALUE! | #VALUE! | #VALUE! | #N/A | #N/A | 2025-01-30 16:03 | #VALUE! | #VALUE! | #N/A | 30 | #N/A | #N/A | #N/A | 60 | 57 | 52 | #VALUE! | [11 empty] | #VALUE! | #VALUE! | [18 empty] | 2024-12-19 | B8-6311,B8-5575,ALB1-1211,513940,58-6313,513940,B8-6313,513941,B8-8161,B8-6316,212061,B8-8162,B8-8163,B8-8164,B8-8165,B8-8166,B8-8167,B8-8168,B8-8169,B8-8170,B8-8171,B8-8172,B8-8173,B8-8175,B8-8176 | 0 | #VALUE! | 0 | #VALUE! | #VALUE! | #VALUE! |  | #N/A | #N/A | #VALUE! |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114498829', | ME185284 |  |  |  |  | Isan Carlo Lazaro
2024-12-19 |  |  | HMB | X24093717312 | MARIA PERLA G DATINGALING | J. DIAZ, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For schedule of digging |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 222.6366 | 222.64 | 20 | MODIFICATION | 693321.27 | 179284.96 |  | 0% | 2024-12-11 17:03 | 2024-12-18 09:43 | 2024-12-17 |  | 2025-06-09 |  | 179.2898 | 172.5951 | -45817 | 2025-01-02 13:53 | 2025-01-12 05:03 | 2025-01-30 17:03 | 5.4072 | -763.6167 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-08-08 | 78 | [8 empty] | NO COC |  | 2025-06-24 | #VALUE! | [10 empty] | Y | 2025-06-16 | [6 empty] | 2024-12-19 | CR9-0785, CR9-8043, CR9-8044, CR9-8045, CR9-8046, 526228, CR9-8047 | 0 | 179.2898 | 0 | 179.2898 | 5.4072 | 52 |  | 6.9754 | 6.9754 | 0.86667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093717312', | ME166067 |  |  |  |  | JSP
2025-03-04 | 2024-12-21 |  | BIZ | X24072720259 | RAMON GALVEZ VIZMONTE | MAMBOG IV, BACOOR | BACOOR CITY | DASMA |  | For Force Fcomp | AVECO | TECO | Ronilo Gange Jr. | 27.4528 | 59.46 | 196 | NEW | 647847.98 | 41915.62 | 50099.08 | 119.5% | 2024-12-12 | 2025-01-02 12:26 | 2024-12-19 | 2025-01-14 | 2025-01-14 | 2025-07-15 | 33 | 11.4819 | 182 | 2024-12-30 11:29 | 2025-01-08 04:57 | 2025-01-31 | 1.1523 | 3.0333 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-03-15 | 224 | [8 empty] | PAID |  | 2025-01-29 | -6 | 2025-01-17 | 2025-01-23 | 2025-06-23 | AGD | Y | [5 empty] | Y | 2025-01-13 | [6 empty] | 2025-03-04 | TLN-211819 | 0 | 33 | 0 | 33 | 1.1523 | 198 |  | 8.0662 | 8.0662 | 3.3 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072720259', | ME155242 |  |  |  |  | RONILO GANGE JR.
2024-12-23 | 2024-12-21 |  | CBG | X24062437670 | DITO TELECOMMUNITY CORPORATION | BETTERLIVING SUBD ANNEX 45, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | NEW HOA Members refused the energization of the tower |  | POWERHOUSE | PCAN3 | Isan Carlo Lazaro | 134.781 | #N/A | 22 | NEW | 567073.32 | 108536.04 |  | 0% | 2024-12-13 | 2024-12-20 13:08 | 2024-12-19 |  |  |  | -45639 | -45646.5472 | 0 | #N/A | #N/A | 2025-02-01 | #N/A | 0 | #N/A | 36 | #N/A | #N/A | #N/A | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2024-12-23 | A6-1003,A6-8032,A6-1404,A6-1010,TLN-522577,A6-1402 | 0 | -45639 | 0 | -45639 | #N/A | 0 |  | #N/A | #N/A | 0 | 217 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062437670', | ME185284 |  |  |  |  | RONILO GANGE JR.
2024-12-23 | 2024-12-21 |  | HMB | X24010237993 | ALEXANDER CREUS BONDOC | ARDEN, ST. JOSEPH SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | CLOSE | Jemuel Peralta | 24.9403 | 26.37 | 87.25 | NEW | 211369.87 | 20083.77 | 21352.49 | 106.3% | 2024-12-16 | 2024-12-20 13:12 | 2024-12-19 |  | 2025-01-15 | 2025-03-30 | 30 | 25.45 | 74 | 2025-01-03 01:47 | 2025-01-11 16:40 | 2025-02-04 | 1.0676 | 1.2333 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-03-16 | 223 | [8 empty] | PAID |  | 2025-01-30 | -5 | 2025-01-15 | 2025-01-25 | 2025-02-06 | ECI | Y |  |  |  | 2025-02-07 | NVP | Y | 2025-01-14 | [6 empty] | 2024-12-23 | CU9-2288,TLN-520302 | 0 | 30 | 0 | 30 | 1.0676 | 197 |  | 8.0785 | 8.0785 | 3.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010237993', | ME185130 |  |  |  |  | RONILO GANGE JR.
2024-12-23 | 2024-12-21 |  | HMB | X24010241125 | ALEXANDER CREUS BONDOC | ARDEN, ST. JOSEPH SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | CLOSE | Jemuel Peralta | 22.5203 | 24.15 | 87.25 | NEW | 206120.13 | 18135.01 | 19564.78 | 107.9% | 2024-12-16 | 2024-12-20 13:25 | 2024-12-19 |  | 2025-01-15 | 2025-03-30 | 30 | 25.441 | 74 | 2025-01-03 01:47 | 2025-01-11 16:40 | 2025-02-04 | 1.0676 | 1.2333 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-03-16 | 223 | [8 empty] | PAID |  | 2025-01-30 | -5 | 2025-01-15 | 2025-01-25 | 2025-02-06 | ECI | Y |  |  |  | 2025-02-07 | NVP | Y | 2025-01-14 | [6 empty] | 2024-12-23 | CU9-8036,TLN-520301 | 0 | 30 | 0 | 30 | 1.0676 | 197 |  | 8.0785 | 8.0785 | 3.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010241125', | ME185130 |  |  |  |  | Jenneth Madrid
2024-12-23 | 2024-12-27 |  | HMB | X24020497540 | THAYNE JARRETT TAN RECATO DY | BETTERLIVING SUBD ANNEX 29/32, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 69.3441 | 147.63 | 31 | MODIFICATION | 324019.03 | 55841.25 |  | 0% | 2024-12-16 | 2024-12-20 13:30 | 2024-12-27 |  |  |  | -45642 | -45646.5625 | 0 | 2025-01-06 04:58 | 2025-01-15 15:53 | 2025-02-04 | -1414.1218 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2024-12-27 | CY9-0660,TLN-520599 | 0 | -45642 | 0 | -45642 | -1414.1218 | 0 |  | 7.0331 | 7.0331 | 0 | 214 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020497540', | ME155242 |  |  |  |  | Jenneth Madrid
2025-01-03 | 2024-12-21 |  | HMB | X24114453678 | JENNIFER GALANG UY | KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 193.6015 | 193.6 | 83 | MODIFICATION | 746852.49 | 155928.48 |  | 0% | 2024-12-16 | 2024-12-20 13:29 | 2024-12-19 |  | 2025-05-29 14:52 |  | 164.6194 | 160.0576 | -45806.6194 | 2025-01-05 08:17 | 2025-01-14 13:41 | 2025-02-04 | 5.2887 | -763.4437 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-07-28 14:52 | 88.3806 | [8 empty] | NO COC |  | 2025-06-13 14:52 | #VALUE! | [10 empty] | Y | 2025-05-29 | [6 empty] | 2025-01-03 | CR9-0789,CR9-2362,CR9-8049,CR9-5016,CR9-5017,CR9-5010,CR9-8050,TLN-526521,CR9-5011 | 0 | 164.6194 | 0 | 164.6194 | 5.2887 | 62.3806 |  | 7.2928 | 7.2928 | 1.0397 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114453678', | ME185284 |  |  |  |  | RONILO GANGE JR.
2025-01-03 | 2024-12-27 |  | HMB | X24020423392 | GERMAN SELDAS MOTAR | MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 132.8714 | 166.07 | 140 | MODIFICATION | 613121.03 | 106644.8 | 85085.01 | 79.78% | 2024-12-17 | 2024-12-23 12:47 | 2024-12-27 | 2025-02-22 | 2025-02-22 |  | 67 | 60.4674 | -45710 | 2025-01-05 10:42 | 2025-01-14 10:22 | 2025-02-05 | 2.2387 | -761.8333 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-04-23 | 185 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-03-09 | -17 | 2025-04-11 | 2025-02-20 | [8 empty] | Y | 2025-02-20 | [6 empty] | 2025-01-03 | CZ8-0913,TLN-034953,CZ8-0915,TLN-520549,CZ8-0916,CZ8-0914 | 0 | 67 | 0 | 67 | 2.2387 | 159 |  | 7.5514 | 7.5514 | 2.65 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020423392', | ME155242 |  |  |  |  | Jenneth Madrid
2025-01-03 | 2024-12-21 |  | BIZ | X24114622443 | NELSON BALIGUAT RODRIGUEZ | ENLISTED PERSONNEL VIL 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | COMP | Jenneth Madrid | 39.92 | 39.92 | 21 | MODIFICATION | 78921.54 | 32146.36 | 15300.13 | 47.6% | 2024-12-17 | 2024-12-23 12:43 | 2024-12-19 | 2025-01-26 | 2025-01-26 | 2025-08-19 | 40 | 33.4701 | 205 | 2025-01-04 18:35 | 2025-01-13 13:56 | 2025-02-05 | 1.3778 | 3.4167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-27 | 212 | [8 empty] | PAID |  | 2025-02-10 | 25 | 2025-03-26 | 2025-03-07 | 2025-07-10 | RCL |  |  |  |  | 2025-08-16 | NVP | Y | 2025-01-23 | [6 empty] | N/A | B8-0946,TLN-117028,C8-0523, | 0 | 40 | 0 | 40 | 1.3778 | 186 |  | 7.7844 | 7.7844 | 3.1 |  | NON-REV |  | 2025-08-18 | 26877.28 | NTC ISSUED | 2025-08-18 |  | 8 |  |  |  | 'X24114622443', | ME185284 |  |  |  |  | Isan Carlo Lazaro
2025-01-06 | 2025-01-02 |  | HMB | X23093703275 | BARANGAY MANUYO DOS | TOLENTINO, GATCHALIAN SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 124.1581 | 146.68 | 17.8 | NEW | 650762.17 | 117362.26 |  | 0% | 2024-12-19 | 2024-12-23 12:52 | 2024-12-21 | 2025-04-17 | 2025-05-20 10:49 |  | 152.4507 | 0 | -45797.4507 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 4.7234 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 28.6 | 2025-07-19 10:49 | 97.5493 | [8 empty] | FOR AUDIT |  | 2025-06-04 10:49 | 32.5493 | 2025-04-17 | 2025-07-07 | [8 empty] | Y | 2025-05-16 | [6 empty] | 2025-01-06 | CY8-8023,CY8-8024,CY8-8025,TLN-518841 | 0 | 152.4507 | 0 | 152.4507 | 4.7234 | 71.5493 |  | 6.9402 | 6.9402 | 1.1925 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23093703275', | ME166067 |  |  |  |  | Jenneth Madrid
2025-01-03 | 2025-01-06 |  | HMB | X24093865089 | JOVY BITANGCOL LOSERIAGA | BLOCK 8, AFP OVAI PH 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | COMP | Jenneth Madrid | 3.58 | 11.56 | 42 | MODIFICATION | 41516.72 | 9308.95 |  | 0% | 2024-12-19 | 2024-12-23 12:44 | 2024-12-21 | 2025-01-11 | 2025-01-11 | 2025-08-21 | 23 | 0 | 222 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 0.79222 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 28.6 | 2025-03-12 | 227 | [8 empty] | PAID |  | 2025-01-26 | 40 | 2025-01-11 | 2025-03-07 | [6 empty] | 2025-08-12 | NVP | Y | 2025-01-07 | [6 empty] | N/A | TLN-142955 | 0 | 23 | 0 | 23 | 0.79222 | 201 |  | 7.7156 | 7.7156 | 3.35 |  | NON-REV |  | 2025-08-12 | 7540.14 | NTC ISSUED | 2025-08-15 |  | 11 |  |  |  | 'X24093865089', | ME185284 |  |  |  |  | Jenneth Madrid
2025-01-03 | 2025-01-03 |  | BIZ | X24114564095 | ROMAN CATHOLIC BISHOP OF IMUS, INCORPORATED | CAMELLA SPV CENTRAL PH 2, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 47.6185 | 149.93 | 54 | NEW | 434824.49 | 57699.09 |  | 0% | 2024-12-19 | 2024-12-23 12:41 | 2024-12-21 |  | 2025-04-22 |  | 124 | 0 | -45769 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 3.9837 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 28.6 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [10 empty] | Y | 2025-04-16 | [6 empty] | 2025-01-03 | CS7-0545,CS7-8118,TLN-522171,CS7-0685,CS7-0686 | 0 | 124 | 0 | 124 | 3.9837 | 100 |  | 7.1964 | 7.1964 | 1.6667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114564095', | ME155242 |  |  |  |  | RONILO GANGE JR.
2025-01-03 | 2025-01-02 |  | HMB | X24041002556 | STA. LUCIA REALTY & DEVELOPMENT, INC. | VISTA VERDE SOUTH EXEC PH4, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 125.0909 | 162.27 | 20 | NEW | 796877.5 | 130293.83 |  | 0% | 2024-12-20 | 2024-12-23 12:39 | 2024-12-21 | 2025-03-22 | 2025-05-12 |  | 143 | 0 | -45789 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 4.4306 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 28.6 | 2025-07-11 | 106 | [8 empty] | FOR AUDIT |  | 2025-05-27 | 62 | 2025-03-22 | 2025-07-28 | [8 empty] | Y | 2025-05-27 | [6 empty] | 2025-01-03 | CU6-2127,CT6-8032,CT6-8033,CT6-8034,TLN-52113,CT6-8035,CU6-2128 | 0 | 143 | 0 | 143 | 4.4306 | 80 |  | 6.9092 | 6.9092 | 1.3333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041002556', | ME185284 |  |  |  |  | RONILO GANGE JR.
2025-01-09 | 2025-01-07 |  | BIZ | X24114565283 | FANTASTICBAKA INCORPORATED | TAGUIG BAGUMBAYAN INDL ASS INC, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  | W/O ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 6.79 | 33.96 | 115 | NEW | 73436.03 | 27371.28 |  | 0% | 2024-12-20 18:00 | 2024-12-26 14:19 | 2024-12-27 |  | 2025-01-11 |  | 21.25 | 0 | -45668 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 0.78359 | 0 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 28.6 | 2025-03-12 | 227 | [8 empty] | FOR AUDIT |  | 2025-01-26 | -15 | 2025-06-25 | 2025-01-11 | [8 empty] | Y | 2025-01-10 | [6 empty] | N/A | DY1-1208 | 0 | 21.25 | 0 | 21.25 | 0.78359 | 201 |  | 8.1955 | 8.1955 | 3.35 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114565283', | ME155242 |  |  |  |  | Jenneth Madrid
2025-01-06 | 2025-01-02 |  | BIZ | X24072572239 | ROMEO ICASAS ABAD JR. | NIOG III, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 42.7347 | 56.38 | 40 | NEW | 376178.98 | 45404.78 |  | 0% | 2024-12-23 13:17 | 2024-12-26 14:21 | 2024-12-26 |  | 2025-03-31 |  | 97.4465 | 0 | -45747 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 3.1658 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 28.6 | 2025-05-30 | 148 | [8 empty] | NO COC |  | 2025-04-15 | #VALUE! | [10 empty] | Y | 2025-04-02 | [6 empty] | 2025-01-06 | CV6-8050,TLN-522707, | 0 | 97.4465 | 0 | 97.4465 | 3.1658 | 122 |  | 7.1294 | 7.1294 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072572239', | ME185284 |  |  |  |  | Isan Carlo Lazaro
2025-01-06 | OK | Y | HMB | X24124692677 | CITY GOVERNMENT OF BACOOR | MOLINO HOMES I SUBD, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 299.6567 | 447.14 | 250 | NEW | 1901958.33 | 354962.15 |  | 0% | 2024-12-26 12:54 | 2025-01-03 12:26 | 2025-01-02 |  | 2025-03-12 14:39 |  | 76.0729 | 0 | -45728.6104 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 2.4882 | 0 | 32 | 30 | 22.9299 | 29.0446 | 19.9299 | 60 | 57 | 28.6 | 2025-05-11 14:39 | 166.3896 | [8 empty] | NO COC |  | 2025-03-27 14:39 | #VALUE! | [10 empty] | Y | 2025-03-08 | [6 empty] | 2025-01-06 | CS7-8128,CS7-8129,CS7-8130,CS7-8131,CS7-8132,TLN-367789,TLN-523727 | 0 | 76.0729 | 0 | 76.0729 | 2.4882 | 140.3896 |  | 7.0801 | 7.0801 | 2.3398 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124692677', | ME185284 |  |  |  |  | Jenneth Madrid
2025-01-06 | OK |  | HMB | X23051529972 | ERIC ANTHONY S CASTAÑEDA | TIERRA NUEVA SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 34.5195 | 58.03 | 70.5 | NEW | 363155.38 | 46727.63 |  | 0% | 2024-12-27 09:17 | 2025-01-03 12:24 | 2025-01-02 |  | 2025-02-12 |  | 46.6132 | 0 | -45700 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 1.5677 | 0 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 28.6 | 2025-04-13 | 195 | [8 empty] | MATERIAL BALANCING |  | 2025-02-27 | -6 | 2025-02-12 | 2025-02-21 | [8 empty] | Y | 2025-02-11 | [6 empty] | 2025-01-06 | CV9-8016,TLN-516928 | 0 | 46.6132 | 0 | 46.6132 | 1.5677 | 169 |  | 7.2514 | 7.2514 | 2.8167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23051529972', | ME166067 |  |  |  |  | RONILO GANGE JR.
2025-01-06 | 2025-01-03 |  | BIZ | X24124714328 | AC AUTOMOTIVE BUSINESS SERVICES, INC. | MOLINO BLVD., BAYANAN, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | TECO | Ronilo Gange Jr. | 14.2433 | 52.96 | 60 | NEW | 383052.97 | 38382.07 | 48645.26 | 126.7% | 2024-12-27 09:19 | 2025-01-03 12:27 | 2025-01-02 | 2025-01-15 | 2025-01-15 | 2025-07-03 | 18.6118 | 0 | 169 | 2025-01-15 16:32 | 2025-01-24 15:15 | 2025-02-15 09:19 | 0.62595 | 2.8167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-03-16 | 223 | [8 empty] | PAID |  | 2025-01-30 | -8 | 2025-01-15 | 2025-01-22 | 2025-06-23 | AGD | N | [13 empty] | 2025-01-06 | TLN-526795 | 0 | 18.6118 | 0 | 18.6118 | 0.62595 | 197 |  | 7.2514 | 7.2514 | 3.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124714328', | ME155242 |  |  |  |  | RONILO GANGE JR.
2025-01-09 | 2025-01-07 |  | HMB | X23083241618 | ROMEO P. CAMBA | SAN ANTONIO VALLEY 11, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 255.582 | 781.63 | 74 | NEW | 1386868.07 | 250439.28 |  | 0% | 2024-12-27 15:18 | 2025-01-03 12:36 | 2025-01-02 |  |  |  | -45653.6375 | 0 | 0 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | -1282.3301 | 0 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 28.6 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-01-09 | DY1-0380,DY1-0379,DY1-0378,DY1-0377,DY1-0376,DY1-0375 | 0 | -45653.6375 | 0 | -45653.6375 | -1282.3301 | 0 |  | 6.0492 | 6.0492 | 0 | 202.3625 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23083241618', | ME155242 |  |  |  |  | Isan Carlo Lazaro
2025-01-06 | 2025-01-03 |  | BIZ | X24041187305 | CATHEDRAL OF THE KING, INC. (CORPORATION SOLE) | MARIMAR VILLAGE, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For survey |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 70.2848 | 95.46 | 62 | NEW | 546397.23 | 76869.35 |  | 0% | 2024-12-27 15:21 | 2025-01-03 12:46 | 2025-01-02 |  | 2025-04-08 |  | 101.3604 | 0 | -45755 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 3.4089 | 0 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 28.6 | 2025-06-07 | 140 | [7 empty] | 2025-04-03 | FOR AUDIT |  | 2025-04-23 | 22 | 2025-04-08 | 2025-05-15 | [8 empty] | Y | 2025-03-31 | [6 empty] | 2025-01-06 | DZI-0029,TLN-054237,TLN-514500 | 0 | 101.3604 | 0 | 101.3604 | 3.4089 | 114 |  | 7.2429 | 7.2429 | 1.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041187305', | ME166067 |  |  |  |  | Jenneth Madrid
2025-01-27 | 2025-01-11 |  | HMB | X24124856516 | RAUL GABRIEL II S. DIMATATAC | SUSANA HEIGHTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  | Error in FCOMP due to Budget Issues Email for Force FCOMP already Sent to Mam Zarah | AVECO | FCOMP | Ronilo Gange Jr. | 25.0823 | 36.25 | 82 | NEW | 273825.69 | 27854.74 |  | 0% | 2025-01-02 14:30 | 2025-01-03 08:38 | 2025-01-06 |  | 2025-01-04 |  | 1.3958 | 0 | -45661 | 2025-01-20 16:17 | 2025-01-29 07:10 | 2025-02-21 14:30 | 0.049675 | -761.0167 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-03-05 | 234 | [8 empty] | NO COC |  | 2025-01-19 | 11 | 2025-01-04 | 2025-01-30 | [16 empty] | 2025-01-27 | TLN-526858 | 0 | 1.3958 | 0 | 1.3958 | 0.049675 | 208 |  | 7.452 | 7.452 | 3.4667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124856516', | ME155242 |  |  | 0.75556 |  | RONILO GANGE JR.
2025-01-09 | 2025-01-11 |  | BIZ | X24114563541 | MONOCRETE CONSTRUCTION PHILIPPINES, INC. | PRES. DIOSDADO MACAPAGAL, ASIAWORLD CITY, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 20.65 | 35.07 | 0 | TERMINATION | 34239.42 | 30141.65 |  | 0% | 2025-01-02 16:09 | 2025-01-06 07:58 | 2025-01-06 |  |  |  | -45659.6729 | 0 | 0 | 2025-01-06 02:03 | 2025-01-30 06:05 | 2025-02-05 | -1572.7221 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 28.6 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | TLN-186673 | 0 | -45659.6729 | 0 | -45659.6729 | -1572.7221 | 0 |  | 7.2102 | 7.2102 | 0 | 196.3271 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114563541', | ME185284 |  |  | 3.659 |  | RONILO GANGE JR.
2025-01-13 | 2025-01-11 |  | CBG | X24124737940 | PETRON CORPORATION | ALABANG-ZAPOTE, TALON II, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | CLOSE | Jemuel Peralta | 46.2 | 122.63 | 117 | NEW | 879274.36 | 82635.45 | 100779.99 | 122% | 2025-01-03 09:49 | 2025-01-08 15:23 | 2025-01-06 |  | 2025-01-15 | 2025-03-11 | 11.591 | 6.359 | 55 | 2025-01-06 02:03 | 2025-01-15 05:48 | 2025-02-05 | 0.38729 | 0 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 28.6 | 2025-03-16 | 223 | [8 empty] | PAID |  | 2025-01-30 | -5 | 2025-01-15 | 2025-01-25 | 2025-02-06 | ECI | N | [5 empty] | Y | 2025-01-13 | [6 empty] | N/A | CW7-1144,TLN-068771 | 0 | 11.591 | 0 | 11.591 | 0.38729 | 197 |  | 6.9697 | 6.9697 | 3.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124737940', | ME185130 |  |  | 5.2319 |  | JSP
2025-01-13 | 2025-01-11 |  | BIZ | X24104149594 | NORTH PHILIPPINE UNION CONFERENCE CORP OF THE SEVE | BAYANAN, BAYANAN, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 53.162 | 269.33 | 34 | NEW | 465517.05 | 45678.36 |  | 0% | 2025-01-03 09:52 | 2025-01-08 15:25 | 2025-01-06 |  | 2025-04-07 07:56 |  | 93.9194 | 0 | -45754.3306 | 2025-01-06 02:03 | 2025-02-03 21:52 | 2025-02-05 | 2.8325 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-06-06 07:56 | 140.6694 | [8 empty] | NO COC |  | 2025-04-22 07:56 | #VALUE! | [10 empty] | Y | 2025-04-07 | [6 empty] | 2025-01-13 | CU9-0191,CU6-8094,TLN-526350 | 0 | 93.9194 | 0 | 93.9194 | 2.8325 | 114.6694 |  | 6.2908 | 6.2908 | 1.9112 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104149594', | ME155242 |  |  | 5.2312 |  | RONILO GANGE JR.
2025-01-13 | 2025-01-10 |  | HMB | X24093710813 | ALLAN RAMIREZ SORBITO | CAMELLA SPRINGVILLE HEIGHTS III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 27.34 | 27.34 | 5 | NEW | 55291.05 | 23492.09 |  | 0% | 2025-01-06 10:11 | 2025-01-10 15:07 | 2025-01-09 |  | 2025-02-07 |  | 31.5757 | 27.3701 | -45695 | 2025-01-25 04:46 | 2025-02-03 00:07 | 2025-02-25 10:11 | 1.0876 | -761.5833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | NO COC |  | 2025-02-22 | #VALUE! | [18 empty] | N/A | CS8-8003,CS8-8002,CS8-8001,CS8-0129 | 0 | 31.5757 | 0 | 31.5757 | 1.0876 | 174 |  | 7.0809 | 7.0809 | 2.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093710813', | ME155242 |  |  | 4.2056 |  | RONILO GANGE JR.
2025-01-13 | 2025-01-10 |  | HMB | X24104283780 | GOLDEN LARIELLE, INC., | BLOCK 1, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 147.7586 | 500.38 | 45 | NEW | 890781.19 | 150792.13 |  | 0% | 2025-01-06 10:11 | 2025-01-10 15:12 | 2025-01-09 |  |  |  | -45663.4243 | -45667.6333 | 0 | 2025-01-29 10:46 | 2025-02-08 09:19 | 2025-02-25 10:11 | -1315.9945 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-01-13 | DR1-6046,DR1-6047,DR1-6048,TLN-173161,DR1-6069 | 0 | -45663.4243 | 0 | -45663.4243 | -1315.9945 | 0 |  | 5.9246 | 5.9246 | 0 | 192.5757 | REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104283780', | ME155242 |  |  | 4.209 |  | RONILO GANGE JR.
2025-01-13 | 2025-01-13 |  | BIZ | X24124874147 | EMPIRE METAL WORKS, INC. | NIOG III, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | C2 | INPRG | Ian Patrick Perez | 6.77 | 92.36 | 0 | TERMINATION | 70611.97 | 79358.02 |  | 0% | 2025-01-06 11:59 | 2025-01-10 15:10 | 2025-01-13 |  |  |  | -45663.4993 | -45667.6319 | 0 | 2025-01-26 14:02 | 2025-02-04 17:47 | 2025-02-25 11:59 | -1483.5122 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | TLN-071870, | 0 | -45663.4993 | 0 | -45663.4993 | -1483.5122 | 0 |  | 6.6763 | 6.6763 | 0 | 192.5007 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124874147', | ME155242 |  |  | 4.1326 |  | RONILO GANGE JR.
2025-01-13 | 2025-01-13 |  | BIZ | X24124873554 | SHANZHEN HAIWEI FOOD CORP. DOING BUSINESS UNDER TH | GEN. EMILIO AGUINALDO, PANAPAAN I, BACOOR | BACOOR CITY | DASMA |  |  | C2 | FCOMP | Ian Patrick Perez | 11.3 | 17.86 | 0 | TERMINATION | 24072.27 | 15354.35 |  | 0% | 2025-01-06 12:07 | 2025-01-10 15:11 | 2025-01-13 |  | 2025-08-08 |  | 213.4951 | 209.3674 | -45877 | 2025-01-25 06:42 | 2025-02-03 02:03 | 2025-02-25 12:07 | 7.3537 | -764.6167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-07 | 18 | [8 empty] | NO COC |  | 2025-08-23 | #VALUE! | [18 empty] | N/A | TLN-169874 | 0 | 213.4951 | 0 | 213.4951 | 7.3537 | -8 |  | 7.0782 | 7.0782 | -0.13333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124873554', | ME155242 |  |  | 4.1278 |  | RONILO GANGE JR.
2025-01-17 |  |  | HMB | X24062324373 | MANUEL ANTONIO S BOCALING | BLOCK 19, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | CLOSE | Isan Carlo Lazaro | 22.41 | 22.07 | 87 | MODIFICATION | 238527.99 |  |  | #DIV/0! | 2025-01-07 14:57 | 2025-01-14 14:46 | N/A |  | 2025-01-21 | 2025-02-11 14:03 | 13.3767 | 6.3847 | 21.5854 | 2025-01-25 16:45 | 2025-02-03 07:37 | 2025-02-26 14:57 | 0.47605 | 0.35976 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-03-22 | 217 | [8 empty] | PAID | WITH BACKJOB | 2025-02-05 | #VALUE! |  |  | 2025-02-05 | ECI | Y | [5 empty] | Y | 2025-01-20 | [8 empty] | 0 | 13.3767 | 0 | 13.3767 | 0.47605 | 191 |  | 7.2734 | 7.2734 | 3.1833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062324373', | ME166067 |  |  | 6.992 |  | Jenneth Madrid
2025-01-13 | 2025-01-10 |  | BIZ | X25010007601 | ACASYS DEVELOPMENT CORP. | SAN ANDRES, SUN VALLEY, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 277.3716 | 826.39 | 1680 | NEW | 3356230.93 | 413605.22 |  | 0% | 2025-01-07 15:58 | 2025-01-10 15:05 | 2025-01-10 | 2025-04-30 | 2025-02-01 |  | 24.3347 | 21.3715 | -45689 | 2025-01-22 07:30 | 2025-01-30 00:26 | 2025-02-26 15:58 | 1.0342 | -761.4833 | 40 | 20 | 17.6471 | 22.3529 | 14.6471 | 60 | 57 | 52 | 2025-04-02 | 206 | With scheduled PAI / Applicant facility not ready | Y | Y |  |  | 2025-01-22 | 6 | 2025-01-28 | ON GOING MAT RETURN |  | 2025-02-16 | 73 | 2025-02-01 | 2025-04-30 | [6 empty] | 2025-08-16 | NVP | Y | 2025-01-22 | [6 empty] | 2025-01-13 | A7-0063,A7-0371,A7-8016,A7-8017,A7-0372,A7-0373,A7-0374,A7-8018,A7-8019,TLN-515608 | 0 | 24.3347 | 6 | 18.3347 | 0.77923 | 180 | 1.0342 | 8.6842 | 7.65 | 3 |  | REV |  | 2025-08-18 | 123186.33 | NTC ISSUED | 2025-08-18 |  | 8 |  |  |  | 'X25010007601', | ME185284 |  |  | 2.9632 |  | Jenneth Madrid
2025-01-13 | 2025-01-10 |  | BIZ | X24103955636 | DELECTABLE FEAST CORPORATION | AGUIRRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 37.2695 | 46.79 | 68 | NEW | 381005.41 | 37323.41 |  | 0% | 2025-01-07 15:58 | 2025-01-10 15:09 | 2025-01-10 |  | 2025-02-01 |  | 24.3347 | 21.3688 | -45689 | 2025-01-25 17:45 | 2025-02-03 08:38 | 2025-02-26 15:58 | 0.86603 | -761.4833 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-02 | 206 | [8 empty] | ON GOING MAT RETURN | WITH BACKJOB | 2025-02-16 | 5 | 2025-02-01 | 2025-02-21 | 2025-03-21 | AGD | Y |  |  |  | 2025-08-07 | NVP | [8 empty] | 2025-01-13 | CW9-8056,TLN-526116 | 0 | 24.3347 | 0 | 24.3347 | 0.86603 | 180 |  | 7.2719 | 7.2719 | 3 |  | REV |  | 2025-08-07 | 4622.34 | NTC ISSUED | 2025-08-07 |  | 19 |  |  |  | 'X24103955636', | ME166067 |  |  | 2.9659 |  | RONILO GANGE JR.
| 2025-01-10 |  | HMB | X24020621621 | RHOEY LEE CANLAS DAKIS | BLOCK 14, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 11.4428 | 29.6 | 60 | MODIFICATION | 227308.27 | 23833.94 |  | 0% | 2025-01-07 16:38 | 2025-01-14 14:49 | 2025-01-10 |  | 2025-02-05 |  | 28.3069 | 21.3826 | -45693 | 2025-01-25 18:25 | 2025-02-03 09:18 | 2025-02-26 16:38 | 1.0074 | -761.55 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-06 | 202 | [8 empty] | NO COC |  | 2025-02-20 | #VALUE! | [18 empty] | N/A |  | 0 | 28.3069 | 0 | 28.3069 | 1.0074 | 176 |  | 7.2709 | 7.2709 | 2.9333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020621621', | ME155242 |  |  | 6.9243 |  | Jenneth Madrid
2025-01-27 | 2025-01-16 |  | CBG | X24030860881 | FILIPINAS BENSON INDUSTRIAL AND DEVELOPMENT CORPOR | RODRIGUEZ, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 209.1735 | 243.08 | 730 | NEW | 1864204.78 | 203044.77 |  | 0% | 2025-01-08 | 2025-01-13 14:50 | 2025-01-13 |  | 2025-01-20 |  | 12 | 6.3819 | -45677 | 2025-01-23 05:26 | 2025-01-31 02:05 | 2025-02-27 | 0.49379 | -761.2833 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 2025-03-21 | 218 | [8 empty] | NO COC |  | 2025-02-04 | #VALUE! | [18 empty] | 2025-01-27 | DR2-8014,DR2-8015,TLN-520871 | 0 | 12 | 0 | 12 | 0.49379 | 192 |  | 8.3944 | 8.3944 | 3.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030860881', | ME155242 |  |  | 5.6181 |  | Jenneth Madrid
2025-01-13 | 2025-01-10 |  | HMB | X24072803104 | PATRICK SOON NGO | AZUCENA, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 109.6198 | 136.18 | 67 | MODIFICATION | 479799.06 | 108263.2 | 45984.06 | 42.47% | 2025-01-08 08:26 | 2025-01-10 15:10 | 2025-01-10 |  | 2025-02-10 | 2025-07-23 08:28 | 32.6489 | 30.3681 | 163.3528 | 2025-01-28 16:42 | 2025-02-06 22:07 | 2025-02-27 08:26 | 1.0489 | 2.7225 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-04-11 | 197 | [8 empty] | PAID | WITH BACKJOB | 2025-02-25 | 2 | 2025-02-10 | 2025-02-27 | 2025-04-01 | ECI | N |  |  |  | 2025-05-28 | NVP | Y | 2025-02-06 | [6 empty] | 2025-01-13 | CW9-0399,DW1-8035,CW9-0400,CW9-0400,DW1-8036,CW9-0470,CW9-0470,TLN-523026 | 0 | 32.6489 | 0 | 32.6489 | 1.0489 | 171 |  | 6.5426 | 6.5426 | 2.85 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072803104', | ME166067 |  |  | 2.2809 |  | Isan Carlo Lazaro
2025-01-27 |  |  | BIZ | X24083059434 | ALFAMART TRADING PHILIPPINES, INC. | BLOCK 1, SAN NICOLAS III, BACOOR | BACOOR CITY | DASMA |  |  | C2 | CLOSE | Isan Carlo Lazaro | 28.61 | 26.67 | 28 | NEW | 224520.24 |  |  | #DIV/0! | 2025-01-08 13:20 | 2025-01-14 14:47 | N/A |  | 2025-01-24 | 2025-02-11 14:00 | 15.4447 | 9.384 | 18.5833 | 2025-01-27 07:55 | 2025-02-05 03:16 | 2025-02-27 13:20 | 0.53198 | 0.30972 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-25 | 214 | [8 empty] | PAID |  | 2025-02-08 | #VALUE! |  |  | 2025-02-05 | ECI | N | [5 empty] | Y | 2025-01-23 | [6 empty] | 2025-01-27 | TLN-523235 | 0 | 15.4447 | 0 | 15.4447 | 0.53198 | 188 |  | 7.0075 | 7.0075 | 3.1333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083059434', | ME166067 |  |  | 6.0606 |  | Isan Carlo Lazaro
2025-01-15 | 2025-01-10 | Y | HMB | X24093778968 | CITY GOVERNMENT OF TAGUIG | M.L. QUEZON, LOWER BICUTAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 296.2991 | 1116.82 | 73 | NEW | 2732739.46 | 648325.44 |  | 0% | 2025-01-08 16:28 | 2025-01-14 14:50 | 2025-01-10 |  | 2025-02-25 |  | 47.3139 | 41.3819 | -45713 | 2025-02-02 21:27 | 2025-02-13 09:59 | 2025-02-27 16:28 | 1.258 | -761.8833 | 50 | 34 | 28.208 | 35.7301 | 25.208 | 60 | 57 | 52 | 2025-04-26 | 182 | With scheduled PAI | Y | Y |  |  | 2025-02-12 | 6 | 2025-02-18 | NO COC |  | 2025-03-12 | #VALUE! | [10 empty] | Y | 2025-02-18 | [6 empty] | 2025-01-15 | B8-8156,B8-8157,A8-8106,A8-8107,TLN-526017 | 0 | 47.3139 | 6 | 41.3139 | 1.0985 | 156 | 1.258 | 5.4058 | 4.1478 | 2.6 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093778968', | ME185284 |  |  | 5.9319 |  | Isan Carlo Lazaro
2025-01-20 | 2025-01-10 |  | BIZ | X24103973963 | IMV GEMINI PHARMA INC. | BF HOMES-HERNANDEZ PORTION, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 20.259 | 40.33 | 98 | NEW | 458087.14 | 32512.64 |  | 0% | 2025-01-08 16:35 | 2025-01-14 14:57 | 2025-01-10 | 2025-02-27 | 2025-02-07 | 2025-06-25 | 29.3089 | 23.3771 | 138 | 2025-01-26 18:22 | 2025-02-04 09:15 | 2025-02-27 16:35 | 1.0431 | 2.3 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | PAID |  | 2025-02-22 | 27 | 2025-02-07 | 2025-03-21 | 2025-05-27 | ECI | N |  |  |  | 2025-06-11 | NVP | [8 empty] | 2025-01-20 | TLN-517778 | 0 | 29.3089 | 0 | 29.3089 | 1.0431 | 174 |  | 7.2354 | 7.2354 | 2.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103973963', | ME166067 |  |  | 5.9318 |  | Isan Carlo Lazaro
2025-03-04 | 2025-01-10 |  | BIZ | X25010012239 | FRANCIS ARANEZ REYES | DAANG BATA, MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 42.149 | 75.92 | 58 | NEW | 544190.66 | 65233.33 |  | 0% | 2025-01-08 17:30 | 2025-01-13 11:04 | 2025-01-10 |  | 2025-03-26 |  | 76.2709 | 71.5389 | -45742 | 2025-01-28 00:42 | 2025-02-05 23:26 | 2025-02-27 17:30 | 2.5651 | -762.3667 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-25 | 153 | [8 empty] | NO COC |  | 2025-04-10 | #VALUE! | [18 empty] | 2025-03-04 | A5-8029,TLN-520796 | 0 | 76.2709 | 0 | 76.2709 | 2.5651 | 127 |  | 6.8363 | 6.8363 | 2.1167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010012239', | ME185284 |  |  | 4.732 |  | Isan Carlo Lazaro
2025-01-27 | 2025-01-10 |  | BIZ | X24041122874 | ST.MICHAEL'S INST. OF BACOOR | GEN. EVANGELISTA, TABING DAGAT, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 142.3595 | 239.64 | 384 | MODIFICATION | 1446562.4 | 193011.7 |  | 0% | 2025-01-09 13:21 | 2025-01-14 14:59 | 2025-01-10 |  | 2025-04-22 |  | 102.4437 | 97.3757 | -45769 | 2025-01-27 13:21 | 2025-02-05 03:45 | 2025-02-28 13:21 | 3.6587 | -762.8167 | 28 | 28 | 21 | 26.6 | 18 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [10 empty] | Y | 2025-04-02 | [6 empty] | 2025-01-27 | TLN-138990,CX5-8002 | 0 | 102.4437 | 0 | 102.4437 | 3.6587 | 100 |  | 7.2301 | 7.2301 | 1.6667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041122874', | ME185284 |  |  | 5.068 |  | RONILO GANGE JR.
2025-01-16 | 2025-01-16 |  | BIZ | X24103963394 | HERSTAL SECURITY AGENCY, INC. | DOÑA SOLEDAD, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 50.1975 | 50.2 | 55 | NEW | 391521.04 | 43156.97 |  | 0% | 2025-01-09 18:06 | 2025-01-15 15:25 | 2025-01-14 | 2025-05-14 | 2025-05-15 |  | 125.2458 | 119.3576 | -45792 | 2025-01-27 19:53 | 2025-02-05 10:46 | 2025-02-28 18:06 | 4.4573 | -763.2 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-07-14 | 103 | [8 empty] | FOR AUDIT |  | 2025-05-30 | 56 | 2025-05-14 | 2025-07-25 | [8 empty] | Y | 2025-05-13 | [6 empty] | 2025-01-16 | DZI-8031,TLN-522411 | 0 | 125.2458 | 0 | 125.2458 | 4.4573 | 77 |  | 7.1976 | 7.1976 | 1.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103963394', | ME185284 |  |  | 5.8882 |  | Isan Carlo Lazaro
2025-01-16 | 2025-01-16 |  | BIZ | X24104022803 | PRECILLE DOHINOG ARQUILLANO | SAMPALOC SITE 2, SAMPALOC SITE 2, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 37.6395 | 63.1 | 20 | NEW | 407227.17 | 39598.5 | 19745.32 | 49.86% | 2025-01-09 18:08 | 2025-01-15 15:23 | 2025-01-14 |  | 2025-02-11 |  | 32.2444 | 26.359 | -45699 | 2025-01-29 20:11 | 2025-02-07 23:56 | 2025-02-28 18:08 | 1.0476 | -761.65 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-26 | 9 | 2025-02-12 | 2025-03-07 | [8 empty] | Y | 2025-02-11 | [6 empty] | 2025-01-16 | DXI-8100,TLN-526189 | 0 | 32.2444 | 0 | 32.2444 | 1.0476 | 170 |  | 6.5705 | 6.5705 | 2.8333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104022803', | ME155242 |  |  | 5.8854 |  | Jenneth Madrid
2025-01-21 | 2025-01-16 |  | HMB | R23155273 | ALVAREZ, SAIMON LOUISE | VISTA VERDE SOUTH, VISTA VERDE SOUTH EXEC VILL 1, BACOOR | BACOOR CITY | DASMA | Hindi pa ito nahukayan sir. |  | AVECO | SCHED | Ronilo Gange Jr. | 60.6207 | 220.52 | - | RELOC | 321730.1 | 54956.67 |  | 0% | 2025-01-10 13:30 | 2025-01-20 14:26 | 2025-01-14 |  |  |  | -45667.5625 | -45677.6014 | 0 | 2025-01-23 23:15 | 2025-01-31 08:15 | 2025-03-01 13:30 | -2087.66 | 0 | 28 | 20 | 16.4063 | 20.7813 | 13.4063 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-01-21 | CU6-8046,CU6-8047 | 0 | -45667.5625 | 0 | -45667.5625 | -2087.66 | 0 |  | 9.2086 | 9.2086 | 0 | 188.4375 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23155273', | ME155242 |  |  | 10.0389 |  | RONILO GANGE JR.
2025-01-14 | 2025-01-16 |  | BIZ | X24124846054 | PASONG TAMO Z2 GAS STATION INC. | WEST SERVICE, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 1.73 | 3.4 | 16 | NEW | 18039.03 | 2737.93 |  | 0% | 2025-01-10 15:57 | 2025-01-15 15:29 | 2025-01-14 |  | 2025-01-30 |  | 19.3354 | 14.3549 | -45687 | 2025-01-29 10:32 | 2025-02-07 05:53 | 2025-03-01 15:57 | 0.666 | -761.45 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | NO COC |  | 2025-02-14 | #VALUE! | [10 empty] | Y | 2025-01-22 | [8 empty] | 0 | 19.3354 | 0 | 19.3354 | 0.666 | 182 |  | 6.9349 | 6.9349 | 3.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124846054', | ME185284 |  |  | 4.9806 |  | RONILO GANGE JR.
| 2025-01-16 |  | CBG | X24083245022 | EDGEPOINT TOWERS INC. | C6 ROAD, HAGONOY, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 207.1843 | 1072.7 | 35 | NEW | 1348054.07 | 197215.95 |  | 0% | 2025-01-13 16:12 | 2025-01-17 09:16 | 2025-01-14 |  | 2025-02-22 |  | 39.325 | 35.6139 | -45710 | 2025-02-09 03:37 | 2025-02-20 00:16 | 2025-03-04 16:12 | 1.0006 | -761.8333 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-04-23 | 185 | With ROW problem / Applicant facility not ready | Y | Y |  |  | 2025-01-29 | 22 | 2025-02-20 | NO COC |  | 2025-03-09 | #VALUE! | [20 empty] | 0 | 39.325 | 22 | 17.325 | 0.44082 | 159 | 1.0006 | 5.0463 | 4.0457 | 2.65 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083245022', | ME185284 |  |  | 3.7111 |  | Jenneth Madrid
2025-01-21 | 2025-01-16 |  | CBG | X24093598451 | DITO TELECOMMUNITY CORPORATION | DR. A. SANTOS, SAN ISIDRO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 12.3128 | 52.4 | 31 | NEW | 267072.85 | 42193.72 | 32033.67 | 75.92% | 2025-01-14 13:05 | 2025-01-20 14:31 | 2025-01-14 |  | 2025-01-25 |  | 10.4549 | 4.3951 | -45682 | 2025-02-03 15:08 | 2025-02-12 18:53 | 2025-03-05 13:05 | 0.33966 | -761.3667 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-03-26 | 213 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-09 | 5 | 2025-01-25 | 2025-02-14 | [16 empty] | 2025-01-21 | TLN-523779 | 0 | 10.4549 | 0 | 10.4549 | 0.33966 | 187 |  | 6.4149 | 6.4149 | 3.1167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093598451', | ME155242 |  |  | 6.0597 |  | Jenneth Madrid
2025-01-21 | 2025-01-16 |  | CBG | X24041165850 | DITO TELECOMMUNITY CORPORATION | TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 41.2093 | 77.39 | 20 | NEW | 1017553.36 | 33184.8 | 40104.55 | 120.9% | 2025-01-14 13:46 | 2025-01-20 14:29 | 2025-01-14 |  | 2025-02-07 |  | 23.4264 | 17.3965 | -45695 | 2025-02-03 15:49 | 2025-02-12 19:34 | 2025-03-05 13:46 | 0.76107 | -761.5833 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-22 | 5 | 2025-02-07 | 2025-02-27 | [16 empty] | 2025-01-21 | DR2-8016,TLN-521435 | 0 | 23.4264 | 0 | 23.4264 | 0.76107 | 174 |  | 6.414 | 6.414 | 2.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041165850', | ME166067 |  |  | 6.0299 |  | Isan Carlo Lazaro
2025-01-21 | 2025-01-20 |  | HMB | X24093725597 | RAV MC LESTER SALCEDO ASI | ST. GEORGE, METROCOR SOUTH GATE HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 123.3395 | 149.84 | 3.8 | NEW | 740394.49 | 119149.37 |  | 0% | 2025-01-15 17:02 | 2025-01-20 14:34 | 2025-01-20 |  | 2025-01-30 |  | 14.2903 | 9.3931 | -45687 | 2025-02-05 22:00 | 2025-02-15 08:55 | 2025-03-06 17:02 | 0.44275 | -761.45 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-03-31 | 208 | [8 empty] | MATERIAL BALANCING |  | 2025-02-14 | 13 | 2025-01-30 | 2025-02-27 | 2025-05-27 | ECI | Y | [13 empty] | 2025-01-21 | CV9-8054,TLN-523885,CV9-8055,CV9-8056,CV9-8057 | 0 | 14.2903 | 0 | 14.2903 | 0.44275 | 182 |  | 6.0816 | 6.0816 | 3.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093725597', | ME166067 |  |  | 4.8972 |  | Jenneth Madrid
2025-02-27 | 2025-01-20 |  | BIZ | X24103906652 | BERNADETTE A. NAVALTA | B. CAPISTRANO, HAGONOY, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 85.5451 | 135.91 | 111 | NEW | 693459.93 | 113948.9 |  | 0% | 2025-01-15 18:53 | 2025-01-21 13:52 | 2025-01-16 |  | 2025-03-19 |  | 62.2132 | 56.4222 | -45735 | 2025-02-04 05:35 | 2025-02-13 05:15 | 2025-03-06 18:53 | 2.0788 | -762.25 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-05-18 | 160 | With scheduled PAI | Y | Y |  |  | 2025-03-05 | 6 | 2025-03-11 | ON GOING MAT RETURN |  | 2025-04-03 | 57 | 2025-03-19 | 2025-05-30 | [6 empty] | 2025-08-16 | NVP | Y | 2025-03-17 | [6 empty] | 2025-01-27 | B9-0717,B9-8085 | 0 | 62.2132 | 6 | 56.2132 | 1.8783 | 134 | 2.0788 | 6.5562 | 4.4774 | 2.2333 |  | REV |  | 2025-08-18 | 11326.6 | NTC ISSUED | 2025-08-18 |  | 8 |  |  |  | 'X24103906652', | ME185284 |  |  | 5.791 |  | Jenneth Madrid
2025-01-23 | 2025-01-20 |  | CBG | X24104068733 | DITO TELECOMMUNITY CORPORATION | M.L. QUEZON, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 53.5563 | 1016.94 | 22 | NEW | 1033388.17 | 43127.53 | 24641.33 | 57.14% | 2025-01-15 18:53 | 2025-01-21 13:50 | 2025-01-16 | 2025-06-30 | 2025-06-30 |  | 165.2132 | 159.4236 | -45838 | 2025-02-11 06:18 | 2025-02-22 02:57 | 2025-03-06 18:53 | 4.2038 | -763.9667 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-08-29 | 57 | Third party concern (Other than the applicant) | Y | Y |  |  | 2025-03-26 | 79 | 2025-06-13 | FOR AUDIT |  | 2025-07-15 | 13 | 2025-06-30 | 2025-07-28 | [8 empty] | Y | 2025-06-27 | [6 empty] | 2025-01-23 | DZ2-5886,TLN-187901,DZ2-8121,TLN-526225 | 0 | 165.2132 | 79 | 86.2132 | 2.1936 | 31 | 4.2038 | 4.9925 | 0.78878 | 0.51667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104068733', | ME185284 |  |  | 5.7896 |  | RONILO GANGE JR.
2025-01-21 | 2025-01-20 |  | HMB | X24114453763 | ANGELO CALVO PICARDAL | M. BRIONES, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 20.12 | 103.37 | 5 | MODIFICATION | 137086.4 | 21332.08 |  | 0% | 2025-01-15 18:53 | 2025-01-20 14:43 | 2025-01-16 |  |  |  | -45672.7868 | -45677.6132 | 0 | 2025-02-05 23:51 | 2025-02-15 10:46 | 2025-03-06 18:53 | -1415.0757 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-01-21 | CR9-8048 | 0 | -45672.7868 | 0 | -45672.7868 | -1415.0757 | 0 |  | 6.0793 | 6.0793 | 0 | 183.2132 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114453763', | ME155242 |  |  | 4.8264 |  | Isan Carlo Lazaro
2025-01-21 | 2025-01-20 |  | HMB | X24114634882 | CHRISTOPHER JOSEPH REYES TSUI | DAYAP LOOP TAMARIND COVE, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.65 | 15.65 | 27.1 | NEW | 196704.22 | 12602.54 |  | 0% | 2025-01-15 18:53 | 2025-01-20 14:36 | 2025-01-17 |  | 2025-02-15 |  | 30.2132 | 25.3917 | -45703 | 2025-02-03 13:28 | 2025-02-12 08:49 | 2025-03-06 18:53 | 1.0407 | -761.7167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-16 | 192 | [8 empty] | ON GOING MAT RETURN | CONJ. X24114634928 | 2025-03-02 | 1 | 2025-02-15 | 2025-03-03 | 2025-04-01 | ECI | N |  |  |  | 2025-06-21 | NVP | Y | 2025-02-15 | [6 empty] | 2025-01-21 | TLN-526706 | 0 | 30.2132 | 0 | 30.2132 | 1.0407 | 166 |  | 6.7585 | 6.7585 | 2.7667 |  | REV |  | 2025-06-23 | 7232.96 | NTC ISSUED | 2025-06-25 |  | 62 |  |  |  | 'X24114634882', | ME166067 |  |  | 4.8215 |  | Isan Carlo Lazaro
2025-01-21 | 2025-01-20 |  | HMB | X24114634928 | CHRISTOPHER JOSEPH REYES TSUI | DAYAP LOOP TAMARIND COVE, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 36.8255 | 36.83 | - | NEW | 177491.79 | 29654.69 |  | 0% | 2025-01-15 18:53 | 2025-01-20 14:38 | 2025-01-17 |  | 2025-02-15 | 2025-07-10 | 30.2132 | 25.3903 | 145 | 2025-01-27 18:53 | 2025-02-03 18:53 | 2025-03-06 18:53 | 1.5107 | 2.4167 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-04-16 | 192 | [8 empty] | PAID |  | 2025-03-02 | 1 | 2025-02-15 | 2025-03-03 | 2025-04-01 | ECI | N |  |  |  | 2025-06-21 | NVP | Y | 2025-02-15 | [6 empty] | 2025-01-21 | DSI-8150 | 0 | 30.2132 | 0 | 30.2132 | 1.5107 | 166 |  | 9.8107 | 9.8107 | 2.7667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114634928', | ME166067 |  |  | 4.8229 |  | RONILO GANGE JR.
2025-01-23 | 2025-01-20 |  | CBG | X24124943162 | RICARDO DELOS SANTOS ABELARDO JR. | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 3.58 | 14.98 | 39 | MODIFICATION | 46265.45 | 12871.34 |  | 0% | 2025-01-15 18:53 | 2025-01-21 13:43 | 2025-01-16 |  | 2025-02-07 |  | 22.2132 | 16.4285 | -45695 | 2025-02-03 13:28 | 2025-02-12 08:49 | 2025-03-06 18:53 | 0.76512 | -761.5833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-08 | 200 | [8 empty] | NO COC |  | 2025-02-22 | #VALUE! | [18 empty] | N/A |  | 0 | 22.2132 | 0 | 22.2132 | 0.76512 | 174 |  | 6.7585 | 6.7585 | 2.9 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124943162', | ME155242 |  |  | 5.7847 |  | RONILO GANGE JR.
2025-01-21 | 2025-01-20 |  | HMB | R23885137 | OMNI INVESTMENT BUILDING CORPORATION | MAGDIWANG, MOLINO III, BACOOR | BACOOR CITY | DASMA | done fcomp |  | AVECO | SCHED | Ronilo Gange Jr. | 113.854 | 250.35 | 0 | RELOC | 340822.52 | 117184.96 |  | 0% | 2025-01-15 18:53 | 2025-01-20 14:45 | 2025-01-16 |  |  |  | -45672.7868 | -45677.6146 | 0 | 2025-02-06 15:44 | 2025-02-16 06:53 | 2025-03-06 18:53 | -1377.4333 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-01-21 | CT7-8083,TLN-108907 | 0 | -45672.7868 | 0 | -45672.7868 | -1377.4333 | 0 |  | 5.9175 | 5.9175 | 0 | 183.2132 | NON-REV | 7-9 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23885137', | ME155242 |  |  | 4.8278 |  | Isan Carlo Lazaro
2025-01-27 | 2025-01-22 |  | HMB | X24093485481 | ANIELYN OCAMPO BALICUDIONG | HABAY I, HABAY I, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 152.4547 | 508.34 | 9 | NEW | 879151.54 | 167732.49 |  | 0% | 2025-01-16 13:40 | 2025-01-27 14:15 | 2025-01-21 |  | 2025-07-23 |  | 187.4306 | 176.4062 | -45861 | 2025-02-10 09:42 | 2025-02-20 19:51 | 2025-03-07 13:40 | 5.0502 | -764.35 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-09-21 | 34 | [8 empty] | NO COC |  | 2025-08-07 | #VALUE! | [18 empty] | 2025-01-27 | CW5-6406,CW5-8037,CW5-8038,CW5-8039,CW5-8040,TLN-523671 | 0 | 187.4306 | 0 | 187.4306 | 5.0502 | 8 |  | 5.2658 | 5.2658 | 0.13333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093485481', | ME155242 |  |  | 11.0243 |  | Isan Carlo Lazaro
2025-01-27 | 2025-01-22 |  | HMB | X24083472331 | ROBERTO N. LIM | MOLAVE, MOLAVE PARK VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 187.622 | 497.95 | 100 | NEW | 910341.91 | 150333.31 |  | 0% | 2025-01-16 13:44 | 2025-01-23 12:58 | 2025-01-21 |  | 2025-08-03 08:08 |  | 198.7667 | 191.7986 | -45872.3389 | 2025-02-07 14:28 | 2025-02-17 06:40 | 2025-03-07 13:44 | 5.9557 | -764.539 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-10-02 08:08 | 22.6611 | With pole / drainage / digging / manhole / pole attachment issue | Y | Y |  |  | 2025-03-21 | 102 | 2025-07-01 | NO COC |  | 2025-08-18 08:08 | #VALUE! | [18 empty] | 2025-01-27 | A7-8045,A7-8046,A7-8047,TLN-523665,A7-8048 | 0 | 198.7667 | 102 | 96.7667 | 2.8994 | -3.3389 | 5.9557 | 5.8556 | -0.10004 | -0.055648 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083472331', | ME185284 |  |  | 6.9681 |  | Jenneth Madrid
2025-01-27 | 2025-01-22 |  | BIZ | X24124805811 | NOEMI FRESNEDI CACHUELA | ESPELETA, POBLACION, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 12.0433 | 18.35 | 54 | NEW | 235553.06 | 14779.45 | 10702.08 | 72.41% | 2025-01-16 14:19 | 2025-01-27 13:57 | 2025-01-21 |  | 2025-02-05 |  | 19.4035 | 8.4187 | -45693 | 2025-02-03 16:06 | 2025-02-12 06:59 | 2025-03-07 14:19 | 0.69054 | -761.55 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-06 | 202 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-20 | 15 | 2025-02-05 | 2025-03-07 | [8 empty] | Y | 2025-02-05 | [6 empty] | 2025-01-27 | TLN-526847 | 0 | 19.4035 | 0 | 19.4035 | 0.69054 | 176 |  | 6.9541 | 6.9541 | 2.9333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124805811', | ME155242 |  |  | 10.9847 |  | Jenneth Madrid
2025-01-27 | 2025-01-22 |  | HMB | X24104341977 | MARGARITA OROSA FELIX | TANAUAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 57.1795 | 91.42 | 80 | NEW | 402458.69 | 52921.16 | 33495.04 | 63.29% | 2025-01-16 16:33 | 2025-01-23 12:56 | 2025-01-21 |  | 2025-02-15 |  | 29.3104 | 22.4611 | -45703 | 2025-02-04 23:46 | 2025-02-13 22:29 | 2025-03-07 16:33 | 0.98576 | -761.7167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-04-16 | 192 | [8 empty] | MATERIAL BALANCING | PARTIALLY BILLED; WITH BACKJOB | 2025-03-02 | -3 | 2025-02-15 | 2025-02-27 | 2025-04-30 | AGD/RLM | Y | [5 empty] | Y | 2025-02-14 | [6 empty] | 2025-01-27 | CS9-8083,CS9-0167,TLN-526463 | 0 | 29.3104 | 0 | 29.3104 | 0.98576 | 166 |  | 6.5686 | 6.5686 | 2.7667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104341977', | ME166067 |  |  | 6.8493 |  | Jenneth Madrid
2025-01-27 | 2025-01-22 |  | HMB | X24103967581 | VIRGILIO BRILLIANTES SY | LAPU-LAPU, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 33.7385 | 38.17 | 24 | NEW | 279847.61 | 32794.14 |  | 0% | 2025-01-16 16:44 | 2025-01-27 14:07 | 2025-01-21 |  | 2025-05-12 |  | 115.3028 | 104.4118 | -45789 | 2025-02-04 11:19 | 2025-02-13 06:40 | 2025-03-07 16:44 | 3.9715 | -763.15 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-11 | 106 | [8 empty] | NO COC |  | 2025-05-27 | #VALUE! | [10 empty] | Y | 2025-05-07 | [6 empty] | 2025-01-27 | D5-8103,TLN-526118 | 0 | 115.3028 | 0 | 115.3028 | 3.9715 | 80 |  | 6.7271 | 6.7271 | 1.3333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103967581', | ME185284 |  |  | 10.891 |  | Jenneth Madrid
2025-01-27 | 2025-01-22 |  | CBG | X24103896053 | DITO TELECOMMUNITY CORPORATION | BLOCK 80, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | resolved pole location issue on tasks 2 and 3, for sched of digging |  | VJC | FCOMP | Jenneth Madrid | 153.2359 | 214.08 | 22 | NEW | 554173.09 | 123019.83 |  | 0% | 2025-01-17 09:20 | 2025-01-23 13:00 | 2025-01-21 |  | 2025-03-28 |  | 69.6111 | 63.4583 | -45744 | 2025-02-08 06:11 | 2025-02-17 21:20 | 2025-03-08 09:20 | 2.0994 | -762.4 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-05-27 | 151 | [8 empty] | NO COC |  | 2025-04-12 | #VALUE! | [18 empty] | 2025-01-27 | A8-5982,A8-5983,A8-0411,TLN-526056 | 0 | 69.6111 | 0 | 69.6111 | 2.0994 | 125 |  | 5.8692 | 5.8692 | 2.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103896053', | ME185284 |  |  | 6.1528 |  | Jenneth Madrid
2025-02-27 | 2025-01-22 | Y | HMB | X24124906791 | VILLA LIGHT NEIGHBORHOOD ASSOCIATION INC. | BLOCK 10, VILLA LIGHT SUBD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 459.0968 | 3541.54 | 225 | NEW | 4039465.57 | 439590.53 |  | 0% | 2025-01-17 14:32 | 2025-01-27 14:02 | 2025-01-21 |  | 2025-06-28 |  | 161.3944 | 151.4153 | -45836 | 2025-02-09 04:10 | 2025-02-18 23:48 | 2025-03-08 14:32 | 4.7342 | -763.9333 | 50 | 30 | 25.5682 | 32.3864 | 22.5682 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | NO COC | Cancel/ Supersedes: X24114498829 | 2025-07-13 | #VALUE! | [10 empty] | Y | 2025-06-27 | [6 empty] | 2025-01-28 | B8-6311,B8-5575,ALB1-1211,B8-6313,B8-8160,B8-6316,B8-8162,B8-8163,B8-8164,B8-8164,B8-8166,B8-8167,B8-8168,B8-8169,B8-8170,B8-8171,B8-8172,B8-8173,B8-8174,B8-8175,B8-8176,TLN-513940,TLN-513941,TLN-212061 | 0 | 161.3944 | 0 | 161.3944 | 4.7342 | 33 |  | 5.7022 | 5.7022 | 0.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124906791', | ME185284 |  |  | 9.9792 |  | RONILO GANGE JR.
2025-01-27 | 2025-01-22 | Y | CBG | X25010079615 | CMSTAR MANAGEMENT INC. | DAANG-HARI RD., MOLINO IV, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 1155.0618 | 1160.74 | 45 | NEW | 3660384.15 | 992062.56 |  | 0% | 2025-01-17 15:21 | 2025-01-23 12:32 | 2025-01-21 |  | 2025-03-10 |  | 51.3604 | 45.4778 | -45726 | 2025-02-13 02:46 | 2025-02-23 23:25 | 2025-03-08 15:21 | 1.3068 | -762.1 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-05-09 | 169 | [8 empty] | NO COC |  | 2025-03-25 | #VALUE! | [10 empty] | Y | 2025-03-05 | [6 empty] | 2025-01-27 | CQ8-8010,CQ8-8011,CQ8-8012,CQ8-8013,CQ8-8014,CQ8-8015,CQ8-8016,CQ8-8017,CQ8-8018,CQ8-8019,CQ8-8020,CQ8-8021,CQ8-8022,CR8-8027,CR8-8028,CR8-8029,CR8-8030,CR8-8031,CR8-8032,CR8-8033,CR8-8034,CR8-8035,CR8-8036,CR8-8037, | 0 | 51.3604 | 0 | 51.3604 | 1.3068 | 143 |  | 4.9454 | 4.9454 | 2.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010079615', | ME185284 |  |  | 5.8826 |  | RONILO GANGE JR.
2025-01-27 | 2025-01-22 |  | HMB | X24083428614 | DENNIS CALDERON SAN PEDRO | CONCORDE, CONCORDE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 41.789 | 129.06 | 85 | NEW | 379680 | 48102.1 |  | 0% | 2025-01-17 15:43 | 2025-01-27 13:59 | 2025-01-21 |  | 2025-02-09 |  | 22.3451 | 12.4174 | -45697 | 2025-02-07 | 2025-02-16 05:24 | 2025-03-08 15:43 | 0.71788 | -761.6167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-04-10 | 198 | [8 empty] | NO COC |  | 2025-02-24 | #VALUE! | [10 empty] | Y | 2025-02-07 | [6 empty] | 2025-01-27 | TLN-523631,B5-8084 | 0 | 22.3451 | 0 | 22.3451 | 0.71788 | 172 |  | 6.2437 | 6.2437 | 2.8667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083428614', | ME185284 |  |  | 9.9278 |  | RONILO GANGE JR.
2025-02-27 | 2025-01-22 |  | CBG | R23797682 | CAVITEX INFRASTRUCTURE CORP., | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 29.5181 | 67.87 | 0 | RELOC | 86997.81 | 54655.92 | 40684.31 | 74.44% | 2025-01-20 09:07 | 2025-01-21 12:22 | 2025-01-21 |  | 2025-02-05 |  | 15.6201 | 14.4847 | -45693 | 2025-02-09 11:10 | 2025-02-18 14:55 | 2025-03-11 09:07 | 0.50747 | -761.55 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-06 | 202 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-02-20 | 1 | 2025-01-22 | 2025-02-21 | [16 empty] | N/A |  | 0 | 15.6201 | 0 | 15.6201 | 0.50747 | 176 |  | 6.2253 | 6.2253 | 2.9333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23797682', | ME155242 |  |  | 1.1354 |  | RONILO GANGE JR.
2025-02-27 | 2025-01-22 | Y | CBG | R23797676 | CAVITEX INFRASTRUCTURE CORP., | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 123.7648 | 196.43 | 0 | RELOC | 584843.86 | 158179.17 | 62538.81 | 39.54% | 2025-01-20 09:07 | 2025-01-21 12:18 | 2025-01-21 | 2025-03-13 | 2025-03-17 08:43 |  | 55.9833 | 54.8507 | -45733.3632 | 2025-02-10 14:05 | 2025-02-20 01:00 | 2025-03-11 09:07 | 1.7345 | -762.2227 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-05-16 08:43 | 161.6368 | [8 empty] | NO COC | PARTIALLY BILLED | 2025-04-01 08:43 | #VALUE! | [18 empty] | 2025-01-27 | A5-8052,A5-8053,A5-8045 | 0 | 55.9833 | 0 | 55.9833 | 1.7345 | 135.6368 |  | 5.9369 | 5.9369 | 2.2606 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23797676', | ME155242 |  |  | 1.1326 |  | Jenneth Madrid
2025-01-27 | 2025-01-22 |  | HMB | X23010262595 | FRANCISCO ARANETA CLIMENT | BANAWE, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 5.58 | 11.61 | 98 | NEW | 44190.67 | 9373.38 |  | 0% | 2025-01-20 12:31 | 2025-01-23 12:57 | 2025-01-21 |  | 2025-02-15 | 2025-07-10 | 25.4785 | 22.4604 | 145 | 2025-02-07 14:18 | 2025-02-16 05:11 | 2025-03-11 12:31 | 0.90673 | 2.4167 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-16 | 192 | [8 empty] | PAID |  | 2025-03-02 | -3 | 2025-02-15 | 2025-02-27 | 2025-04-30 | AGD/RLM | N |  |  |  | 2025-06-21 | NVP | Y | 2025-02-14 | [6 empty] | N/A |  | 0 | 25.4785 | 0 | 25.4785 | 0.90673 | 166 |  | 6.8144 | 6.8144 | 2.7667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23010262595', | ME166067 |  |  | 3.0181 |  | Jenneth Madrid
2025-01-28 | 2025-01-27 |  | HMB | R23895778 | BREIGHTON LAND INC. | BLOCK 6, BELLEFORT ESTATES PH 2, BACOOR | BACOOR CITY | DASMA |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 1.0495 | 1.29 | 0 | RELOC | 10873.51 | 1038.46 | 1038.46 | 100% | 2025-01-21 | 2025-01-28 08:53 | 2025-01-28 |  | 2025-01-28 |  | 7 | -0.37014 | -45685 | 2025-02-08 18:35 | 2025-02-17 13:56 | 2025-03-12 | 0.24111 | -761.4167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-03-29 | 210 | [8 empty] | NO COC | FULLY BILLED | 2025-02-12 | #VALUE! | [18 empty] | N/A |  | 0 | 7 | 0 | 7 | 0.24111 | 184 |  | 6.5789 | 6.5789 | 3.0667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23895778', | ME155242 |  |  | 7.3701 |  | Isan Carlo Lazaro
2025-01-31 | 2025-01-24 |  | BIZ | X24103942328 | MAXBLOCK CONSTRUCTION CORP. | PANORAMA CPD, VETERANS CENTER, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 3.92 | 18.12 | 30 | NEW | 48533.7 | 14591.57 |  | 0% | 2025-01-21 14:12 | 2025-01-28 07:54 | 2025-01-24 |  | 2025-02-09 |  | 18.4083 | 11.6708 | -45697 | 2025-02-09 08:47 | 2025-02-18 04:08 | 2025-03-12 14:12 | 0.63406 | -761.6167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-10 | 198 | [8 empty] | FOR AUDIT |  | 2025-02-24 | #VALUE! | [10 empty] | Y | 2025-02-07 | [6 empty] | N/A |  | 0 | 18.4083 | 0 | 18.4083 | 0.63406 | 172 |  | 6.5585 | 6.5585 | 2.8667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103942328', | ME185284 |  |  | 6.7375 |  | Jenneth Madrid
2025-01-28 | 2025-01-24 |  | HMB | X24062425520 | LICELLE GUMABAO YANG | BLOCK 2, BRAZILIA HEIGHTS, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 72.1226 | 91.33 | 49 | NEW | 431235.62 | 78471.11 |  | 0% | 2025-01-22 12:40 | 2025-01-28 07:48 | 2025-01-24 |  | 2025-02-11 |  | 19.4722 | 13.675 | -45699 | 2025-02-11 14:43 | 2025-02-20 18:28 | 2025-03-13 12:40 | 0.63261 | -761.65 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | NO COC |  | 2025-02-26 | #VALUE! | [10 empty] | Y | 2025-02-10 | [6 empty] | 2025-01-28 | TLN-522587,DRI-6079 | 0 | 19.4722 | 0 | 19.4722 | 0.63261 | 170 |  | 6.1556 | 6.1556 | 2.8333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062425520', | ME185284 |  |  | 5.7972 |  | Jenneth Madrid
2025-02-11 | 2025-01-24 |  | BIZ | X24104105713 | ECLECTUS FOOD VENTURES CORPORATION | M.L. QUEZON, PUROK 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | TECO | Jenneth Madrid | 68.7459 | 138.23 | 215 | NEW | 833032.22 | 97339.4 |  | 0% | 2025-01-22 12:45 | 2025-01-28 07:55 | 2025-01-24 |  | 2025-02-01 | 2025-06-30 | 9.4688 | 3.6701 | 149 | 2025-02-10 00:56 | 2025-02-18 18:34 | 2025-03-13 12:45 | 0.33019 | 2.4833 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-04-02 | 206 | [8 empty] | PAID |  | 2025-02-16 | 103 | 2025-02-01 | 2025-05-30 | 2025-06-25 | AGD | Y | Y |  |  | 2025-06-28 | NVP | Y | 2025-01-30 | [6 empty] | 2025-02-11 | B9-8088,TLN-526275 | 0 | 9.4688 | 0 | 9.4688 | 0.33019 | 180 |  | 6.6071 | 6.6071 | 3 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104105713', | ME185284 |  |  | 5.7986 |  | Isan Carlo Lazaro
2025-01-31 | 2025-01-24 |  | BIZ | X25010119071 | SPX PHILIPPINES, INC. | MIMC CPD, CERVANTES CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 301.8037 | 123.22 | 97 | NEW | 753143.29 | 211552.3 | 35306.57 | 16.69% | 2025-01-22 16:58 | 2025-01-28 08:21 | 2025-01-24 |  | 2025-02-05 | 2025-06-10 | 13.2931 | 7.6521 | 125 | 2025-02-12 01:15 | 2025-02-21 06:39 | 2025-03-13 16:58 | 0.42706 | 2.0833 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-04-06 | 202 | [8 empty] | PAID |  | 2025-02-20 | 1 | 2025-02-05 | 2025-02-21 | 2025-05-12 | ECI | N |  |  |  | 2025-05-27 | NVP | Y | 2025-02-03 | [6 empty] | 2025-01-31 | DYI-0933,DY1-8069,TLN-526556,TLN-025831 | 0 | 13.2931 | 0 | 13.2931 | 0.42706 | 176 |  | 6.0814 | 6.0814 | 2.9333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010119071', | ME166067 |  |  | 5.641 |  | Isan Carlo Lazaro
2025-01-28 | 2025-01-24 | Y | BIZ | X25010119305 | VICENTE P PEREZ | EL GRANDE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 33.4983 | 33.5 | 35 | NEW | 241637.84 | 26975.31 | 6007.35 | 22.27% | 2025-01-22 17:00 | 2025-01-28 08:26 | 2025-01-24 | 2025-03-04 04:21 | 2025-03-04 |  | 40.2917 | 34.6486 | -45720 | 2025-02-10 11:35 | 2025-02-19 06:56 | 2025-03-13 17:00 | 1.3878 | -762 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-03 | 175 | [8 empty] | ON GOING MAT RETURN | PARTIALLY BILLED | 2025-03-19 | -8 | 2025-03-07 | 2025-03-11 | 2025-03-24 | AGD |  |  |  |  | 2025-06-20 | NVP | Y | 2025-03-05 | [8 empty] | 0 | 40.2917 | 0 | 40.2917 | 1.3878 | 149 |  | 6.52 | 6.52 | 2.4833 |  | REV |  | 2025-06-23 | 8901.51 | NTC ISSUED | 2025-06-25 |  | 62 |  |  |  | 'X25010119305', | ME166067 |  |  | 5.6431 |  | Jenneth Madrid
2025-02-03 | 2025-01-24 |  | HMB | X25010138377 | GOLDEN DONUTS, INC. | NINOY AQUINO, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 2.73 | 29.81 | 29 | NEW | 79996.16 | 24005.18 |  | 0% | 2025-01-22 17:01 | 2025-01-28 08:43 | 2025-01-24 |  | 2025-01-31 |  | 8.291 | 2.6368 | -45688 | 2025-02-10 11:36 | 2025-02-19 06:57 | 2025-03-13 17:01 | 0.28558 | -761.4667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-01 | 207 | [8 empty] | NO COC |  | 2025-02-15 | #VALUE! | [18 empty] | N/A |  | 0 | 8.291 | 0 | 8.291 | 0.28558 | 181 |  | 6.52 | 6.52 | 3.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010138377', | ME155242 |  |  | 5.6542 |  | RONILO GANGE JR.
2025-01-31 | 2025-01-24 |  | HMB | X24072542131 | RAMONCHITO DIZON JAVIER | BEIRUT, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 260.1303 | 260.13 | 49 | MODIFICATION | 1097209.19 | 209100.43 |  | 0% | 2025-01-22 17:04 | 2025-01-28 08:19 | 2025-01-24 |  | 2025-03-10 19:46 |  | 47.1125 | 41.4771 | -45726.8236 | 2025-02-13 13:55 | 2025-02-23 05:04 | 2025-03-13 17:04 | 1.4209 | -762.1137 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-05-09 19:46 | 168.1764 | With scheduled PAI | Y |  |  | Y | 2025-03-11 | 7 | 2025-03-25 | ON GOING MAT RETURN |  | 2025-03-25 19:46 | 30.1764 | 2025-03-10 | 2025-04-25 | [6 empty] | 2025-08-14 | NVP | [8 empty] | 2025-01-31 | CX8-8159,CX8-8160,CX8-0648,TLN-036703,CX8-0757,CX8-8161,CX8-0647,CX8-8162,TLN-522796 | 7 | 40.1125 | 7 | 40.1125 | 1.2097 | 142.1764 |  | 5.7087 | 5.7087 | 2.3696 |  | NON-REV |  | 2025-08-14 | 95143.43 | NTC ISSUED | 2025-08-15 |  | 11 |  |  |  | 'X24072542131', | ME166067 |  |  | 5.6354 |  | RONILO GANGE JR.
2025-01-27 | 2025-01-24 |  | HMB | X24124701904 | LISA ARCILIA LAW | 17 DE MARZO, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | TECO | Ronilo Gange Jr. | 16.0428 | 57.36 | 155 | NEW | 465687.7 | 31619.43 | 36417.2 | 115.2% | 2025-01-22 17:07 | 2025-01-27 13:54 | 2025-01-24 |  | 2025-01-27 | 2025-06-20 10:45 | 4.2868 | -0.57917 | 144.4479 | 2025-02-10 04:36 | 2025-02-18 22:04 | 2025-03-13 17:07 | 0.14969 | 2.4075 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-03-28 | 211 | [8 empty] | PAID |  | 2025-02-11 | 3 | 2025-01-25 | 2025-02-14 | 2025-04-24 | ECI | N |  |  |  | 2025-06-11 | NVP | [8 empty] | 2025-01-27 | TLN-526770 | 0 | 4.2868 | 0 | 4.2868 | 0.14969 | 185 |  | 6.6096 | 6.6096 | 3.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124701904', | ME155242 |  |  | 4.866 |  | Jenneth Madrid
2025-01-31 | 2025-01-24 |  | BIZ | X24093630108 | KOBE Z. CHAN | BLOCK 24, ENLISTED PERSONNEL VIL 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 17.0728 | 20.45 | 20 | NEW | 227982.95 | 16467.33 |  | 0% | 2025-01-23 13:09 | 2025-01-28 08:54 | 2025-01-24 |  | 2025-03-27 08:14 |  | 62.7951 | 57.9722 | -45743.3431 | 2025-02-11 07:44 | 2025-02-20 03:05 | 2025-03-14 13:09 | 2.1629 | -762.3891 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-26 08:14 | 151.6569 | With scheduled PAI | Y | Y |  |  | 2025-03-21 | 5 | 2025-03-26 | FOR AUDIT |  | 2025-04-11 08:14 | 79.6569 | 2025-03-27 | 2025-06-30 | [8 empty] | Y | 2025-03-24 | [6 empty] | N/A |  | 0 | 62.7951 | 5 | 57.7951 | 1.9907 | 125.6569 | 2.1629 | 6.4911 | 4.3282 | 2.0943 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093630108', | ME185284 |  |  | 4.8229 |  | RONILO GANGE JR.
2025-02-03 | 2025-01-24 |  | BIZ | X25010064088 | TIANLALA PHILIPPINES CORPORATION | REDEMPTORIST, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 9.75 | 9.9 | 10 | NEW | 30397.4 | 10452.54 |  | 0% | 2025-01-23 17:25 | 2025-01-28 09:00 | 2025-01-24 |  | 2025-02-14 |  | 21.2743 | 16.625 | -45702 | 2025-02-11 12:00 | 2025-02-20 07:21 | 2025-03-14 17:25 | 0.73278 | -761.7 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-15 | 193 | [8 empty] | NO COC |  | 2025-03-01 | #VALUE! | [10 empty] | Y | 2025-02-14 | [6 empty] | 2025-02-03 | D5-8119,D5-0447,D5-5353 | 0 | 21.2743 | 0 | 21.2743 | 0.73278 | 167 |  | 6.485 | 6.485 | 2.7833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010064088', | ME185284 |  |  | 4.6493 |  | RONILO GANGE JR.
2025-02-03 | 2025-01-31 |  | HMB | X24083258065 | KENNETH NGO CHUA | DOÑA INES, ALABANG HILLS SUBD PH 1, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 37.5495 | 66.49 | 57 | MODIFICATION | 286792.48 | 37209.3 |  | 0% | 2025-01-24 14:01 | 2025-01-31 15:06 | 2025-01-30 |  |  |  | -45681.584 | -45688.6292 | 0 | 2025-02-12 21:14 | 2025-02-21 19:57 | 2025-03-15 14:01 | -1536.3499 | 0 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 1900-02-28 | 45895 | [8 empty] | Conj. X22114887149 |  | 1900-01-14 | 0 | [18 empty] | 2025-02-03 | DV1-8071,TLN-523455 | 0 | -45681.584 | 0 | -45681.584 | -1536.3499 | 0 |  | 6.3031 | 6.3031 | 0 | 174.416 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083258065', | ME155242 |  |  | 7.0451 |  | RONILO GANGE JR.
2025-02-03 | 2025-01-31 | Y | BIZ | X24093766158 | ALFAMART TRADING PHILIPPINES, INC. | QUEEN'S MAIN, QUEEN'S ROW AREA A SUBD, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 36.5195 | 39.53 | 28 | NEW | 281351.55 | 33962.66 |  | 0% | 2025-01-24 14:08 | 2025-01-31 15:08 | 2025-01-30 |  | 2025-03-31 |  | 65.4111 | 58.3694 | -45747 | 2025-02-12 08:43 | 2025-02-21 04:04 | 2025-03-15 14:08 | 2.253 | -762.45 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-30 | 148 | [8 empty] | NO COC |  | 2025-04-15 | #VALUE! | [10 empty] | Y | 2025-03-25 | [6 empty] | 2025-02-03 | CS8-8051,TLN-522457 | 0 | 65.4111 | 0 | 65.4111 | 2.253 | 122 |  | 6.4553 | 6.4553 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093766158', | ME185284 |  |  | 7.0417 |  | RONILO GANGE JR.
2025-02-03 | 2025-01-31 |  | HMB | X24104141244 | SERVEQUEST INC. | SUMMIT CIRCLE SUBD, SUMMIT CIRCLE SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 100.2485 | 104.47 | 294 | NEW | 846988.2 | 80751.9 | 84452.5 | 104.6% | 2025-01-24 14:19 | 2025-01-31 15:09 | 2025-01-30 | 2025-02-11 | 2025-02-11 | 2025-05-20 07:32 | 17.4035 | 10.3688 | 98.3139 | 2025-02-12 02:30 | 2025-02-20 20:08 | 2025-03-15 14:19 | 0.60689 | 1.6386 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | PAID |  | 2025-02-26 | -5 | 2025-02-11 | 2025-02-21 | 2025-04-01 | ECI | N |  | 2025-04-24 |  | 2025-04-24 | NVP | Y | 2025-02-11 | [6 empty] | 2025-02-03 | DT1-8088,TLN-526306 | 0 | 17.4035 | 0 | 17.4035 | 0.60689 | 170 |  | 6.5351 | 6.5351 | 2.8333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104141244', | ME166067 |  |  | 7.0347 |  | RONILO GANGE JR.
2025-02-06 | 2025-02-05 |  | BIZ | X25010119836 | YOLANDA E REYES | DOÑA SOLEDAD, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 1.72 | 3.58 | 15 | NEW | 16056.92 | 3075.97 |  | 0% | 2025-01-27 | 2025-02-03 13:31 | 2025-02-04 |  | 2025-03-19 |  | 51 | 43.4368 | -45735 | 2025-02-14 18:35 | 2025-02-23 13:56 | 2025-03-18 | 1.7567 | -762.25 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-18 | 160 | [8 empty] | NO COC |  | 2025-04-03 | #VALUE! | [10 empty] | Y | 2025-03-10 | [6 empty] | N/A |  | 0 | 51 | 0 | 51 | 1.7567 | 134 |  | 6.3722 | 6.3722 | 2.2333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010119836', | ME185284 |  |  | 7.5632 |  | Jenneth Madrid
2025-02-04 | 2025-01-31 | Y | BIZ | X24072540238 | HARD DISCOUNT PHILIPPINES, INC. | GOV. P.F. ESPIRITU, PANAPAAN II, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 9.9328 | 13.29 | 20 | NEW | 145240.66 | 11416.91 |  | 0% | 2025-01-27 12:16 | 2025-02-03 | 2025-01-30 | 2025-04-29 | 2025-04-30 |  | 92.4889 | 86 | -45777 | 2025-02-15 06:51 | 2025-02-24 02:12 | 2025-03-18 12:16 | 3.1857 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-04-28 | [6 empty] | 2025-02-05 | TLN-522711 | 0 | 92.4889 | 0 | 92.4889 | 3.1857 | 92 |  | 6.3546 | 6.3546 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072540238', | ME155242 |  |  | 6.4889 |  | Jenneth Madrid
2025-02-06 | 2025-01-31 |  | HMB | R23512370 | CARPIO, EMILIO III S | BELMONT, ALABANG 400 VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 9.29 | 10.7 | 0 | RELOC | 35440.5 | 8616.68 |  | 0% | 2025-01-27 14:02 | 2025-02-03 13:30 | 2025-01-30 |  | 2025-05-16 |  | 108.4153 | 101.4375 | -45793 | 2025-02-15 08:37 | 2025-02-24 03:58 | 2025-03-18 14:02 | 3.7343 | -763.2167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-15 | 102 | [8 empty] | FOR AUDIT |  | 2025-05-31 | -4 | 2025-05-17 | 2025-05-27 | [16 empty] | 2025-02-06 | DV1-2256,DV1-0802 | 0 | 108.4153 | 0 | 108.4153 | 3.7343 | 76 |  | 6.3521 | 6.3521 | 1.2667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23512370', | ME155242 |  |  | 6.9778 |  | Isan Carlo Lazaro
2025-02-04 | 2025-01-31 |  | HMB | X25010133145 | SPEED CONSTRUCTION & DEVELOPMENT CORP., | BLOCK 51, GEORGETOWN HEIGHTS SUBD PH II, BACOOR | BACOOR CITY | DASMA |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 327.9879 | 413.38 | 60 | NEW | 2137566.1 | 332128 | 82065.53 | 24.71% | 2025-01-27 15:58 | 2025-02-03 12:48 | 2025-01-30 |  | 2025-03-13 |  | 44.3347 | 37.4667 | -45729 | 2025-02-18 16:42 | 2025-02-28 08:54 | 2025-03-18 15:58 | 1.3284 | -762.15 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-05-12 | 166 | [8 empty] | ON GOING MAT RETURN | PARTIALLY BILLED | 2025-03-28 | 13 | 2025-03-13 | 2025-04-10 | 2025-06-30 | AGD | Y |  |  |  | 2025-07-12 | NVP | Y | 2025-03-11 | [6 empty] | 2025-02-04 | CQ7-8048,CQ7-8049,TLN-523429,CQ7-8050,CQ7-8051,CQ7-8056,CQ7-8057,CQ7-8058,CQ7-8059,CQ7-8060,CQ7-8061 | 0 | 44.3347 | 0 | 44.3347 | 1.3284 | 140 |  | 5.5233 | 5.5233 | 2.3333 |  | REV |  | 2025-07-16 | 78054.88 | NTC ISSUED | 2025-07-18 |  | 39 | 2025-07-29 | 78054.88 |  | 'X25010133145', | ME166067 |  |  | 6.8681 |  | Isan Carlo Lazaro
2025-02-04 | 2025-01-31 |  | HMB | X25010133146 | F & E DE CASTRO CORPORATION | BLOCK 1, ELISA HOMES PH 4 EXTENSION, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 434.5248 | 1557.75 | 130 | NEW | 2659180.85 | 481239.29 |  | 0% | 2025-01-27 15:59 | 2025-02-03 | 2025-01-30 |  |  |  | -45684.666 | -45691 | 0 | 2025-02-20 13:43 | 2025-03-02 17:55 | 2025-03-18 15:59 | -1273.4601 | 0 | 50 | 32 | 26.9058 | 34.0807 | 23.9058 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-05 | CQ7-8064,CQ7-8065,CQ7-8066,CQ7-8072,CQ7-8073,TLN-523943,CQ7-8079,CQ7-8082,CQ7-8084,CQ7-8086,CQ7-8088,TLN-523945,CQ7-8090,CQ7-8091,CQ7-8092 | 0 | -45684.666 | 0 | -45684.666 | -1273.4601 | 0 |  | 5.1383 | 5.1383 | 0 | 171.334 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010133146', | ME155242 |  |  | 6.334 |  | Isan Carlo Lazaro
2025-02-04 | 2025-02-03 |  | HMB | X24104152226 | MARY ROSE CUTARAN BAYLON | BLOCK 25, VISTA VERDE PH III, BACOOR | BACOOR CITY | DASMA | for digging on going 8-14-25 |  | AVECO | SCHED | Ronilo Gange Jr. | 238.2955 | 717.03 | 25 | NEW | 1198475.06 | 279373.34 |  | 0% | 2025-01-28 15:09 | 2025-02-03 | 2025-01-31 |  |  |  | -45685.6312 | -45691 | 0 | 2025-02-22 11:11 | 2025-03-04 21:20 | 2025-03-19 15:09 | -1230.974 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-05 | CU6-8071,CU6-8072,CU6-8073,CU6-8074,CU6-8075,TLN-523173 | 0 | -45685.6312 | 0 | -45685.6312 | -1230.974 | 0 |  | 4.9408 | 4.9408 | 0 | 170.3688 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104152226', | ME155242 |  |  | 5.3688 |  | RONILO GANGE JR.
|  |  | BIZ | X25010059565 | ALFAMETRO MARKETING, INC. | SAN PEDRO, SAN ANTONIO VALLEY 2, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | CLOSE | Ian Patrick Perez | 17.11 | 17.11 | 31 | NEW | 201536.4 | 26159.77 |  | 0% | 2025-01-28 15:12 | 2025-02-03 | 2025-01-31 |  | 2025-02-10 | 2025-05-01 09:32 | 12.3667 | 7 | 80.3972 | 2025-02-16 09:47 | 2025-02-25 05:08 | 2025-03-19 15:12 | 0.42596 | 1.34 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-11 | 197 | [8 empty] | PAID |  | 2025-02-25 | #VALUE! | [10 empty] | Y | 2025-02-06 | [6 empty] | 2025-02-05 | TLN-520860 | 0 | 12.3667 | 0 | 12.3667 | 0.42596 | 171 |  | 6.316 | 6.316 | 2.85 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010059565', | ME194579 |  |  | 5.3667 |  | RONILO GANGE JR.
|  |  | BIZ | X25010059526 | ALFAMETRO MARKETING, INC. | PAPA PIO - SAV 13, SAN ISIDRO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | CLOSE | Ian Patrick Perez | 9.31 | 9.11 | 31 | NEW | 35550.33 | 19424.84 |  | 0% | 2025-01-28 15:12 | 2025-02-03 | 2025-01-31 |  | 2025-02-10 | 2025-04-14 07:33 | 12.3667 | 7 | 63.3146 | 2025-02-16 09:47 | 2025-02-25 05:08 | 2025-03-19 15:12 | 0.42596 | 1.0552 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-11 | 197 | [8 empty] | PAID |  | 2025-02-25 | #VALUE! | [10 empty] | Y | 2025-02-06 | [6 empty] | 2025-02-05 | CY8-0502,TLN-516761 | 0 | 12.3667 | 0 | 12.3667 | 0.42596 | 171 |  | 6.316 | 6.316 | 2.85 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010059526', | ME194579 |  |  | 5.3667 |  | Isan Carlo Lazaro
2025-02-04 | 2025-02-03 |  | CBG | X24083093382 | DITO TELECOMMUNITY CORPORATION | BUENDIA, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | on-going digging |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 273.9374 | 321.07 | 31 | NEW | 4553436.26 | 253515.88 | 56118.73 | 22.14% | 2025-01-28 15:16 | 2025-02-03 12:52 | 2025-01-31 | 2025-02-24 | 2025-02-24 |  | 26.3639 | 20.4639 | -45712 | 2025-02-20 02:35 | 2025-03-01 21:36 | 2025-03-19 15:16 | 0.77627 | -761.8667 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-04-25 | 183 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-03-11 | 0 | 2025-02-24 | 2025-03-11 | [8 empty] | Y | 2025-02-21 | [6 empty] | 2025-02-05 | DR2-8032,DQ2-0033,DQ2-5060,DQ2-8075,DQ2-0035,TLN-198894 | 0 | 26.3639 | 0 | 26.3639 | 0.77627 | 157 |  | 5.399 | 5.399 | 2.6167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083093382', | ME166067 |  |  | 5.9 |  | IJP
2025-03-13 |  | Y | BIZ | X25010059547 | ALFAMETRO MARKETING INC. (CORCUERRA - BANNER 4TH ESTATE) | BANNER, 4TH ESTATE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 10.8028 | 19.97 | 31 | NEW | 202246.77 | 17159.97 |  | 0% | 2025-01-28 15:26 | 2025-02-03 13:38 | 2025-01-31 | 2025-03-04 04:21 | 2025-03-04 | 2025-07-10 | 34.3569 | 28.4319 | 128 | 2025-02-16 10:01 | 2025-02-25 05:22 | 2025-03-19 15:26 | 1.1834 | 2.1333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-03 | 175 | [8 empty] | PAID | Conj. X25010134670 -termination | 2025-03-19 | -6 | 2025-02-24 | 2025-03-13 | 2025-03-25 | AGD | N |  |  |  | 2025-06-20 | NVP | Y | 2025-03-03 | [6 empty] | 2025-03-13 | TLN-521778 | 0 | 34.3569 | 0 | 34.3569 | 1.1834 | 149 |  | 6.3156 | 6.3156 | 2.4833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010059547', | ME166067 |  |  | 5.925 |  | IJP
2025-02-04 | 2025-02-03 |  | HMB | X25010173661 | MJ RIAN P ROM | SAN PEDRO, CARMENCITA VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 4.32 | 4.32 | 1.5 | NEW | 25562.85 | 3478.78 |  | 0% | 2025-01-28 17:06 | 2025-02-03 | 2025-01-31 |  | 2025-02-24 |  | 26.2875 | 21 | -45712 | 2025-02-16 11:41 | 2025-02-25 07:02 | 2025-03-19 17:06 | 0.90546 | -761.8667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-25 | 183 | [8 empty] | FOR AUDIT |  | 2025-03-11 | -20 | 2025-04-25 | 2025-02-19 | [8 empty] | Y | 2025-02-25 | [6 empty] | N/A |  | 0 | 26.2875 | 0 | 26.2875 | 0.90546 | 157 |  | 6.3132 | 6.3132 | 2.6167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010173661', | ME155242 |  |  | 5.2875 |  | Jenneth Madrid
2025-04-04 | 2025-02-05 |  | HMB | X24072855187 | MANUEL SARIANA BOLON | A. ROLDAN, PUROK 2A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 54.0117 | 31.58 | 7.5 | NEW | 32522.29 | 202490.13 |  | 0% | 2025-01-30 21:35 | 2025-02-06 08:04 | 2025-02-04 | 2025-06-11 | 2025-06-11 |  | 131.1007 | 124.6639 | -45819 | 2025-02-18 16:10 | 2025-02-27 11:31 | 2025-03-21 21:35 | 4.5157 | -763.65 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-10 | 76 | With major design modifications | Y | Y |  |  | 2025-05-29 | 13 | 2025-06-11 | FOR AUDIT |  | 2025-06-26 | 22 | 2025-06-11 | 2025-07-18 | [8 empty] | Y | 2025-05-29 | [6 empty] | 2025-04-07 | A5-5443,TLN-523109 | 0 | 131.1007 | 13 | 118.1007 | 4.0679 | 50 | 4.5157 | 6.2379 | 1.7222 | 0.83333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072855187', | ME185284 |  |  | 6.4368 |  | Jenneth Madrid
2025-02-25 | 2025-02-05 | Y | BIZ | X24093683073 | ELECTRO-SYSTEMS INDUSTRIES CORPORATION | BAES, PERPETUAL VILLAGE, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 214.8948 | 257.28 | 42 | MODIFICATION | 589728.55 | 173057.12 | 96239.21 | 55.61% | 2025-01-31 | 2025-02-05 08:13 | 2025-02-04 |  | 2025-02-27 |  | 27 | 21.6576 | -45715 | 2025-02-21 20:51 | 2025-03-03 12:00 | 2025-03-22 | 0.81429 | -761.9167 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-04-28 | 180 | [8 empty] | ON GOING MAT RETURN | PARTIALLY BILLED | 2025-03-14 | 38 | 2025-02-27 | 2025-04-21 | 2025-07-01 | ECI | Y |  |  |  | 2025-07-12 | NVP | Y | 2025-02-25 | [6 empty] | 2025-02-27 | DY2-8110,TLN-035055 | 0 | 27 | 0 | 27 | 0.81429 | 154 |  | 5.4587 | 5.4587 | 2.5667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093683073', | ME185284 |  |  | 5.3424 |  | RONILO GANGE JR.
|  |  | BIZ | X24103965259 | TEVERE AVANDY HOLDINGS INC. | AGUIRRE, BF HOMES, PARANAQUE | TAGUIG CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 27.26 | 27.26 | 57 | NEW | 242559.2 | 33951.28 |  | 0% | 2025-01-31 | 2025-02-05 12:17 | N/A |  | 2025-02-11 | 2025-07-01 12:25 | 11 | 5.4882 | 140.5174 | 2025-02-18 01:47 | 2025-02-26 16:40 | 2025-03-22 | 0.39147 | 2.342 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | PAID |  | 2025-02-26 | #VALUE! | [10 empty] | Y | 2025-02-05 | [8 empty] | 0 | 11 | 0 | 11 | 0.39147 | 170 |  | 6.4415 | 6.4415 | 2.8333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103965259', | ME194579 |  |  | 5.5118 |  | IJP
|  |  | HMB | X24114657334 | BUENA MONTES BASCUGUIN | BLOCK 18 , KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | C2 | CLOSE | Ian Patrick Perez | 5.78 | 6.41 | 15 | NEW | 23600.21 | 15220.48 |  | 0% | 2025-01-31 | 2025-02-06 07:47 | N/A |  | 2025-02-10 | 2025-04-14 | 10 | 3.6757 | 63 | 2025-02-18 18:35 | 2025-02-27 13:56 | 2025-03-22 | 0.34444 | 1.05 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-11 | 197 | [8 empty] | FOR AUDIT |  | 2025-02-25 | #VALUE! | [20 empty] | 0 | 10 | 0 | 10 | 0.34444 | 171 |  | 6.2344 | 6.2344 | 2.85 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114657334', | ME194579 |  |  | 6.3243 |  | IJP
2025-02-11 | 2025-02-05 |  | HMB | X24103906706 | DAWN ISOBEL YU AQUINO | BATANGAS EAST, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 71.2438 | 173.94 | 89 | NEW | 477133.36 | 81814.33 |  | 0% | 2025-02-03 | 2025-02-07 15:13 | 2025-02-04 |  |  |  | -45691 | -45695.634 | 0 | 2025-02-23 08:17 | 2025-03-04 13:41 | 2025-03-25 | -1467.9009 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-11 | CS9-8081,TLN-526089 | 0 | -45691 | 0 | -45691 | -1467.9009 | 0 |  | 5.7186 | 5.7186 | 0 | 165 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103906706', | ME155242 |  |  | 4.634 |  | Isan Carlo Lazaro
2025-02-11 |  |  | BIZ | X25010134670 | C N C CONSTRUCTION & DEV'T. CORPORATION | BANNER, 4TH ESTATE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 7.16 | 7.4 | - | TERMINATION | 17205.11 | 6358.25 |  | 0% | 2025-02-03 | 2025-02-06 07:52 |  |  | 2025-03-05 |  | 30 | 26.6722 | -45721 | 2025-02-15 | 2025-02-22 | 2025-03-25 | 1.5 | -762.0167 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-05-04 | 174 | [8 empty] | FOR AUDIT | Conj. X25010059547 | 2025-03-20 | 22 | 2025-03-05 | 2025-04-11 | [16 empty] | N/A |  | 0 | 30 | 0 | 30 | 1.5 | 148 |  | 8.9 | 8.9 | 2.4667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010134670', | ME166067 |  |  | 3.3278 |  | RONILO GANGE JR.
2025-02-17 | 2025-02-11 |  | CBG | X24051849062 | DITO TELECOMMUNITY CORPORATION | BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for survey |  | POWERHOUSE | FCOMP | Jenneth Madrid | 37.6161 | 46.96 | 22 | NEW | 808167.06 | 40352.42 |  | 0% | 2025-02-04 | 2025-02-12 09:51 | 2025-02-10 |  | 2025-05-28 14:41 |  | 113.6118 | 105.2014 | -45805.6118 | 2025-02-22 18:35 | 2025-03-03 13:56 | 2025-03-26 | 3.9133 | -763.4269 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 14:41 | 89.3882 | [8 empty] | NO COC |  | 2025-06-12 14:41 | #VALUE! | [10 empty] | Y | 2025-05-27 | [6 empty] | 2025-02-17 | CZ9-5983,TLN-201460 | 0 | 113.6118 | 0 | 113.6118 | 3.9133 | 63.3882 |  | 6.0967 | 6.0967 | 1.0565 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051849062', | ME185284 |  |  | 8.4104 |  | RONILO GANGE JR.
2025-02-17 | 2025-02-11 |  | CBG | X24072866458 | DITO TELECOMMUNITY CORPORATION | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for survey; FOR SCHED DIGGING |  | VJC | SCHED | Jenneth Madrid | 57.99 | 963.39 | 31 | NEW | 1025199.32 | 37538.23 |  | 0% | 2025-07-07 10:09 | 2025-07-11 07:19 | 2025-02-10 |  |  |  | -45845.4229 | -45849.3049 | 0 | 2025-08-01 06:11 | 2025-08-11 16:20 | 2025-08-26 10:09 | -1235.2795 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | With pole / drainage / digging / manhole / pole attachment issue | Y | Y |  |  | 2025-02-19 | 138 | 2025-07-07 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-02-17 | B7-5441,TLN-198570 | 0 | -45845.4229 | 138 | -45983.4229 | -1238.9978 | 0 | 0.63527 | 0.63527 | 0 | 0 | 10.5771 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072866458', | ME185284 |  |  | 3.8819 |  | RONILO GANGE JR.
2025-02-25 | 2025-02-11 |  | CBG | X24072535895 | DITO TELECOMMUNITY CORPORATION | SINIGUELAS, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | With new design released | W/ ISSUE | CHALLENGER | SCHED | Isan Carlo Lazaro | 49.4332 | 81.7 | 22 | NEW | 306884.92 | 49458.75 |  | 0% | 2025-02-04 14:03 | 2025-02-12 09:54 | 2025-02-10 |  |  |  | -45692.5854 | -45700.4125 | 0 | 2025-02-24 16:06 | 2025-03-05 19:51 | 2025-03-26 14:03 | -1484.4572 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | With pole / drainage / digging / manhole / pole attachment issue | Y |  |  |  | 2025-05-16 |  |  |  |  | 1900-01-14 | 0 | [18 empty] | 2025-02-25 | B8-5039,B8-8103,TLN-522699 | 0 | -45692.5854 | 0 | -45692.5854 | -1484.4572 | 0 | 5.7313 | 5.7313 | 0 | 0 | 163.4146 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072535895', | ME166067 |  |  | 7.8271 |  | RONILO GANGE JR.
2025-02-17 | 2025-02-11 |  | CBG | X24041261990 | DITO TELECOMMUNITY CORPORATION | NATIONAL, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 49.4332 | 78.87 | 20 | NEW | 346656.97 | 52965.51 | 46902 | 88.55% | 2025-02-04 15:25 | 2025-02-12 09:53 | 2025-02-10 |  | 2025-03-18 |  | 41.3576 | 33.5882 | -45734 | 2025-02-24 17:28 | 2025-03-05 21:13 | 2025-03-26 15:25 | 1.3436 | -762.2333 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-05-17 | 161 |  | Y |  |  | Y | 2025-03-12 | 6 | 2025-03-18 | FOR AUDIT | PARTIALLY BILLED | 2025-04-02 | 8 | 2025-03-18 | 2025-04-10 | [16 empty] | 2025-02-17 | DR1-8042,TLN-521305 | 6 | 35.3576 | 6 | 35.3576 | 1.1487 | 135 |  | 5.7295 | 5.7295 | 2.25 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041261990', | ME166067 |  |  | 7.7694 |  | Jenneth Madrid
2025-02-17 |  |  | CBG | X24083132605 | DITO TELECOMMUNITY CORPORATION | BUENCAMINO, BUENCAMINO, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For survey |  | MAINTENANCE | FCOMP | Isan Carlo Lazaro | 20.78 | 20.78 | 31 | NEW | 61546.71 | 37641.08 |  | #VALUE! | 2025-02-04 15:49 | 2025-02-12 09:55 | 2025-02-10 |  | 2025-04-22 |  | 76.341 | 68.5868 | -45769 | 2025-02-23 10:24 | 2025-03-04 05:45 | 2025-03-26 15:49 | 2.6295 | -762.8167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [18 empty] | N/A |  | 0 | 76.341 | 0 | 76.341 | 2.6295 | 100 |  | 6.074 | 6.074 | 1.6667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083132605', | ME166067 |  |  | 7.7542 |  | Jenneth Madrid
2025-02-25 | 2025-02-11 |  | HMB | X24093618242 | PRIME ACERS HOLDINGS CORPORATION | DIEGO SILANG, AFP OVAI PH 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 122.5708 | 333.45 | 263 | NEW | 1097984.13 | 142064.77 | 61066.72 | 42.99% | 2025-02-05 | 2025-02-12 10:25 | 2025-02-10 | 2025-06-21 | 2025-06-21 |  | 136 | 128.566 | -45829 | 2025-02-24 12:00 | 2025-03-05 12:00 | 2025-03-27 | 4.5333 | -763.8167 | 30 | 30 | 22.5 | 28.5 | 19.5 | 60 | 57 | 52 | 2025-08-20 | 66 | Third party concern (Other than the applicant) | Y | Y |  |  | 2025-03-13 | 99 | 2025-06-20 | FOR AUDIT |  | 2025-07-06 | 22 | 2025-06-21 | 2025-07-28 | [8 empty] | Y | 2025-06-18 | [6 empty] | 2025-02-25 | C7-8037,C7-8038,TLN-523806 | 0 | 136 | 99 | 37 | 1.2333 | 40 | 4.5333 | 5.8667 | 1.3333 | 0.66667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093618242', | ME185284 |  |  | 7.434 |  | Jenneth Madrid
2025-02-21 | 2025-02-11 |  | BIZ | X25010095532 | MINA B. TAPISPISAN | BALLECER, ZONE 4, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 2.58 | 4.59 | 10 | NEW | 21877.86 | 3696.19 |  | 0% | 2025-02-05 | 2025-02-12 10:26 | 2025-02-10 |  | 2025-02-25 |  | 20 | 12.5653 | -45713 | 2025-02-23 18:35 | 2025-03-04 13:56 | 2025-03-27 | 0.68889 | -761.8833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-04-26 | 182 | [8 empty] | FOR AUDIT |  | 2025-03-12 | 79 | 2025-02-25 | 2025-05-30 | [8 empty] | Y | 2025-02-24 | [6 empty] | N/A |  | 0 | 20 | 0 | 20 | 0.68889 | 156 |  | 6.0622 | 6.0622 | 2.6 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010095532', | ME185284 |  |  | 7.4347 |  | Jenneth Madrid
2025-02-17 | 2025-02-11 |  | HMB | X24103896457 | CITY GOVT OF LAS PIÑAS | DOÑA PILAR AGUIRRE, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 123.4425 | 399.38 | 339 | MODIFICATION | 1353967.43 | 182994.22 | 84000.89 | 45.9% | 2025-02-05 13:14 | 2025-02-12 10:23 | 2025-02-10 |  | 2025-03-17 08:43 |  | 39.8118 | 32.9306 | -45733.3632 | 2025-02-23 23:31 | 2025-03-04 16:40 | 2025-03-27 13:14 | 1.3934 | -762.2227 | 30 | 28 | 21.4286 | 27.1429 | 18.4286 | 60 | 57 | 52 | 2025-05-16 08:43 | 161.6368 | [8 empty] | NO COC | PARTIALLY BILLED | 2025-04-01 08:43 | #VALUE! | [10 empty] | Y | 2025-03-11 | [6 empty] | 2025-02-17 | CU8-8105,CU8-8058,TLN-522058,CU8-0148 | 0 | 39.8118 | 0 | 39.8118 | 1.3934 | 135.6368 |  | 6.1407 | 6.1407 | 2.2606 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103896457', | ME155242 |  |  | 6.8812 |  | Jenneth Madrid
2025-02-17 |  |  | HMB | X24124766675 | PATRICK SANVICTORES GARCIA | BEGONIA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For survey |  | MAINTENANCE | FCOMP | Isan Carlo Lazaro | 19.13 | 19.13 | 100 | MODIFICATION | 58152.36 | 26972.79 |  | 0% | 2025-02-05 16:16 | 2025-02-12 10:26 | 2025-02-10 |  | 2025-03-28 |  | 50.3222 | 43.5653 | -45744 | 2025-02-23 18:03 | 2025-03-04 08:56 | 2025-03-27 16:16 | 1.7909 | -762.4 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-05-27 | 151 | [8 empty] | FOR AUDIT |  | 2025-04-12 | #VALUE! | [18 empty] | N/A |  | 0 | 50.3222 | 0 | 50.3222 | 1.7909 | 125 |  | 6.2394 | 6.2394 | 2.0833 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124766675', | ME166067 |  |  | 6.7569 |  | Jenneth Madrid
2025-04-04 | 2025-02-11 |  | HMB | X24103884052 | CARMELINDELLE PALMA MATERNAL | MOLAVE, MANILA DOCTOR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 281.947 | 740.63 | 63.1 | MODIFICATION | 1339954.29 | 300056.58 |  | 0% | 2025-02-06 | 2025-02-12 10:30 | 2025-02-10 |  |  |  | -45694 | -45700.4375 | 0 | 2025-03-01 16:50 | 2025-03-11 19:44 | 2025-03-28 | -1283.4638 | 0 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-07 | CV9-8061,CV9-8062,CV9-8063,CV9-8064,CV9-8065,TLN-526062 | 0 | -45694 | 0 | -45694 | -1283.4638 | 0 |  | 4.9154 | 4.9154 | 0 | 162 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103884052', | ME155242 |  |  | 6.4375 |  | Isan Carlo Lazaro
2025-02-21 | 2025-02-11 |  | HMB | X25010222043 | NOEMI A SUMINISTRADO | MILLARES, PUROK 4B, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 59.175 | 151.12 | 15 | NEW | 344593.38 | 58274.76 |  | 0% | 2025-02-06 | 2025-02-12 10:33 | 2025-02-10 |  | 2025-02-27 |  | 21 | 14.5604 | -45715 | 2025-02-27 04:58 | 2025-03-08 15:53 | 2025-03-28 | 0.65064 | -761.9167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-04-28 | 180 | [8 empty] | NO COC | supersedes X24104029330 | 2025-03-14 | #VALUE! | [18 empty] | 2025-02-21 | TLN-527101,A8-1154,A8-8128 | 0 | 21 | 0 | 21 | 0.65064 | 154 |  | 5.422 | 5.422 | 2.5667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010222043', | ME185284 |  |  | 6.4396 |  | Isan Carlo Lazaro
2025-02-17 | 2025-02-11 |  | CBG | X23093504208 | YIHUA PHILIPPINES GROUP INC. | QUIRINO, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 198.1774 | 396.26 | 838 | NEW | 2855707.96 | 318164.19 |  | 0% | 2025-02-06 07:34 | 2025-02-11 17:23 | 2025-02-10 |  | 2025-03-20 |  | 41.6847 | 36.2757 | -45736 | 2025-02-21 20:44 | 2025-03-01 19:26 | 2025-03-28 07:34 | 1.6855 | -762.2667 | 30 | 23 | 18.5484 | 23.4946 | 15.5484 | 60 | 57 | 52 | 2025-05-19 | 159 | [8 empty] | NO COC |  | 2025-04-04 | #VALUE! | [18 empty] | 2025-02-17 | B5-8022,B5-8023,B5-8024,B5-8025,TLN-518634 | 0 | 41.6847 | 0 | 41.6847 | 1.6855 | 133 |  | 7.0633 | 7.0633 | 2.2167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23093504208', | ME155242 |  |  | 5.409 |  | IJP
|  |  | BIZ | X25020425086 | C N C CONSTRUCTION & DEV'T. CORPORATION | SAN PEDRO, SAN ANTONIO VALLEY 2, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 7.46 | 7.46 | - | TERMINATION | 17390.27 | 16969.79 |  | 0% | 2025-02-06 08:59 | 2025-02-06 08:59 | 2025-02-10 |  | 2025-02-11 | 2025-06-03 08:40 | 4.6257 | 4.6257 | 112.3611 | 2025-02-18 08:59 | 2025-02-25 08:59 | 2025-03-28 08:59 | 0.23128 | 1.8727 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-04-12 | 196 | [8 empty] | FOR AUDIT | conj. X25010059565 | 2025-02-26 | #VALUE! | [20 empty] | 0 | 4.6257 | 0 | 4.6257 | 0.23128 | 170 |  | 8.7313 | 8.7313 | 2.8333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020425086', | ME194579 |  |  | 0 |  | Isan Carlo Lazaro
2025-02-17 | 2025-02-11 | Y | BIZ | X25010120302 | CDC REALTY INC. | DOVE LOFTS, LION'S PARK RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  | with follow up from Ma'am Cecille, Head Enterprise & National Government | VJC | FCOMP | Jenneth Madrid | 70.6731 | 120.1 | 193 | NEW | 813015.11 | 97030.13 | 47759.31 | 49.22% | 2025-02-06 13:14 | 2025-02-12 10:32 | 2025-02-10 | 2025-03-03 | 2025-03-03 |  | 24.4486 | 18.5611 | -45719 | 2025-02-25 23:56 | 2025-03-06 23:36 | 2025-03-28 13:14 | 0.81691 | -761.9833 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-05-02 | 176 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-03-18 | 43 | 2025-03-03 | 2025-04-30 | [8 empty] | Y | 2025-02-28 | [6 empty] | 2025-02-17 | DZ1-8092,TLN-523746 | 0 | 24.4486 | 0 | 24.4486 | 0.81691 | 150 |  | 5.8289 | 5.8289 | 2.5 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010120302', | ME185284 |  |  | 5.8875 |  | Isan Carlo Lazaro
2025-02-17 | 2025-02-11 |  | HMB | R23792026 | NEW PACIFIC RESOURCES MANAGEMENT (SPV- AMC), INC., HMB | BLOCK 27, SOLVIENTO VILLAS PH 2, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 13.4136 | 18.46 | - | RELOC | 40378.97 | 15581.73 |  | 0% | 2025-02-06 15:16 | 2025-02-12 10:31 | 2025-02-10 |  | 2025-05-26 09:54 |  | 108.7764 | 102.9743 | -45803.4125 | 2025-02-18 15:16 | 2025-02-25 15:16 | 2025-03-28 15:16 | 5.4388 | -763.3902 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-25 09:54 | 91.5875 | [8 empty] | NO COC |  | 2025-06-10 09:54 | #VALUE! | [18 empty] | N/A |  | 0 | 108.7764 | 0 | 108.7764 | 5.4388 | 65.5875 |  | 8.7182 | 8.7182 | 1.0931 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23792026', | ME155242 |  |  | 5.8021 |  | Jenneth Madrid
2025-02-18 | 2025-02-18 |  | CBG | X25010314175 | BGST PRIME DEVELOPMENT CORP. | COASTAL RD, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 9.42 | 19.34 | - | TERMINATION | 25833.16 | 16625.89 |  | 0% | 2025-02-07 15:27 | 2025-02-13 12:54 | 2025-02-17 |  | 2025-04-07 |  | 58.3562 | 52.4625 | -45754 | 2025-02-19 15:27 | 2025-02-26 15:27 | 2025-03-29 15:27 | 2.9178 | -762.5667 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-06-06 | 141 | [8 empty] | NO COC |  | 2025-04-22 | #VALUE! | [18 empty] | N/A |  | 0 | 58.3562 | 0 | 58.3562 | 2.9178 | 115 |  | 8.6678 | 8.6678 | 1.9167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010314175', | ME155242 |  |  | 5.8937 |  | Jenneth Madrid
2025-02-11 | 2025-02-26 | Y | BIZ | X24030689569 | PILIPINAS SHELL PETROLEUM CORPORATION | SAMPAGUITA, CAMP SAMPAGUITA, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | TECO | Ronilo Gange Jr. | 666.3304 | 2874.93 | 78 | NEW | 3575972.05 | 828522.98 | 1303521.46 | 157.3% | 2025-02-08 20:10 | 2025-02-11 12:55 | 2025-02-21 | 2025-02-26 | 2025-02-26 | 2025-07-30 | 17.1597 | 14.4618 | 154 | 2025-03-06 01:09 | 2025-03-16 13:41 | 2025-03-30 20:10 | 0.45625 | 2.5667 | 50 | 34 | 28.208 | 35.7301 | 25.208 | 60 | 57 | 52 | 2025-04-27 | 181 | [8 empty] | PAID |  | 2025-03-13 | 29 | 2025-02-26 | 2025-04-11 | 2025-06-26 | ECI | Y |  |  |  | 2025-07-25 | NVP | Y | 2025-02-21 | [6 empty] | 2025-02-11 | CQ9-5764,CQ9-5765,CQ9-5766,CQ9-5767,CQ9-5768,CQ9-5768,CQ9-5770,CQ9-5771,CQ9-5772,CQ9-5773,CQ9-5774,CQ9-5775,CQ9-5777,CQ9-5778,TLN-520793 | 0 | 17.1597 | 0 | 17.1597 | 0.45625 | 155 |  | 4.5774 | 4.5774 | 2.5833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030689569', | ME155242 |  |  | 2.6979 |  | RONILO GANGE JR.
2025-02-21 | 2025-02-18 |  | HMB | X24083222197 | AUREA PEÑERO BANAO | BLOCK 101, SITIO IMELDA, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | FOR SCHED INSTALLATION OF POLE (BUSY ROAD |  | VJC | SCHED | Jenneth Madrid | 22.31 | 102.16 | 5 | NEW | 141015.84 | 20357.32 |  | 0% | 2025-02-10 12:12 | 2025-02-18 14:33 | 2025-02-17 |  |  |  | -45698.5083 | -45706.6062 | 0 | 2025-03-03 17:10 | 2025-03-13 04:05 | 2025-04-01 12:12 | -1415.8726 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-21 | A8-8096 | 0 | -45698.5083 | 0 | -45698.5083 | -1415.8726 | 0 |  | 5.2823 | 5.2823 | 0 | 157.4917 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083222197', | ME185284 |  |  | 8.0979 |  | RONILO GANGE JR.
2025-03-04 |  |  | HMB | X22125058629 | CITY GOVERNMENT OF MUNTINLUPA | FILINVEST SOCIALIZED HOUSING, FILINVEST SOCIALIZED HOUSING, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | PCAN | Isan Carlo Lazaro | 30.6 | 30.6 | 60 | MODIFICATION | 209537.97 |  |  | #DIV/0! | 2025-02-10 14:37 |  | 2025-02-17 |  |  |  | -45698.609 | 0 | 0 | 2025-02-28 16:24 | 2025-03-09 07:17 | 2025-04-01 14:37 | -1626.3329 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45698.609 | 0 | -45698.609 | -1626.3329 | 0 |  | 6.0639 | 6.0639 | 0 | 157.391 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22125058629', | ME166067 |  |  | -45698.609 |  | Isan Carlo Lazaro
2025-02-19 |  |  | HMB | X25010133520 | MICHAEL GERARD TANTOCO MORADA | BUNGA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Isan Carlo Lazaro | 20.14 | 20.14 | 110 | NEW | 242142.06 | 31416.7 |  | 0% | 2025-02-10 14:41 | 2025-02-18 11:04 | 2025-02-17 |  | 2025-02-28 |  | 17.3882 | 9.5389 | -45716 | 2025-02-27 22:49 | 2025-03-08 08:59 | 2025-04-01 14:41 | 0.64119 | -761.9333 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-04-29 | 179 | [8 empty] | FOR AUDIT |  | 2025-03-15 | #VALUE! | [18 empty] | 2025-02-19 | TLN-527063 | 0 | 17.3882 | 0 | 17.3882 | 0.64119 | 153 |  | 6.2831 | 6.2831 | 2.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010133520', | ME166067 |  |  | 7.8493 |  | Isan Carlo Lazaro
2025-02-19 | 2025-02-18 |  | BIZ | X24103959118 | MILES AND LEVELS PHILIPPINES, INC. | WEST SERVICE, PHILCREST CPD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 55.5593 | 65.08 | 16 | NEW | 335303.64 | 52409 | 40226.7 | 76.76% | 2025-02-10 17:00 | 2025-02-18 14:35 | 2025-02-17 |  | 2025-03-19 16:13 |  | 36.9674 | 29.0681 | -45735.6757 | 2025-03-02 19:03 | 2025-03-11 22:48 | 2025-04-01 17:00 | 1.201 | -762.2613 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-05-18 16:13 | 159.3243 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-04-03 16:13 | 7.3243 | 2025-03-13 | 2025-04-11 | [16 empty] | 2025-02-19 | DV1-8081,TLN-526114 | 0 | 36.9674 | 0 | 36.9674 | 1.201 | 133.3243 |  | 5.5324 | 5.5324 | 2.2221 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103959118', | ME166067 |  |  | 7.8993 |  | Isan Carlo Lazaro
2025-02-18 | 2025-02-18 | Y | CBG | X24124769477 | CMSTAR MANAGEMENT INC. | DAANG-HARI RD., MOLINO IV, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 18.5428 | 24.46 | 45 | NEW | 364258.38 | 21017.78 |  | 0% | 2025-02-11 13:39 | 2025-02-18 14:45 | 2025-02-17 |  | 2025-03-11 07:21 |  | 27.7375 | 20.6917 | -45727.3063 | 2025-03-02 08:14 | 2025-03-11 03:35 | 2025-04-02 13:39 | 0.9554 | -762.1218 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-10 07:21 | 167.6937 | [8 empty] | NO COC | conj.X25010079615 | 2025-03-26 07:21 | #VALUE! | [18 empty] | 2025-02-18 | TLN-526895 | 0 | 27.7375 | 0 | 27.7375 | 0.9554 | 141.6937 |  | 5.836 | 5.836 | 2.3616 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124769477', | ME185284 |  |  | 7.0458 |  | Jenneth Madrid
2025-02-18 | 2025-02-18 |  | BIZ | X24124786551 | OMNICO CONSORTIUM INC. | CARLO, TAGUIG BAGUMBAYAN INDL ASS INC, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | sadang:Ayaw pahukayan ng may bahay n Yan |  | ECOM | FCOMP | Ronilo Gange Jr. | 101.1783 | 257.92 | 220 | NEW | 1023594.08 | 144686.01 | 27500.98 | 19.01% | 2025-02-11 16:31 | 2025-02-18 14:41 | 2025-02-17 |  | 2025-03-25 13:56 |  | 41.8924 | 34.9688 | -45741.5806 | 2025-03-02 17:11 | 2025-03-11 14:10 | 2025-04-02 16:31 | 1.4263 | -762.3597 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 60 | 57 | 52 | 2025-05-24 13:56 | 153.4194 | [8 empty] | ON GOING MAT RETURN | PARTIALLY BILLED | 2025-04-09 13:56 | -24.5806 | 2025-04-11 | 2025-03-16 | [6 empty] | 2025-08-05 | NVP | Y | 2025-03-08 | [6 empty] | 2025-02-18 | DY2-8123,TLN-526843 | 0 | 41.8924 | 0 | 41.8924 | 1.4263 | 127.4194 |  | 5.7647 | 5.7647 | 2.1237 |  | REV |  | 2025-08-05 | 65037.66 | NTC ISSUED | 2025-08-07 |  | 19 |  |  |  | 'X24124786551', | ME155242 |  |  | 6.9236 |  | Jenneth Madrid
2025-02-21 | 2025-02-18 |  | HMB | X24104024806 | JUNEL PENALBA | JUDGE BIENVENIDO TAN SR., BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 43.7061 | 43.71 | 72.75 | NEW | 431455.57 | 51274.68 |  | 0% | 2025-02-12 14:29 | 2025-02-18 14:54 | 2025-02-17 |  | 2025-05-21 |  | 97.3965 | 91.3792 | -45798 | 2025-03-02 16:16 | 2025-03-11 07:09 | 2025-04-03 14:29 | 3.4662 | -763.3 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-07-20 | 97 | [8 empty] | ON GOING MAT RETURN |  | 2025-06-05 | -13 | 2025-04-14 | 2025-05-23 | [6 empty] | 2025-08-07 | NVP | [8 empty] | 2025-02-21 | CV7-8150,TLN-526196 | 0 | 97.3965 | 0 | 97.3965 | 3.4662 | 71 |  | 5.9929 | 5.9929 | 1.1833 |  | REV |  | 2025-08-07 | 6727.15 | NTC ISSUED | 2025-08-07 |  | 19 |  |  |  | 'X24104024806', | ME166067 |  |  | 6.0174 |  | Jenneth Madrid
2025-02-18 | 2025-02-18 |  | HMB | R23915658 | CERNAL ARNOLD BONUS | SINIGUELAS, CAMELLA SPV WEST PH 1, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 13.4836 | 16.61 | 0 | RELOC | 41482.86 | 14273.35 |  | 0% | 2025-02-12 15:57 | 2025-02-18 14:52 | 2025-02-17 |  |  |  | -45700.6646 | -45706.6194 | 0 | 2025-03-03 10:32 | 2025-03-12 05:53 | 2025-04-03 15:57 | -1574.134 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45700.6646 | 0 | -45700.6646 | -1574.134 | 0 |  | 5.7982 | 5.7982 | 0 | 155.3354 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23915658', | ME155242 |  |  | 5.9549 |  | Isan Carlo Lazaro
2025-02-18 | 2025-02-18 |  | HMB | R23697156 | MORALES, LESLIE DIANNE VITAL | DAFFODIL, GSIS TOWNHOMES, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Donard Elija Bencito | 48.2066 | 57.77 | 0 | RELOC | 202633.21 | 48879.26 |  | 0% | 2025-02-12 16:33 | 2025-02-18 14:48 | 2025-02-17 |  | 2025-03-18 |  | 33.3104 | 27.3833 | -45734 | 2025-03-04 18:36 | 2025-03-13 22:21 | 2025-04-03 16:33 | 1.0822 | -762.2333 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-05-17 | 161 | [8 empty] | NO COC |  | 2025-04-02 | #VALUE! | [18 empty] | 2025-02-18 | CT7-8120 | 0 | 33.3104 | 0 | 33.3104 | 1.0822 | 135 |  | 5.4681 | 5.4681 | 2.25 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23697156', | ME188529 |  |  | 5.9271 |  | Isan Carlo Lazaro
2025-02-21 | 2025-02-18 |  | HMB | X24124774979 | CITY GOV'T OF LAS PIÑAS | NAGA, PULANGLUPA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | done:digging and pole erect |  | ECOM | SCHED | Ronilo Gange Jr. | 34.6795 | 119.51 | 16.4 | NEW | 295706.76 | 33199.84 |  | 0% | 2025-02-12 17:01 | 2025-02-18 14:56 | 2025-02-17 |  |  |  | -45700.709 | -45706.6222 | 0 | 2025-03-05 21:59 | 2025-03-15 08:54 | 2025-04-03 17:01 | -1415.9408 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-21 | CY7-8111,TLN-526838 | 0 | -45700.709 | 0 | -45700.709 | -1415.9408 | 0 |  | 5.2141 | 5.2141 | 0 | 155.291 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124774979', | ME155242 |  |  | 5.9132 |  | RONILO GANGE JR.
2025-02-24 | 2025-02-18 |  | HMB | X23083154356 | CITY GOVERNMENT OF PARAÑAQUE | MANGGA, MASVILLE, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 308.1928 | 674.76 | 167 | NEW | 2792430.39 | 484145.49 | 39469.99 | 8.153% | 2025-02-13 13:55 | 2025-02-21 15:07 | 2025-02-17 |  | 2025-05-12 09:00 |  | 87.7951 | 79.7451 | -45789.375 | 2025-03-08 02:41 | 2025-03-17 22:05 | 2025-04-04 13:55 | 2.579 | -763.1562 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 2025-07-11 09:00 | 105.625 | With scheduled PAI | Y | Y |  |  | 2025-05-01 | 8 | 2025-05-09 | NO COC | PARTIALLY BILLED | 2025-05-27 09:00 | #VALUE! | [10 empty] | Y | 2025-05-08 | [6 empty] | 2025-02-24 | DW1-1292,DW1-8020,TLN-170991 | 0 | 87.7951 | 8 | 79.7951 | 2.344 | 79.625 | 2.579 | 4.918 | 2.339 | 1.3271 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23083154356', | ME185284 |  |  | 8.05 |  | RONILO GANGE JR.
2025-04-04 | 2025-02-18 |  | HMB | R23771915 | SALITA, HERMIE | ST. MARK, PARKDALE II SUBD, BACOOR | BACOOR CITY | DASMA | digging only |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 52.9761 | 145.91 | 0 | RELOC | 226387.26 | 58107.39 |  | 0% | 2025-02-13 14:03 | 2025-02-21 15:08 | 2025-02-17 |  |  |  | -45701.5854 | -45709.6306 | 0 | 2025-03-06 19:01 | 2025-03-16 05:56 | 2025-04-04 14:03 | -1415.9679 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-07 | CV6-8056 | 0 | -45701.5854 | 0 | -45701.5854 | -1415.9679 | 0 |  | 5.187 | 5.187 | 0 | 154.4146 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23771915', | ME185284 |  |  | 8.0451 |  | RONILO GANGE JR.
2025-02-21 | 2025-02-18 |  | HMB | X24020448821 | ROSE NONO LIN | COUNTRY CLUB, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 103.3295 | 75.05 | 240 | NEW | 606460.99 | 68634.49 | 29061.85 | 42.34% | 2025-02-14 10:11 | 2025-02-20 13:38 | 2025-02-17 |  | 2025-03-13 |  | 26.5757 | 20.4319 | -45729 | 2025-03-04 01:00 | 2025-03-12 12:57 | 2025-04-05 10:11 | 0.96674 | -762.15 | 23 | 30 | 20.6175 | 26.1155 | 17.6175 | 60 | 57 | 52 | 2025-05-12 | 166 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-03-28 | 14 | 2025-03-13 | 2025-04-11 | [8 empty] | Y | 2025-03-12 | [6 empty] | 2025-02-21 | CS9-8071,TLN-520526 | 0 | 26.5757 | 0 | 26.5757 | 0.96674 | 140 |  | 6.0595 | 6.0595 | 2.3333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24020448821', | ME166067 |  |  | 6.1438 |  | RONILO GANGE JR.
2025-02-21 | 2025-02-18 |  | HMB | R23915467 | CUEVAS JONATHAN SANTOS | M.L. QUEZON, PUROK 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 9.29 | 9.29 | 0 | RELOC | 27294.78 | 7481 |  | 0% | 2025-02-14 10:13 | 2025-02-21 15:14 | 2025-02-17 |  | 2025-08-09 09:16 |  | 175.9604 | 168.7514 | -45878.3861 | 2025-03-05 04:48 | 2025-03-14 00:09 | 2025-04-05 10:13 | 6.0609 | -764.6398 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-08 09:16 | 16.6139 | [8 empty] | NO COC |  | 2025-08-24 09:16 | #VALUE! | [18 empty] | N/A |  | 0 | 175.9604 | 0 | 175.9604 | 6.0609 | -9.3861 |  | 5.7376 | 5.7376 | -0.15644 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23915467', | ME185284 |  |  | 7.209 |  | RONILO GANGE JR.
2025-02-26 | 2025-02-18 |  | HMB | X25010310283 | MERFE A GAMAS | CHALLENGER, MOONWALK VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 3.53 | 11.15 | 7.5 | NEW | 30919.77 | 6562.97 |  | 0% | 2025-02-14 10:16 | 2025-02-21 15:13 | 2025-02-17 |  | 2025-04-30 |  | 74.5722 | 67.366 | -45777 | 2025-03-05 04:51 | 2025-03-14 00:12 | 2025-04-05 10:16 | 2.5686 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | FOR AUDIT |  | 2025-05-15 | 34 | 2025-04-29 | 2025-06-18 | [8 empty] | Y | 2025-04-30 | [6 empty] | N/A |  | 0 | 74.5722 | 0 | 74.5722 | 2.5686 | 92 |  | 5.7375 | 5.7375 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010310283', | ME155242 |  |  | 7.2063 |  | Isan Carlo Lazaro
2025-02-28 | 2025-02-27 |  | BIZ | X25010278743 | RIZALYN G TAYAG | NIOG III, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 154.5003 | 376.38 | 150 | NEW | 1179326.2 | 188897.18 |  | 0% | 2025-02-14 14:41 | 2025-02-24 07:09 | 2025-02-21 |  | 2025-06-11 |  | 116.3882 | 106.7021 | -45819 | 2025-03-07 03:23 | 2025-03-16 09:59 | 2025-04-05 14:41 | 3.7099 | -763.65 | 30 | 32 | 23.5294 | 29.8039 | 20.5294 | 60 | 57 | 52 | 2025-08-10 | 76 | [8 empty] | NO COC |  | 2025-06-26 | #VALUE! | [10 empty] | Y | 2025-06-09 | [6 empty] | 2025-02-28 | CV6-8058,CV6-8059,TLN-689612,TLN-527272 | 0 | 116.3882 | 0 | 116.3882 | 3.7099 | 50 |  | 5.3036 | 5.3036 | 0.83333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010278743', | ME155242 |  |  | 9.6861 |  | Isan Carlo Lazaro
2025-02-19 | 2025-02-18 |  | CBG | R21631426 | CAVITEX INFRASTRUCTURE CORP | NINOY AQUINO, LA HUERTA, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done energize pole retirement only |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 341.8208 | 492.4 | 0 | RELOC | 1183621.73 | 389602.36 |  | 0% | 2025-02-17 08:33 | 2025-02-17 09:47 | 2025-02-17 |  |  |  | -45705.3562 | -45705.4076 | 0 | 2025-03-12 09:08 | 2025-03-22 07:41 | 2025-04-08 08:33 | -1317.203 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-19 | CZ8-8105,CZ8-8106,CZ8-8107 | 0 | -45705.3562 | 0 | -45705.3562 | -1317.203 | 0 |  | 4.7161 | 4.7161 | 0 | 150.6438 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R21631426', | ME155242 |  |  | 0.051389 |  | Isan Carlo Lazaro
2025-02-24 | OK |  | CBG | X24041266844 | AYALA LAND, INC., | LANGKA, FTI CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 58.6368 | 74.97 | 17 | NEW | 347379.65 | 58230.82 |  | 0% | 2025-02-18 15:38 | 2025-02-24 07:06 | 2025-02-21 |  | 2025-03-26 |  | 35.3486 | 29.7042 | -45742 | 2025-03-10 17:41 | 2025-03-19 21:26 | 2025-04-09 15:38 | 1.1484 | -762.3667 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-05-25 | 153 | [8 empty] | FOR AUDIT |  | 2025-04-10 | 50 | 2025-03-26 | 2025-05-30 | [8 empty] | Y | 2025-03-24 | [6 empty] | 2025-02-24 | B8-1850,TLN-185837 | 0 | 35.3486 | 0 | 35.3486 | 1.1484 | 127 |  | 5.2744 | 5.2744 | 2.1167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041266844', | ME185284 |  |  | 5.6444 |  | Jenneth Madrid
2025-02-24 |  |  | BIZ | X25010209691 | ALMALOUNA COMALING QU | EL GRANDE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Isan Carlo Lazaro | 47.14 | 47.14 | 55 | NEW | 293761.53 | 45194.86 |  | 0% | 2025-02-18 15:38 | 2025-02-24 10:35 | 2025-02-21 |  | 2025-06-02 |  | 103.3486 | 97.559 | -45810 | 2025-03-08 17:25 | 2025-03-17 08:18 | 2025-04-09 15:38 | 3.678 | -763.5 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-08-01 | 85 | [8 empty] | NO COC |  | 2025-06-17 | #VALUE! | [18 empty] | 2025-02-24 | N/A | 0 | 103.3486 | 0 | 103.3486 | 3.678 | 59 |  | 5.7777 | 5.7777 | 0.98333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010209691', | ME166067 |  |  | 5.7896 |  | Jenneth Madrid
2025-02-24 |  |  | HMB | X25020386591 | SHEENA LORRAINE CHUA LAO | IPIL-IPIL, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For survey |  | MAINTENANCE | FCOMP | Isan Carlo Lazaro | 29.91 | 29.91 | 104 | NEW | 77784.02 | 34288.88 |  | 0% | 2025-02-18 15:57 | 2025-02-24 09:22 | 2025-02-21 |  | 2025-03-28 |  | 37.3354 | 31.6097 | -45744 | 2025-03-08 00:05 | 2025-03-16 10:15 | 2025-04-09 15:57 | 1.3767 | -762.4 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-05-27 | 151 | [8 empty] | FOR AUDIT |  | 2025-04-12 | #VALUE! | [18 empty] | 2025-02-24 | N/A | 0 | 37.3354 | 0 | 37.3354 | 1.3767 | 125 |  | 5.9861 | 5.9861 | 2.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020386591', | ME166067 |  |  | 5.7257 |  | Jenneth Madrid
2025-02-24 | 2025-02-26 |  | CBG | X25010271342 | ALVEO LAND CORP., | ALABANG-ZAPOTE, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 31.3685 | 152.97 | - | NEW | 269622.12 | 36004.72 |  | 0% | 2025-02-18 15:59 | 2025-02-24 10:40 | 2025-02-21 |  |  |  | -45706.666 | -45712.4444 | 0 | 2025-03-03 18:46 | 2025-03-11 01:54 | 2025-04-09 15:59 | -2127.1179 | 0 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-02-24 | CU9-8094 | 0 | -45706.666 | 0 | -45706.666 | -2127.1179 | 0 |  | 7.5548 | 7.5548 | 0 | 149.334 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010271342', | ME155242 |  |  | 5.7785 |  | Jenneth Madrid
2025-02-27 | 2025-02-27 |  | HMB | X24093781077 | ARNULFO CAL TABLIZO | 1ST, BAGUMBAYAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 50.6785 | 213.43 | 9 | NEW | 407209.07 | 50064.5 |  | 0% | 2025-02-18 16:07 | 2025-02-24 10:38 | 2025-02-21 | 2025-03-28 | 2025-03-28 |  | 37.3285 | 31.5569 | -45744 | 2025-03-12 12:58 | 2025-03-22 04:07 | 2025-04-09 16:07 | 1.1258 | -762.4 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-05-27 | 151 | [8 empty] | FOR AUDIT |  | 2025-04-12 | 117 | 2025-03-28 | 2025-08-07 | [16 empty] | 2025-02-27 | DY2-8104,DY2-8105,TLN-523960 | 0 | 37.3285 | 0 | 37.3285 | 1.1258 | 125 |  | 4.8956 | 4.8956 | 2.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093781077', | ME185284 |  |  | 5.7715 |  | Jenneth Madrid
2025-02-24 |  | Y | BIZ | X24093492216 | ALFAMART TRADING PHILIPPINES, INC. | SUMMIT CIRCLE SUBD, SUMMIT CIRCLE SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 9.9328 | 13.04 | 28 | NEW | 186146.6 | 11202.05 |  | 0% | 2025-02-18 16:09 | 2025-02-24 09:23 | 2025-02-21 | 2025-03-04 04:21 | 2025-03-04 |  | 13.3271 | 7.609 | -45720 | 2025-03-09 10:44 | 2025-03-18 06:05 | 2025-04-09 16:09 | 0.45904 | -762 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-03 | 175 | [8 empty] | FOR AUDIT |  | 2025-03-19 | -2 | 2025-03-04 | 2025-03-17 | [8 empty] | Y | 2025-03-03 | [6 empty] | 2025-02-24 | TLN-523641 | 0 | 13.3271 | 0 | 13.3271 | 0.45904 | 149 |  | 5.5913 | 5.5913 | 2.4833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093492216', | ME166067 |  |  | 5.7181 |  | RONILO GANGE JR.
2025-02-24 | 2025-02-27 | Y | HMB | X24010064473 | ALEXANDER SANTOS ISIP | LANCASTER, HILLSBOROUGH SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 38.0585 | 48.2 | 110 | MODIFICATION | 391390.73 | 41443.2 |  | 0% | 2025-02-18 16:27 | 2025-02-24 07:05 | 2025-02-21 |  | 2025-03-25 08:10 |  | 34.6549 | 29.0451 | -45741.3403 | 2025-03-08 00:35 | 2025-03-16 10:45 | 2025-04-09 16:27 | 1.2779 | -762.3557 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-05-24 08:10 | 153.6597 | [8 empty] | FOR AUDIT |  | 2025-04-09 08:10 | 4.6597 | 2025-03-25 | 2025-04-14 | [16 empty] | 2025-02-24 | DWI-8024,TLN-520040 | 0 | 34.6549 | 0 | 34.6549 | 1.2779 | 127.6597 |  | 5.9854 | 5.9854 | 2.1277 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010064473', | ME166067 |  |  | 5.6097 |  | RONILO GANGE JR.
2025-02-28 | 2025-02-27 | Y | HMB | X25010176215 | MARY GRACE MESINA MANDAP | BASILIO ESTANISLAO, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 119.7629 | 308.41 | 33 | NEW | 601808.84 | 130472.59 |  | 0% | 2025-02-18 17:43 | 2025-02-24 10:39 | 2025-02-21 |  | 2025-07-26 |  | 157.2618 | 151.5563 | -45864 | 2025-03-13 05:02 | 2025-03-23 00:03 | 2025-04-09 17:43 | 4.6305 | -764.4 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-09-24 | 31 | [8 empty] | NO COC |  | 2025-08-10 | #VALUE! | [18 empty] | 2025-02-28 | CV7-8161,CV7-8162,ALB1-3032,TLN-527110 | 0 | 157.2618 | 0 | 157.2618 | 4.6305 | 5 |  | 4.7777 | 4.7777 | 0.083333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010176215', | ME155242 |  |  | 5.7056 |  | Jenneth Madrid
2025-03-05 | 2025-02-27 | Y | CBG | R23926303 | CAVITEX INFRASTRUCTURE CORP., CBG | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 365.078 | 633.77 | 0 | RELOC | 1683427.63 | 498912.29 |  | 0% | 2025-02-19 08:19 | 2025-02-25 12:43 | 2025-02-21 |  | 2025-03-20 |  | 28.6535 | 22.4701 | -45736 | 2025-03-16 04:21 | 2025-03-26 14:30 | 2025-04-10 08:19 | 0.77205 | -762.2667 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-05-19 | 159 | [8 empty] | NO COC |  | 2025-04-04 | #VALUE! | [18 empty] | 2025-03-05 | A5-8062,A5-8063,A5-5570,A5-5569,A5-8064,A5-5568,A5-8066,A5-5571,A5-8067 | 0 | 28.6535 | 0 | 28.6535 | 0.77205 | 133 |  | 4.3557 | 4.3557 | 2.2167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23926303', | ME155242 |  |  | 6.1833 |  | RONILO GANGE JR.
2025-03-05 | 2025-02-27 | Y | CBG | R23926307 | CAVITEX INFRASTRUCTURE CORP., CBG | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 79.5357 | 202.88 | 0 | RELOC | 216676.78 | 173073.31 |  | 0% | 2025-02-19 08:25 | 2025-02-25 12:44 | 2025-02-21 |  | 2025-04-04 |  | 43.6493 | 37.4694 | -45751 | 2025-03-13 05:16 | 2025-03-22 20:25 | 2025-04-10 08:25 | 1.3164 | -762.5167 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-06-03 | 144 | [8 empty] | NO COC |  | 2025-04-19 | #VALUE! | [18 empty] | N/A |  | 0 | 43.6493 | 0 | 43.6493 | 1.3164 | 118 |  | 4.8751 | 4.8751 | 1.9667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23926307', | ME155242 |  |  | 6.1799 |  | RONILO GANGE JR.
2025-03-05 | 2025-02-27 |  | CBG | R23924589 | CAVITEX INFRASTRUCTURE CORP., CBG | ALLEY 1, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 307.8817 | 418.77 | 0 | RELOC | 1430545.13 | 359825.97 |  | 0% | 2025-02-19 08:34 | 2025-02-25 12:38 | 2025-02-21 | 2025-04-14 | 2025-05-08 |  | 77.6431 | 71.4736 | -45785 | 2025-03-14 09:09 | 2025-03-24 07:42 | 2025-04-10 08:34 | 2.2376 | -763.0833 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 2025-07-07 | 110 | [8 empty] | FOR AUDIT |  | 2025-05-23 | 50 | 2025-04-14 | 2025-07-12 | [16 empty] | 2025-03-05 | A5-8068,A5-8069,A5-8070,A5-8071,A5-8072,A5-8073,A5-8074,TLN-527297 | 0 | 77.6431 | 0 | 77.6431 | 2.2376 | 84 |  | 4.6585 | 4.6585 | 1.4 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23924589', | ME166067 |  |  | 6.1694 |  | RONILO GANGE JR.
2025-02-26 | 2025-02-27 |  | BIZ | X25010070942 | ERNELIA O. SANCHEZ | BLOCK 26, PINAGSAMA PH 2 VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 2.58 | 5.73 | 16 | NEW | 25829.16 | 5954.42 |  | 0% | 2025-02-19 15:46 | 2025-02-25 12:40 | 2025-02-21 |  | 2025-03-08 |  | 16.3431 | 10.4722 | -45724 | 2025-03-10 10:21 | 2025-03-19 05:42 | 2025-04-10 15:46 | 0.56293 | -762.0667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-07 | 171 | [8 empty] | FOR AUDIT |  | 2025-03-23 | -4 | 2025-03-08 | 2025-03-19 | [8 empty] | Y | 2025-03-14 | [6 empty] | N/A |  | 0 | 16.3431 | 0 | 16.3431 | 0.56293 | 145 |  | 5.5574 | 5.5574 | 2.4167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010070942', | ME185284 |  |  | 5.8708 |  | RONILO GANGE JR.
2025-03-03 | 2025-02-27 |  | HMB | X24114520845 | ERIC GERARD TURLA OLIVA | WALING-WALING, TAHANAN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Done Nnergize |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 37.0495 | 121.89 | 36 | NEW | 291805.32 | 37465.15 |  | 0% | 2025-02-19 15:53 | 2025-02-25 12:46 | 2025-02-21 |  | 2025-08-19 07:38 |  | 180.6562 | 174.7861 | -45888.3181 | 2025-03-12 20:51 | 2025-03-22 07:46 | 2025-04-10 15:53 | 5.5973 | -764.8053 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-10-18 07:38 | 6.6819 | [8 empty] | NO COC |  | 2025-09-03 07:38 | #VALUE! | [18 empty] | 2025-03-04 | DWI-8050,TLN-526676,DWI-2066 | 0 | 180.6562 | 0 | 180.6562 | 5.5973 | -19.3181 |  | 4.9987 | 4.9987 | -0.32197 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114520845', | ME185284 |  |  | 5.8701 |  | RONILO GANGE JR.
2025-02-28 | 2025-02-26 |  | HMB | R23922888 | ANG CARMEN GAN, HMB | MARCUS AURELIUS, ITALIA 500-BF HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Isan Carlo Lazaro | 1.0195 | 1.14 | 0 | RELOC | 12476.61 | 980.15 |  | 0% | 2025-02-19 17:06 | 2025-02-25 12:47 | 2025-02-21 |  | 2025-06-23 |  | 123.2875 | 117.4674 | -45831 | 2025-03-10 11:41 | 2025-03-19 07:02 | 2025-04-10 17:06 | 4.2466 | -763.85 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-22 | 64 | [8 empty] | NO COC |  | 2025-07-08 | #VALUE! | [18 empty] | N/A |  | 0 | 123.2875 | 0 | 123.2875 | 4.2466 | 38 |  | 5.5555 | 5.5555 | 0.63333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23922888', | ME155242 |  |  | 5.8201 |  | Jenneth Madrid
|  |  | BIZ | X25010099398 | REYNALDO BAUTISTA SALVADOR | J.P. RIZAL, TUAZON SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 17.38 | 17.38 | 30 | NEW | 252346.4 | 27843.34 |  | 0% | 2025-02-20 12:17 | 2025-02-27 12:28 | 2025-02-21 |  | 2025-03-06 | 2025-05-18 14:29 | 13.4882 | 6.4806 | 73.6035 | 2025-03-11 06:52 | 2025-03-20 02:13 | 2025-04-11 12:17 | 0.46459 | 1.2267 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-05 | 173 | [8 empty] | FOR AUDIT |  | 2025-03-21 | #VALUE! | [18 empty] | 2025-03-04 | TLN-526967 | 0 | 13.4882 | 0 | 13.4882 | 0.46459 | 147 |  | 5.5279 | 5.5279 | 2.45 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010099398', | ME194579 |  |  | 7.0076 |  | IJP
2025-02-27 | 2025-02-27 |  | BIZ | X24104277254 | JOHN PAULO H. ALBIS | BLOCK 9, ENLISTED PERSONNEL VIL 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 52.1926 | 151.04 | 46 | NEW | 442979.07 | 62518.65 |  | 0% | 2025-02-20 15:33 | 2025-02-27 12:09 | 2025-02-21 |  | 2025-03-31 |  | 38.3521 | 31.4938 | -45747 | 2025-03-13 20:31 | 2025-03-23 07:26 | 2025-04-11 15:33 | 1.1883 | -762.45 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-05-30 | 148 | [8 empty] | FOR AUDIT |  | 2025-04-15 | #VALUE! | [10 empty] | Y | 2025-04-11 | [6 empty] | 2025-02-27 | B8-8177,TLN-526380 | 0 | 38.3521 | 0 | 38.3521 | 1.1883 | 122 |  | 4.9682 | 4.9682 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104277254', | ME185284 |  |  | 6.8583 |  | Isan Carlo Lazaro
2025-03-03 | 2025-02-26 |  | BIZ | X24114622519 | OLIVAREZ REALTY CORPORATION | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 79.929 | 330.03 | 97 | NEW | 1165982.58 | 149046.37 | 40857.8 | 27.41% | 2025-02-20 15:33 | 2025-02-27 12:16 | 2025-02-21 | 2025-06-28 | 2025-06-28 |  | 127.3521 | 120.4889 | -45836 | 2025-03-14 04:01 | 2025-03-23 16:56 | 2025-04-11 15:33 | 3.8955 | -763.9333 | 30 | 34 | 24.5192 | 31.0577 | 21.5192 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | FOR AUDIT |  | 2025-07-13 | 15 | 2025-06-28 | 2025-07-28 | [16 empty] | 2025-03-04 | CZ8-8103,CZ8-8104,TLN-526713 | 0 | 127.3521 | 0 | 127.3521 | 3.8955 | 33 |  | 4.9049 | 4.9049 | 0.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114622519', | ME155242 |  |  | 6.8632 |  | Isan Carlo Lazaro
2025-03-03 | 2025-02-27 |  | HMB | R23652915 | GATDULA, RICARDO, HMB | ST. MARY, ADDAS VILLAGE PH II-A, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 31.5 | 185.26 | 0 | RELOC | 224608.3 | 27065.63 |  | 0% | 2025-02-20 15:34 | 2025-02-27 12:14 | 2025-02-21 |  |  |  | -45708.6486 | -45715.5097 | 0 | 2025-03-13 20:32 | 2025-03-23 07:27 | 2025-04-11 15:34 | -1416.1868 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-04 | CT6-8056,CT6-8057 | 0 | -45708.6486 | 0 | -45708.6486 | -1416.1868 | 0 |  | 4.9682 | 4.9682 | 0 | 147.3514 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23652915', | ME155242 |  |  | 6.8611 |  | Isan Carlo Lazaro
2025-03-04 | 2025-02-27 |  | HMB | X25020524328 | CITY GOVT OF LAS PIÑAS, | BF RESORT, TALON II, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 11.7328 | 14.76 | 29 | MODIFICATION | 188123.61 | 12279.67 |  | 0% | 2025-02-20 15:36 | 2025-02-27 12:14 | 2025-02-21 |  | 2025-03-17 09:41 |  | 24.7535 | 17.8937 | -45733.4035 | 2025-03-11 10:11 | 2025-03-20 05:32 | 2025-04-11 15:36 | 0.85262 | -762.2234 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-16 09:41 | 161.5965 | [8 empty] | FOR AUDIT |  | 2025-04-01 09:41 | 26.5965 | 2025-03-17 | 2025-04-28 | [8 empty] | Y | 2025-03-17 | [6 empty] | 2025-03-04 | CW7-0130,TLN-523280 | 0 | 24.7535 | 0 | 24.7535 | 0.85262 | 135.5965 |  | 5.5232 | 5.5232 | 2.2599 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020524328', | ME166067 |  |  | 6.8597 |  | RONILO GANGE JR.
2025-02-27 | 2025-02-27 |  | HMB | X25010223485 | CITY GOVERNMENT OF TAGUIG | MIRANDA, ZONE 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Transfer to VJC |  | VJC | FCOMP | Jenneth Madrid | 72.6693 | 246.89 | 66 | NEW | 546721.35 | 78010.61 |  | 0% | 2025-02-21 12:15 | 2025-02-27 12:07 | 2025-02-21 | 2025-05-10 | 2025-06-18 |  | 116.4896 | 110.4951 | -45826 | 2025-03-14 11:17 | 2025-03-23 20:38 | 2025-04-12 12:15 | 3.6464 | -763.7667 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 2025-08-17 | 69 | [8 empty] | FOR AUDIT |  | 2025-07-03 | 15 | 2025-05-10 | 2025-07-18 | [8 empty] | Y | 2025-06-16 | [6 empty] | 2025-02-27 | B8-8184,B8-8185,TLN-527195 | 0 | 116.4896 | 0 | 116.4896 | 3.6464 | 43 |  | 4.9924 | 4.9924 | 0.71667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010223485', | ME166067 |  |  | 5.9944 |  | Jenneth Madrid
2025-03-04 | 2025-02-28 |  | HMB | X24124701777 | NELLY YAP RAÑOLA | JUAN ALEGRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Done Nnergize |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 79.9595 | 258.96 | 38 | NEW | 504136.5 | 87176.68 |  | 0% | 2025-02-21 15:51 | 2025-03-03 12:56 | 2025-02-28 |  |  |  | -45709.6604 | -45719.5389 | 0 | 2025-03-15 12:42 | 2025-03-25 03:51 | 2025-04-12 15:51 | -1378.5453 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-04 | CW9-8064,CW9-8065,TLN-526779 | 0 | -45709.6604 | 0 | -45709.6604 | -1378.5453 | 0 |  | 4.8055 | 4.8055 | 0 | 146.3396 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124701777', | ME185284 |  |  | 9.8785 |  | Jenneth Madrid
2025-03-10 | 2025-02-28 |  | BIZ | X25010133238 | CITY GOVERNMENT OF TAGUIG | M.L. QUEZON, PUROK 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 88.9013 | 209.76 | 239 | NEW | 1044923.65 | 130705.4 |  | 0% | 2025-02-24 12:07 | 2025-03-06 13:23 | 2025-02-28 | 2025-03-28 | 2025-03-28 |  | 31.4951 | 21.4424 | -45744 | 2025-03-15 12:47 | 2025-03-24 09:46 | 2025-04-15 12:07 | 1.0723 | -762.4 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 60 | 57 | 52 | 2025-05-27 | 151 | With scheduled PAI | Y | Y |  |  | 2025-03-21 | 6 | 2025-03-27 | FOR AUDIT |  | 2025-04-12 | 117 | 2025-03-28 | 2025-08-07 | [8 empty] | Y | 2025-03-24 | [6 empty] | 2025-03-11 | B8-8183,B8-8186,TLN-527120 | 0 | 31.4951 | 6 | 25.4951 | 0.86805 | 125 | 1.0723 | 5.3283 | 4.256 | 2.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010133238', | ME185284 |  |  | 10.0528 |  | Jenneth Madrid
2025-03-10 | 2025-05-28 |  | CBG | X25010359335 | JOLLIBEE FOODS CORPORATION | AGUIRRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 20.14 | 79.3 | - | TERMINATION | 61797.09 | 68145.2 |  | 0% | 2025-02-24 14:31 | 2025-03-06 13:28 | 2025-03-11 |  |  |  | -45712.6049 | -45722.5611 | 0 | 2025-03-09 05:11 | 2025-03-16 09:05 | 2025-04-15 14:31 | -2196.1925 | 0 | 23 | 20 | 15.6109 | 19.7738 | 12.6109 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45712.6049 | 0 | -45712.6049 | -2196.1925 | 0 |  | 7.5138 | 7.5138 | 0 | 143.3951 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010359335', | ME155242 |  |  | 9.9563 |  | Jenneth Madrid
2025-03-03 | 2025-02-28 |  | BIZ | X25020539755 | LIONS PARK RESIDENCES CONDOMINIUM CORPORATION ASSO | ALPACA, LION'S PARK RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 11.9433 | 14.57 | 22 | NEW | 243992.07 | 12521.73 |  | 0% | 2025-02-24 16:39 | 2025-03-06 13:27 | 2025-02-28 |  | 2025-03-31 |  | 34.3063 | 24.4396 | -45747 | 2025-03-15 11:14 | 2025-03-24 06:35 | 2025-04-15 16:39 | 1.1817 | -762.45 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-30 | 148 | Conjunct work order not released / completed | Y | Y |  |  | 2025-03-10 | 21 | 2025-03-31 | NO COC |  | 2025-04-15 | #VALUE! | [10 empty] | Y | 2025-03-31 | [6 empty] | 2025-03-04 | TLN-521157 | 0 | 34.3063 | 21 | 13.3063 | 0.45833 | 122 | 1.1817 | 5.3839 | 4.2022 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020539755', | ME185284 |  |  | 9.8667 |  | Jenneth Madrid
2025-04-03 |  | Y | BIZ | X25010136657 | COFFEE MASTERS, INC. | MOLINO BLVD, MOLINO III, BACOOR | BACOOR CITY | DASMA |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.6428 | 48.36 | 142 | NEW | 472661.66 | 41560.12 |  | 0% | 2025-02-24 16:50 | 2025-03-01 04:21 | 2025-02-28 | 2025-03-04 04:21 | 2025-03-04 |  | 7.2986 | 2.8187 | -45720 | 2025-03-14 00:58 | 2025-03-22 11:08 | 2025-04-15 16:50 | 0.26914 | -762 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-05-03 | 175 | [8 empty] | MATERIAL BALANCING |  | 2025-03-19 | 8 | 2025-03-04 | 2025-03-27 | [8 empty] | Y | 2025-03-03 | [6 empty] | 2025-04-07 | CT6-5089,TLN-527036 | 0 | 7.2986 | 0 | 7.2986 | 0.26914 | 149 |  | 5.7635 | 5.7635 | 2.4833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010136657', | ME166067 |  |  | 4.4799 |  | Jenneth Madrid
N/A | N/A |  | BIZ | X24030853956 | MARIFE GARCIA PARCON | QUIRINO, ZAPOTE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | C2 | SCHED | Ian Patrick Perez | 76.36 | 76.36 | 237 | NEW | 674882.29 | 66120.04 |  | 0% | 2025-02-25 08:36 | 2025-03-06 15:26 | 2025-02-28 |  |  |  | -45713.3583 | -45722.6431 | 0 | 2025-03-14 23:25 | 2025-03-23 11:22 | 2025-04-16 08:36 | -1662.9062 | 0 | 23 | 30 | 20.6175 | 26.1155 | 17.6175 | 60 | 57 | 52 | 1900-02-28 | 45895 | With pole / drainage / digging / manhole / pole attachment issue | Y |  |  |  | 2025-04-25 |  |  |  |  | 1900-01-14 | 0 | [20 empty] | 0 | -45713.3583 | 0 | -45713.3583 | -1662.9062 | 0 | 5.6617 | 5.6617 | 0 | 0 | 142.6417 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030853956', | ME194579 |  |  | 9.2847 |  | RONILO GANGE JR.
2025-03-17 | OK |  | CBG | R23094079 | DEPARTMENT OF TRANSPORTATION,, CBG | EAST SERVICE, BICUTAN INTERCHANGE, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 19.4167 | 19.42 | 0 | RELOC | 43757.1 | 16683.33 |  | 0% | 2025-02-25 09:50 | 2025-03-06 15:03 | 2025-03-11 |  | 2025-06-11 |  | 105.5903 | 96.3729 | -45819 | 2025-03-16 04:25 | 2025-03-24 23:46 | 2025-04-16 09:50 | 3.637 | -763.65 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-10 | 76 | [8 empty] | NO COC |  | 2025-06-26 | #VALUE! | [18 empty] | N/A |  | 0 | 105.5903 | 0 | 105.5903 | 3.637 | 50 |  | 5.3592 | 5.3592 | 0.83333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23094079', | ME185284 |  |  | 9.2174 |  | RONILO GANGE JR.
2025-03-10 | 2025-02-28 |  | HMB | X24072566400 | JOHN TULAO CENICA | CORDILLERA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.2828 | 20.34 | 80 | NEW | 233355.21 | 17502.76 |  | 0% | 2025-02-25 14:53 | 2025-03-06 15:22 | 2025-02-28 |  | 2025-03-14 |  | 16.3799 | 7.3597 | -45730 | 2025-03-15 16:40 | 2025-03-24 07:33 | 2025-04-16 14:53 | 0.58293 | -762.1667 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-05-13 | 165 | [8 empty] | FOR AUDIT |  | 2025-03-29 | 18 | 2025-03-13 | 2025-04-16 | [8 empty] | Y | 2025-03-12 | [6 empty] | 2025-03-11 | TLN-522684 | 0 | 16.3799 | 0 | 16.3799 | 0.58293 | 139 |  | 5.5297 | 5.5297 | 2.3167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072566400', | ME166067 |  |  | 9.0201 |  | RONILO GANGE JR.
2025-04-15 | 2025-02-28 |  | BIZ | X24083333203 | ACHIEVERS BUSINESS GROUP INC. | C-5 , KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 5.92 | 25.56 | 139 | NEW | 61294.92 | 21987.52 |  | 0% | 2025-02-25 16:02 | 2025-03-06 14:56 | 2025-02-28 |  | 2025-03-08 |  | 10.3319 | 1.3778 | -45724 | 2025-03-15 00:10 | 2025-03-23 10:20 | 2025-04-16 16:02 | 0.38099 | -762.0667 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-05-07 | 171 | [8 empty] | NO COC |  | 2025-03-23 | #VALUE! | [10 empty] | Y | 2025-06-27 | [6 empty] | N/A |  | 0 | 10.3319 | 0 | 10.3319 | 0.38099 | 145 |  | 5.7279 | 5.7279 | 2.4167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083333203', | ME185284 |  |  | 8.9542 |  | RONILO GANGE JR.
2025-03-10 | 2025-02-28 |  | HMB | X24072802567 | GREGORIO JR. MANALO GONZALVO | CADENA DE AMOR, TAHANAN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 88.1362 | 126.79 | 42 | MODIFICATION | 373208.99 | 91119.3 |  | 0% | 2025-02-25 16:46 | 2025-03-06 15:07 | 2025-02-28 |  | 2025-06-23 |  | 117.3014 | 108.3701 | -45831 | 2025-03-18 21:44 | 2025-03-28 08:39 | 2025-04-16 16:46 | 3.6343 | -763.85 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-08-22 | 64 | [8 empty] | NO COC |  | 2025-07-08 | #VALUE! | [10 empty] | Y | 2025-06-20 | [6 empty] | 2025-03-11 | DW1-8034,TLN-520322 | 0 | 117.3014 | 0 | 117.3014 | 3.6343 | 38 |  | 4.8117 | 4.8117 | 0.63333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072802567', | ME155242 |  |  | 8.9313 |  | RONILO GANGE JR.
2025-03-10 | 2025-02-28 |  | BIZ | X25010209684 | UNIOIL PETROLEUM PHILIPPINES, INC. | EAST SERVICE, SN MARTIN DE PORRES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | TECO | Isan Carlo Lazaro | 10.3328 | 13.92 | 16 | NEW | 143724.53 | 10792.18 | 8332.46 | 77.21% | 2025-02-25 16:48 | 2025-03-06 15:24 | 2025-02-28 |  | 2025-03-14 | 2025-07-10 | 16.3 | 7.3583 | 118 | 2025-03-16 11:23 | 2025-03-25 06:44 | 2025-04-16 16:48 | 0.56144 | 1.9667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-13 | 165 | [8 empty] | PAID |  | 2025-03-29 | 12 | 2025-03-14 | 2025-04-10 | 2025-05-21 | ECI | N |  |  |  | 2025-06-20 | NVP | Y | 2025-03-13 | [6 empty] | 2025-03-11 | TLN-527412 | 0 | 16.3 | 0 | 16.3 | 0.56144 | 139 |  | 5.3492 | 5.3492 | 2.3167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010209684', | ME166067 |  |  | 8.9417 |  | RONILO GANGE JR.
2025-03-11 | 2025-02-28 | Y | HMB | X25010341636 | TERESITA G MANAHAN | BOEING, CONCORDE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | sadang:Pag uusapan padaw sa clubhouse mam Jen, puro usap na Sila haha! Extension of facilities na to sa Dami ng hukay ,Good am Po, hndi pa Po nahuhukay yong gustong location ni customer, approval pa Po sa HOA…Hndi pa boss, hndi ko pa Po alam kung nag ka sundo na sa club house pra sa final relocation ng transformer pole.. pahuhukayan ko sana |  | ECOM | FCOMP | Ronilo Gange Jr. | 51.0195 | 75.67 | 80 | NEW | 439221.4 | 65045.18 |  | 0% | 2025-02-25 17:05 | 2025-03-11 08:05 | 2025-02-28 |  | 2025-04-24 |  | 57.2882 | 43.6632 | -45771 | 2025-03-17 00:18 | 2025-03-25 23:01 | 2025-04-16 17:05 | 1.9267 | -762.85 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-06-23 | 124 | [8 empty] | MATERIAL BALANCING |  | 2025-05-09 | 11 | 2025-04-23 | 2025-05-20 | [8 empty] | Y | 2025-04-23 | [6 empty] | 2025-03-14 | TLN-527257 | 0 | 57.2882 | 0 | 57.2882 | 1.9267 | 98 |  | 5.2226 | 5.2226 | 1.6333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010341636', | ME155242 |  |  | 13.625 |  | Isan Carlo Lazaro
2025-03-10 | 2025-02-28 |  | HMB | X24041166209 | RENAISSANCE VILLAGE HOMEOWNERS ASSOCIATION INC. | BLOCK 3, RENAISSANCE VILLAGE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 352.5931 | 592.45 | 135 | NEW | 1859854.9 | 416660.75 |  | 0% | 2025-02-26 12:47 | 2025-03-06 16:30 | 2025-02-28 | 2025-05-08 | 2025-05-08 14:22 |  | 71.066 | 62.9111 | -45785.5986 | 2025-03-21 01:33 | 2025-03-30 20:57 | 2025-04-17 12:47 | 2.0876 | -763.0933 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 2025-07-07 14:22 | 109.4014 | [8 empty] | FOR AUDIT |  | 2025-05-23 14:22 | 44.4014 | 2025-05-08 | 2025-07-07 | [8 empty] | Y | 2025-06-20 | [6 empty] | 2025-03-12 | CY7-8078,CY7-8079,CY7-8080,CY7-8081,CY7-8082,CY7-8083,CY7-8084,TLN-521439 | 0 | 71.066 | 0 | 71.066 | 2.0876 | 83.4014 |  | 4.5375 | 4.5375 | 1.39 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041166209', | ME166067 |  |  | 8.1549 |  | Isan Carlo Lazaro
2025-03-10 |  |  | BIZ | X24072764755 | OSAVE TRADING PHILIPPINES CORPORATION | GEN. EVANGELISTA, POBLACION, BACOOR | BACOOR CITY | DASMA | For survey |  | MAINTENANCE | CLOSE | Reyzon Matienzo | 13.95 | 15.58 | 18 | NEW | 143807.71 | 26763.63 |  | 0% | 2025-02-26 12:51 | 2025-03-10 14:16 | 2025-02-28 |  | 2025-05-06 | 2025-05-07 | 68.4646 | 56.4056 | 1 | 2025-03-17 07:26 | 2025-03-26 02:47 | 2025-04-17 12:51 | 2.3582 | 0.016667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-05 | 112 | [8 empty] | PAID |  | 2025-05-21 | #VALUE! |  |  | 2025-05-05 | RPR |  |  | 2025-05-14 | [11 empty] | 2025-03-14 | DSM1-3840,TLN-522951 | 0 | 68.4646 | 0 | 68.4646 | 2.3582 | 86 |  | 5.3204 | 5.3204 | 1.4333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072764755', | ME189046 |  |  | 12.059 |  | Isan Carlo Lazaro
2025-03-10 | 2025-02-28 |  | CBG | X22093878578 | FIRSTAR HVAC INC. | NIGERIA, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 53.726 | 83.13 | 22 | NEW | 332579.9 | 53997.88 |  | 0% | 2025-02-26 13:24 | 2025-03-06 16:14 | 2025-02-28 |  |  |  | -45714.5583 | -45722.6764 | 0 | 2025-03-18 15:27 | 2025-03-27 19:12 | 2025-04-17 13:24 | -1485.171 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-11 | DZ1-0498,TLN-514223 | 0 | -45714.5583 | 0 | -45714.5583 | -1485.171 | 0 |  | 5.0175 | 5.0175 | 0 | 141.4417 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X22093878578', | ME155242 |  |  | 8.1181 |  | Isan Carlo Lazaro
2025-03-10 | 2025-02-28 |  | HMB | X24114668949 | GIDEON KURT FABABIER GODOY | GUIJO, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 69.2095 | 83.71 | 80 | NEW | 558159.82 | 71925.46 |  | 0% | 2025-02-26 13:44 | 2025-03-06 16:15 | 2025-02-28 |  | 2025-03-26 |  | 27.4278 | 19.3229 | -45742 | 2025-03-17 20:57 | 2025-03-26 19:40 | 2025-04-17 13:44 | 0.92244 | -762.3667 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-25 | 153 | [8 empty] | NO COC |  | 2025-04-10 | #VALUE! | [18 empty] | 2025-03-12 | CY9-8068,CY9-8069,TLN-52736 | 0 | 27.4278 | 0 | 27.4278 | 0.92244 | 127 |  | 5.1937 | 5.1937 | 2.1167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114668949', | ME185284 |  |  | 8.1049 |  | Isan Carlo Lazaro
2025-04-04 | 2025-02-28 |  | HMB | X25010310664 | NEBUCHADNEZZAR C RABAYA | MARINER, MOONWALK VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | For schedule of pole erection |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 47.4962 | 51 | 22.5 | NEW | 290132.07 | 43421.75 |  | 0% | 2025-02-26 19:17 | 2025-03-06 16:28 | 2025-02-28 |  | 2025-04-21 |  | 53.1965 | 45.3139 | -45768 | 2025-03-18 21:20 | 2025-03-28 01:05 | 2025-04-17 19:17 | 1.7282 | -762.8 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-06-20 | 127 | [8 empty] | FOR AUDIT |  | 2025-05-06 | -6 | 2025-04-21 | 2025-04-30 | [16 empty] | 2025-04-07 | CU8-8140,TLN-527331 | 0 | 53.1965 | 0 | 53.1965 | 1.7282 | 101 |  | 5.0095 | 5.0095 | 1.6833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010310664', | ME166067 |  |  | 7.8826 |  | Isan Carlo Lazaro
2025-03-10 | 2025-02-28 |  | HMB | X24103967818 | ELPIDIO THOMAS SANTIAGO ACERO III | WASHINGTON, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 50.9802 | 136.92 | 82 | NEW | 398405.14 | 50006.08 |  | 0% | 2025-02-27 07:31 | 2025-03-06 16:32 | 2025-02-28 |  | 2025-03-31 |  | 31.6868 | 24.3111 | -45747 | 2025-03-19 15:48 | 2025-03-28 21:12 | 2025-04-18 07:31 | 1.018 | -762.45 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-05-30 | 148 | [8 empty] | FOR AUDIT |  | 2025-04-15 | -15 | 2025-06-03 | 2025-03-31 | [8 empty] | Y | 2025-03-31 | [6 empty] | 2025-03-14 | A6-8051,TLN-526120 | 0 | 31.6868 | 0 | 31.6868 | 1.018 | 122 |  | 4.9374 | 4.9374 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103967818', | ME155242 |  |  | 7.3757 |  | IJP
2025-03-10 | 2025-02-28 |  | HMB | X24093657207 | SONNY HABOC BURIAS | WASHINGTON, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 48.3026 | 62.72 | 80 | NEW | 415129.66 | 53886.46 |  | 0% | 2025-02-27 07:33 | 2025-03-06 16:34 | 2025-02-28 |  | 2025-04-02 |  | 33.6854 | 26.3097 | -45749 | 2025-03-18 14:46 | 2025-03-27 13:29 | 2025-04-18 07:33 | 1.1329 | -762.4833 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-06-01 | 146 | [8 empty] | FOR AUDIT |  | 2025-04-17 | -17 | 2025-06-03 | 2025-03-31 | [8 empty] | Y | 2025-03-31 | [6 empty] | 2025-03-03 | A6-1028,A6-8050,TLN-523826 | 0 | 33.6854 | 0 | 33.6854 | 1.1329 | 120 |  | 5.1687 | 5.1687 | 2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093657207', | ME155242 |  |  | 7.3757 |  | RONILO GANGE JR.
2025-03-10 | 2025-03-12 |  | HMB | X25020529420 | BARANGAY TALON UNO | MARCOS ALVAREZ, GOLDEN ACRES SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 9.9133 | 12.75 | 10.5 | NEW | 145803.3 | 10957.9 |  | 0% | 2025-02-28 12:13 | 2025-03-10 14:38 | 2025-03-10 |  | 2025-07-16 |  | 137.491 | 127.3903 | -45854 | 2025-03-19 06:48 | 2025-03-28 02:09 | 2025-04-19 12:13 | 4.7358 | -764.2333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-14 | 41 | [8 empty] | NO COC |  | 2025-07-31 | #VALUE! | [18 empty] | 2025-03-14 | TLN-527605 | 0 | 137.491 | 0 | 137.491 | 4.7358 | 15 |  | 5.2525 | 5.2525 | 0.25 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020529420', | ME155242 |  |  | 10.1007 |  | RONILO GANGE JR.
2025-03-10 | 2025-03-12 |  | HMB | R23894387 | ADDAS DEVELOPMENT CORPORATION | MASAITO, MOLINO III, BACOOR | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 32.0287 | 113.32 | - | RELOC | 146325.04 | 31308.56 |  | 0% | 2025-02-28 12:13 | 2025-03-10 15:05 | 2025-03-10 |  |  |  | -45716.509 | -45726.6285 | 0 | 2025-03-13 15:00 | 2025-03-20 22:08 | 2025-04-19 12:13 | -2127.576 | 0 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-14 | CT7-8094 | 0 | -45716.509 | 0 | -45716.509 | -2127.576 | 0 |  | 7.0967 | 7.0967 | 0 | 139.491 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23894387', | ME155242 |  |  | 10.1194 |  | RONILO GANGE JR.
2025-03-11 | 2025-03-12 |  | HMB | X25010054654 | SUZENNE MARGARETH TEE TANG-DONOVAN | WASHINGTON, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 52.8507 | 165.62 | 80 | NEW | 416189.14 | 58969.42 | 43597.25 | 73.93% | 2025-02-28 15:05 | 2025-03-10 15:05 | 2025-03-10 | 2025-03-31 | 2025-03-31 |  | 30.3715 | 20.3715 | -45747 | 2025-03-20 23:22 | 2025-03-30 04:46 | 2025-04-19 15:05 | 0.97574 | -762.45 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-05-30 | 148 | [8 empty] | FOR AUDIT | PARTIALLY BILLED | 2025-04-15 | 29 | 2025-03-31 | 2025-05-14 | [16 empty] | 2025-03-14 | A6-8058,TLN-527022 | 0 | 30.3715 | 0 | 30.3715 | 0.97574 | 122 |  | 4.8952 | 4.8952 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010054654', | ME155242 |  |  | 10 |  | RONILO GANGE JR.
2025-03-14 | 2025-03-12 |  | CBG | X24083238472 | LAND TRANSPORTATION OFFICE | NATIONAL, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 40.5895 | 64.8 | 95 | MODIFICATION | 588364.44 | 55307.66 | 24818.29 | 44.87% | 2025-03-03 14:55 | 2025-03-10 15:09 | 2025-03-11 |  | 2025-03-17 09:10 |  | 13.7604 | 6.7507 | -45733.3819 | 2025-03-22 22:08 | 2025-03-31 20:51 | 2025-04-22 14:55 | 0.46279 | -762.223 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-16 09:10 | 161.6181 | [8 empty] | ON GOING MAT RETURN | PARTIALLY BILLED | 2025-04-01 09:10 | 9.6181 | 2025-03-17 | 2025-04-11 | [6 empty] | 2025-08-07 | NVP | [8 empty] | 2025-03-14 | DR1-8087,TLN-523395 | 0 | 13.7604 | 0 | 13.7604 | 0.46279 | 135.6181 |  | 5.0239 | 5.0239 | 2.2603 |  | NON-REV |  | 2025-08-07 | 4137.78 | NTC ISSUED | 2025-08-07 |  | 19 |  |  |  | 'X24083238472', | ME166067 |  |  | 7.0097 |  | RONILO GANGE JR.
2025-03-17 | 2025-03-11 |  | BIZ | X25010149592 | HARD DISCOUNT PHILIPPINES, INC. | 8TH, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | COMP | Jenneth Madrid | 29.9069 | 35.82 | 19 | NEW | 220841.32 | 30781.12 |  | 0% | 2025-03-03 15:00 | 2025-03-10 15:11 | 2025-03-11 | 2025-03-27 | 2025-03-27 08:12 | 2025-08-21 | 23.7167 | 16.709 | 146.6583 | 2025-03-22 09:35 | 2025-03-31 04:56 | 2025-04-22 15:00 | 0.81691 | 2.4443 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-26 08:12 | 151.6583 | With scheduled PAI | Y | Y |  |  | 2025-03-21 | 5 | 2025-03-26 | PAID |  | 2025-04-11 08:12 | 32.6583 | 2025-03-27 | 2025-05-14 | [6 empty] | 2025-08-12 | NVP | Y | 2025-03-24 | [6 empty] | 2025-03-18 | TLN-211260 | 0 | 23.7167 | 5 | 18.7167 | 0.64469 | 125.6583 | 0.81691 | 5.1451 | 4.3282 | 2.0943 |  | REV |  | 2025-08-12 | 38194.26 | NTC ISSUED | 2025-08-15 |  | 11 |  |  |  | 'X25010149592', | ME185284 |  |  | 7.0076 |  | RONILO GANGE JR.
2025-03-17 | 2025-03-11 |  | BIZ | X25010268677 | GENELITO H. MORENO | VRCC, VETERANS CENTER, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 10.1328 | 12.2 | 19 | NEW | 146700.63 | 10482.84 |  | 0% | 2025-03-03 15:03 | 2025-03-10 15:10 | 2025-03-11 |  | 2025-03-26 |  | 22.3729 | 15.3681 | -45742 | 2025-03-22 09:38 | 2025-03-31 04:59 | 2025-04-22 15:03 | 0.77062 | -762.3667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-25 | 153 | [8 empty] | FOR AUDIT |  | 2025-04-10 | 81 | 2025-03-26 | 2025-06-30 | [8 empty] | Y | 2025-03-24 | [6 empty] | 2025-03-18 | B8-0220,TLN-527188 | 0 | 22.3729 | 0 | 22.3729 | 0.77062 | 127 |  | 5.1451 | 5.1451 | 2.1167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010268677', | ME185284 |  |  | 7.0049 |  | RONILO GANGE JR.
2025-03-13 | 2025-03-12 |  | BIZ | X24104087935 | FIRSTAR HVAC INC. | COASTAL, LONGOS, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 144.3689 | 144.47 | 40 | NEW | 793304.39 | 124045.43 |  | 0% | 2025-03-03 16:41 | 2025-03-12 14:17 | 2025-03-11 |  | 2025-05-20 |  | 77.3049 | 68.4049 | -45797 | 2025-03-24 21:39 | 2025-04-03 08:34 | 2025-04-22 16:41 | 2.3951 | -763.2833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-07-19 | 98 | [8 empty] | NO COC |  | 2025-06-04 | #VALUE! | [10 empty] | Y | 2025-05-02 | [6 empty] | 2025-03-14 | CY6-8024,CY6-8025,TLN-522865 | 0 | 77.3049 | 0 | 77.3049 | 2.3951 | 72 |  | 4.6259 | 4.6259 | 1.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104087935', | ME185284 |  |  | 8.9 |  | RONILO GANGE JR.
2025-03-17 | 2025-03-11 |  | HMB | X25020632623 | PAUL ERWIN SALAZAR CANTOS | BLOCK 14-B, LINDENWOOD RESIDENCES, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 14.6933 | 22.7 | 80 | MODIFICATION | 252394.2 | 19533.16 |  | 0% | 2025-03-04 10:44 | 2025-03-10 15:13 | 2025-03-11 |  | 2025-03-14 |  | 9.5528 | 3.366 | -45730 | 2025-03-22 12:31 | 2025-03-31 03:24 | 2025-04-23 10:44 | 0.33997 | -762.1667 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-05-13 | 165 | [8 empty] | FOR AUDIT |  | 2025-03-29 | 27 | 2025-03-14 | 2025-04-25 | [8 empty] | Y | 2025-03-13 | [6 empty] | 2025-03-18 | TLN-527650 | 0 | 9.5528 | 0 | 9.5528 | 0.33997 | 139 |  | 5.2867 | 5.2867 | 2.3167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020632623', | ME166067 |  |  | 6.1868 |  | Isan Carlo Lazaro
2025-03-11 | 2025-03-11 |  | HMB | X25010270222 | NELISA CHAVEZ BANATE | KALAYAAN VILL, KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 35.5089 | 153.2 | 21 | NEW | 208132.44 | 131636.9 |  | 0% | 2025-03-04 16:15 | 2025-03-10 15:13 | 2025-03-11 |  | 2025-08-09 09:08 |  | 157.7035 | 151.7465 | -45878.3806 | 2025-03-25 21:13 | 2025-04-04 08:08 | 2025-04-23 16:15 | 4.8861 | -764.6397 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-10-08 09:08 | 16.6194 | With scheduled PAI | Y | Y |  |  | 2025-06-04 | 6 | 2025-06-10 | NO COC |  | 2025-08-24 09:08 | #VALUE! | [18 empty] | N/A |  | 0 | 157.7035 | 6 | 151.7035 | 4.7002 | -9.3806 | 4.8861 | 4.5955 | -0.29064 | -0.15634 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010270222', | ME185284 |  |  | 5.9569 |  | Isan Carlo Lazaro
2025-03-11 | 2025-03-11 |  | CBG | X25020633295 | ASEANA BUSINESS PARK ESTATE ASSOCIATION, INC. | BRADCO, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 10.8167 | 12.42 | 27 | NEW | 189975.78 | 10668.75 |  | 0% | 2025-03-04 16:20 | 2025-03-10 15:12 | 2025-03-11 |  | 2025-06-04 |  | 91.3194 | 85.3667 | -45812 | 2025-03-23 10:55 | 2025-04-01 06:16 | 2025-04-23 16:20 | 3.1454 | -763.5333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-03 | 83 | [8 empty] | NO COC |  | 2025-06-19 | #VALUE! | [10 empty] | Y | 2025-05-30 | [6 empty] | 2025-03-14 | TLN-526558 | 0 | 91.3194 | 0 | 91.3194 | 3.1454 | 57 |  | 5.1088 | 5.1088 | 0.95 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020633295', | ME185284 |  |  | 5.9528 |  | Isan Carlo Lazaro
2025-03-17 | 2025-03-12 |  | HMB | X24093717402 | ROGER ABANDO DUNGAN | Q. PAREDES, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 210.0296 | 256.96 | 32 | MODIFICATION | 1240286.08 | 220788.86 |  | 0% | 2025-03-05 09:51 | 2025-03-12 14:23 | 2025-03-11 | 2025-04-24 | 2025-04-24 |  | 49.5896 | 42.4007 | -45771 | 2025-03-27 06:42 | 2025-04-05 21:51 | 2025-04-24 09:51 | 1.4956 | -762.85 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-06-23 | 124 | [8 empty] | FOR AUDIT |  | 2025-05-09 | 6 | 2025-04-24 | 2025-05-15 | [8 empty] | Y | 2025-04-24 | [6 empty] | 2025-03-18 | CR9-8034,CR9-8035,CR9-8036,CR9-8037,CR9-8039,TLN-523850 | 0 | 49.5896 | 0 | 49.5896 | 1.4956 | 98 |  | 4.4511 | 4.4511 | 1.6333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093717402', | ME166067 |  |  | 7.1889 |  | Isan Carlo Lazaro
2025-03-13 | 2025-03-12 |  | HMB | X24103945947 | ROLANDO SURIA BUCU | STERLINGLIFE, STERLINGLIFE HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 32.9195 | 113.09 | 32.6 | NEW | 271232.9 | 29907.08 |  | 0% | 2025-03-05 16:33 | 2025-03-12 14:21 | 2025-03-10 |  |  |  | -45721.6896 | -45728.5979 | 0 | 2025-03-26 21:31 | 2025-04-05 08:26 | 2025-04-24 16:33 | -1416.5908 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45721.6896 | 0 | -45721.6896 | -1416.5908 | 0 |  | 4.5641 | 4.5641 | 0 | 134.3104 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24103945947', | ME155242 |  |  | 6.9083 |  | Isan Carlo Lazaro
2025-03-13 | 2025-03-12 |  | HMB | X23051592518 | BARANGAY MANUYO DOS | S. MARQUEZ, GATCHALIAN SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 34.6533 | 118.72 | 11.9 | NEW | 327573.94 | 35944.4 |  | 0% | 2025-03-05 16:57 | 2025-03-12 14:22 | 2025-03-10 |  |  |  | -45721.7063 | -45728.5986 | 0 | 2025-03-26 21:55 | 2025-04-05 08:50 | 2025-04-24 16:57 | -1416.5913 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-14 | CY8-8013 | 0 | -45721.7063 | 0 | -45721.7063 | -1416.5913 | 0 |  | 4.5636 | 4.5636 | 0 | 134.2937 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X23051592518', | ME155242 |  |  | 6.8924 |  | Jenneth Madrid
2025-03-17 | 2025-03-11 |  | CBG | X24072786899 | DITO TELECOMMUNITY CORPORATION | CAMELLA, CAMELLA HOMES ALABANG 1 SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 18.1428 | 39.48 | 31 | NEW | 267147.11 | 33918.39 |  | 0% | 2025-03-06 14:00 | 2025-03-13 13:17 | 2025-03-11 |  | 2025-03-21 |  | 14.4167 | 7.4465 | -45737 | 2025-03-25 08:35 | 2025-04-03 03:56 | 2025-04-25 14:00 | 0.49657 | -762.2833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-20 | 158 | With scheduled PAI | Y |  |  | Y | 2025-03-15 | 6 | 2025-03-21 | FOR AUDIT |  | 2025-04-05 | 9 | 2025-03-21 | 2025-04-14 | [18 empty] | 6 | 8.4167 | 6 | 8.4167 | 0.28991 | 132 |  | 5.0432 | 5.0432 | 2.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072786899', | ME166067 |  |  | 6.9701 |  | Jenneth Madrid
2025-03-13 |  |  | MN | P2502182413 | C1 55GG Reconductoring of primary line from bare to covered from B9-0258 to B9-0260 | M.L. QUEZON PUROK 1 LOWER BICUTAN TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 109.69 | 109.69 | - | SUPPLEMENTAL MN FOR PCA | 234068.93 | 102134.84 |  | 0% | 2025-03-06 16:08 | 2025-03-12 14:45 |  |  | 2025-03-19 |  | 12.3278 | 6.3854 | -45735 | 2025-03-19 18:55 | 2025-03-27 02:03 | 2025-04-25 16:08 | 0.57372 | -762.25 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 2025-05-18 | 160 | [8 empty] | NO COC |  | 2025-04-03 | #VALUE! | [18 empty] | NA |  | 0 | 12.3278 | 0 | 12.3278 | 0.57372 | 134 |  | 6.8099 | 6.8099 | 2.2333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'P2502182413', | ME185284 |  |  | 5.9424 |  | Jenneth Madrid
2025-03-18 | 2025-03-12 |  | HMB | X24114468464 | CITY GOVT OF LAS PIÑAS | PILI, GOLDEN ACRES SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | SADANG:Sir city govt laspiñas, digging issue uli, hanapan pa ng customer kung sn ppwd ilipat, gawa ng may widening pa.. |  | ECOM | SCHED | Ronilo Gange Jr. | 89.3826 | 273.37 | 9 | MODIFICATION | 532048.99 | 100358.97 |  | 0% | 2025-03-06 16:36 | 2025-03-13 13:25 | 2025-03-11 |  |  |  | -45722.6917 | -45729.559 | 0 | 2025-03-28 13:27 | 2025-04-07 04:36 | 2025-04-25 16:36 | -1378.9383 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-18 | CU8-8123,CU8-8124,TLN-526539 | 0 | -45722.6917 | 0 | -45722.6917 | -1378.9383 | 0 |  | 4.4125 | 4.4125 | 0 | 133.3083 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114468464', | ME155242 |  |  | 6.8674 |  | Jenneth Madrid
2025-03-13 | 2025-03-12 |  | HMB | X24072851266 | CITY GOVERNMENT OF LAS PIÑAS | DANDELION, DOÑA MANUELA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 53.5228 | 103.13 | 287.2 | MODIFICATION | 851846.96 | 104930.69 |  | 0% | 2025-03-06 16:58 | 2025-03-13 13:14 | 2025-03-11 |  |  |  | -45722.7069 | -45729.5514 | 0 | 2025-03-25 05:09 | 2025-04-02 22:47 | 2025-04-25 16:58 | -1594.4329 | 0 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | 2025-04-02 | [6 empty] | 2025-03-17 | TLN-844456 | 0 | -45722.7069 | 0 | -45722.7069 | -1594.4329 | 0 |  | 5.1015 | 5.1015 | 0 | 133.2931 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072851266', | ME185284 |  |  | 6.8444 |  | Jenneth Madrid
2025-03-13 | 2025-03-12 |  | HMB | X24104280468 | CITY GOVERNMENT OF LAS PIÑAS | DANDELION, DOÑA MANUELA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 585.3798 | 1699.21 | 287.2 | MODIFICATION | 3468548.84 | 853471.38 |  | 0% | 2025-03-06 17:05 | 2025-03-13 13:01 | 2025-03-11 |  |  |  | -45722.7118 | -45729.5424 | 0 | 2025-03-29 06:43 | 2025-04-08 02:21 | 2025-04-25 17:05 | -1341.1995 | 0 | 50 | 30 | 25.5682 | 32.3864 | 22.5682 | 60 | 57 | 52 | 1900-02-28 | 45895 | [9 empty] | conj. X24072851266 | 1900-01-14 | 0 | [18 empty] | 2025-03-17 | CX7-8166,CX7-8117,CX7-8118,CX7-8119,CX7-8120,CX7-8121,CX7-8122,CX7-8123,CX7-8093,TLN-201003,TLN-844456 | 0 | -45722.7118 | 0 | -45722.7118 | -1341.1995 | 0 |  | 4.2911 | 4.2911 | 0 | 133.2882 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104280468', | ME185284 |  |  | 6.8306 |  | Jenneth Madrid
2025-03-13 | 2025-03-11 |  | HMB | X24114480257 | CITY GOV'T OF LAS PIÑAS | ALABANG-ZAPOTE, PAMPLONA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 10.9328 | 17.06 | 32.6 | NEW | 192652.59 | 14659.57 |  | 0% | 2025-03-06 17:05 | 2025-03-13 13:18 | 2025-03-11 |  | 2025-06-17 06:08 |  | 102.5438 | 95.7014 | -45825.2556 | 2025-03-25 11:40 | 2025-04-03 07:01 | 2025-04-25 17:05 | 3.5321 | -763.7543 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-16 06:08 | 69.7444 | [8 empty] | NO COC |  | 2025-07-02 06:08 | #VALUE! | [18 empty] | 2025-03-14 | TLN-526587 | 0 | 102.5438 | 0 | 102.5438 | 3.5321 | 43.7444 | 3.5321 | 5.0388 | 1.5068 | 0.72907 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114480257', | ME185284 |  |  | 6.8424 |  | Jenneth Madrid
2025-03-13 | 2025-03-11 |  | HMB | X25020514312 | CITY GOV'T OF LAS PIÑAS | PULO, SITIO PULO, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 10.4428 | 11.92 | 18.5 | MODIFICATION | 140707.86 | 10242.26 |  | 0% | 2025-03-06 17:05 | 2025-03-13 13:19 | 2025-03-11 |  | 2025-05-28 14:39 |  | 82.8986 | 76.0556 | -45805.6104 | 2025-03-25 11:40 | 2025-04-03 07:01 | 2025-04-25 17:05 | 2.8554 | -763.4268 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 14:39 | 89.3896 | [8 empty] | NO COC |  | 2025-06-12 14:39 | #VALUE! | [10 empty] | Y | 2025-05-28 | [6 empty] | 2025-03-17 | TLN-527589 | 0 | 82.8986 | 0 | 82.8986 | 2.8554 | 63.3896 |  | 5.0388 | 5.0388 | 1.0565 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020514312', | ME185284 |  |  | 6.8431 |  | Jenneth Madrid
2025-03-13 | 2025-03-12 |  | CBG | X25030763572 | IGLESIA NI CRISTO | P. BURGOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 9.934 | 9.93 | - | MODIFICATION | 19780.38 | 8535.56 |  | 0% | 2025-03-06 17:32 | 2025-03-13 13:24 | 2025-03-10 |  |  |  | -45722.7306 | -45729.5583 | 0 | 2025-03-18 17:32 | 2025-03-25 17:32 | 2025-04-25 17:32 | -2286.1365 | 0 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45722.7306 | 0 | -45722.7306 | -2286.1365 | 0 |  | 7.3135 | 7.3135 | 0 | 133.2694 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030763572', | ME155242 |  |  | 6.8278 |  | Jenneth Madrid
2025-03-17 | 2025-03-12 |  | CBG | X24041057959 | GLOBE TELECOM, INC. | WEST SERVICE, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 72.0884 | 1035.48 | 23 | NEW | 1052989.58 | 61948.89 |  | 0% | 2025-03-07 12:28 | 2025-03-13 15:24 | 2025-03-11 |  |  |  | -45723.5194 | -45729.6417 | 0 | 2025-04-02 23:53 | 2025-04-13 20:32 | 2025-04-26 12:28 | -1163.4096 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-03-18 | DZ1-1498,TLN-035411 | 0 | -45723.5194 | 0 | -45723.5194 | -1163.4096 | 0 |  | 3.7017 | 3.7017 | 0 | 132.4806 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041057959', | ME155242 |  |  | 6.1222 |  | Jenneth Madrid
2025-03-17 | 2025-03-12 |  | CBG | X24030854536 | DITO TELECOMMUNITY CORPORATION | ESTEHONOR CPD, ESTEHONOR CPD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 98.4871 | 113.7 | 20 | NEW | 1900472.29 | 97287.75 |  | 0% | 2025-03-07 12:38 | 2025-03-13 15:25 | 2025-03-11 |  | 2025-06-27 |  | 111.4736 | 105.3576 | -45835 | 2025-03-28 17:36 | 2025-04-07 04:31 | 2025-04-26 12:38 | 3.4538 | -763.9167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-08-26 | 60 | Special LGU permits/With Scheduled PAI | Y | Y |  |  | 2025-05-14 | 27 | 2025-06-19 | NO COC |  | 2025-07-12 | #VALUE! | [10 empty] | Y | 2025-06-27 | [8 empty] | 0 | 111.4736 | 45827 | 84.4736 | 2.6172 | 34 | 3.4538 | 4.5072 | 1.0534 | 0.56667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24030854536', | ME166067 |  |  | 6.116 |  | Jenneth Madrid
2025-03-18 | 2025-03-12 |  | HMB | X25010318884 | D88 BOULEVARD RESTOBAR | MOLINO, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 53.2787 | 144.51 | 5 | NEW | 337200.19 | 56906.67 |  | 0% | 2025-03-07 16:44 | 2025-03-13 15:15 | 2025-03-12 |  | 2025-04-02 |  | 25.3028 | 19.3646 | -45749 | 2025-03-28 21:42 | 2025-04-07 08:37 | 2025-04-26 16:44 | 0.78395 | -762.4833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-06-01 | 146 | [8 empty] | NO COC |  | 2025-04-17 | #VALUE! | [10 empty] | Y | 2025-04-02 | [6 empty] | 2025-03-18 | CW6-8117,TLN-527355 | 0 | 25.3028 | 0 | 25.3028 | 0.78395 | 120 |  | 4.5019 | 4.5019 | 2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010318884', | ME155242 |  |  | 5.9382 |  | Jenneth Madrid
2025-03-18 | 2025-03-12 |  | HMB | X25010318012 | REBACE REAL ESTATE AND DEVELOPMENT (REBACE) CORP. | REBACE BACOOR RESIDENCES, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 202.2694 | 236.56 | 24 | NEW | 1005969.01 | 202858.23 |  | 0% | 2025-03-07 16:48 | 2025-03-13 15:23 | 2025-03-12 |  | 2025-05-29 14:57 |  | 82.9229 | 76.9819 | -45806.6229 | 2025-03-29 13:39 | 2025-04-08 04:48 | 2025-04-26 16:48 | 2.5008 | -763.4437 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-07-28 14:57 | 88.3771 | [8 empty] | NO COC |  | 2025-06-13 14:57 | #VALUE! | [10 empty] | Y | 2025-06-26 | [6 empty] | 2025-03-18 | CW5-8047,CW5-8048,CW5-0725,CW5-8049,CW5-8050,CW5-8051,TLN-527345 | 0 | 82.9229 | 0 | 82.9229 | 2.5008 | 62.3771 |  | 4.3821 | 4.3821 | 1.0396 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010318012', | ME185284 |  |  | 5.941 |  | Isan Carlo Lazaro
2025-04-15 | 2025-03-12 |  | BIZ | X24083217792 | L.T. SOUTHVILLE SCHOOL, INC. | LUXEMBOURG, BF HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 151.474 | 269.11 | 492 | MODIFICATION | 1535974.57 | 197109.85 |  | 0% | 2025-03-10 12:00 | 2025-03-17 09:55 | 2025-03-12 |  |  |  | -45726.5 | -45733.4132 | 0 | 2025-03-27 10:15 | 2025-04-04 17:47 | 2025-04-29 12:00 | -1721.0249 | 0 | 28 | 26 | 19.927 | 25.2409 | 16.927 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-15 | CX8-8166,TLN-523410 | 0 | -45726.5 | 0 | -45726.5 | -1721.0249 | 0 |  | 5.3633 | 5.3633 | 0 | 129.5 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083217792', | ME155242 |  |  | 6.9132 |  | RONILO GANGE JR.
2025-04-15 | 2025-03-12 | Y | CBG | X24093485695 | POSH PROPERTIES DEVELOPMENT CORPORATION | BELLE, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | TECO | Jenneth Madrid | 35.6185 | 72 | 1062 | NEW | 149903.73 | 41002.37 |  | 0% | 2025-03-10 16:59 | 2025-03-17 08:24 | 2025-03-12 | 2025-04-12 | 2025-04-12 | 2025-07-30 14:01 | 32.2924 | 25.65 | 109.584 | 2025-03-23 07:39 | 2025-03-30 11:33 | 2025-04-29 16:59 | 1.5514 | 1.8264 | 23 | 20 | 15.6109 | 19.7738 | 12.6109 | 60 | 57 | 52 | 2025-06-11 | 136 | [8 empty] | PAID |  | 2025-04-27 | 17 | 2025-04-12 | 2025-05-14 | [16 empty] | 2025-04-15 | C5-8082 | 0 | 32.2924 | 0 | 32.2924 | 1.5514 | 110 |  | 6.8362 | 6.8362 | 1.8333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093485695', | ME185284 |  |  | 6.6424 |  | RONILO GANGE JR.
2025-03-13 | 2025-03-12 |  | BIZ | X25010269534 | AMVEL LAND DEVELOPMENT CORP., | PHASE 2 ACCESS ROAD, AMVEL COMMERCIAL COMPLEX, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 7.97 | 42.53 | 21 | MODIFICATION | 41565.68 | 36542.85 |  | 0% | 2025-03-10 17:02 | 2025-03-13 14:32 | 2025-03-12 |  | 2025-03-31 09:28 |  | 20.6847 | 17.7889 | -45747.3944 | 2025-03-29 11:37 | 2025-04-07 06:58 | 2025-04-29 17:02 | 0.71247 | -762.4566 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-05-30 09:28 | 147.6056 | With scheduled PAI | Y |  |  | Y | 2025-03-21 | 35 | 2025-04-25 | FOR AUDIT |  | 2025-04-15 09:28 | -1.3944 | 2025-03-31 | 2025-04-14 | [16 empty] | N/A |  | 35 | -14.3153 | 35 | -14.3153 | -0.49308 | 121.6056 |  | 4.9011 | 4.9011 | 2.0268 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010269534', | ME166067 |  |  | 2.8958 |  | RONILO GANGE JR.
2025-03-24 | 2025-03-12 |  | BIZ | X25020477740 | ECEAS CORPORATION | FRANCE, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 36.5095 | 75.83 | 54 | NEW | 307792.24 | 47727.65 |  | 0% | 2025-03-10 17:04 | 2025-03-17 09:55 | 2025-03-12 |  | 2025-06-21 |  | 102.2889 | 95.5868 | -45829 | 2025-03-30 00:17 | 2025-04-07 23:00 | 2025-04-29 17:04 | 3.4402 | -763.8167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-08-20 | 66 | [8 empty] | NO COC |  | 2025-07-06 | #VALUE! | [20 empty] | 0 | 102.2889 | 0 | 102.2889 | 3.4402 | 40 |  | 4.7854 | 4.7854 | 0.66667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020477740', | ME155242 |  |  | 6.7021 |  | RONILO GANGE JR.
2025-03-24 |  |  | HMB | X24041002125 | CDC REALTY INC. | STA. ANA, SUN VALLEY SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 11.45 | 19.38 | - | TERMINATION | 24195.92 | 16660.36 |  | 0% | 2025-03-10 17:13 | 2025-03-17 09:53 |  |  | 2025-03-31 |  | 20.2826 | 13.5882 | -45747 | 2025-03-22 17:13 | 2025-03-29 17:13 | 2025-04-29 17:13 | 1.0141 | -762.45 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-05-30 | 148 | [8 empty] | NO COC | conj. X25020539755 | 2025-04-15 | #VALUE! | [20 empty] | 0 | 20.2826 | 0 | 20.2826 | 1.0141 | 122 |  | 7.1141 | 7.1141 | 2.0333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041002125', | ME185284 |  |  | 6.6944 |  | Jenneth Madrid
2025-04-15 | 2025-05-28 |  | BIZ | X25020583083 | DAVID'S FUSION INT'L. FOOD INC. DOING BUSINESS UND | QUIRINO, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 20.17 | 27.61 | - | TERMINATION | 29537.03 | 23757.59 |  | 0% | 2025-03-11 10:50 | 2025-03-17 10:21 | 2025-03-12 |  |  |  | -45727.4514 | -45733.4313 | 0 | 2025-03-23 10:50 | 2025-03-30 10:50 | 2025-04-30 10:50 | -2286.3726 | 0 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45727.4514 | 0 | -45727.4514 | -2286.3726 | 0 |  | 7.0774 | 7.0774 | 0 | 128.5486 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020583083', | ME155242 |  |  | 5.9799 |  | Jenneth Madrid
2025-03-21 | 2025-03-17 |  | BIZ | X24104308728 | JOHN GABRIEL FERRER VERGEL | BAYABAS, GOLDEN ACRES SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 15.5528 | 35.5 | 56 | NEW | 366702.33 | 30500.21 |  | 0% | 2025-03-11 13:44 | 2025-03-17 10:21 | 2025-03-14 |  | 2025-03-25 |  | 13.4278 | 7.5687 | -45741 | 2025-03-29 15:31 | 2025-04-07 06:24 | 2025-04-30 13:44 | 0.47787 | -762.35 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-05-24 | 154 | [8 empty] | NO COC |  | 2025-04-09 | #VALUE! | [10 empty] | Y | 2025-03-18 | [8 empty] | 0 | 13.4278 | 0 | 13.4278 | 0.47787 | 128 |  | 5.0332 | 5.0332 | 2.1333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104308728', | ME185284 |  |  | 5.859 |  | RONILO GANGE JR.
2025-03-26 | 2025-03-17 |  | HMB | X25020594777 | CITY GOVERNMENT OF MUNTINLUPA | FILINVEST SOCIALIZED HOUSING, FILINVEST SOCIALIZED HOUSING, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 57.3666 | 160.37 | 60 | MODIFICATION | 439898.81 | 70527.93 |  | 0% | 2025-03-11 13:54 | 2025-03-17 10:20 | 2025-03-14 |  | 2025-06-14 14:53 |  | 95.041 | 89.1896 | -45822.6201 | 2025-03-31 22:11 | 2025-04-10 03:35 | 2025-04-30 13:54 | 3.0534 | -763.7103 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-13 14:53 | 72.3799 | [8 empty] | FOR AUDIT |  | 2025-06-29 14:53 | 7.3799 | 2025-06-14 | 2025-07-07 | [8 empty] | Y | 2025-06-16 | [6 empty] | 2025-03-26 | DV1-8109 | 0 | 95.041 | 0 | 95.041 | 3.0534 | 46.3799 |  | 4.5434 | 4.5434 | 0.773 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020594777', | ME155242 |  |  | 5.8514 |  | RONILO GANGE JR.
2025-03-21 | 2025-03-17 |  | HMB | X25030761116 | RIGUERA REALTY & DEV'T CORP. | CYPRESS, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 0.33 | 0.99 | 10.5 | NEW | 13519 | 850.62 |  | 0% | 2025-03-11 15:32 | 2025-03-17 10:20 | 2025-03-14 |  | 2025-04-11 |  | 30.3528 | 24.5694 | -45758 | 2025-03-30 10:07 | 2025-04-08 05:28 | 2025-04-30 15:32 | 1.0455 | -762.6333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-10 | 137 | [8 empty] | NO COC |  | 2025-04-26 | #VALUE! | [20 empty] | 0 | 30.3528 | 0 | 30.3528 | 1.0455 | 111 |  | 4.8688 | 4.8688 | 1.85 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030761116', | ME155242 |  |  | 5.7833 |  | Isan Carlo Lazaro
2025-03-21 |  |  | BIZ | X25020672144 | SYNERGYAUTO VENTURES CORPORATION | DR. A. SANTOS, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 59.97 | 69.2 | 97 | NEW | 456559.36 | 43236.61 |  | 0% | 2025-03-12 12:48 | 2025-03-17 10:23 | 2025-03-14 |  | 2025-03-31 | 2025-05-18 18:15 | 18.4667 | 13.5674 | 48.7604 | 2025-03-31 20:01 | 2025-04-09 18:44 | 2025-05-01 12:48 | 0.62107 | 0.81267 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-30 | 148 | [8 empty] | FOR AUDIT |  | 2025-04-15 | #VALUE! | [20 empty] | 0 | 18.4667 | 0 | 18.4667 | 0.62107 | 122 |  | 4.7241 | 4.7241 | 2.0333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020672144', | ME194579 |  |  | 4.8993 |  | Jenneth Madrid
2025-03-21 | 2025-03-17 |  | HMB | R23910052 | SOLIVA PETER PAUL ACHURRA | SAPLUNGAN, MEADOWOOD EXEC. VILLAGE PHASE 3B, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 15.2723 | 17.09 | - | RELOC | 30551.07 | 14685.11 |  | 0% | 2025-03-13 13:31 | 2025-03-20 09:01 | 2025-03-14 |  |  |  | -45729.5632 | -45736.3757 | 0 | 2025-03-25 13:31 | 2025-04-01 13:31 | 2025-05-02 13:31 | -2286.4782 | 0 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45729.5632 | 0 | -45729.5632 | -2286.4782 | 0 |  | 6.9718 | 6.9718 | 0 | 126.4368 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23910052', | ME155242 |  |  | 6.8125 |  | RONILO GANGE JR.
2025-03-24 | 2025-03-17 |  | BIZ | R23462615 | UNIOIL PETROLEUM INC | DONA SOLEDAD EXTN, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 49.6652 | 135.03 | - | RELOC | 212124.87 | 48759.62 |  | 0% | 2025-03-13 13:33 | 2025-03-20 09:01 | 2025-03-14 |  | 2025-06-14 14:49 |  | 93.0528 | 86.2417 | -45822.6174 | 2025-03-26 16:20 | 2025-04-02 23:28 | 2025-05-02 13:33 | 4.3305 | -763.7103 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 2025-08-13 14:49 | 72.3826 | [8 empty] | FOR AUDIT |  | 2025-06-29 14:49 | -16.6174 | 2025-06-24 | 2025-06-13 | [18 empty] | 0 | 93.0528 | 0 | 93.0528 | 4.3305 | 46.3826 |  | 6.4891 | 6.4891 | 0.77304 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23462615', | ME155242 |  |  | 6.8111 |  | IJP
2025-03-26 | 2025-03-17 |  | HMB | X24093522671 | A & T RESOURCES & DEV'T | CORREGIDOR, TIERRA NUEVA SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 36.6695 | 41.47 | 83 | NEW | 368913.31 | 35655.36 |  | 0% | 2025-03-13 16:30 | 2025-03-20 09:01 | 2025-03-14 |  | 2025-05-07 09:27 |  | 54.7063 | 48.0181 | -45784.3938 | 2025-03-31 18:17 | 2025-04-09 09:10 | 2025-05-02 16:30 | 1.9469 | -763.0732 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-07-06 09:27 | 110.6062 | [8 empty] | FOR AUDIT |  | 2025-05-22 09:27 | 18.6062 | 2025-05-07 | 2025-06-10 | [8 empty] | Y | 2025-05-07 | [6 empty] | 2025-03-26 | CV9-8044 | 0 | 54.7063 | 0 | 54.7063 | 1.9469 | 84.6062 |  | 4.9579 | 4.9579 | 1.4101 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24093522671', | ME166067 |  |  | 6.6882 |  | RONILO GANGE JR.
2025-03-26 | 2025-03-20 |  | BIZ | X24051834109 | MOBILITY GROUP CORP. | MOLINO-PALIPARAN, MOLINO IV, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 10.6428 | 13.24 | 24 | NEW | 139650.67 | 11374.74 |  | 0% | 2025-03-14 16:05 | 2025-03-25 14:48 | 2025-03-20 |  | 2025-04-30 |  | 46.3299 | 35.3833 | -45777 | 2025-04-02 10:40 | 2025-04-11 06:01 | 2025-05-03 16:05 | 1.5958 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-04-28 | [6 empty] | 2025-03-26 | CR7-2360,TLN-522030 | 0 | 46.3299 | 0 | 46.3299 | 1.5958 | 92 |  | 4.7647 | 4.7647 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24051834109', | ME155242 |  |  | 10.9465 |  | RONILO GANGE JR.
2025-03-28 | 2025-03-20 |  | HMB | X25020478582 | NESTOR R LLORCA | PINAGKAISA, PUROK 1A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 950.7477 | 1102.11 | 45 | NEW | 1710317.87 | 627471.27 |  | 0% | 2025-03-14 16:11 | 2025-03-25 14:51 | 2025-03-20 |  |  |  | -45730.6743 | -45741.6188 | 0 | 2025-04-10 03:36 | 2025-04-21 00:15 | 2025-05-03 16:11 | -1163.5916 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45730.6743 | 0 | -45730.6743 | -1163.5916 | 0 |  | 3.5196 | 3.5196 | 0 | 125.3257 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020478582', | ME155242 |  |  | 10.9444 |  | RONILO GANGE JR.
2025-03-26 | 2025-03-20 |  | BIZ | X24072839965 | LOLA NENA'S PICHI PICHI, INC. | MOLINO ROAD, MOLINO III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 14.3228 | 40.53 | 54 | NEW | 373305.64 | 34825.53 |  | 0% | 2025-03-17 12:26 | 2025-03-25 15:10 | 2025-03-20 |  | 2025-04-30 |  | 43.4819 | 35.3681 | -45777 | 2025-04-04 14:13 | 2025-04-13 05:06 | 2025-05-06 12:26 | 1.5474 | -762.95 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-05-02 | [6 empty] | 2025-03-26 | TLN-523101 | 0 | 43.4819 | 0 | 43.4819 | 1.5474 | 92 |  | 4.8216 | 4.8216 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072839965', | ME155242 |  |  | 8.1139 |  | RONILO GANGE JR.
2025-03-31 | 2025-03-20 |  | HMB | X24114473729 | GREENLAND NEW LOWER BICUTAN NEIGHBORHOOD ASSOCIATI | STO NIÑO, PUROK 1A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | FOR SCHED DIGGING |  | VJC | SCHED | Jenneth Madrid | 218.2782 | 1760.71 | 60 | NEW | 2078054.38 | 253118.34 |  | 0% | 2025-03-19 10:47 | 2025-03-25 15:13 | 2025-03-20 |  |  |  | -45735.4493 | -45741.634 | 0 | 2025-04-13 15:46 | 2025-04-24 04:18 | 2025-05-08 10:47 | -1216.0249 | 0 | 50 | 34 | 28.208 | 35.7301 | 25.208 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45735.4493 | 0 | -45735.4493 | -1216.0249 | 0 |  | 3.5509 | 3.5509 | 0 | 120.5507 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114473729', | ME185284 |  |  | 6.1847 |  | Jenneth Madrid
2025-03-31 | 2025-03-20 |  | HMB | X24114473614 | GREENLAND NEW LOWER BICUTAN NEIGHBORHOOD ASSOCIATI | RANGER, PUROK 1A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | FOR SCHED DIGGING |  | VJC | SCHED | Jenneth Madrid | 109.0874 | 257.64 | 60 | NEW | 963714.39 | 111642.05 |  | 0% | 2025-03-19 10:51 | 2025-03-25 15:11 | 2025-03-20 |  |  |  | -45735.4521 | -45741.6326 | 0 | 2025-04-09 09:53 | 2025-04-18 19:14 | 2025-05-08 10:51 | -1431.6349 | 0 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [20 empty] | 0 | -45735.4521 | 0 | -45735.4521 | -1431.6349 | 0 |  | 4.1804 | 4.1804 | 0 | 120.5479 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114473614', | ME185284 |  |  | 6.1806 |  | Jenneth Madrid
2025-04-15 | 2025-03-20 |  | HMB | X25030837914 | BARANGAY ALABANG | MONTILLANO, ALABANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | Executed 3/23/25 |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 5.92 | 75.96 | 76 | NEW | 153594.65 | 65266.75 |  | 0% | 2025-03-19 11:02 | 2025-03-20 12:13 | 2025-03-20 |  | 2025-03-27 08:30 |  | 7.8944 | 6.8451 | -45743.3542 | 2025-04-07 18:15 | 2025-04-16 16:58 | 2025-05-08 11:02 | 0.2655 | -762.3892 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-05-26 08:30 | 151.6458 | [8 empty] | FOR AUDIT | Supersede : X24062428692 | 2025-04-11 08:30 | 4.6458 | 2025-03-27 | 2025-04-16 | [16 empty] | N/A |  | 0 | 7.8944 | 0 | 7.8944 | 0.2655 | 125.6458 |  | 4.4912 | 4.4912 | 2.0941 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030837914', | ME166067 |  |  | 1.0493 |  | Isan Carlo Lazaro
2025-03-31 | 2025-03-20 |  | HMB | X25020617611 | CONNIE LAO YU | N. ARMSTRONG, MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | TECO | Ronilo Gange Jr. | 1.86 | 4.35 | 12 | NEW | 20856.59 | 3737.67 |  | 0% | 2025-03-19 17:12 | 2025-03-25 15:11 | 2025-03-20 |  | 2025-04-15 | 2025-07-22 19:51 | 26.2833 | 20.3674 | 98.8271 | 2025-04-07 11:47 | 2025-04-16 07:08 | 2025-05-08 17:12 | 0.90531 | 1.6471 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-14 | 133 | [8 empty] | PAID |  | 2025-04-30 | 14 | 2025-04-06 | 2025-05-14 | 2025-06-12 | ECI | N |  |  |  | 2025-07-18 | NVP | Y | 2025-04-07 | [8 empty] | 0 | 26.2833 | 0 | 26.2833 | 0.90531 | 107 |  | 4.5909 | 4.5909 | 1.7833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020617611', | ME155242 |  |  | 5.916 |  | Isan Carlo Lazaro
2025-03-31 | 2025-03-26 | Y | BIZ | X24114614743 | PTR PREMIER HOLDINGS INC. | ST. JOSEPH, ST. JOSEPH SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 42.4455 | 134.28 | 77 | NEW | 395516.39 | 48111.19 |  | 0% | 2025-03-20 15:14 | 2025-03-28 10:34 | 2025-03-26 | 2025-06-11 | 2025-06-11 |  | 82.3653 | 74.5597 | -45819 | 2025-04-09 23:31 | 2025-04-19 04:55 | 2025-05-09 15:14 | 2.6461 | -763.65 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-10 | 76 | [8 empty] | FOR AUDIT |  | 2025-06-26 | 13 | 2025-06-11 | 2025-07-09 | [8 empty] | Y | 2025-05-23 | [8 empty] | 0 | 82.3653 | 0 | 82.3653 | 2.6461 | 50 |  | 4.2525 | 4.2525 | 0.83333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114614743', | ME185284 |  |  | 7.8056 |  | RONILO GANGE JR.
| 2025-03-26 |  | HMB | R23858401 | ACTIVE REALTY & DEVELOPMENT CORPORATION,, HMB | GUADARAMA, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 13.4041 | 16.68 | - | RELOC | 38725.93 | 14335.24 |  | 0% | 2025-03-20 15:49 | 2025-03-28 10:36 | 2025-03-26 |  | 2025-05-22 |  | 62.341 | 54.5583 | -45799 | 2025-04-01 15:49 | 2025-04-08 15:49 | 2025-05-09 15:49 | 3.117 | -763.3167 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [20 empty] | 0 | 62.341 | 0 | 62.341 | 3.117 | 70 |  | 6.617 | 6.617 | 1.1667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23858401', | ME155242 |  |  | 7.7826 |  | RONILO GANGE JR.
2025-03-31 | 2025-03-26 |  | HMB | X25020498390 | MANUKA REALTY, INC. | TALISAY, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 59.2121 | 71.46 | 80 | NEW | 427747.65 | 61024.15 |  | 0% | 2025-03-21 09:51 | 2025-03-28 10:40 | 2025-03-26 |  | 2025-05-15 16:35 |  | 55.2806 | 48.2465 | -45792.691 | 2025-04-09 17:04 | 2025-04-18 15:47 | 2025-05-10 09:51 | 1.8592 | -763.2115 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-07-14 16:35 | 102.309 | [8 empty] | FOR AUDIT |  | 2025-05-30 16:35 | 10.309 | 2025-05-15 | 2025-06-10 | [8 empty] | Y | 2025-05-14 | [8 empty] | 0 | 55.2806 | 0 | 55.2806 | 1.8592 | 76.309 |  | 4.4256 | 4.4256 | 1.2718 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020498390', | ME166067 |  |  | 7.034 |  | RONILO GANGE JR.
2025-04-08 | 2025-03-26 |  | HMB | X25030873001 | JEIKA PROPERTIES CORPORATION | BLOCK 6, KATHLEEN PLACE 5 SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 8.37 | 13.64 | 1.5 | NEW | 27968.07 | 11720.04 |  | 0% | 2025-03-21 12:27 | 2025-03-28 10:44 | 2025-03-26 |  | 2025-05-24 |  | 63.4812 | 56.5528 | -45801 | 2025-04-09 07:02 | 2025-04-18 02:23 | 2025-05-10 12:27 | 2.1866 | -763.35 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-23 | 94 | [8 empty] | NO COC |  | 2025-06-08 | #VALUE! | [10 empty] | Y | 2025-05-24 | [6 empty] | N/A |  | 0 | 63.4812 | 0 | 63.4812 | 2.1866 | 68 |  | 4.5288 | 4.5288 | 1.1333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030873001', | ME155242 |  |  | 6.9285 |  | Isan Carlo Lazaro
2025-03-28 | 2025-03-26 |  | CBG | X25030858073 | CENTURY LIMITLESS CORPORATION, | WEST SERVICE, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 88.0707 | 96.03 | - | TERMINATION | 81510.35 | 82512.06 |  | 0% | 2025-03-24 14:06 | 2025-03-28 10:45 | 2025-03-26 |  | 2025-04-22 |  | 28.4125 | 24.5521 | -45769 | 2025-04-06 04:46 | 2025-04-13 08:40 | 2025-05-13 14:06 | 1.365 | -762.8167 | 23 | 20 | 15.6109 | 19.7738 | 12.6109 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [20 empty] | 0 | 28.4125 | 0 | 28.4125 | 1.365 | 100 |  | 6.1694 | 6.1694 | 1.6667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030858073', | ME155242 |  |  | 3.8604 |  | Isan Carlo Lazaro
2025-04-15 | 2025-03-26 | Y | HMB | X25020466847 | NADINE G ABELA | LUZON, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For execution 3/26/25 |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 13.1828 | 29.57 | 46 | MODIFICATION | 222665.25 | 25003.23 |  | 0% | 2025-03-25 11:06 | 2025-03-25 12:32 | 2025-03-26 |  | 2025-04-04 |  | 9.5375 | 9.4778 | -45751 | 2025-04-13 05:41 | 2025-04-22 01:02 | 2025-05-14 11:06 | 0.32851 | -762.5167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-03 | 144 | [8 empty] | FOR AUDIT |  | 2025-04-19 | -5 | 2025-04-04 | 2025-04-14 | [8 empty] | Y | 2025-03-25 | [6 empty] | 2025-04-15 | TLN-527522 | 0 | 9.5375 | 0 | 9.5375 | 0.32851 | 118 |  | 4.393 | 4.393 | 1.9667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020466847', | ME166067 |  |  | 0.059722 |  | Isan Carlo Lazaro
2025-03-28 | 2025-03-31 |  | BIZ | X25010330816 | GOLDILOCKS BAKESHOP, INC. | ST. FRANCIS, SAN AGUSTIN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 1.73 | 5.08 | 19 | NEW | 23015.62 | 4364.97 |  | 0% | 2025-03-25 15:43 | 2025-03-31 12:28 | 2025-03-28 |  | 2025-06-04 |  | 70.3451 | 64.4806 | -45812 | 2025-04-13 10:18 | 2025-04-22 05:39 | 2025-05-14 15:43 | 2.423 | -763.5333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-03 | 83 | [8 empty] | NO COC |  | 2025-06-19 | #VALUE! | [10 empty] | Y | 2025-05-29 | [8 empty] | 0 | 70.3451 | 0 | 70.3451 | 2.423 | 57 |  | 4.3863 | 4.3863 | 0.95 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010330816', | ME185284 |  |  | 5.8646 |  | Jenneth Madrid
2025-04-03 | 2025-03-31 |  | HMB | X25010076395 | ANANTA REALTY CORP. | PASAMANCA, SOUTH GREEN PARK SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 190.6914 | 554.97 | 120 | NEW | 1004604.96 | 207420.67 |  | 0% | 2025-03-25 23:02 | 2025-03-31 12:30 | 2025-03-28 |  | 2025-04-28 10:50 |  | 33.4917 | 27.9306 | -45775.4514 | 2025-04-17 11:48 | 2025-04-27 07:12 | 2025-05-14 23:02 | 0.98382 | -762.9242 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 2025-06-27 10:50 | 119.5486 | [8 empty] | NO COC |  | 2025-05-13 10:50 | #VALUE! | [10 empty] | Y | 2025-04-24 | [8 empty] | 0 | 33.4917 | 0 | 33.4917 | 0.98382 | 93.5486 |  | 3.7318 | 3.7318 | 1.5591 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010076395', | ME185284 |  |  | 5.5611 |  | Jenneth Madrid
2025-03-28 | 2025-03-31 | Y | HMB | X25010329960 | RODRIGO SANGALANG LA TORRE | TOPAZ, SEVERINA DIAMOND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 36.03 | 63.43 | 66 | NEW | 359972.84 | 54526.82 |  | 0% | 2025-03-25 23:02 | 2025-03-28 10:51 | 2025-03-28 |  | 2025-04-22 |  | 27.0403 | 24.5479 | -45769 | 2025-04-14 06:15 | 2025-04-23 04:58 | 2025-05-14 23:02 | 0.90941 | -762.8167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | ON GOING MAT RETURN |  | 2025-05-07 | -16 | 2025-06-03 | 2025-04-21 | 2025-06-12 | ECI | N |  |  |  | 2025-07-18 | NVP | Y | 2025-04-16 | [6 empty] | 2025-04-01 | DY1-8087,-TLN-527411 | 0 | 27.0403 | 0 | 27.0403 | 0.90941 | 100 |  | 4.2726 | 4.2726 | 1.6667 |  | REV |  | 2025-07-21 | 3020.83 | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010329960', | ME155242 |  |  | 2.4924 |  | Jenneth Madrid
2025-03-28 | 2025-03-31 | Y | HMB | X25010249951 | ALEX JUSTINIANO CLAVERIA | SANTIAGO LOOP, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 56.1126 | 69.62 | 110 | NEW | 417348.14 | 59036.1 |  | 0% | 2025-03-26 10:00 | 2025-03-28 10:46 | 2025-03-27 |  | 2025-04-15 14:12 |  | 20.175 | 18.1431 | -45762.5917 | 2025-04-13 21:29 | 2025-04-22 14:57 | 2025-05-15 10:00 | 0.70448 | -762.7099 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-06-14 14:12 | 132.4083 | [8 empty] | MATERIAL BALANCING |  | 2025-04-30 14:12 | -2.5917 | 2025-04-15 | 2025-04-28 | [18 empty] | 0 | 20.175 | 0 | 20.175 | 0.70448 | 106.4083 |  | 4.4201 | 4.4201 | 1.7735 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010249951', | ME166067 |  |  | 2.0319 |  | Jenneth Madrid
2025-04-03 | 2025-03-31 | Y | HMB | X24083316199 | ADEL MUNDAN BALOGO | SAUDI ARABIA, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | COMP | Jenneth Madrid | 37.9685 | 138.31 | 60 | NEW | 391146.94 | 43717.18 |  | 0% | 2025-03-26 16:23 | 2025-03-31 12:32 | 2025-03-28 |  | 2025-04-29 | 2025-08-21 | 33.3174 | 28.4778 | 114 | 2025-04-16 00:40 | 2025-04-25 06:04 | 2025-05-15 16:23 | 1.0704 | 1.9 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-06-28 | 119 | [8 empty] | PAID |  | 2025-05-14 | 16 | 2025-04-29 | 2025-05-30 | [8 empty] | Y | 2025-04-25 | [8 empty] | 0 | 33.3174 | 0 | 33.3174 | 1.0704 | 93 |  | 4.0582 | 4.0582 | 1.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24083316199', | ME155242 |  |  | 4.8396 |  | Jenneth Madrid
2025-04-04 | 2025-03-31 |  | HMB | X24124723768 | BRGY. MARCELO GREEN | MARCELO, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 66.286 | 155.54 | 35 | MODIFICATION | 381652.72 | 66357.21 |  | 0% | 2025-03-26 16:23 | 2025-03-31 12:33 | 2025-03-28 |  |  |  | -45742.6826 | -45747.5229 | 0 | 2025-04-16 21:21 | 2025-04-26 08:16 | 2025-05-15 16:23 | -1417.2412 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-07 | DY1-8072,TLN-526892 | 0 | -45742.6826 | 0 | -45742.6826 | -1417.2412 | 0 |  | 3.9137 | 3.9137 | 0 | 113.3174 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124723768', | ME155242 |  |  | 4.8403 |  | RONILO GANGE JR.
2025-03-28 | 2025-03-31 |  | HMB | X25010066825 | JOE VINCENT J. ABIERA | BULUSAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 63.1026 | 92.81 | 90 | NEW | 474663.13 | 78962.68 |  | 0% | 2025-03-26 16:23 | 2025-03-28 10:53 | 2025-03-28 |  | 2025-05-06 08:29 |  | 40.6708 | 38.9 | -45783.3535 | 2025-04-14 23:36 | 2025-04-23 22:19 | 2025-05-15 16:23 | 1.3678 | -763.0559 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-07-05 08:29 | 111.6465 | [8 empty] | FOR AUDIT |  | 2025-05-21 08:29 | 19.6465 | 2025-05-06 | 2025-06-10 | [8 empty] | Y | 2025-05-06 | [8 empty] | 0 | 40.6708 | 0 | 40.6708 | 1.3678 | 85.6465 |  | 4.2483 | 4.2483 | 1.4274 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010066825', | ME166067 |  |  | 1.7708 |  | RONILO GANGE JR.
2025-04-03 | 2025-03-31 |  | HMB | X25030802747 | KATHRYN ANG ZARATE | ROSEMALLOW, SUN VALLEY SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 91.4729 | 269.13 | 66.62 | MODIFICATION | 561135.26 | 95917.15 |  | 0% | 2025-03-26 16:28 | 2025-03-31 12:31 | 2025-03-28 |  | 2025-08-09 09:00 |  | 135.6889 | 130.8535 | -45878.375 | 2025-04-16 15:30 | 2025-04-26 00:51 | 2025-05-15 16:28 | 4.2474 | -764.6396 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 2025-10-08 09:00 | 16.625 | Third party concern (Applicant-related compliance) | Y | Y |  |  | 2025-04-07 | 67 | 2025-06-13 | NO COC |  | 2025-08-24 09:00 | #VALUE! | [20 empty] | 0 | 135.6889 | 67 | 68.6889 | 2.1501 | -9.375 |  | 3.9539 | 3.9539 | -0.15625 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030802747', | ME185284 |  |  | 4.8354 |  | RONILO GANGE JR.
2025-03-28 | 2025-03-31 |  | HMB | X24041299813 | MAXWELL PATRICK JOVEN ALVAREZ | ST. PETER, SAN JOSE SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 41.1395 | 127.4 | 80 | MODIFICATION | 383978.78 | 41823.95 |  | 0% | 2025-03-26 17:13 | 2025-03-28 10:50 | 2025-03-28 | 2025-06-18 | 2025-07-22 |  | 117.2826 | 115.5486 | -45860 | 2025-04-16 01:30 | 2025-04-25 06:54 | 2025-05-15 17:13 | 3.7679 | -764.3333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-09-20 | 35 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | FOR AUDIT |  | 2025-08-06 | 2 | 2025-06-18 | 2025-08-08 | [18 empty] | 0 | 117.2826 | 34 | 83.2826 | 2.6756 | 9 |  | 4.057 | 4.057 | 0.15 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24041299813', | ME185284 |  |  | 1.734 |  | Isan Carlo Lazaro
2025-04-07 | 2025-04-02 |  | HMB | X24010242621 | MICHELLE MARTELINO YU | OXFORD, HILLSBOROUGH SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | digging only |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 127.88 | 317.23 | 80 | NEW | 663984 | 136862.4 |  | 0% | 2025-03-27 | 2025-04-03 14:59 | 2025-04-01 |  |  |  | -45743 | -45750.6243 | 0 | 2025-04-17 12:28 | 2025-04-27 01:23 | 2025-05-16 | -1399.1976 | 0 | 30 | 34 | 24.5192 | 31.0577 | 21.5192 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-07 | DV1-1220,DV1-8035,TLN-520316 | 0 | -45743 | 0 | -45743 | -1399.1976 | 0 |  | 3.8541 | 3.8541 | 0 | 113 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24010242621', |  |  |  | 7.6243 |  | Jenneth Madrid
2025-04-04 | 2025-04-02 |  | BIZ | X25020421060 | MARK CHRISTIANE D. MIJARES | DIEGO SILANG, AFP OVAI PHASE IV, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 10.58 | 14.23 | 16 | NEW | 146020.44 | 12224.56 |  | 0% | 2025-03-27 | 2025-04-03 14:56 | 2025-04-01 |  | 2025-04-10 09:28 |  | 14.3944 | 6.7722 | -45757.3944 | 2025-04-14 18:35 | 2025-04-23 13:56 | 2025-05-16 | 0.49581 | -762.6232 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-09 09:28 | 137.6056 | [8 empty] | FOR AUDIT |  | 2025-04-25 09:28 | 65.6056 | 2025-04-10 | 2025-06-30 | [8 empty] | Y | 2025-04-07 | [6 empty] | 2025-04-07 | TLN-527462 | 0 | 14.3944 | 0 | 14.3944 | 0.49581 | 111.6056 |  | 4.34 | 4.34 | 1.8601 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020421060', |  |  |  | 7.6222 |  | Jenneth Madrid
2025-04-08 | 2025-04-02 |  | BIZ | X24124844490 | JEROME CASIO DIANO | MOLINO, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 10.93 | 20.11 | 26 | NEW | 163905.52 | 17280.28 |  | 0% | 2025-03-27 | 2025-04-03 14:58 | 2025-04-01 |  | 2025-04-30 |  | 34 | 26.3764 | -45777 | 2025-04-14 18:35 | 2025-04-23 13:56 | 2025-05-16 | 1.1711 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-05-02 | [6 empty] | 2025-04-08 | TLN-526906 | 0 | 34 | 0 | 34 | 1.1711 | 92 |  | 4.34 | 4.34 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124844490', |  |  |  | 7.6236 |  | Jenneth Madrid
2025-04-08 | 2025-03-31 | Y | BIZ | X24062169287 | ALFAMART TRADING PHILIPPINES, INC. | MADRID, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 10.9328 | 34.7 | 28 | NEW | 229386.46 | 29815.7 |  | 0% | 2025-03-27 12:42 | 2025-04-03 14:52 | 2025-03-28 | 2025-04-29 | 2025-04-30 |  | 33.4708 | 26.3806 | -45777 | 2025-04-15 07:17 | 2025-04-24 02:38 | 2025-05-16 12:42 | 1.1529 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-04-28 | [6 empty] | 2025-04-08 | TLN-522397 | 0 | 33.4708 | 0 | 33.4708 | 1.1529 | 92 |  | 4.3218 | 4.3218 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24062169287', | ME155242 |  |  | 7.0903 |  | Isan Carlo Lazaro
2025-04-08 | 2025-04-02 |  | BIZ | X25030941835 | YIQUN YANG | MANILA DOCTOR VILL, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | done retirement |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 89.25 | 123.28 | - | TERMINATION | 101812.28 | 105926 |  | 0% | 2025-03-28 | 2025-04-03 15:06 | 2025-04-01 |  |  |  | -45744 | -45750.6292 | 0 | 2025-04-10 02:47 | 2025-04-17 09:55 | 2025-05-17 | -2128.8554 | 0 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45744 | 0 | -45744 | -2128.8554 | 0 |  | 5.8173 | 5.8173 | 0 | 112 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030941835', |  |  |  | 6.6292 |  | Isan Carlo Lazaro
2025-04-07 | 2025-04-02 |  | HMB | X25030955124 | TIN PHO LIM | CADENA DE AMOR, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 104.55 | 131.86 | 150 | MODIFICATION | 686686.21 | 113331.9 |  | 0% | 2025-03-28 | 2025-04-03 15:07 | 2025-04-01 | 2025-05-31 | 2025-05-31 |  | 64 | 57.3701 | -45808 | 2025-04-16 10:42 | 2025-04-25 10:22 | 2025-05-17 | 2.1385 | -763.4667 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | FOR AUDIT |  | 2025-06-15 | 24 | 2025-05-31 | 2025-07-09 | [8 empty] | Y | 2025-05-29 | [6 empty] | 2025-04-07 | CS9-8089,TLN-527524,TLN-060608 | 0 | 64 | 0 | 64 | 2.1385 | 61 |  | 4.1767 | 4.1767 | 1.0167 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030955124', |  |  |  | 6.6299 |  | Isan Carlo Lazaro
2025-04-07 | 2025-04-02 |  | HMB | X25010271934 | DANILO FLORES TARRIELA | BATANGAS SOUTH, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 74.99 | 122.97 | 80 | MODIFICATION | 535624.28 | 105279.94 |  | 0% | 2025-03-28 | 2025-04-03 15:07 | 2025-04-01 | 2025-06-11 | 2025-06-11 |  | 75 | 68.3701 | -45819 | 2025-04-17 08:17 | 2025-04-26 13:41 | 2025-05-17 | 2.4095 | -763.65 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-10 | 76 | [8 empty] | FOR AUDIT |  | 2025-06-26 | 11 | 2025-06-11 | 2025-07-07 | [8 empty] | Y | 2025-06-04 | [6 empty] | 2025-04-07 | CS9-8088,TLN-527142 | 0 | 75 | 0 | 75 | 2.4095 | 50 |  | 4.0158 | 4.0158 | 0.83333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010271934', |  |  |  | 6.6299 |  | Jenneth Madrid
2025-04-03 | 2025-04-02 | Y | BIZ | X25010350650 | ICE & WATER STOP, INC. | SAN ANTONIO VALLEY 1, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 120.88 | 225.66 | 456 | MODIFICATION | 1392661.74 | 194181.44 |  | 0% | 2025-03-28 | 2025-04-02 10:21 | 2025-04-01 |  | 2025-04-16 09:45 |  | 19.4062 | 13.975 | -45763.4062 | 2025-04-13 22:15 | 2025-04-22 05:47 | 2025-05-17 | 0.7304 | -762.7234 | 28 | 26 | 19.927 | 25.2409 | 16.927 | 60 | 57 | 52 | 2025-06-15 09:45 | 131.5938 | [8 empty] | FOR AUDIT |  | 2025-05-01 09:45 | -3.4062 | 2025-04-16 | 2025-04-28 | [8 empty] | Y | 2025-04-16 | [8 empty] | 0 | 19.4062 | 0 | 19.4062 | 0.7304 | 105.5938 |  | 4.7047 | 4.7047 | 1.7599 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010350650', |  |  |  | 5.4313 |  | RONILO GANGE JR.
2025-04-08 | 2025-04-02 |  | BIZ | X25030745343 | OLIVAREZ REALTY CORPORATION | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 36.78 | 120.71 | 97 | NEW | 492628.15 | 103760.22 | 8686.77 | 8.372% | 2025-03-28 | 2025-04-03 15:03 | 2025-04-01 | 2025-06-28 | 2025-06-28 |  | 92 | 85.3729 | -45836 | 2025-04-17 08:17 | 2025-04-26 13:41 | 2025-05-17 | 2.9557 | -763.9333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | FOR AUDIT |  | 2025-07-13 | 15 | 2025-06-28 | 2025-07-28 | [8 empty] | Y | 2025-06-27 | [6 empty] | N/A |  | 0 | 92 | 0 | 92 | 2.9557 | 33 |  | 4.0158 | 4.0158 | 0.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030745343 ', |  |  |  | 6.6271 |  | RONILO GANGE JR.
2025-04-15 | 2025-04-02 |  | BIZ | X25030933327 | JHOY MEDINA MATILLA | ROSAL, T.S. CRUZ SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 18.52 | 62 | - | TERMINATION | 62981.53 | 53438.1 |  | 0% | 2025-03-28 | 2025-04-03 15:04 | 2025-04-01 |  |  |  | -45744 | -45750.6278 | 0 | 2025-04-09 14:40 | 2025-04-16 18:34 | 2025-05-17 | -2197.7009 | 0 | 23 | 20 | 15.6109 | 19.7738 | 12.6109 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A |  | 0 | -45744 | 0 | -45744 | -2197.7009 | 0 |  | 6.0054 | 6.0054 | 0 | 112 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030933327', |  |  |  | 6.6278 |  | RONILO GANGE JR.
2025-04-14 | 2025-04-02 |  | BIZ | X24114372683 | ALEXANDER SY CO JR | ALABANG-ZAPOTE, TALON I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 75.79 | 149.59 | 153 | NEW | 799778.14 | 111130.79 |  | 0% | 2025-03-28 | 2025-04-03 15:02 | 2025-04-01 |  | 2025-05-22 |  | 55 | 48.3736 | -45799 | 2025-04-16 10:42 | 2025-04-25 10:22 | 2025-05-17 | 1.8377 | -763.3167 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [10 empty] | Y | 2025-05-22 | [6 empty] | 2025-04-14 | CV8-8084 | 0 | 55 | 0 | 55 | 1.8377 | 70 |  | 4.1767 | 4.1767 | 1.1667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24114372683', |  |  |  | 6.6264 |  | Isan Carlo Lazaro
2025-04-10 | 2025-04-08 |  | HMB | X24124706560 | A2Z REAL ESTATE CORPORATION | MADRIGAL, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ( POLE ERECTION & POLE DRESSING ) ENERGIZATION 8-9-25 |  | AVECO | SCHED | Ronilo Gange Jr. | 80.7057 | 222.71 | 84.4 | MODIFICATION | 706651.19 | 123699.74 |  | 0% | 2025-03-31 14:39 | 2025-04-10 06:43 | 2025-04-04 |  |  |  | -45747.6104 | -45757.2799 | 0 | 2025-04-21 13:41 | 2025-04-30 23:02 | 2025-05-20 14:39 | -1432.0155 | 0 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-10 | CT9-8083,CU9-1834-S | 0 | -45747.6104 | 0 | -45747.6104 | -1432.0155 | 0 |  | 3.7998 | 3.7998 | 0 | 108.3896 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24124706560', |  |  |  | 9.6694 |  | Isan Carlo Lazaro
2025-04-21 | 2025-04-08 | Y | BIZ | X25010222514 | PHILIPPINE SEVEN CORPORATION | MAHOGANY, VICTORIA HOMES-PEARL HTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 11.6428 | 24.54 | 38 | NEW | 216246.34 | 21087.55 |  | 0% | 2025-03-31 14:45 | 2025-04-10 06:41 | 2025-04-04 |  | 2025-04-14 |  | 13.3854 | 3.7215 | -45761 | 2025-04-19 09:20 | 2025-04-28 04:41 | 2025-05-20 14:45 | 0.46105 | -762.6833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-13 | 134 | [8 empty] | ON GOING MAT RETURN |  | 2025-04-29 | 10 | 2025-04-04 | 2025-05-09 | [6 empty] | 2025-08-14 | NVP | [8 empty] | 2025-04-21 | CP8-0235,TLN-527167 | 0 | 13.3854 | 0 | 13.3854 | 0.46105 | 108 |  | 4.1811 | 4.1811 | 1.8 |  | REV |  | 2025-08-14 | 2037.72 | NTC ISSUED | 2025-08-15 |  | 11 |  |  |  | 'X25010222514', |  |  |  | 9.6639 |  | Isan Carlo Lazaro
2025-04-21 | 2025-04-08 |  | BIZ | X25010234795 | HERLENE SANTOS TAN | R.M.T. INDUSTRIAL COMPLEX, R.M.T. INDUSTRIAL COMPLEX, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.1833 | 20.75 | 8 | NEW | 165644.55 | 17825.95 |  | 0% | 2025-03-31 14:49 | 2025-04-10 06:44 | 2025-04-04 |  | 2025-05-06 08:24 |  | 35.7326 | 26.0694 | -45783.35 | 2025-04-19 09:24 | 2025-04-28 04:45 | 2025-05-20 14:49 | 1.2308 | -763.0558 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-05 08:24 | 111.65 | [8 empty] | NO COC |  | 2025-05-21 08:24 | #VALUE! | [18 empty] | 2025-04-21 | TLN-527179 | 0 | 35.7326 | 0 | 35.7326 | 1.2308 | 85.65 |  | 4.181 | 4.181 | 1.4275 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010234795', |  |  |  | 9.6632 |  | Isan Carlo Lazaro
2025-04-21 | 2025-04-08 |  | BIZ | X25010341987 | THE PLASTIC FLAMINGO PHILIPPINES INC. | R.M.T. INDUSTRIAL COMPLEX, R.M.T. INDUSTRIAL COMPLEX, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 123.1366 | 255.47 | 695 | MODIFICATION | 2063465.67 | 219675.44 |  | 0% | 2025-03-31 14:52 | 2025-04-10 06:45 | 2025-04-04 | 2025-05-07 | 2025-05-07 09:13 |  | 36.7646 | 27.1028 | -45784.384 | 2025-04-15 20:18 | 2025-04-23 16:57 | 2025-05-20 14:52 | 1.5128 | -763.0731 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 2025-07-06 09:13 | 110.616 | With scheduled PAI | Y |  |  |  | 2025-05-02 | 28 | 2025-05-30 | FOR AUDIT |  | 2025-05-22 09:13 | 45.616 | 2025-05-07 | 2025-07-07 | [8 empty] | Y | 2025-05-28 | [6 empty] | N/A |  | 0 | 36.7646 | 28 | 8.7646 | 0.36065 | 84.616 |  | 4.9947 | 4.9947 | 1.4103 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25010341987', |  |  |  | 9.6618 |  | RONILO GANGE JR.
2025-04-14 | 2025-04-08 |  | CBG | X24051959665 | PHINMA PROPERTY HOLDINGS CORPORATION | VILLONGCO, VILLONGCO, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 85.4139 | 85.41 | 51 | NEW | 465236.61 | 73415.59 |  | 0% | 2025-03-31 15:02 | 2025-04-10 06:46 | 2025-04-04 | 2025-05-16 | 2025-05-20 |  | 49.3736 | 39.7181 | -45797 | 2025-04-19 22:15 | 2025-04-28 20:58 | 2025-05-20 15:02 | 1.6605 | -763.2833 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-07-19 | 98 | [8 empty] | FOR AUDIT |  | 2025-06-04 | 33 | 2025-05-16 | 2025-07-07 | [8 empty] | Y | 2025-05-16 | [6 empty] | #N/A | #N/A | 0 | 49.3736 | 0 | 49.3736 | 1.6605 | 72 |  | 4.082 | 4.082 | 1.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | X24051959665', |  |  |  | 9.6556 |  | RONILO GANGE JR.
2025-04-10 | 2025-04-08 |  | HMB | R23852881 | PALAGANAS, GRACE B, HMB | APITONG, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 119.1799 | 287.3 | - | RELOC | 411270.88 | 112337.44 |  | 0% | 2025-03-31 16:22 | 2025-04-08 15:55 | 2025-04-04 |  |  |  | -45747.6819 | -45755.6632 | 0 | 2025-04-14 02:07 | 2025-04-21 11:07 | 2025-05-20 16:22 | -2091.3226 | 0 | 28 | 20 | 16.4063 | 20.7813 | 13.4063 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-04-10 | CU9-8092,CU9-8093,TLN-194837 | 0 | -45747.6819 | 0 | -45747.6819 | -2091.3226 | 0 |  | 5.546 | 5.546 | 0 | 108.3181 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'R23852881', |  |  |  | 7.9813 |  | RONILO GANGE JR.
2025-04-10 | 2025-04-08 |  | HMB | X25020497025 | CITY GOVERNMENT OF PARANAQUE | COL. E. DE LEON, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 55.8826 | 146.94 | 91 | NEW | 634279.83 | 72144.73 |  | 0% | 2025-04-01 01:17 | 2025-04-08 15:54 | 2025-04-04 |  | 2025-05-09 |  | 37.9465 | 30.3375 | -45786 | 2025-04-21 09:34 | 2025-04-30 14:58 | 2025-05-21 01:17 | 1.2191 | -763.1 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-07-08 | 109 | With scheduled PAI | Y | Y |  |  | 2025-04-26 | 10 | 2025-05-06 | NO COC |  | 2025-05-24 | #VALUE! | [10 empty] | Y | 2025-05-07 | [7 empty] | A5-0565,A5-8083,TLN-527761 | 0 | 37.9465 | 10 | 27.9465 | 0.89783 | 83 | 1.2191 | 3.8856 | 2.6665 | 1.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020497025', |  |  |  | 7.609 |  | RONILO GANGE JR.
2025-04-21 | 2025-04-08 |  | BIZ | X25030779813 | SUYOSA CORP, | R.M.T. INDUSTRIAL COMPLEX, R.M.T. INDUSTRIAL COMPLEX, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 90.73 | 92.27 | - | TERMINATION | 79917.76 | 79289.36 |  | 0% | 2025-04-01 13:46 | 2025-04-10 08:09 | 2025-04-04 |  | 2025-05-06 08:23 |  | 34.7757 | 26.0097 | -45783.3493 | 2025-04-14 04:26 | 2025-04-21 08:20 | 2025-05-21 13:46 | 1.6707 | -763.0558 | 23 | 20 | 15.6109 | 19.7738 | 12.6109 | 60 | 57 | 52 | 2025-07-05 08:23 | 111.6507 | [8 empty] | NO COC | conj. X25010234795 | 2025-05-21 08:23 | #VALUE! | [10 empty] | Y | 2025-05-02 | [6 empty] | N/A |  | 0 | 34.7757 | 0 | 34.7757 | 1.6707 | 85.6507 |  | 5.7857 | 5.7857 | 1.4275 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030779813', |  |  |  | 8.766 |  | Jenneth Madrid
2025-04-21 | 2025-04-08 |  | HMB | X25020687800 | STEVE LAURENCE UY CHAN | CAMBRIDGE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 39.7285 | 114.07 | 80 | NEW | 391425.78 | 44523.53 |  | 0% | 2025-04-02 10:32 | 2025-04-10 08:17 | 2025-04-04 |  | 2025-05-17 10:04 |  | 44.9806 | 37.0743 | -45794.4194 | 2025-04-22 18:49 | 2025-05-02 00:13 | 2025-05-22 10:32 | 1.4451 | -763.2403 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-07-16 10:04 | 100.5806 | With scheduled PAI | Y | Y |  |  | 2025-05-08 | 7 | 2025-05-15 | NO COC |  | 2025-06-01 10:04 | #VALUE! | [10 empty] | Y | 2025-05-14 | [6 empty] | 2025-04-21 | CX8-8140,TLN-521448 | 0 | 44.9806 | 7 | 37.9806 | 1.2202 | 74.5806 | 1.4451 | 3.8411 | 2.396 | 1.243 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020687800', |  |  |  | 7.9062 |  | Jenneth Madrid
2025-04-10 | 2025-04-08 | Y | BIZ | X25020551884 | VAS SOLUTIONS INC. | PHASE 2 ACCESS ROAD, AMVEL COMMERCIAL COMPLEX, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 14.3228 | 32.8 | 42 | NEW | 364286.5 | 28180.26 |  | 0% | 2025-04-02 12:59 | 2025-04-08 15:50 | 2025-04-04 |  | 2025-05-12 09:03 |  | 39.8361 | 33.7174 | -45789.3771 | 2025-04-21 07:34 | 2025-04-30 02:55 | 2025-05-22 12:59 | 1.3721 | -763.1563 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-11 09:03 | 105.6229 | [8 empty] | NO COC |  | 2025-05-27 09:03 | #VALUE! | [10 empty] | Y | 2025-05-09 | [6 empty] | #N/A | #N/A | 0 | 39.8361 | 0 | 39.8361 | 1.3721 | 79.6229 |  | 4.1147 | 4.1147 | 1.327 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25020551884', |  |  |  | 6.1187 |  | Jenneth Madrid
2025-04-11 | 2025-04-08 |  | BIZ | X25030745130 | ENRIQUE FELIPE OLIVA GUSTILO | GNG. ELSIE GACHES, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 82.04 | 133.58 | 517 | NEW | 1246883.75 | 114887.14 |  | 0% | 2025-04-02 13:01 | 2025-04-10 08:13 | 2025-04-04 |  | 2025-05-17 10:10 |  | 44.8812 | 37.0812 | -45794.4236 | 2025-04-17 09:52 | 2025-04-25 04:13 | 2025-05-22 13:01 | 1.8838 | -763.2404 | 26 | 23 | 17.8685 | 22.6335 | 14.8685 | 60 | 57 | 52 | 2025-07-16 10:10 | 100.5764 | With scheduled PAI | Y | Y |  |  | 2025-05-08 | 8 | 2025-05-16 | FOR AUDIT |  | 2025-06-01 10:10 | 28.5764 | 2025-05-17 | 2025-06-30 | [8 empty] | Y | 2025-05-14 | [6 empty] | 2025-04-11 | TLN-527459 | 0 | 44.8812 | 8 | 36.8812 | 1.548 | 74.5764 | 1.8838 | 5.014 | 3.1302 | 1.2429 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030745130', |  |  |  | 7.8 |  | Jenneth Madrid
2025-04-11 | 2025-04-08 |  | BIZ | X25030745122 | ENRIQUE FELIPE OLIVA GUSTILO | GNG. ELSIE GACHES, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 140.9845 | 267.49 | 517 | NEW | 603710.94 | 195261.37 |  | 0% | 2025-04-02 13:12 | 2025-04-10 08:11 | 2025-04-04 |  | 2025-05-17 10:08 |  | 44.8722 | 37.0813 | -45794.4222 | 2025-04-17 18:38 | 2025-04-25 15:17 | 2025-05-22 13:12 | 1.8465 | -763.2404 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 2025-07-16 10:08 | 100.5778 | With scheduled PAI | Y | Y |  |  | 2025-05-08 | 8 | 2025-05-16 | NO COC | conj. X25030745130 | 2025-06-01 10:08 | #VALUE! | [10 empty] | Y | 2025-05-14 | [6 empty] | 2025-04-11 | DW1-8056,CW9-8067,CW9-8068 | 0 | 44.8722 | 8 | 36.8722 | 1.5173 | 74.5778 | 1.8465 | 4.9153 | 3.0688 | 1.243 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25030745122', |  |  |  | 7.791 |  | Jenneth Madrid
2025-04-21 | 2025-04-08 |  | BIZ | X24104306412 | DON ANTONIO ROXAS CHUA FOUNDATION. INC. | A.R. CHUA, PACIFIC VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 43.4902 | 71.34 | 32 | NEW | 320989.74 | 61295.49 |  | 0% | 2025-04-02 14:21 | 2025-04-10 08:15 | 2025-04-04 |  | 2025-06-14 10:39 |  | 72.8458 | 65.1 | -45822.4437 | 2025-04-22 16:24 | 2025-05-01 20:09 | 2025-05-22 14:21 | 2.3666 | -763.7074 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-08-13 10:39 | 72.5563 | [8 empty] | NO COC |  | 2025-06-29 10:39 | #VALUE! | [10 empty] | Y | 2025-06-13 | [6 empty] | 2025-04-21 | DV1-8083,TLN-526399 | 0 | 72.8458 | 0 | 72.8458 | 2.3666 | 46.5563 |  | 3.8791 | 3.8791 | 0.77594 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24104306412', |  |  |  | 7.7458 |  | Jenneth Madrid
2025-05-22 | 2025-04-08 |  | CBG | X24072739034 | DITO TELECOMMUNITY CORPORATION | NARRA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 13.0428 | 24.19 | 31 | NEW | 211117.13 | 20380.93 |  | 0% | 2025-04-02 16:24 | 2025-04-10 08:14 | 2025-04-04 |  | 2025-04-30 |  | 27.3167 | 19.6569 | -45777 | 2025-04-21 10:59 | 2025-04-30 06:20 | 2025-05-22 16:24 | 0.94091 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | NO COC |  | 2025-05-15 | #VALUE! | [10 empty] | Y | 2025-05-02 | [6 empty] | N/A | N/A | 0 | 27.3167 | 0 | 27.3167 | 0.94091 | 92 |  | 4.1098 | 4.1098 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X24072739034', |  |  |  | 7.6597 |  | Isan Carlo Lazaro
2025-05-22 | 2025-04-08 |  | BIZ | X25031001944 | CROWN-PHILS, | GEN. EMILIO AGUINALDO, PANAPAAN VII, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 15.92 | 18.3 | - | TERMINATION | 22049.65 | 15732.43 |  | 0% | 2025-04-02 17:56 | 2025-04-10 08:16 | 2025-04-04 |  | 2025-05-02 |  | 29.2528 | 21.6556 | -45779 | 2025-04-14 17:56 | 2025-04-21 17:56 | 2025-05-22 17:56 | 1.4626 | -762.9833 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-01 | 116 | [8 empty] | NO COC |  | 2025-05-17 | #VALUE! | [18 empty] | N/A | N/A | 0 | 29.2528 | 0 | 29.2528 | 1.4626 | 90 |  | 5.9626 | 5.9626 | 1.5 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 |  |  |  | 'X25031001944', |  |  |  | 7.5972 |  | Isan Carlo Lazaro
2025-04-21 | 2025-04-10 |  | HMB | X25030817116 | LLOYD ELGENE ASUNCION APOSTOL | LINDENWOOD RESIDENCES, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.4828 | 35.4 | 84 | MODIFICATION | 274127.23 | 30442.88 |  | 0% | 2025-04-03 09:38 | 2025-04-14 15:03 | 2025-04-10 |  | 2025-04-14 |  | 10.5986 | -0.62708 | -45761 | 2025-04-21 11:25 | 2025-04-30 02:18 | 2025-05-23 09:38 | 0.37719 | -762.6833 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-06-13 | 134 | [8 empty] | FOR AUDIT |  | 2025-04-29 | 7 | 2025-04-14 | 2025-05-06 | [16 empty] | N/A | #N/A | 0 | 10.5986 | 0 | 10.5986 | 0.37719 | 108 |  | 4.2207 | 4.2207 | 1.8 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 11.2257 |  | Isan Carlo Lazaro
2025-05-22 | 2025-04-11 |  | HMB | X24103952853 | ANITA JALANDONI FERRER | BLOCK 19, CUEVASVILLE SUBD., BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 40.0187 | 200.9 | 5 | NEW | 254891.8 | 40502.96 |  | 0% | 2025-04-03 15:52 | 2025-04-14 06:26 | 2025-04-10 |  |  |  | -45750.6611 | -45761.2681 | 0 | 2025-04-24 20:50 | 2025-05-04 07:45 | 2025-05-23 15:52 | -1417.4884 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-23 | CR8-8024,CR8-8025 | 0 | -45750.6611 | 0 | -45750.6611 | -1417.4884 | 0 |  | 3.6665 | 3.6665 | 0 | 105.3389 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 10.6069 |  | Isan Carlo Lazaro
2025-04-24 | 2025-04-11 |  | HMB | X24083326772 | JONALYN PICAHE | CATTLEYA, SOUTH GREENPARK SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | WITH DIGGING PROBLEM 3RD PARTY |  | VJC | SCHED | Jenneth Madrid | 35.1895 | 116.03 | 40 | MODIFICATION | 285332.49 | 32433.24 |  | 0% | 2025-04-03 23:27 | 2025-04-14 15:07 | 2025-04-10 |  |  |  | -45750.9771 | -45761.6299 | 0 | 2025-04-25 04:25 | 2025-05-04 15:20 | 2025-05-23 23:27 | -1417.4982 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | Third party concern (Other than the applicant) | Y | Y |  |  | 2025-06-09 | 31 | 2025-07-10 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-04-21 | TLN-527934 | 0 | -45750.9771 | 31 | -45781.9771 | -1418.4587 | 0 |  | 3.6567 | 3.6567 | 0 | 105.0229 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 10.6528 |  | Isan Carlo Lazaro
2025-04-10 | 2025-04-11 | Y | HMB | X25030992057 | ANTONITA MOYNIHAN DAYRIT | YELLOW STONE, SOUTH GREEN PARK SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 160.5779 | 440.47 | 85 | NEW | 873159.92 | 175896.21 |  | 0% | 2025-04-03 23:29 | 2025-04-08 17:36 | 2025-04-10 |  | 2025-04-30 |  | 26.0215 | 21.2667 | -45777 | 2025-04-26 00:13 | 2025-05-05 16:25 | 2025-05-23 23:29 | 0.77969 | -762.95 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 2025-06-29 | 118 | Third party concern (Other than the applicant) | Y | Y |  |  | 2025-04-14 | 9 | 2025-04-23 | NO COC |  | 2025-05-15 | #VALUE! | [18 empty] | 2025-04-15 | DX1-8104,DX1-8105,DX1-8106,DX1-8107,TLN-526825 | 0 | 26.0215 | 9 | 17.0215 | 0.51002 | 92 | 0.77969 | 3.5363 | 2.7566 | 1.5333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 4.7549 |  | Isan Carlo Lazaro
2025-04-24 | 2025-04-11 |  | CBG | X24114461949 | DITO TELECOMMUNITY CORPORATION | BLOCK 1, AGUAHAN VILLAGE, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 235.392 | 2034.6 | 31 | NEW | 1960706.97 | 921156.78 |  | 0% | 2025-04-04 08:23 | 2025-04-14 15:12 | 2025-04-10 |  |  |  | -45751.3493 | -45761.6333 | 0 | 2025-04-30 19:48 | 2025-05-11 16:27 | 2025-05-24 08:23 | -1164.1177 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | #N/A | 0 | -45751.3493 | 0 | -45751.3493 | -1164.1177 | 0 |  | 2.9936 | 2.9936 | 0 | 104.6507 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 10.284 |  | Isan Carlo Lazaro
2025-04-22 | 2025-04-08 | Y | CBG | X24104075973 | TOTAL GAMEZONE XTREME INCORPORATED | WEST SERVICE, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 83.7633 | 133.31 | 2530 | MODIFICATION | 1070121.16 | 112876.91 |  | 0% | 2025-04-04 15:13 | 2025-04-04 15:13 | 2025-04-08 |  | 2025-04-11 |  | 6.366 | 6.366 | -45758 | 2025-04-17 18:00 | 2025-04-25 01:08 | 2025-05-24 15:13 | 0.29626 | -762.6333 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 2025-06-10 | 137 | [8 empty] | FOR AUDIT |  | 2025-04-26 | 19 | 2025-04-11 | 2025-05-15 | [16 empty] | N/A | #N/A | 0 | 6.366 | 0 | 6.366 | 0.29626 | 111 |  | 5.462 | 5.462 | 1.85 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 0 |  | RONILO GANGE JR.
2025-04-23 | 2025-04-11 |  | HMB | X25010307845 | REYEL CRUZ SANTOS | GALAXY, BRICKTOWN PH 3 SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 179.0775 | 569.93 | 36 | MODIFICATION | 961178.65 | 221450.98 |  | 0% | 2025-04-04 17:51 | 2025-04-14 15:10 | 2025-04-10 |  |  |  | -45751.7438 | -45761.6319 | 0 | 2025-04-29 13:53 | 2025-05-10 00:02 | 2025-05-24 17:51 | -1232.7553 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45751.7438 | 34 | -45785.7438 | -1233.6714 | 0 |  | 3.1594 | 3.1594 | 0 | 104.2562 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 9.8882 |  | RONILO GANGE JR.
2025-04-15 | 2025-04-10 |  | HMB | X24083428939 | ROBERTO C VASQUEZ | PRES. AGUINALDO, TEOVILLE SUBD EAST, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 203.7934 | 237.06 | 55 | MODIFICATION | 722190.92 | 202879.54 |  | 0% | 2025-04-04 17:52 | 2025-04-14 15:37 | 2025-04-10 | 2025-05-28 | 2025-05-28 09:51 |  | 53.666 | 43.7597 | -45805.4104 | 2025-04-25 16:54 | 2025-05-05 02:15 | 2025-05-24 17:52 | 1.6799 | -763.4235 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 2025-07-27 09:51 | 89.5896 | [8 empty] | FOR AUDIT |  | 2025-06-12 09:51 | 29.5896 | 2025-05-28 | 2025-07-12 | [16 empty] | 2025-04-25 | CT9-8081,CT9-8082,TLN-52647 | 0 | 53.666 | 0 | 53.666 | 1.6799 | 63.5896 |  | 3.6704 | 3.6704 | 1.0598 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 9.9062 |  | RONILO GANGE JR.
2025-04-23 | 2025-04-11 |  | HMB | X25010249268 | SITIO SUNRISE NEIGHBORHOOD ASS | GALAXY, BRICKTOWN PH 3 SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For Energize |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 114.5162 | 307.16 | 90 | NEW | 631365.34 | 128587.98 |  | 0% | 2025-04-04 17:53 | 2025-04-14 15:09 | 2025-04-10 |  |  |  | -45751.7451 | -45761.6312 | 0 | 2025-04-26 06:21 | 2025-05-05 19:16 | 2025-05-24 17:53 | -1399.4651 | 0 | 30 | 34 | 24.5192 | 31.0577 | 21.5192 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-04-21 | TLN-530015 | 0 | -45751.7451 | 34 | -45785.7451 | -1400.5051 | 0 |  | 3.5866 | 3.5866 | 0 | 104.2549 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 9.8861 |  | RONILO GANGE JR.
2025-04-21 | 2025-04-11 | Y | HMB | X25030863021 | S3A UNITED INC. | PACIFIC AVE, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 14.3728 | 50.27 | 133.5 | NEW | 395842.01 | 43192.67 |  | 0% | 2025-04-04 17:54 | 2025-04-14 | 2025-04-10 | 2025-05-05 | 2025-05-05 |  | 30.2542 | 21 | -45782 | 2025-04-22 02:02 | 2025-04-30 12:12 | 2025-05-24 17:54 | 1.1156 | -763.0333 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-07-04 | 113 | [8 empty] | NO COC |  | 2025-05-20 | #VALUE! | [18 empty] | 2025-04-25 | CS7-8169,TLN-527890 | 0 | 30.2542 | 0 | 30.2542 | 1.1156 | 87 |  | 4.3237 | 4.3237 | 1.45 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 9.2542 |  | RONILO GANGE JR.
2025-04-25 | 2025-04-11 | Y | HMB | X25030881259 | HEIDELBERG BORJA CRUZ | HERRERA ST., TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 77.1231 | 169.2 | 15 | NEW | 375527.67 | 77719.68 |  | 0% | 2025-04-07 09:18 | 2025-04-15 13:00 | 2025-04-10 |  | 2025-06-28 |  | 81.6125 | 73.4583 | -45836 | 2025-04-28 14:16 | 2025-05-08 01:11 | 2025-05-27 09:18 | 2.5286 | -763.9333 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | NO COC |  | 2025-07-13 | #VALUE! | [18 empty] | N/A | #N/A | 0 | 81.6125 | 0 | 81.6125 | 2.5286 | 33 |  | 3.551 | 3.551 | 0.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 8.1542 |  | Jenneth Madrid
2025-04-24 | 2025-04-10 |  | BIZ | X25030890010 | STO. CRISTO PROPERTIES AND HOLDINGS CORP. | PASCUAL, PARANAQUE GREEN HEIGHTS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 7.67 | 8.27 | - | TERMINATION | 18349.78 | 7105.76 |  | 0% | 2025-04-07 13:24 | 2025-04-15 12:59 | 2025-04-10 |  | 2025-08-14 |  | 128.4417 | 120.459 | -45883 | 2025-04-19 13:24 | 2025-04-26 13:24 | 2025-05-27 13:24 | 6.4221 | -764.7167 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-10-13 | 12 | [10 empty] | 2025-08-29 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 128.4417 | 0 | 128.4417 | 6.4221 | -14 |  | 5.7221 | 5.7221 | -0.23333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.9826 |  | Jenneth Madrid
2025-04-21 | 2025-04-11 |  | BIZ | X25031039951 | YEUNG MARINE PRODUCTS, INC. | D. CAMPOS, DON GALO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 105.6807 | 187.75 | - | TERMINATION | 141776.26 | 161328.84 |  | 0% | 2025-04-07 13:27 | 2025-04-15 12:55 | 2025-04-10 | 2025-08-09 | 2025-08-09 08:14 |  | 123.7826 | 115.8049 | -45878.3431 | 2025-04-20 16:14 | 2025-04-27 23:22 | 2025-05-27 13:27 | 5.7607 | -764.6391 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 2025-10-08 08:14 | 16.6569 | [8 empty] | FOR AUDIT |  | 2025-08-24 08:14 | -9.3431 | 2025-08-09 | 2025-08-15 | [16 empty] | #N/A | #N/A | 0 | 123.7826 | 0 | 123.7826 | 5.7607 | -9.3431 |  | 5.3258 | 5.3258 | -0.15572 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.9778 |  | Jenneth Madrid
2025-04-24 | 2025-04-11 |  | BIZ | X25031039757 | R & G CONSTRUCTION DEVELOPMENT | DR. A. SANTOS, SEACOM CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 16.71 | 36.84 | - | TERMINATION | 34903.08 | 31748.35 |  | 0% | 2025-04-07 13:29 | 2025-04-14 12:10 | 2025-04-10 | 2025-04-22 | 2025-04-22 |  | 14.4382 | 7.4931 | -45769 | 2025-04-19 13:29 | 2025-04-26 13:29 | 2025-05-27 13:29 | 0.72191 | -762.8167 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | FOR AUDIT |  | 2025-05-07 | 64 | 2025-04-22 | 2025-07-10 | [16 empty] | 2025-04-23 | A5-8077,A5-8078,A5-8079,A5-8080,TLN-527409 | 0 | 14.4382 | 0 | 14.4382 | 0.72191 | 100 |  | 5.7219 | 5.7219 | 1.6667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 6.9451 |  | Jenneth Madrid
2025-04-29 | 2025-04-11 |  | BIZ | X25031040315 | FIRST ASSOCIATED MEDICAL DISTRIBUTION CO.,INC., | PHILIP, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 2.04 | 4.94 | - | TERMINATION | 15000.91 | 4244.52 |  | 0% | 2025-04-07 13:31 | 2025-04-15 12:57 | 2025-04-10 | 2025-04-26 | 2025-05-29 15:00 |  | 52.0618 | 44.0854 | -45806.625 | 2025-04-19 13:31 | 2025-04-26 13:31 | 2025-05-27 13:31 | 2.6031 | -763.4438 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-28 15:00 | 88.375 | [8 empty] | FOR AUDIT |  | 2025-06-13 15:00 | 54.375 | 2025-04-26 | 2025-08-07 | [16 empty] | #N/A | #N/A | 0 | 52.0618 | 0 | 52.0618 | 2.6031 | 62.375 |  | 5.7218 | 5.7218 | 1.0396 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.9764 |  | Jenneth Madrid
2025-04-21 | 2025-04-10 |  | BIZ | X25031038391 | DONG FANG JITUAN CORPORATION | BRADCO, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Transfer to VJC |  | VJC | FCOMP | Jenneth Madrid | 39.7234 | 39.72 | - | TERMINATION | 50172.66 | 44676.99 |  | 0% | 2025-04-07 13:34 | 2025-04-10 06:23 | 2025-04-10 |  | 2025-06-04 |  | 57.4347 | 54.734 | -45812 | 2025-04-19 13:34 | 2025-04-26 13:34 | 2025-05-27 13:34 | 2.8717 | -763.5333 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-08-03 | 83 | [8 empty] | NO COC |  | 2025-06-19 | #VALUE! | [10 empty] | Y | 2025-05-30 | [6 empty] | 2025-04-10 | A6-8029,A6-8030,A6-8031,TLN-521988 | 0 | 57.4347 | 0 | 57.4347 | 2.8717 | 57 |  | 5.7217 | 5.7217 | 0.95 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 2.7007 |  | Jenneth Madrid
2025-04-24 | 2025-04-11 |  | BIZ | X25031040438 | CSE DRAGON VENEER CORPORATION, | WEST SERVICE, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 21.1067 | 50.13 | - | TERMINATION | 56610.84 | 43081.66 |  | 0% | 2025-04-07 13:38 | 2025-04-15 12:56 | 2025-04-10 |  | 2025-04-26 |  | 18.4319 | 10.4611 | -45773 | 2025-04-19 13:38 | 2025-04-26 13:38 | 2025-05-27 13:38 | 0.9216 | -762.8833 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-06-25 | 122 | [8 empty] | FOR AUDIT |  | 2025-05-11 | 50 | 2025-04-26 | 2025-06-30 | [16 empty] | N/A | #N/A | 0 | 18.4319 | 0 | 18.4319 | 0.9216 | 96 |  | 5.7216 | 5.7216 | 1.6 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.9708 |  | Jenneth Madrid
2025-04-21 | 2025-04-11 |  | BIZ | X25031040100 | SUNSHINE TRANSPORTATION INCORPORATED, | SANTOS CPD, KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 3.33 | 15.98 | - | TERMINATION | 20762.45 | 13781.96 |  | 0% | 2025-04-07 13:39 | 2025-04-15 12:58 | 2025-04-10 |  |  |  | -45754.5687 | -45762.5403 | 0 | 2025-04-19 13:39 | 2025-04-26 13:39 | 2025-05-27 13:39 | -2287.7284 | 0 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | #N/A | 0 | -45754.5687 | 0 | -45754.5687 | -2287.7284 | 0 |  | 5.7216 | 5.7216 | 0 | 101.4313 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.9715 |  | Jenneth Madrid
2025-04-10 | 2025-04-11 | Y | HMB | X25030992093 | MARCO ANGELO FELIX LIM LOPEZ | YELLOW STONE, SOUTH GREEN PARK SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 1.73 | 4.31 | 31 | MODIFICATION | 20761.28 | 3703.32 |  | 0% | 2025-04-07 13:43 | 2025-04-08 17:38 | 2025-04-10 |  | 2025-04-30 |  | 22.4285 | 21.2653 | -45777 | 2025-04-26 08:18 | 2025-05-05 03:39 | 2025-05-27 13:43 | 0.77254 | -762.95 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-06-29 | 118 | [8 empty] | FOR AUDIT |  | 2025-05-15 | -1 | 2025-04-30 | 2025-05-14 | [16 empty] | 2025-04-24 | DY1-8055,TLN-523487 | 0 | 22.4285 | 0 | 22.4285 | 0.77254 | 92 |  | 3.9414 | 3.9414 | 1.5333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 1.1632 |  | Jenneth Madrid
2025-05-02 | 2025-04-10 |  | BIZ | X25010349367 | FLORANTE CRUZ DEL MUNDO | PRESIDENT'S, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | INSTALL SERVICE DROP 8/21; |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 1.73 | 4.1 | 16 | NEW | 20046.55 | 3522.87 |  | 0% | 2025-04-08 09:38 | 2025-04-15 13:05 | 2025-04-10 |  |  |  | -45755.4014 | -45762.5451 | 0 | 2025-04-27 04:13 | 2025-05-05 23:34 | 2025-05-28 09:38 | -1576.0194 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | #N/A | 0 | -45755.4014 | 0 | -45755.4014 | -1576.0194 | 0 |  | 3.9128 | 3.9128 | 0 | 100.5986 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.1438 |  | Jenneth Madrid
2025-04-25 | 2025-04-10 |  | BIZ | X24114389576 | PYC FOODS CORPORATION | DAANG HARI, ALABANG WEST, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 140.5253 | 366.44 | 324 | NEW | 1571457.38 | 181137.63 |  | 0% | 2025-04-08 10:49 | 2025-04-15 13:10 | 2025-04-10 |  | 2025-04-22 |  | 13.5493 | 6.4514 | -45769 | 2025-04-26 21:06 | 2025-05-05 14:15 | 2025-05-28 10:49 | 0.47423 | -762.8167 | 30 | 28 | 21.4286 | 27.1429 | 18.4286 | 60 | 57 | 52 | 2025-06-21 | 126 | [8 empty] | NO COC |  | 2025-05-07 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 13.5493 | 0 | 13.5493 | 0.47423 | 100 |  | 3.9742 | 3.9742 | 1.6667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.0979 |  | RONILO GANGE JR.
2025-05-22 | 2025-04-11 |  | HMB | X25010311115 | EFRAIM MARONILLA OLAN | MELANIE MARQUEZ, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | digging only |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 114.3957 | 127.86 | 28 | MODIFICATION | 308349.94 | 76260.97 |  | 0% | 2025-04-08 10:59 | 2025-04-15 13:07 | 2025-04-10 |  |  |  | -45755.4576 | -45762.5465 | 0 | 2025-04-29 15:57 | 2025-05-09 02:52 | 2025-05-28 10:59 | -1417.637 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45755.4576 | 0 | -45755.4576 | -1417.637 | 0 |  | 3.5179 | 3.5179 | 0 | 100.5424 | NON-REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.0889 |  | Jenneth Madrid
2025-04-28 | 2025-04-15 |  | BIZ | X25020394464 | PINESBEL MFG. & TRADING CORP. | BAES, PERPETUAL VILLAGE, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | TECO | Jenneth Madrid | 138.8073 | 287.32 | 765 | MODIFICATION | 2026310.46 | 230313.24 |  | 0% | 2025-04-08 16:52 | 2025-04-15 13:09 | 2025-04-15 | 2025-05-02 | 2025-05-02 07:30 | 2025-07-08 | 23.6097 | 16.7646 | 66.6875 | 2025-04-23 22:18 | 2025-05-01 18:57 | 2025-05-28 16:52 | 0.97152 | 1.1115 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 2025-07-01 07:30 | 115.6875 | [8 empty] | PAID |  | 2025-05-17 07:30 | -4.3125 | 2025-05-02 | 2025-05-13 | 2025-07-01 | ECI | N |  |  |  | 2025-07-04 | NVP | [8 empty] | #N/A | #N/A | 0 | 23.6097 | 0 | 23.6097 | 0.97152 | 89.6875 |  | 4.6621 | 4.6621 | 1.4948 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 6.8451 |  | Jenneth Madrid
2025-04-28 | 2025-04-16 |  | BIZ | X25030854781 | THE LOOK (ASIA) INC. | PERPECTO DR, BAGUMBAYAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 18.1128 | 68.06 | 124 | NEW | 488486 | 58511.06 |  | 0% | 2025-04-08 16:55 | 2025-04-15 13:08 | 2025-04-15 |  | 2025-05-31 |  | 52.2951 | 45.4528 | -45808 | 2025-04-27 04:24 | 2025-05-05 21:52 | 2025-05-28 16:55 | 1.8261 | -763.4667 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | NO COC |  | 2025-06-15 | #VALUE! | [10 empty] | Y | 2025-05-29 | [6 empty] | #N/A | #N/A | 0 | 52.2951 | 0 | 52.2951 | 1.8261 | 61 |  | 3.9561 | 3.9561 | 1.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 6.8424 |  | Jenneth Madrid
2025-04-25 | 2025-04-16 |  | BIZ | X24114426315 | PYC FOODS CORPORATION | DAANG HARI, ALMANZA II, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 8.18 | 9.81 | - | TERMINATION | 21800.53 | 8437.55 |  | 0% | 2025-04-10 10:32 | 2025-04-15 13:11 | 2025-04-15 |  | 2025-05-02 13:31 |  | 22.1243 | 17.0139 | -45779.5632 | 2025-04-22 10:32 | 2025-04-29 10:32 | 2025-05-30 10:32 | 1.1062 | -762.9927 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-01 13:31 | 115.4368 | [8 empty] | NO COC |  | 2025-05-17 13:31 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 22.1243 | 0 | 22.1243 | 1.1062 | 89.4368 |  | 5.5781 | 5.5781 | 1.4906 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 5.1104 |  | Jenneth Madrid
2025-04-25 | 2025-04-16 |  | BIZ | X24114531063 | FRBPRIME INC. | PALMA, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 66.0936 | 162.66 | 47 | NEW | 422919.26 | 72495.74 |  | 0% | 2025-04-10 10:36 | 2025-04-15 13:16 | 2025-04-15 |  | 2025-05-29 08:08 |  | 48.8972 | 43.7861 | -45806.3389 | 2025-05-01 15:34 | 2025-05-11 02:29 | 2025-05-30 10:36 | 1.515 | -763.439 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-07-28 08:08 | 88.6611 | [8 empty] | NO COC |  | 2025-06-13 08:08 | #VALUE! | [10 empty] | Y | 2025-05-29 | [6 empty] | #N/A | #N/A | 0 | 48.8972 | 0 | 48.8972 | 1.515 | 62.6611 |  | 3.4564 | 3.4564 | 1.0444 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 5.1111 |  | Jenneth Madrid
2025-04-30 | 2025-04-15 |  | HMB | X25020623890 | NILO REQUINTA PERFECTO | CONSTELLATION, MOONWALK VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 9.8533 | 11.89 | 33 | MODIFICATION | 143732.4 | 10219.08 |  | 0% | 2025-04-10 10:40 | 2025-04-15 13:16 | 2025-04-15 |  | 2025-06-02 |  | 52.5556 | 47.4472 | -45810 | 2025-04-29 05:15 | 2025-05-08 00:36 | 2025-05-30 10:40 | 1.8102 | -763.5 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-01 | 85 | [8 empty] | NO COC |  | 2025-06-17 | #VALUE! | [10 empty] | Y | 2025-06-02 | [6 empty] | N/A | #N/A | 0 | 52.5556 | 0 | 52.5556 | 1.8102 | 59 |  | 3.8425 | 3.8425 | 0.98333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 5.1083 |  | Jenneth Madrid
2025-04-30 | 2025-04-16 |  | BIZ | X24114545156 | ST. JAMES THE GREAT PARISH FOUNDATION, INC. | IBAAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 44.1961 | 125.53 | 233 | NEW | 855403.32 | 107882.38 |  | 0% | 2025-04-10 15:36 | 2025-04-15 13:14 | 2025-04-15 | 2025-06-13 | 2025-06-13 |  | 63.35 | 58.4486 | -45821 | 2025-04-29 03:47 | 2025-05-07 21:25 | 2025-05-30 15:36 | 2.2091 | -763.6833 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-08-12 | 74 | [8 empty] | FOR AUDIT |  | 2025-06-28 | 20 | 2025-06-13 | 2025-07-18 | [8 empty] | Y | 2025-06-04 | [6 empty] | 2025-04-30 | TLN-527765 | 0 | 63.35 | 0 | 63.35 | 2.2091 | 48 |  | 3.883 | 3.883 | 0.8 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 4.9014 |  | Jenneth Madrid
2025-05-02 | 2025-04-16 | Y | HMB | X25030752071 | MICHAEL G. DAVID | BLOCK 7, DOÑA ROSARIO HEIGHTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 100.0143 | 141.59 | 60 | MODIFICATION | 555158.87 | 129417.11 |  | 0% | 2025-04-10 16:48 | 2025-04-15 13:15 | 2025-04-15 | 2025-06-13 | 2025-06-13 |  | 63.3 | 58.4479 | -45821 | 2025-05-01 01:05 | 2025-05-10 06:29 | 2025-05-30 16:48 | 2.0336 | -763.6833 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-12 | 74 | [8 empty] | FOR AUDIT |  | 2025-06-28 | 11 | 2025-06-13 | 2025-07-09 | [8 empty] | Y | 2025-06-09 | [6 empty] | 2025-04-30 | TLN-526617,TLN-051030 | 0 | 63.3 | 0 | 63.3 | 2.0336 | 48 |  | 3.5757 | 3.5757 | 0.8 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 4.8521 |  | Isan Carlo Lazaro
2025-04-28 | 2025-04-22 | Y | HMB | X25030872408 | CITY GOVERNMENT OF TAGUIG | BLOCK 27, PINAGSAMA PH 2 VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 53.5395 | 164.6 | 173 | NEW | 840107.52 | 73792.22 | 48164.88 | 65.27% | 2025-04-11 07:43 | 2025-04-18 11:00 | 2025-04-19 | 2025-04-28 | 2025-04-28 10:46 |  | 17.1271 | 9.9903 | -45775.4486 | 2025-04-30 18:25 | 2025-05-09 18:05 | 2025-05-31 07:43 | 0.57228 | -762.9241 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-06-27 10:46 | 119.5514 | [8 empty] | FOR AUDIT |  | 2025-05-13 10:46 | 75.5514 | 2025-04-28 | 2025-07-28 | [16 empty] | 2025-05-06 | DX2-8022,TLN-527354,DX2-8023 | 0 | 17.1271 | 0 | 17.1271 | 0.57228 | 93.5514 |  | 3.6982 | 3.6982 | 1.5592 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.1368 |  | Isan Carlo Lazaro
2025-04-21 | 2025-04-22 |  | CBG | X24103988119 | DITO TELECOMMUNITY CORPORATION | ARIAS CPD, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 3.3295 | 22.72 | 31 | NEW | 63373.46 | 19523.93 |  | 0% | 2025-04-11 09:29 | 2025-04-18 11:03 | 2025-04-19 |  | 2025-06-14 10:37 |  | 64.0472 | 56.9819 | -45822.4424 | 2025-04-30 04:04 | 2025-05-08 23:25 | 2025-05-31 09:29 | 2.2061 | -763.7074 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-13 10:37 | 72.5576 | [8 empty] | NO COC |  | 2025-06-29 10:37 | #VALUE! | [10 empty] | Y | 2025-06-05 | [6 empty] | 2025-04-28 | TLN-530039 | 0 | 64.0472 | 0 | 64.0472 | 2.2061 | 46.5576 |  | 3.8097 | 3.8097 | 0.77596 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 7.0653 |  | RONILO GANGE JR.
| 2025-04-22 |  | BIZ | X25020504155 | SHERWILL REALTY CORPORATION | TERESITA DRIVE, TAGUIG BAGUMBAYAN INDL ASS INC, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | TECO | Jenneth Madrid | 23.4895 | 55.51 | 79 | NEW | 474742.63 | 47716.19 |  | 0% | 2025-04-11 12:38 | 2025-04-18 10:59 | 2025-04-19 |  | 2025-05-02 07:28 | 2025-07-08 | 20.7847 | 13.8535 | 66.6889 | 2025-04-30 19:51 | 2025-05-09 18:34 | 2025-05-31 12:38 | 0.69903 | 1.1115 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-07-01 07:28 | 115.6889 | With scheduled PAI | Y | Y |  |  | 2025-04-25 | 5 | 2025-04-30 | PAID |  | 2025-05-17 07:28 | 12.6889 | 2025-05-02 | 2025-05-30 | 2025-06-12 | ECI | N |  |  |  | 2025-06-28 | NVP | [8 empty] | 2025-04-25 | CS7-8154 - TLN-526661 | 0 | 20.7847 | 5 | 15.7847 | 0.53087 | 89.6889 | 0.69903 | 3.7154 | 3.0164 | 1.4948 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 6.9313 |  | RONILO GANGE JR.
2025-05-02 | 2025-04-22 |  | BIZ | X25031070065 | LANDBANK OF THE PHILIPPINES | GNG. ELSIE GACHES, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 8.48 | 11.03 | - | TERMINATION | 19621.38 | 9485.96 |  | 0% | 2025-04-11 14:45 | 2025-04-18 11:00 | 2025-04-19 |  | 2025-06-10 |  | 59.3854 | 52.5417 | -45818 | 2025-04-23 14:45 | 2025-04-30 14:45 | 2025-05-31 14:45 | 2.9693 | -763.6333 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-08-09 | 77 | [8 empty] | NO COC |  | 2025-06-25 | #VALUE! | [18 empty] | 2025-04-25 | N/A | 0 | 59.3854 | 0 | 59.3854 | 2.9693 | 51 |  | 5.5193 | 5.5193 | 0.85 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 6.8438 |  | RONILO GANGE JR.
2025-04-29 | 2025-04-22 |  | HMB | X24020419372 | CITY GOVERNMENT OF LAS PINAS | MALUNGGAY, CAA CPD PH 3, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | ongoing sched interruption aug. 29, 2025 Friday |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 440.682 | 1142.65 | 99.7 | NEW | 2734783.42 | 623962.89 |  | 0% | 2025-04-11 15:42 | 2025-04-18 11:01 | 2025-04-19 |  |  |  | -45758.6542 | -45765.459 | 0 | 2025-05-06 20:41 | 2025-05-17 09:13 | 2025-05-31 15:42 | -1216.6419 | 0 | 50 | 34 | 28.208 | 35.7301 | 25.208 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | #N/A | 0 | -45758.6542 | 0 | -45758.6542 | -1216.6419 | 0 |  | 2.9339 | 2.9339 | 0 | 97.3458 | REV | 4-6 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [7 empty] | 6.8049 |  | Jenneth Madrid
2025-04-25 | 2025-04-24 | Y | HMB | X25030884434 | RONALD CARANAY CALINGAY | GREEN GRASS, GREEN VALLEY SUBD SECT A, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 18.3928 | 20.28 | 2 | NEW | 197328.6 | 60293.5 |  | 0% | 2025-04-14 10:38 | 2025-04-23 14:42 | 2025-04-24 |  | 2025-05-22 |  | 37.5569 | 28.3875 | -45799 | 2025-05-03 05:13 | 2025-05-12 00:34 | 2025-06-03 10:38 | 1.2936 | -763.3167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [10 empty] | Y | 2025-05-22 | [6 empty] | 2025-05-07 | A7-8057,TLN-186963 | 0 | 37.5569 | 0 | 37.5569 | 1.2936 | 70 |  | 3.7047 | 3.7047 | 1.1667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-02 | 2025-04-28 |  | BIZ | X25041141247 | ALABANG HILLS VILLAGE ASS INC | DOÑA INES, ALABANG HILLS SUBD PH 2, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 17.22 | 33.18 | - | TERMINATION | 35546.77 | 28577.83 |  | 0% | 2025-04-14 15:46 | 2025-04-23 14:46 | 2025-04-24 |  | 2025-05-29 15:00 |  | 44.9681 | 36.0097 | -45806.625 | 2025-04-26 15:46 | 2025-05-03 15:46 | 2025-06-03 15:46 | 2.2484 | -763.4438 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-28 15:00 | 88.375 | [8 empty] | NO COC |  | 2025-06-13 15:00 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 44.9681 | 0 | 44.9681 | 2.2484 | 62.375 |  | 5.3672 | 5.3672 | 1.0396 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-04-29 | 2025-04-28 | Y | BIZ | X25010118641 | HIJO GREENS, INC. | EDISON, EDISON INDUSTRIAL COMPLEX, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 80.9174 | 216.64 | 183 | NEW | 911302.13 | 118917.61 |  | 0% | 2025-04-15 10:51 | 2025-04-23 14:45 | 2025-04-24 |  | 2025-05-16 |  | 30.5479 | 22.3854 | -45793 | 2025-05-05 11:11 | 2025-05-14 14:28 | 2025-06-04 10:51 | 0.99553 | -763.2167 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 2025-07-15 | 102 | [8 empty] | FOR AUDIT |  | 2025-05-31 | -4 | 2025-05-11 | 2025-05-27 | [8 empty] | Y | 2025-05-08 | [6 empty] | 2025-04-22 | B4-8031,TLN-530185 | 0 | 30.5479 | 0 | 30.5479 | 0.99553 | 76 |  | 3.4723 | 3.4723 | 1.2667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-22 | 2025-04-28 |  | BIZ | X25020460575 | LINAHEIM CORPORATE SERVICES, INC. | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 103.6063 | 228.7 | 330 | NEW | 1348450.36 | 130058.29 |  | 0% | 2025-04-15 13:57 | 2025-04-23 14:44 | 2025-04-24 |  | 2025-07-04 |  | 79.4187 | 71.3861 | -45842 | 2025-05-03 13:57 | 2025-05-12 04:21 | 2025-06-04 13:57 | 2.8364 | -764.0333 | 28 | 28 | 21 | 26.6 | 18 | 60 | 57 | 52 | 2025-09-02 | 53 | [8 empty] | NO COC |  | 2025-07-19 | #VALUE! | [18 empty] | 2025-04-25 | N/A | 0 | 79.4187 | 0 | 79.4187 | 2.8364 | 27 |  | 3.8007 | 3.8007 | 0.45 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-04-22 | 2025-04-24 |  | HMB | X25030992144 | SONNY MACARAIG NG | LEYTE, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 45.2095 | 71.08 | 82 | MODIFICATION | 367939.35 | 60293.5 |  | 0% | 2025-04-15 13:57 | 2025-04-21 14:56 | 2025-04-22 |  | 2025-04-29 |  | 13.4187 | 7.3778 | -45776 | 2025-05-04 21:10 | 2025-05-13 19:53 | 2025-06-04 13:57 | 0.4513 | -762.9333 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-06-28 | 119 | [8 empty] | FOR AUDIT |  | 2025-05-14 | 13 | 2025-04-28 | 2025-05-27 | [16 empty] | #N/A | #N/A | 0 | 13.4187 | 0 | 13.4187 | 0.4513 | 93 |  | 3.579 | 3.579 | 1.55 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-05 | 2025-04-29 |  | BIZ | X25020681892 | HARD DISCOUNT PHILIPPINES, INC. | DAANG HARI, PERPETUAL VILLAGE, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 11.2928 | 13.42 | 19 | NEW | 143125.62 | 11531.12 |  | 0% | 2025-04-21 15:18 | 2025-04-28 | 2025-04-28 14:44 | 2025-05-29 | 2025-06-28 |  | 67.3625 | 61 | -45836 | 2025-05-10 09:53 | 2025-05-19 05:14 | 2025-06-10 15:18 | 2.3203 | -763.9333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | FOR AUDIT |  | 2025-07-13 | 12 | 2025-05-29 | 2025-07-25 | [8 empty] | Y | 2025-06-26 | [6 empty] | 2025-05-06 | A8-8144, TLN-527757 | 0 | 67.3625 | 0 | 67.3625 | 2.3203 | 33 |  | 3.4569 | 3.4569 | 0.55 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-05 | 2025-04-29 |  | BIZ | X25031010090 | LILIA T. AMADOR | PRES. QUIRINO AVE, ZONE 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 12.2133 | 18.82 | 37 | NEW | 201,524.06 | 16173.54 |  | 0% | 2025-04-21 15:27 | 2025-04-28 14:43 | 2025-04-28 14:44 |  | 2025-06-09 |  | 48.3562 | 41.3868 | -45817 | 2025-05-10 10:02 | 2025-05-19 05:23 | 2025-06-10 15:27 | 1.6656 | -763.6167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-08 | 78 | [8 empty] | NO COC |  | 2025-06-24 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 48.3562 | 0 | 48.3562 | 1.6656 | 52 |  | 3.4567 | 3.4567 | 0.86667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-04-23 | 2025-04-24 | Y | HMB | X25031019727 | CITY GOVERNMENT OF TAGUIG | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 171.3066 | 415.57 | 896 | NEW | 2903581.15 | 323053.56 |  | 0% | 2025-04-21 15:58 | 2025-04-22 06:55 | 2025-04-23 | 2025-04-28 | 2025-04-28 10:39 |  | 6.7785 | 6.1556 | -45775.4437 | 2025-05-07 12:07 | 2025-05-15 12:41 | 2025-06-10 15:58 | 0.26985 | -762.9241 | 32 | 23 | 18.8396 | 23.8635 | 15.8396 | 60 | 57 | 52 | 2025-06-27 10:39 | 119.5563 | [8 empty] | FOR AUDIT |  | 2025-05-13 10:39 | 85.5563 | 2025-04-28 | 2025-08-07 | [16 empty] | #N/A | #N/A | 0 | 6.7785 | 0 | 6.7785 | 0.26985 | 93.5563 |  | 3.9943 | 3.9943 | 1.5593 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-04-28 | 2025-04-29 |  | BIZ | X25020679066 | WILFREDO URDAS ABUEVA | NIOG III, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 3.66 | 36.54 | - | TERMINATION | 40059.87 | 31524.93 |  | 0% | 2025-04-21 16:09 | 2025-04-28 14:45 | 2025-04-28 |  |  |  | -45768.6729 | -45775.6146 | 0 | 2025-05-03 16:09 | 2025-05-10 16:09 | 2025-06-10 16:09 | -2288.4336 | 0 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-06 | DZ1-8102, DZ2-8103 | 0 | -45768.6729 | 0 | -45768.6729 | -2288.4336 | 0 |  | 5.0164 | 5.0164 | 0 | 87.3271 | NON-REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-05 | 2025-05-06 |  | CBG | R23928639 | METALS INDUSTRY RESEARCH AND DEVELOPMENT CENTER | GEN. SANTOS, DOST CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 79.0808 | 247.46 | - | RELOC | 332492.52 | 78104.06 |  | 0% | 2025-04-22 10:31 | 2025-04-30 12:59 | 2025-05-02 |  | 2025-07-28 |  | 96.5618 | 88.459 | -45866 | 2025-05-05 20:16 | 2025-05-13 05:16 | 2025-06-11 10:31 | 4.4143 | -764.4333 | 28 | 20 | 16.4063 | 20.7813 | 13.4063 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | NO COC |  | 2025-08-12 | #VALUE! | [18 empty] | 2025-05-06 | DX1-8116, TLN-527713 | 0 | 96.5618 | 0 | 96.5618 | 4.4143 | 3 |  | 4.5514 | 4.5514 | 0.05 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-02 | 2025-05-06 |  | HMB | X25020413672 | DAJ PROPERTY HOLDINGS CORP. | ANONAS, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 93.2524 | 163.04 | 157 | NEW | 949149.04 | 140114.53 |  | 0% | 2025-04-22 12:16 | 2025-04-30 13:04 | 2025-05-02 |  | 2025-05-15 16:30 |  | 23.1764 | 15.1431 | -45792.6875 | 2025-05-11 22:58 | 2025-05-20 22:38 | 2025-06-11 12:16 | 0.7744 | -763.2115 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-14 16:30 | 102.3125 | [8 empty] | FOR AUDIT |  | 2025-05-30 16:30 | 11.3125 | 2025-05-15 | 2025-06-11 | [8 empty] | Y | 2025-05-14 | [6 empty] | 2025-05-06 | TLN-527768 | 0 | 23.1764 | 0 | 23.1764 | 0.7744 | 76.3125 |  | 3.3243 | 3.3243 | 1.2719 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-05 | 2025-05-06 |  | BIZ | X25041184011 | ELENA M KIKUCHI | ARAGON CPD, ARAGON CPD, BACOOR | BACOOR CITY | DASMA |  |  | ECOM | SCHED | Ronilo Gange Jr. | 13.05 | 43.15 | 15 | NEW | 73226.16 | 37075.65 |  | 0% | 2025-04-22 12:26 | 2025-04-30 13:02 | 2025-05-02 |  |  |  | -45769.5181 | -45777.5431 | 0 | 2025-05-11 07:01 | 2025-05-20 02:22 | 2025-06-11 12:26 | -1576.5056 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-06 | TLN-530232 | 0 | -45769.5181 | 0 | -45769.5181 | -1576.5056 | 0 |  | 3.4266 | 3.4266 | 0 | 86.4819 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-04-28 | 2025-04-29 | Y | HMB | X25010318160 | METRO SOUTH PROPERTIES CORPORATION | RAVENGA, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 236.4671 | 712.49 | 100 | NEW | 1276315.37 | 275877.53 |  | 0% | 2025-04-22 13:18 | 2025-04-28 14:49 | 2025-04-28 14:44 |  | 2025-07-10 |  | 78.4458 | 72.3826 | -45848 | 2025-05-16 06:08 | 2025-05-26 09:02 | 2025-06-11 13:18 | 2.2034 | -764.1333 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 52 | 2025-09-08 | 47 | [8 empty] | NO COC |  | 2025-07-25 | #VALUE! | [18 empty] | 2025-05-06 | CU9-8031,TLN-578073 | 0 | 78.4458 | 0 | 78.4458 | 2.2034 | 21 |  | 2.7933 | 2.7933 | 0.35 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-05 | 2025-05-06 |  | HMB | X25020671305 | CITY GOVERNMENT OF TAGUIG | M.L. QUEZON, PUROK 4, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 65.6361 | 170.73 | 173 | NEW | 862746.36 | 79457.51 |  | 0% | 2025-04-22 15:16 | 2025-04-30 13:09 | 2025-05-02 | 2025-05-09 | 2025-05-09 |  | 16.3639 | 8.4521 | -45786 | 2025-05-12 01:58 | 2025-05-21 01:38 | 2025-06-11 15:16 | 0.54677 | -763.1 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-08 | 109 | [8 empty] | FOR AUDIT |  | 2025-05-24 | 55 | 2025-05-09 | 2025-07-18 | [8 empty] | Y | 2025-05-07 | [6 empty] | 2025-05-06 | TLN-080048 | 0 | 16.3639 | 0 | 16.3639 | 0.54677 | 83 |  | 3.3201 | 3.3201 | 1.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-04-28 | 2025-04-29 |  | HMB | X25030844140 | CITY GOVERNMENT OF TAGUIG | PINAGSAMA PH 1 VILL, PINAGSAMA PH 1 VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 80.0575 | 166.1 | 221 | NEW | 923476.79 | 125315.52 |  | 0% | 2025-04-22 15:20 | 2025-04-28 14:52 | 2025-04-28 |  | 2025-05-09 |  | 16.3611 | 10.3806 | -45786 | 2025-05-11 03:31 | 2025-05-19 21:09 | 2025-06-11 15:20 | 0.57054 | -763.1 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-07-08 | 109 | [8 empty] | NO COC |  | 2025-05-24 | #VALUE! | [10 empty] | Y | 2025-05-07 | [6 empty] | 2025-05-06 | CT9-8085,TLN-527431 | 0 | 16.3611 | 0 | 16.3611 | 0.57054 | 83 |  | 3.4649 | 3.4649 | 1.3833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-08 | 2025-05-06 |  | HMB | X25030949251 | CITY GOVERNMENT OF TAGUIG | LAPU-LAPU, PUROK 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | ONGOING WITH PAI |  | VJC | SCHED | Jenneth Madrid | 263.59 | 843.07 | 151 | NEW | 1686610.42 | 320882.64 |  | 0% | 2025-04-22 15:20 | 2025-04-30 13:07 | 2025-05-02 |  |  |  | -45769.6389 | -45777.5465 | 0 | 2025-05-15 04:06 | 2025-05-24 23:30 | 2025-06-11 15:20 | -1344.4831 | 0 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 1900-02-28 | 45895 | No pole stake / Materials unavailability | Y | Y |  |  | 2025-05-28 | 42 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45769.6389 | 42 | -45811.6389 | -1345.7169 | 0 | 2.9187 | 2.9187 | 0 | 0 | 86.3611 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-02 | 2025-05-06 |  | HMB | X25020572372 | JEFFREY ANG SY | WHITE, GOODWILL 2 SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Done energize with meter |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 63.1031 | 172.56 | 66.5 | MODIFICATION | 447247.07 | 80599.67 |  | 0% | 2025-04-22 15:54 | 2025-04-30 13:00 | 2025-05-02 |  |  |  | -45769.6625 | -45777.5417 | 0 | 2025-05-13 00:11 | 2025-05-22 05:35 | 2025-06-11 15:54 | -1470.4281 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-05 | CW4-8021-TLN-516593 | 0 | -45769.6625 | 0 | -45769.6625 | -1470.4281 | 0 |  | 3.1914 | 3.1914 | 0 | 86.3375 | NON-REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-02 | 2025-05-06 |  | CBG | X23072870847 | DITO TELECOMMUNITY CORPORATION | BANABA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 35.1818 | 46.79 | 31 | NEW | 306,894.22 | 40203.11 |  | 0% | 2025-04-22 16:01 | 2025-04-30 12:09 | 2025-05-02 | 2025-05-23 | 2025-05-23 |  | 30.3326 | 22.4938 | -45800 | 2025-05-11 10:36 | 2025-05-20 05:57 | 2025-06-11 16:01 | 1.0448 | -763.3333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-22 | 95 | [8 empty] | FOR AUDIT |  | 2025-06-07 | 35 | 2025-05-23 | 2025-07-12 | [8 empty] | Y | 2025-05-23 | [6 empty] | 2025-04-29 | CS7-8160,CS7-8161,CS7-8162,CS7-8163,CS7-8164 - TLN-527319 | 0 | 30.3326 | 0 | 30.3326 | 1.0448 | 69 |  | 3.4215 | 3.4215 | 1.15 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-05 | 2025-05-06 | Y | BIZ | X23031056287 | ALFAMART TRADING PHILIPPINES, INC | GEN. TIRONA, MABOLO I, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 48.5935 | 131.89 | 28 | NEW | 293996.61 | 46063.97 |  | 0% | 2025-04-22 16:44 | 2025-04-30 13:02 | 2025-05-02 |  | 2025-05-24 |  | 31.3028 | 23.4569 | -45801 | 2025-05-13 21:42 | 2025-05-23 08:37 | 2025-06-11 16:44 | 0.96985 | -763.35 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-07-23 | 94 | [8 empty] | NO COC |  | 2025-06-08 | #VALUE! | [10 empty] | Y | 2025-05-24 | [6 empty] | 2025-05-05 | CV7-1408,CV7-1409 | 0 | 31.3028 | 0 | 31.3028 | 0.96985 | 68 |  | 3.0767 | 3.0767 | 1.1333 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-06 | 2025-05-06 |  | CBG | X24072722048 | DITO TELECOMMUNITY CORPORATION | C. ARELLANO, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 18.1028 | 25.69 | 31 | NEW | 247,309.59 | 22074.28 |  | 0% | 2025-04-23 08:24 | 2025-04-30 12:13 | 2025-05-02 | 2025-05-28 | 2025-05-28 14:34 |  | 35.2569 | 28.0979 | -45805.6069 | 2025-05-12 02:59 | 2025-05-20 22:20 | 2025-06-12 08:24 | 1.2144 | -763.4268 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 14:34 | 89.3931 | [8 empty] | FOR AUDIT |  | 2025-06-12 14:34 | 24.3931 | 2025-05-28 | 2025-07-07 | [8 empty] | Y | 2025-06-10 | [6 empty] | 2025-05-05 | CW5-0031-TLN-526381 | 0 | 35.2569 | 0 | 35.2569 | 1.2144 | 63.3931 |  | 3.3979 | 3.3979 | 1.0566 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-22 | 2025-05-06 |  | HMB | X25041128269 | ALDOUS JEROME ROTAIRO SARMIENTO | BLOCK 12, KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 3.0633 | 5.15 | 22.4 | MODIFICATION | 21401.6 | 4427.88 |  | 0% | 2025-04-23 16:03 | 2025-04-30 13:10 | 2025-05-02 | 2025-05-29 | 2025-05-28 08:29 |  | 34.6847 | 27.8049 | -45805.3535 | 2025-05-12 10:38 | 2025-05-21 05:59 | 2025-06-12 16:03 | 1.1947 | -763.4226 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 08:29 | 89.6465 | [8 empty] | FOR AUDIT |  | 2025-06-12 08:29 | 45.6465 | 2025-05-29 | 2025-07-28 | [8 empty] | Y | 2025-05-29 | [6 empty] | 2025-05-05 | CU9-8046,CU9-8047,CU9-8048,CU9-8049,TLN-520428 | 0 | 34.6847 | 0 | 34.6847 | 1.1947 | 63.6465 |  | 3.387 | 3.387 | 1.0608 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-05 | 2025-05-06 |  | CBG | X24072847895 | DITO TELECOMMUNITY CORPORATION | DR. J. GABRIEL, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | diging problem wala po paghukayan |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 55.94 | 1002.04 | 22 | NEW | 966296.42 | 33211.14 |  | 0% | 2025-04-24 12:46 | 2025-04-30 12:15 | 2025-05-02 |  |  |  | -45771.5319 | -45777.5104 | 0 | 2025-05-21 00:11 | 2025-05-31 20:50 | 2025-06-13 12:46 | -1164.6312 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-05 | TLN-522965 | 0 | -45771.5319 | 0 | -45771.5319 | -1164.6312 | 0 |  | 2.48 | 2.48 | 0 | 84.4681 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-09 | 2025-05-06 |  | BIZ | X24030696318 | ALY PLACE PROPERTIES INC. | BOUGAINVILLA, T.S. CRUZ SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | W/ Problem , energization 8-8-25 |  | AVECO | FCOMP | Ronilo Gange Jr. | 173.6814 | 548.67 | 69 | NEW | 1031830.42 | 198660.12 |  | 0% | 2025-04-24 13:22 | 2025-04-30 13:33 | 2025-05-02 |  | 2025-08-09 08:29 |  | 106.7965 | 100.7889 | -45878.3535 | 2025-05-18 06:12 | 2025-05-28 09:06 | 2025-06-13 13:22 | 2.9997 | -764.6392 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 52 | 2025-10-08 08:29 | 16.6465 | Third party concern (Other than the applicant) | Y |  |  | Y | 2025-05-14 |  |  | NO COC |  | 2025-08-24 08:29 | #VALUE! | [18 empty] | 2025-05-06 | C5-8074, TLN-523059 | 0 | 106.7965 | 0 | 106.7965 | 2.9997 | -9.3535 |  | 2.737 | 2.737 | -0.15589 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-06 | 2025-05-06 |  | HMB | X25041106100 | ALAN LIMCAY TAN | R. PARAS, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 53.9877 | 64.25 | 80 | MODIFICATION | 429775.22 | 55232.87 |  | 0% | 2025-04-24 14:09 | 2025-04-30 13:53 | 2025-05-02 |  | 2025-05-30 |  | 35.4104 | 29.4215 | -45807 | 2025-05-13 21:22 | 2025-05-22 20:05 | 2025-06-13 14:09 | 1.1909 | -763.45 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-07-29 | 88 | [8 empty] | NO COC |  | 2025-06-14 | #VALUE! | [10 empty] | Y | 2025-05-29 | [6 empty] | #N/A | #N/A | 0 | 35.4104 | 0 | 35.4104 | 1.1909 | 62 |  | 3.2761 | 3.2761 | 1.0333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-22 | 2025-05-06 | Y | BIZ | X25030864022 | RAHUL DAVE DARYANI | E. RODRIGUEZ JR., STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | COMP | Jenneth Madrid | 33.928 | 70.21 | 135 | NEW | 736986.61 | 60355.24 | 31342.96 | 51.93% | 2025-04-24 16:09 | 2025-04-30 13:34 | 2025-05-02 | 2025-06-19 | 2025-06-19 | 2025-08-19 | 55.3271 | 49.4347 | 61 | 2025-05-13 03:38 | 2025-05-21 21:06 | 2025-06-13 16:09 | 1.9319 | 1.0167 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-08-18 | 68 | With scheduled PAI | Y | Y |  |  | 2025-06-11 | 7 | 2025-06-18 | PAID |  | 2025-07-04 | 24 | 2025-06-19 | 2025-07-28 | 2025-08-11 | RLM |  |  |  |  | 2025-08-16 | NVP | [8 empty] | 2025-05-23 | TLN-522965 | 0 | 55.3271 | 7 | 48.3271 | 1.6875 | 42 |  | 3.3985 | 3.3985 | 0.7 |  | REV |  | 2025-08-18 | 8501.28 | NTC ISSUED | 2025-08-18 |  | 8 | [9 empty] | Jenneth Madrid
2025-05-05 | 2025-05-06 |  | BIZ | X25010277855 | MICHAEL LEANDRO ALINDOGAN NAVARRETE | GEN. EMILIO AGUINALDO, PANAPAAN V, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 35.2957 | 117.49 | 16 | NEW | 293645.59 | 33690.04 |  | 0% | 2025-04-24 16:50 | 2025-04-30 13:12 | 2025-05-02 |  |  |  | -45771.7014 | -45777.55 | 0 | 2025-05-15 21:48 | 2025-05-25 08:43 | 2025-06-13 16:50 | -1418.1403 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45771.7014 | 0 | -45771.7014 | -1418.1403 | 0 |  | 3.0146 | 3.0146 | 0 | 84.2986 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-08 | 2025-05-06 |  | CBG | X25041178117 | DITO TELECOMMUNITY CORPORATION | M.L. QUEZON, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 5.424 | 5.42 | - | NEW | 24329.54 | 4660.44 |  | 0% | 2025-04-25 14:14 | 2025-04-30 12:16 | 2025-05-02 | 2025-06-30 | 2025-06-30 |  | 65.4069 | 60.4889 | -45838 | 2025-05-07 14:14 | 2025-05-14 14:14 | 2025-06-14 14:14 | 3.2703 | -763.9667 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-08-29 | 57 | [8 empty] | FOR AUDIT |  | 2025-07-15 | 23 | 2025-06-30 | 2025-08-07 | [16 empty] | 2025-05-06 | CR9-8055,TLN-530305 | 0 | 65.4069 | 0 | 65.4069 | 3.2703 | 31 |  | 4.8203 | 4.8203 | 0.51667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-07 | 2025-05-06 |  | HMB | X25030814162 | ALMA DY BAGAS | SAMARIA, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Energize with meter |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 46.358 | 77.97 | 80 | MODIFICATION | 348292.59 | 49186.7 |  | 0% | 2025-04-27 10:54 | 2025-04-30 13:38 | 2025-05-02 |  |  |  | -45774.4542 | -45777.5681 | 0 | 2025-05-16 18:07 | 2025-05-25 16:50 | 2025-06-16 10:54 | -1539.4733 | 0 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-08 | #N/A | 0 | -45774.4542 | 0 | -45774.4542 | -1539.4733 | 0 |  | 3.1797 | 3.1797 | 0 | 81.5458 | NON-REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-06 | 2025-05-07 |  | CBG | X23114515533 | DITO TELECOMMUNITY CORPORATION | R. AVANCEÑA, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 22.84 | 45.92 | 35 | NEW | 366995.92 | 39471.53 |  | 0% | 2025-04-28 13:22 | 2025-05-06 12:37 | 2025-05-06 | 2025-05-28 | 2025-05-28 14:41 |  | 30.0549 | 22.0861 | -45805.6118 | 2025-05-17 07:57 | 2025-05-26 03:18 | 2025-06-17 13:22 | 1.0352 | -763.4269 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 14:41 | 89.3882 | [8 empty] | FOR AUDIT |  | 2025-06-12 14:41 | 24.3882 | 2025-05-28 | 2025-07-07 | [8 empty] | Y | 2025-06-10 | [6 empty] | 2025-05-09 | DX1-8108,DX1-8109,DX1-8110,DX1-8111,TLN-527024 | 0 | 30.0549 | 0 | 30.0549 | 1.0352 | 63.3882 |  | 3.2186 | 3.2186 | 1.0565 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-06 | 2025-05-07 |  | HMB | X25010187948 | EDUARDO FRANCISCO CAACBAY | G.SANTOS, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 171.8773 | 231.19 | 45 | MODIFICATION | 992497.65 | 198244.14 |  | 0% | 2025-04-28 14:32 | 2025-05-06 12:39 | 2025-05-06 |  | 2025-05-29 15:59 |  | 31.0604 | 23.1389 | -45806.666 | 2025-05-20 11:23 | 2025-05-30 02:32 | 2025-06-17 14:32 | 0.93674 | -763.4444 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-07-28 15:59 | 88.334 | [8 empty] | NO COC |  | 2025-06-13 15:59 | #VALUE! | [10 empty] | Y | 2025-05-29 | [6 empty] | 2025-05-06 | CR9-8051,CR9-8052,CR9-8053,CR9-8054,CR9-5905 | 0 | 31.0604 | 0 | 31.0604 | 0.93674 | 62.334 |  | 2.8167 | 2.8167 | 1.0389 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-09 | 2025-05-07 | Y | HMB | X25010021411 | FRANCES CHRISTINE RAMIREZ AGUIRRE | DAO, MAYWOOD VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 135.691 | 159.18 | 64 | MODIFICATION | 813670.22 | 136773.92 |  | 0% | 2025-04-28 15:59 | 2025-05-06 13:08 | 2025-05-06 | 2025-06-03 | 2025-06-03 |  | 35.334 | 27.4528 | -45811 | 2025-05-19 00:16 | 2025-05-28 05:40 | 2025-06-17 15:59 | 1.1352 | -763.5167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-02 | 84 | [8 empty] | FOR AUDIT |  | 2025-06-18 | 19 | 2025-06-03 | 2025-07-07 | [16 empty] | 2025-05-09 | TLN-527665 | 0 | 35.334 | 0 | 35.334 | 1.1352 | 58 |  | 2.9985 | 2.9985 | 0.96667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-07 | 2025-05-07 | Y | BIZ | X25020687798 | TWIN KARAT REALTY CORPORATION | QUIRINO, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | POLE DRESSING |  | AVECO | SCHED | Ronilo Gange Jr. | 117.5349 | 275.3 | 526 | NEW | 1305014.67 | 219118.06 |  | 0% | 2025-04-28 16:01 | 2025-05-06 13:10 | 2025-05-06 |  |  |  | -45775.6674 | -45783.5486 | 0 | 2025-05-13 21:27 | 2025-05-21 18:06 | 2025-06-17 16:01 | -1883.6261 | 0 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | #N/A | 0 | -45775.6674 | 0 | -45775.6674 | -1883.6261 | 0 |  | 3.8406 | 3.8406 | 0 | 80.3326 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-09 | 2025-05-07 |  | BIZ | X25010121042 | MODISSOL PROPERTY MANAGEMENT CORPORATION | EL GRANDE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 25.4528 | 55.96 | 306 | NEW | 823914.89 | 48086.01 |  | 0% | 2025-04-28 16:03 | 2025-05-06 13:09 | 2025-05-06 |  | 2025-06-27 |  | 59.3313 | 51.4521 | -45835 | 2025-05-15 09:12 | 2025-05-23 15:22 | 2025-06-17 16:03 | 2.2572 | -763.9167 | 23 | 28 | 19.7143 | 24.9714 | 16.7143 | 60 | 57 | 52 | 2025-08-26 | 60 | [8 empty] | NO COC |  | 2025-07-12 | #VALUE! | [10 empty] | Y | 2025-06-25 | [6 empty] | 2025-05-07 | A4-8009,TLN-527905 | 0 | 59.3313 | 0 | 59.3313 | 2.2572 | 34 |  | 3.5506 | 3.5506 | 0.56667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-08 | 2025-05-07 |  | HMB | X25031083142 | ELOISA R PONCE | BLOCK 132, SITIO IMELDA, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 0.53 | 5.15 | 8 | NEW | 21339.45 | 4424.95 |  | 0% | 2025-04-29 08:11 | 2025-05-06 13:12 | 2025-05-06 | 2025-05-31 | 2025-05-31 |  | 31.659 | 24.45 | -45808 | 2025-05-18 02:46 | 2025-05-26 22:07 | 2025-06-18 08:11 | 1.0905 | -763.4667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | FOR AUDIT |  | 2025-06-15 | 27 | 2025-05-31 | 2025-07-12 | [8 empty] | Y | 2025-05-29 | [6 empty] | 2025-05-06 | N/A | 0 | 31.659 | 0 | 31.659 | 1.0905 | 61 |  | 3.1916 | 3.1916 | 1.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-09 | 2025-05-07 | Y | HMB | X25041129915 | ROSE ANNE A. AGUIRRE | C. PALANCA SR., BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 115.2395 | 387.15 | 42 | MODIFICATION | 733089.1 | 131663.28 |  | 0% | 2025-04-29 16:12 | 2025-05-06 13:13 | 2025-05-06 |  | 2025-07-04 |  | 65.325 | 58.4493 | -45842 | 2025-05-22 03:31 | 2025-05-31 22:32 | 2025-06-18 16:12 | 1.9235 | -764.0333 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 2025-09-02 | 53 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-07-19 | #VALUE! | [10 empty] | Y | 2025-06-27 | [6 empty] | #N/A | #N/A | 0 | 65.325 | 34 | 31.325 | 0.92235 | 27 |  | 2.7185 | 2.7185 | 0.45 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-06 | 2025-05-07 | Y | HMB | X25041129547 | S3A UNTIED INC. | PACIFIC AVE, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 7.61 | 15.61 | - | TERMINATION | 23102.58 | 13412.51 |  | 0% | 2025-04-30 08:20 | 2025-04-14 | 2025-05-06 | 2025-05-05 | 2025-05-05 |  | 4.6528 | 21 | -45782 | 2025-05-12 08:20 | 2025-05-19 08:20 | 2025-06-19 08:20 | 0.23264 | -763.0333 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-07-04 | 113 | [8 empty] | NO COC |  | 2025-05-20 | #VALUE! | [18 empty] | 2025-05-09 | CW9-8098,CW9-8099,CW9-8100,TLN-530415 | 0 | 4.6528 | 0 | 4.6528 | 0.23264 | 87 |  | 4.5826 | 4.5826 | 1.45 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-22 | 2025-05-07 | Y | BIZ | X25041173300 | ALBERT TIONGSON LORENZO | BACOOR, MAMBOG IV, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 43.4047 | 85.69 | 25 | NEW | 479294.17 | 73631.56 |  | 0% | 2025-04-30 08:47 | 2025-05-06 13:17 | 2025-05-06 |  | 2025-05-27 |  | 26.634 | 20.4465 | -45804 | 2025-05-20 10:50 | 2025-05-29 14:35 | 2025-06-19 08:47 | 0.86528 | -763.4 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-07-26 | 91 | [8 empty] | NO COC |  | 2025-06-11 | #VALUE! | [10 empty] | Y | 2025-05-26 | [6 empty] | #N/A | #N/A | 0 | 26.634 | 0 | 26.634 | 0.86528 | 65 |  | 2.977 | 2.977 | 1.0833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-09 | 2025-05-07 |  | BIZ | X25010301742 | CITIHARDWARE BACOLOD, INC. | NATIONAL, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 3.92 | 17.46 | 127 | NEW | 48368.01 | 15002.04 |  | 0% | 2025-04-30 12:32 | 2025-05-06 13:19 | 2025-05-06 |  | 2025-05-20 |  | 19.4778 | 13.4451 | -45797 | 2025-05-17 20:40 | 2025-05-26 06:50 | 2025-06-19 12:32 | 0.71824 | -763.2833 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-07-19 | 98 | [8 empty] | NO COC |  | 2025-06-04 | #VALUE! | [10 empty] | Y | 2025-05-16 | [6 empty] | #N/A | #N/A | 0 | 19.4778 | 0 | 19.4778 | 0.71824 | 72 |  | 3.3732 | 3.3732 | 1.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-19 | 2025-05-07 |  | HMB | X25020573238 | REIGNWOOD DEVELOPMENT CORPORATION | BLOCK 1B, BENEDETTO RESIDENCES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 38.2185 | 129.49 | 49 | NEW | 354540.41 | 43995.98 |  | 0% | 2025-04-30 12:34 | 2025-05-06 13:15 | 2025-05-06 |  | 2025-07-04 |  | 64.4764 | 58.4479 | -45842 | 2025-05-21 17:32 | 2025-05-31 04:27 | 2025-06-19 12:34 | 1.9977 | -764.0333 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-09-02 | 53 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-07-19 | #VALUE! | [18 empty] | 2025-05-19 | CY7-8119,TLN-527642 | 0 | 64.4764 | 34 | 30.4764 | 0.94425 | 27 |  | 2.8342 | 2.8342 | 0.45 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-13 | 2025-05-07 |  | BIZ | X25020460240 | PHILIPPINE SEVEN CORPORATION | 17TH A, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 2.73 | 33.86 | 34 | NEW | 92215.08 | 29093.82 |  | 0% | 2025-04-30 15:21 | 2025-05-06 13:29 | 2025-05-06 |  | 2025-07-28 |  | 88.3604 | 82.4382 | -45866 | 2025-05-19 09:56 | 2025-05-28 05:17 | 2025-06-19 15:21 | 3.0435 | -764.4333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | NO COC |  | 2025-08-12 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 88.3604 | 0 | 88.3604 | 3.0435 | 3 |  | 3.1469 | 3.1469 | 0.05 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-13 | 2025-05-07 | y | BIZ | X24104298635 | ANKONG HOLDINGS, INC. | JAIME, AIRPORT VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | POLE ERECTION & DRESSING 8-6-25 |  | AVECO | SCHED | Ronilo Gange Jr. | 717.2996 | 883.64 | 358 | NEW | 2507240.06 | 774008.21 |  | 0% | 2025-04-30 18:17 | 2025-05-06 13:22 | 2025-05-06 |  |  |  | -45777.7618 | -45783.5569 | 0 | 2025-05-20 20:08 | 2025-05-29 23:49 | 2025-06-19 18:17 | -1487.7773 | 0 | 40 | 28 | 23.0769 | 29.2308 | 20.0769 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45777.7618 | 0 | -45777.7618 | -1487.7773 | 0 |  | 2.9652 | 2.9652 | 0 | 78.2382 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-22 | 2025-05-14 |  | BIZ | X25020417967 | PHILIPPINE SEVEN CORPORATION | RIZAL, POBLACION, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 2.73 | 8.45 | 46 | NEW | 36093.36 | 7260.54 |  | 0% | 2025-05-02 10:06 | 2025-05-09 14:35 | 2025-05-09 | 2025-05-20 | 2025-05-20 |  | 17.5792 | 10.3924 | -45797 | 2025-05-21 04:41 | 2025-05-30 00:02 | 2025-06-21 10:06 | 0.6055 | -763.2833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-19 | 98 | [8 empty] | FOR AUDIT |  | 2025-06-04 | 61 | 2025-05-20 | 2025-08-04 | [8 empty] | Y | 2025-05-16 | [6 empty] | N/A | 158613 | 0 | 17.5792 | 0 | 17.5792 | 0.6055 | 72 |  | 3.0855 | 3.0855 | 1.2 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-21 | 2025-05-14 |  | HMB | X24072778613 | CITY GOVERNMENT OF MUNTINLUPA | TYPE C, NEW BILIBID PRISONS, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ENERGIZE 20KV & DT 3 -167 KVA 8/13; for fcomp |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 498.6334 | 1676.24 | 460 | NEW | 3706759.37 | 634240.72 |  | 0% | 2025-05-02 10:16 | 2025-05-09 14:37 | 2025-05-09 |  | 2025-08-16 08:46 |  | 105.9375 | 98.7562 | -45885.3653 | 2025-05-22 05:00 | 2025-05-31 06:47 | 2025-06-21 10:16 | 3.4878 | -764.7561 | 50 | 26 | 22.7804 | 28.8551 | 19.7804 | 60 | 57 | 52 | 2025-10-15 08:46 | 9.6347 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-08-31 08:46 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 105.9375 | 34 | 71.9375 | 2.3684 | -16.3653 |  | 2.949 | 2.949 | -0.27275 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-22 | 2025-05-14 | Y | BIZ | X25030757040 | AMBICA INTERNATIONAL CORPORATION | MERVILLE ACCESS, KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 153.192 | 402.96 | 378.94 | MODIFICATION | 1682589.76 | 212028.41 |  | 0% | 2025-05-02 16:44 | 2025-05-09 14:42 | 2025-05-09 |  | 2025-05-28 10:13 |  | 25.7285 | 18.8132 | -45805.4257 | 2025-05-21 12:22 | 2025-05-30 08:00 | 2025-06-21 16:44 | 0.88442 | -763.4238 | 32 | 28 | 21.8182 | 27.6364 | 18.8182 | 60 | 57 | 52 | 2025-07-27 10:13 | 89.5743 | [8 empty] | NO COC |  | 2025-06-12 10:13 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 25.7285 | 0 | 25.7285 | 0.88442 | 63.5743 |  | 3.0698 | 3.0698 | 1.0596 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-15 | 2025-05-14 |  | HMB | X25041157540 | DULCINEA BALCE SANTOS | HAITI, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | WO DONE (FCOMP) |  | VJC | SCHED | Jenneth Madrid | 198.7786 | 442.65 | 45.08 | MODIFICATION | 980637.8 | 244599.78 |  | 0% | 2025-05-02 16:45 | 2025-05-09 14:33 | 2025-05-09 |  |  |  | -45779.6979 | -45786.6062 | 0 | 2025-05-25 17:20 | 2025-06-04 15:53 | 2025-06-21 16:45 | -1319.3455 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45779.6979 | 0 | -45779.6979 | -1319.3455 | 0 |  | 2.5736 | 2.5736 | 0 | 76.3021 | NON-REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-15 | 2025-05-14 |  | HMB | X25010240572 | ARARA DEVELOPMENT CORPORATION | ALEXANDER, PALM PLACE PREMIER LEVITOWN 10, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 1.73 | 4.03 | 23 | NEW | 20007.81 | 3462.72 |  | 0% | 2025-05-02 16:53 | 2025-05-09 14:39 | 2025-05-09 |  |  |  | -45779.7035 | -45786.6104 | 0 | 2025-05-21 11:28 | 2025-05-30 06:49 | 2025-06-21 16:53 | -1576.8565 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45779.7035 | 0 | -45779.7035 | -1576.8565 | 0 |  | 3.0758 | 3.0758 | 0 | 76.2965 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-15 | 2025-05-14 |  | HMB | X25010240570 | ARARA DEVELOPMENT CORPORATION | ALEXANDER, PALM PLACE PREMIER LEVITOWN 10, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 147.2826 | 253.71 | 23 | NEW | 654716.53 | 167431.29 |  | 0% | 2025-05-02 16:54 | 2025-05-09 14:39 | 2025-05-09 |  |  |  | -45779.7042 | -45786.6104 | 0 | 2025-05-24 13:45 | 2025-06-03 04:54 | 2025-06-21 16:54 | -1380.6577 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45779.7042 | 0 | -45779.7042 | -1380.6577 | 0 |  | 2.693 | 2.693 | 0 | 76.2958 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-15 | 2025-05-14 |  | HMB | X24083326443 | SIONIL BUILDERS CORPORATION | ROAD 9E, UNITED PARANAQUE 5, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 87.7004 | 405.28 | 5 | NEW | 507884.07 | 83989.75 |  | 0% | 2025-05-02 16:58 | 2025-05-09 14:40 | 2025-05-09 |  |  |  | -45779.7069 | -45786.6111 | 0 | 2025-05-25 17:33 | 2025-06-04 16:06 | 2025-06-21 16:58 | -1319.3457 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-16 | CXP-8167,CXP-8168,CXP-8170 | 0 | -45779.7069 | 0 | -45779.7069 | -1319.3457 | 0 |  | 2.5734 | 2.5734 | 0 | 76.2931 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-22 | 2025-05-14 |  | HMB | X25020485881 | CORAZON SISON MANALO | EVERLASTING, SOUTH GREENHEIGHTS VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 133.1267 | 141.24 | 36 | MODIFICATION | 340226.15 | 87755.27 |  | 0% | 2025-05-05 08:45 | 2025-05-14 12:29 | 2025-05-14 |  | 2025-08-09 09:01 |  | 96.0111 | 86.8556 | -45878.3757 | 2025-05-26 13:43 | 2025-06-05 00:38 | 2025-06-24 08:45 | 2.9747 | -764.6396 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-10-08 09:01 | 16.6243 | [8 empty] | NO COC |  | 2025-08-24 09:01 | #VALUE! | [18 empty] | #N/A | DS1-8164, 054780, 527596 | 0 | 96.0111 | 0 | 96.0111 | 2.9747 | -9.3757 |  | 2.6842 | 2.6842 | -0.15626 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-22 | 2025-05-14 |  | HMB | X25030842100 | CITY GOVERNMENT OF TAGUIG | MAGSAYSAY, PUROK 2A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 11.9833 | 12.9 | 7 | NEW | 148625.41 | 11086.84 |  | 0% | 2025-05-05 08:50 | 2025-05-12 13:46 | 2025-05-13 | 2025-06-04 | 2025-06-04 |  | 29.6319 | 22.4264 | -45812 | 2025-05-24 03:25 | 2025-06-01 22:46 | 2025-06-24 08:50 | 1.0207 | -763.5333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-03 | 83 | [8 empty] | FOR AUDIT |  | 2025-06-19 | 29 | 2025-06-04 | 2025-07-18 | [8 empty] | Y | 2025-06-10 | [6 empty] | 2025-05-22 | TLN-527994 | 0 | 29.6319 | 0 | 29.6319 | 1.0207 | 57 |  | 2.984 | 2.984 | 0.95 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-22 | 2025-05-14 |  | CBG | X24103987583 | DITO TELECOMMUNITY CORPORATION | LIRIO, SAN ISIDRO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 77.1103 | 226.68 | 22 | NEW | 463503.11 | 82828.5 |  | 0% | 2025-05-05 11:16 | 2025-05-12 13:41 | 2025-05-13 |  |  |  | -45782.4694 | -45789.5701 | 0 | 2025-05-27 08:07 | 2025-06-05 23:16 | 2025-06-24 11:16 | -1380.7411 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-23 | cy9-5937,cy9-5938,cy9-8054,tln-201770 | 0 | -45782.4694 | 0 | -45782.4694 | -1380.7411 | 0 |  | 2.6097 | 2.6097 | 0 | 73.5306 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-14 | 2025-05-14 | Y | HMB | X25010252654 | ENRIQUE JOSE NUGUID LIM | BURGOS, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 160.3052 | 451.25 | 25 | NEW | 802915.53 | 185129.56 |  | 0% | 2025-05-05 14:49 | 2025-05-14 12:28 | 2025-05-14 |  | 2025-07-04 |  | 59.3826 | 50.4806 | -45842 | 2025-05-28 15:24 | 2025-06-07 13:57 | 2025-06-24 14:49 | 1.7114 | -764.0333 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 2025-09-02 | 53 | [8 empty] | NO COC |  | 2025-07-19 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 59.3826 | 0 | 59.3826 | 1.7114 | 27 |  | 2.4895 | 2.4895 | 0.45 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-07 | 2025-05-08 | Y | BIZ | X25020524644 | TIERRA BELLA PROPERTIES INC. | PRES. M. ROXAS, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 27.5028 | 53.43 | 131 | NEW | 676674.86 | 45931.94 |  | 0% | 2025-05-05 14:52 | 2025-05-07 13:20 | 2025-05-08 | 2025-05-15 | 2025-05-15 |  | 9.3806 | 7.4444 | -45792 | 2025-05-24 02:21 | 2025-06-01 19:49 | 2025-06-24 14:52 | 0.32755 | -763.2 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-07-14 | 103 | [8 empty] | FOR AUDIT |  | 2025-05-30 | 38 | 2025-05-15 | 2025-07-07 | [8 empty] | Y | 2025-05-14 | [6 empty] | 2025-05-08 | TLN-527785 | 0 | 9.3806 | 0 | 9.3806 | 0.32755 | 77 |  | 3.0163 | 3.0163 | 1.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-07 | 2025-05-08 | Y | BIZ | X25020630582 | TIERRA BELLA PROPERTIES INC. | PRES. M. ROXAS, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 79.0485 | 172.85 | 131 | NEW | 482774.42 | 148527.48 |  | 0% | 2025-05-05 14:54 | 2025-05-07 13:21 | 2025-05-08 | 2025-05-15 | 2025-05-15 |  | 9.3792 | 7.4437 | -45792 | 2025-05-25 01:36 | 2025-06-03 01:16 | 2025-06-24 14:54 | 0.31339 | -763.2 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-14 | 103 | [8 empty] | FOR AUDIT |  | 2025-05-30 | 49 | 2025-05-15 | 2025-07-18 | [16 empty] | 2025-05-08 | C5-8239,C5-5002 | 0 | 9.3792 | 0 | 9.3792 | 0.31339 | 77 |  | 2.8862 | 2.8862 | 1.2833 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-14 | 2025-05-08 | Y | CBG | X25020582768 | MIESCOR INFRASTRUCTURE DEVELOPMENT CORPORATION | BAGONG SILANG INTERIOR, QUEEN'S ROW EAST , BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 18.6528 | 31.3 | 31 | NEW | 263217.11 | 26892.84 |  | 0% | 2025-05-06 09:31 | 2025-05-07 13:22 | 2025-05-08 |  | 2025-05-22 |  | 15.6035 | 14.4431 | -45799 | 2025-05-25 04:06 | 2025-06-02 23:27 | 2025-06-25 09:31 | 0.53745 | -763.3167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [10 empty] | Y | 2025-05-22 | [6 empty] | #N/A | #N/A | 0 | 15.6035 | 0 | 15.6035 | 0.53745 | 70 |  | 2.9486 | 2.9486 | 1.1667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-22 | 2025-05-14 |  | CBG | X23072775098 | DITO TELECOMMUNITY CORPORATION | MANGGA, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 37.5368 | 67.4 | 31 | NEW | 304675.26 | 40481 |  | 0% | 2025-05-06 10:14 | 2025-05-12 13:45 | 2025-05-13 |  | 2025-08-03 |  | 88.5736 | 82.4271 | -45872 | 2025-05-26 12:17 | 2025-06-04 16:02 | 2025-06-25 10:14 | 2.8776 | -764.5333 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-10-02 | 23 | Third party concern (Other than the applicant) | Y | Y |  |  | 2025-06-04 | 27 | 2025-07-01 | NO COC | AUDITED | 2025-08-18 | #VALUE! |  |  | 2025-08-13 | RLM | [14 empty] | 2025-05-22 | DS1-8157, TLN-527237 | 0 | 88.5736 | 27 | 61.5736 | 2.0004 | -3 | 2.8776 | 2.7801 | -0.097464 | -0.05 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Jenneth Madrid
2025-05-13 | 2025-05-14 | Y | BIZ | X25020415616 | SOUTH METRO ICE PLANT CORP. | NATIONAL, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 64.2368 | 141.79 | 280 | NEW | 955389.18 | 104026.12 |  | 0% | 2025-05-06 14:09 | 2025-05-09 14:24 | 2025-05-09 |  | 2025-06-21 |  | 45.4104 | 42.4 | -45829 | 2025-05-25 02:20 | 2025-06-02 19:58 | 2025-06-25 14:09 | 1.5835 | -763.8167 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-08-20 | 66 | Special LGU permits | Y | Y |  |  | 2025-06-03 | 2 | 2025-06-05 | NO COC |  | 2025-07-06 | #VALUE! | [10 empty] | Y | 2025-06-18 | [6 empty] | 2025-05-14 | DQ1-0085, TLN-521955 | 0 | 45.4104 | 2 | 43.4104 | 1.5138 | 40 | 1.5835 | 2.9784 | 1.3949 | 0.66667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | Isan Carlo Lazaro
2025-05-23 | 2025-05-26 |  | MN | P2502183605 | Relocation of Pole along Molino Rd.SM Molino-Zapote Bacoor, Cavite -Segment 14 | LIGAS III LIGAS III BACOOR CAVITE | BACOOR CITY | DASMA | for follow up sa DPWH as per clyde royo |  | AVECO | SCHED | Ronilo Gange Jr. | 1756 | 10030.65 | - | RELOC | 8140554.08 | 1508048.68 |  | 0% | 2025-05-06 18:43 | 2025-05-12 17:30 | 2025-05-26 |  |  |  | -45783.7799 | -45789.7292 | 0 | 2025-05-22 01:44 | 2025-05-29 22:49 | 2025-06-25 18:43 | -1877.135 | 0 | 50 | 20 | 18.2927 | 23.1707 | 15.2927 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-26 | CV6-8176,CW6-8121,CW6-8122,CX6-8166,CX6-1744,CX6-8167,CX6-8165,CX6-8168,CX6-8169,CX6-8170,CX6-8171,CX6-8172,CX6-8173.TLN-047298,TLN-139517,TLN-046577 | 0 | -45783.7799 | 0 | -45783.7799 | -1877.135 | 0 |  | 3.494 | 3.494 | 0 | 72.2201 | NON-REV | 0-3 MONTHS
2025-05-22 | 2025-05-14 |  | CBG | X23072739849 | DITO TELECOMMUNITY CORPORATION | MEDEL, ZONE 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 154.5843 | 891.66 | 31 | NEW | 1183894.26 | 164844.18 |  | 0% | 2025-05-07 07:28 | 2025-05-12 13:44 | 2025-05-13 |  |  |  | -45784.3111 | -45789.5722 | 0 | 2025-06-01 03:30 | 2025-06-11 13:39 | 2025-06-26 07:28 | -1233.6328 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-22 | B8-0910,B8-0911,B8-8058,B8-8059,B8-8060,B8-8061,TLN-518072 | 0 | -45784.3111 | 0 | -45784.3111 | -1233.6328 | 0 |  | 2.2819 | 2.2819 | 0 | 71.6889 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0
2025-05-23 | 2025-05-26 |  | MN | P2502183604 | Relocation of Pole along Molino Rd.SM Molino-Zapote Bacoor, Cavite -Segment 13 | SAPPHIRE LUCKY VILLAGE MOLINO I BACOOR CAVITE | BACOOR CITY | DASMA | pole reloc on going 8-13-25 |  | AVECO | SCHED | Ronilo Gange Jr. | 975.49 | 7332.1 | - | RELOC | 6557578.84 | 837772.58 |  | 0% | 2025-05-07 07:45 | 2025-05-13 09:51 | 2025-05-26 |  |  |  | -45784.3229 | -45790.4104 | 0 | 2025-05-22 14:46 | 2025-05-30 11:51 | 2025-06-26 07:45 | -1877.1572 | 0 | 50 | 20 | 18.2927 | 23.1707 | 15.2927 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-05-26 | CV6-8176.CW6-8121.CW6-8122.CX6-8166.CX6-1744.CX6-8167.CX6-8165.CX6-8168.CX6-8169.CX6-8171.CX6-8172.CX6-8173.-TLN-047298.TLN-139517.TLN-046577 | 0 | -45784.3229 | 0 | -45784.3229 | -1877.1572 | 0 |  | 3.4718 | 3.4718 | 0 | 71.6771 | NON-REV | 0-3 MONTHS
2025-05-22 | 2025-05-15 |  | HMB | X25020424030 | ALMA M. TANWANGCO | BLOCK 8, AFP OVAI PH 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 18.2728 | 68.19 | 195.8 | NEW | 504632.65 | 58620.96 |  | 0% | 2025-05-07 09:56 | 2025-05-14 12:33 | 2025-05-14 | 2025-06-14 | 2025-06-14 08:29 |  | 37.9396 | 30.8306 | -45822.3535 | 2025-05-25 21:25 | 2025-06-03 14:53 | 2025-06-26 09:56 | 1.3248 | -763.7059 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-08-13 08:29 | 72.6465 | [8 empty] | FOR AUDIT |  | 2025-06-29 08:29 | 38.6465 | 2025-06-14 | 2025-08-07 | [8 empty] | Y | 2025-06-11 | [6 empty] | 2025-05-22 | TLN-527463 | 0 | 37.9396 | 0 | 37.9396 | 1.3248 | 46.6465 |  | 2.9536 | 2.9536 | 0.77744 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-14 | 2025-05-14 |  | BIZ | X25010134416 | BROER BUILDERS CONSTRUCTION CORPORATION | NIOG III, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 77.3521 | 234.77 | 270 | NEW | 1131856.17 | 134482.27 |  | 0% | 2025-05-07 10:01 | 2025-05-14 12:31 | 2025-05-14 |  | 2025-06-07 |  | 30.5826 | 23.4785 | -45815 | 2025-05-26 10:41 | 2025-06-04 07:40 | 2025-06-26 10:01 | 1.0413 | -763.5833 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 60 | 57 | 52 | 2025-08-06 | 80 | [8 empty] | NO COC |  | 2025-06-22 | #VALUE! | [10 empty] | Y | 2025-06-05 | [6 empty] | #N/A | #N/A | 0 | 30.5826 | 0 | 30.5826 | 1.0413 | 54 |  | 2.8798 | 2.8798 | 0.9 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-14 | 2025-05-14 |  | HMB | X24103991157 | REBECCA S. GONZALES | NEWPORT, AVIDA SETTINGS CAVITE PH2, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 65.8488 | 162.89 | 23.5 | NEW | 383498.61 | 72698.27 |  | 0% | 2025-05-07 14:40 | 2025-05-14 12:31 | 2025-05-14 |  |  |  | -45784.6111 | -45791.5215 | 0 | 2025-05-28 19:38 | 2025-06-07 06:33 | 2025-06-26 14:40 | -1418.5403 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45784.6111 | 0 | -45784.6111 | -1418.5403 | 0 |  | 2.6146 | 2.6146 | 0 | 71.3889 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0
2025-05-09 | 2025-05-14 |  | HMB | X25051494715 | CITY GOVERNMENT OF TAGUIG | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 13.23 | 31.51 | 896 | NEW | 57603.09 | 11367.57 |  | 0% | 2025-05-08 17:48 | 2025-05-09 07:17 | 2025-05-09 | 2025-05-13 | 2025-05-13 |  | 4.2583 | 3.6965 | -45790 | 2025-05-22 05:58 | 2025-05-29 15:37 | 2025-06-27 17:48 | 0.19348 | -763.1667 | 20 | 23 | 16.5072 | 20.9091 | 13.5072 | 60 | 57 | 52 | 2025-07-12 | 105 | [8 empty] | FOR AUDIT |  | 2025-05-28 | 71 | 2025-05-13 | 2025-08-07 | [16 empty] | #N/A | #N/A | 0 | 4.2583 | 0 | 4.2583 | 0.19348 | 79 |  | 3.7828 | 3.7828 | 1.3167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-20 | 2025-05-14 |  | CBG | X23072871198 | DITO TELECOMMUNITY CORPORATION | SAN JUANICO, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 17.3228 | 25.12 | 31 | NEW | 202562.28 | 21584.09 |  | 0% | 2025-05-09 08:33 | 2025-05-12 13:43 | 2025-05-13 | 2025-05-28 | 2025-05-28 14:27 |  | 19.2458 | 16.0306 | -45805.6021 | 2025-05-28 03:08 | 2025-06-05 22:29 | 2025-06-28 08:33 | 0.66291 | -763.4267 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 14:27 | 89.3979 | [8 empty] | FOR AUDIT |  | 2025-06-12 14:27 | 24.3979 | 2025-05-28 | 2025-07-07 | [8 empty] | Y | 2025-06-11 | [6 empty] | N/A | N/A | 0 | 19.2458 | 0 | 19.2458 | 0.66291 | 63.3979 |  | 2.8466 | 2.8466 | 1.0566 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
| OK |  | MN | P2503186512 | Relocation of pole Due to rd. Widening Buendia St,Tunasan Muntinlupa | ARANDIA TUNASAN TUNASAN MUNTINLUPA METRO MANILA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | INPRG | Justine Ramos | 447.34 | 474.14 | 0 | RELOC | 864852.9 | 362673.97 |  | 0% | 2025-05-09 09:33 | 2025-05-26 08:30 | 2025-05-26 |  |  |  | -45786.3979 | -45803.3542 | 0 | 2025-06-01 10:08 | 2025-06-11 08:41 | 2025-06-28 09:33 | -1319.5386 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [8 empty] | DQ2-0062, DR2-8076 | 0 | -45786.3979 | 0 | -45786.3979 | -1319.5386 | 0 |  | 2.3805 | 2.3805 | 0 | 69.6021 | NON-REV | 0-3 MONTHS
2025-05-22 | 2025-05-16 |  | HMB | X25051535307 | PHILIP SIGFRID ALFARO FORTUN | SAN AGUSTIN, SUSANA HTS SUBD VILL 6, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 65.4447 | 132.4 | 80 | NEW | 447937.96 | 96360.01 |  | 0% | 2025-05-09 10:01 | 2025-05-16 10:47 | 2025-05-16 |  | 2025-05-16 11:31 |  | 7.0625 | 0.030556 | -45793.4799 | 2025-05-29 18:18 | 2025-06-07 23:42 | 2025-06-28 10:01 | 0.22689 | -763.2247 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-07-15 11:31 | 101.5201 | [8 empty] | FOR AUDIT | superseded WO. X23104092125 | 2025-05-31 11:31 | -4.4799 | 2025-05-15 | 2025-05-27 | [8 empty] | Y | 2025-05-13 | [6 empty] | N/A | N/A | 0 | 7.0625 | 0 | 7.0625 | 0.22689 | 75.5201 |  | 2.6531 | 2.6531 | 1.2587 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-19 | 2025-05-16 |  | HMB | X23093793238 | JERRY TIU PURA | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 81.11 | 139.81 | 90 | MODIFICATION | 423863.1 | 52201.72 |  | 0% | 2025-05-09 17:20 | 2025-05-16 10:49 | 2025-05-16 |  |  |  | -45786.7222 | -45793.4507 | 0 | 2025-05-30 01:37 | 2025-06-08 07:01 | 2025-06-28 17:20 | -1470.9761 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45786.7222 | 0 | -45786.7222 | -1470.9761 | 0 |  | 2.6433 | 2.6433 | 0 | 69.2778 | NON-REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0
2025-05-14 | 2025-05-14 | Y | BIZ | X25030926983 | PANCITERIA LIDO CHINESE CUISINE CORP. | MOLINO BLVD., MAMBOG IV, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 111.5933 | 340.66 | 106 | NEW | 961200.12 | 158218.3 |  | 0% | 2025-05-09 17:23 | 2025-05-12 13:28 | 2025-05-13 |  | 2025-05-22 |  | 12.2757 | 9.4389 | -45799 | 2025-05-30 06:05 | 2025-06-08 12:41 | 2025-06-28 17:23 | 0.39129 | -763.3167 | 30 | 32 | 23.5294 | 29.8039 | 20.5294 | 60 | 57 | 52 | 2025-07-21 | 96 | [8 empty] | NO COC |  | 2025-06-06 | #VALUE! | [10 empty] | Y | 2025-05-15 | [6 empty] | #N/A | #N/A | 0 | 12.2757 | 0 | 12.2757 | 0.39129 | 70 |  | 2.6225 | 2.6225 | 1.1667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0 | [9 empty] | RONILO GANGE JR.
2025-05-19 | 2025-05-16 |  | HMB | X25041167301 | CITY GOVERNMENT OF PARAÑAQUE | FAME, 4TH ESTATE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing may tatangalin na bubong kasi po di maka pwesto pag tayo ng poste |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 119.5912 | 319.56 | 184 | NEW | 1207733.9 | 206131.04 |  | 0% | 2025-05-09 17:27 | 2025-05-16 10:51 | 2025-05-16 |  |  |  | -45786.7271 | -45793.4521 | 0 | 2025-05-30 06:09 | 2025-06-08 12:45 | 2025-06-28 17:27 | -1459.4519 | 0 | 30 | 32 | 23.5294 | 29.8039 | 20.5294 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45786.7271 | 0 | -45786.7271 | -1459.4519 | 0 |  | 2.6224 | 2.6224 | 0 | 69.2729 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0
2025-05-19 | 2025-05-16 |  | HMB | X25041167142 | CITY GOVERNMENT OF PARAÑAQUE | STA. LUCIA, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 82.2747 | 144.48 | 200 | MODIFICATION | 870200.65 | 106747.8 |  | 0% | 2025-05-09 17:29 | 2025-05-16 10:54 | 2025-05-16 |  | 2025-07-12 |  | 63.2715 | 56.5458 | -45850 | 2025-05-29 04:11 | 2025-06-07 03:51 | 2025-06-28 17:29 | 2.1141 | -764.1667 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-09-10 | 45 | With scheduled PAI / Materials unavailability | Y | Y |  |  | 2025-06-24 | 14 | 2025-07-08 | NO COC |  | 2025-07-27 | #VALUE! | [18 empty] | 2025-05-19 | CY9-8087 | 0 | 63.2715 | 45846 | 49.2715 | 1.6463 | 19 |  | 2.749 | 2.749 | 0.31667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-22 | 2025-05-16 |  | HMB | X25041167361 | CITY GOVERNMENT OF PARAÑAQUE | NINOY AQUINO, LA HUERTA, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 35.8428 | 115.24 | 176 | MODIFICATION | 792216.4 | 99055.28 |  | 0% | 2025-05-09 17:32 | 2025-05-16 10:52 | 2025-05-16 |  | 2025-06-21 |  | 42.2694 | 35.5472 | -45829 | 2025-05-29 04:14 | 2025-06-07 03:54 | 2025-06-28 17:32 | 1.4124 | -763.8167 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-08-20 | 66 | [8 empty] | NO COC |  | 2025-07-06 | #VALUE! | [18 empty] | N/A | N/A | 0 | 42.2694 | 0 | 42.2694 | 1.4124 | 40 |  | 2.7489 | 2.7489 | 0.66667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-22 | 2025-05-23 | Y | HMB | X25010310869 | CAT COMICS LAND INC. | ROSE OF HEAVEN, TALON VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 93.2287 | 122.65 | 78 | NEW | 585320.96 | 105380.41 |  | 0% | 2025-05-13 13:02 | 2025-05-21 13:14 | 2025-05-23 | 2025-06-13 | 2025-06-13 |  | 30.4569 | 22.4486 | -45821 | 2025-06-02 21:19 | 2025-06-12 02:43 | 2025-07-02 13:02 | 0.97848 | -763.6833 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-12 | 74 | [8 empty] | FOR AUDIT |  | 2025-06-28 | 11 | 2025-06-13 | 2025-07-09 | [8 empty] | Y | 2025-06-12 | [6 empty] | #N/A | 195586, CV8-8114, CV8-8115, 527320 | 0 | 30.4569 | 0 | 30.4569 | 0.97848 | 48 |  | 2.5206 | 2.5206 | 0.8 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-06-05 | 2025-05-21 13:16 |  | BIZ | X24093671155 | CHARLENE L. BILIGAN | OLA, AFP OVAI PHASE IV, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | WITH PROBLEM (ROW) |  | VJC | SCHED | Jenneth Madrid | 76.9916 | 183.37 | 48 | NEW | 526313 | 90297.43 |  | 0% | 2025-05-13 16:49 | 2025-05-21 13:18 | 2025-05-21 13:16 |  |  |  | -45790.7007 | -45798.5542 | 0 | 2025-06-03 21:47 | 2025-06-13 08:42 | 2025-07-02 16:49 | -1418.729 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | #N/A | #N/A | 0 | -45790.7007 | 0 | -45790.7007 | -1418.729 | 0 |  | 2.4259 | 2.4259 | 0 | 65.2993 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0
2025-05-22 | 2025-05-22 |  | BIZ | X25020700828 | ROSALIE MONTEMAYOR CRUZ | ALABANG-ZAPOTE, TALON I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 4.79 | 42.54 | 140 | NEW | 90879.89 | 36551.51 |  | 0% | 2025-05-14 13:22 | 2025-05-21 13:14 | 2025-05-21 13:16 |  | 2025-06-21 |  | 37.4431 | 30.4486 | -45829 | 2025-05-31 21:30 | 2025-06-09 07:40 | 2025-07-03 13:22 | 1.3807 | -763.8167 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-08-20 | 66 | [8 empty] | FOR AUDIT |  | 2025-07-06 | -3 | 2025-06-18 | 2025-07-03 | [8 empty] | Y | 2025-06-17 | [6 empty] | N/A | N/A | 0 | 37.4431 | 0 | 37.4431 | 1.3807 | 40 |  | 2.8557 | 2.8557 | 0.66667 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-22 | 2025-05-23 |  | BIZ | X25041354477 | FLEXI PACK AND PRINT CO. PHILS. INC. | CAPITOLINE HILLS, ITALIA 500-BF HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Jenneth Madrid | 20.35 | 31.31 | - | TERMINATION | 33312.15 | 26945.3 |  | 0% | 2025-05-14 13:32 | 2025-05-21 13:23 | 2025-05-23 |  | 2025-06-23 |  | 39.4361 | 32.4424 | -45831 | 2025-05-26 13:32 | 2025-06-02 13:32 | 2025-07-03 13:32 | 1.9718 | -763.85 | 20 | 20 | 15 | 19 | 12 | 60 | 57 | 52 | 2025-08-22 | 64 | [8 empty] | NO COC |  | 2025-07-08 | #VALUE! | [18 empty] | #N/A | #N/A | 0 | 39.4361 | 0 | 39.4361 | 1.9718 | 38 |  | 3.8718 | 3.8718 | 0.63333 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-21 | 2025-05-19 | Y | BIZ | X25030779048 | A R B CONSTRUCTION COMPANY, INC. | BLOCK 3, SOLDIERS HILLS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 86.9895 | 138.92 | 150 | NEW | 962706.76 | 118986.45 |  | 0% | 2025-05-15 10:20 | 2025-05-16 15:23 | 2025-05-19 |  | 2025-05-31 |  | 15.5694 | 14.359 | -45808 | 2025-06-03 21:02 | 2025-06-12 20:42 | 2025-07-04 10:20 | 0.52023 | -763.4667 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | NO COC |  | 2025-06-15 | #VALUE! | [10 empty] | Y | 2025-05-30 | [6 empty] | 2025-06-09 | DS1-2076, DS1-8178, DS1-1011, DS1-8177, ALB1-2360, DS1-8179, 086951, DS1-8157, 527237, DS1-8181 | 0 | 15.5694 | 0 | 15.5694 | 0.52023 | 61 |  | 2.5585 | 2.5585 | 1.0167 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-26 | 2025-05-21 13:16 |  | HMB | X25010310103 | RODOLFO BEDIONES | KAIMITO, MOLAVE PARK VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 1.73 | 3.47 | 25 | MODIFICATION | 18255.36 | 2981.52 |  | 0% | 2025-05-15 15:22 | 2025-05-21 13:33 | 2025-05-21 13:16 | 2025-05-28 | 2025-05-28 08:24 |  | 12.7097 | 6.7854 | -45805.35 | 2025-06-03 09:57 | 2025-06-12 05:18 | 2025-07-04 15:22 | 0.43778 | -763.4225 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-07-27 08:24 | 89.65 | [8 empty] | FOR AUDIT |  | 2025-06-12 08:24 | 35.65 | 2025-05-28 | 2025-07-18 | [8 empty] | Y | 2025-05-29 | [6 empty] | N/A |  | 0 | 12.7097 | 0 | 12.7097 | 0.43778 | 63.65 |  | 2.6302 | 2.6302 | 1.0608 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-26 | 2025-05-26 |  | BIZ | X25041329943 | HARD DISCOUNT PHILIPPINES, INC. | BENEDICTINE, STA. ANA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 17.78 | 32.94 | 19 | NEW | 201891.36 | 28303 |  | 0% | 2025-05-16 12:38 | 2025-05-23 13:45 | 2025-05-26 |  | 2025-07-28 |  | 72.4736 | 65.4271 | -45866 | 2025-06-04 07:13 | 2025-06-13 02:34 | 2025-07-05 12:38 | 2.4963 | -764.4333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | With scheduled PAI | Y | Y |  |  | 2025-07-02 | 7 | 2025-07-09 | NO COC |  | 2025-08-12 | #VALUE! | [18 empty] | N/A |  | 0 | 72.4736 | 7 | 65.4736 | 2.2552 | 3 |  | 2.5996 | 2.5996 | 0.05 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-28 | 2025-05-28 |  | BIZ | X24124789165 | GERALD LUEGO CHUA | AGUIRRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 1.73 | 3.52 | 23 | NEW | 17775.26 | 3024.46 |  | 0% | 2025-05-16 12:38 | 2025-05-23 13:47 | 2025-05-28 |  | 2025-08-01 07:21 |  | 76.7799 | 69.7319 | -45870.3063 | 2025-06-04 07:13 | 2025-06-13 02:34 | 2025-07-05 12:38 | 2.6446 | -764.5051 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-30 07:21 | 24.6937 | [8 empty] | NO COC |  | 2025-08-16 07:21 | #VALUE! | [18 empty] | N/A | N/A | 0 | 76.7799 | 0 | 76.7799 | 2.6446 | -1.3063 |  | 2.5996 | 2.5996 | -0.021771 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-26 | 2025-05-26 |  | BIZ | X25030908480 | 1DYNAMIX AUTOMOTIVE INC. | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 9.8533 | 12.22 | 17.6 | NEW | 141627.94 | 10502.63 |  | 0% | 2025-05-16 12:40 | 2025-05-23 13:44 | 2025-05-26 |  | 2025-08-09 12:47 |  | 85.0049 | 77.9604 | -45878.5326 | 2025-06-04 07:15 | 2025-06-13 02:36 | 2025-07-05 12:40 | 2.9279 | -764.6422 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-08 12:47 | 16.4674 | [8 empty] | NO COC |  | 2025-08-24 12:47 | #VALUE! | [18 empty] | 2025-05-26 | TLN-530178 | 0 | 85.0049 | 0 | 85.0049 | 2.9279 | -9.5326 |  | 2.5996 | 2.5996 | -0.15888 |  | REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-06-05 | 2025-06-03 |  | HMB | X25020590279 | CHRISTOPHER JOHN YU SAM CHUA | PINE, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 35.5695 | 126.81 | 74 | NEW | 353963.62 | 41695.82 |  | 0% | 2025-05-16 15:24 | 2025-05-23 13:44 | 2025-06-03 |  |  |  | -45793.6417 | -45800.5722 | 0 | 2025-06-05 23:41 | 2025-06-15 05:05 | 2025-07-05 15:24 | -1471.1984 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-06-09 | CT8-8104,TLN-527651 | 0 | -45793.6417 | 0 | -45793.6417 | -1471.1984 | 0 |  | 2.421 | 2.421 | 0 | 62.3583 | REV | 0-3 MONTHS |  |  | FOR ISSUANCE |  |  | 0
2025-06-03 | 2025-05-27 |  | HMB | X24072979788 | JESSICA INTAL COSTUNA | C. ARELLANO, KATARUNGAN VILLAGE, MUNTINLUPA | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.9228 | 54.17 | 85 | MODIFICATION | 393654.99 | 46142.56 |  | 0% | 2025-05-19 14:14 | 2025-05-26 08:32 | 2025-05-27 |  | 2025-06-09 |  | 20.4069 | 13.6444 | -45817 | 2025-06-07 21:27 | 2025-06-16 20:10 | 2025-07-08 14:14 | 0.68632 | -763.6167 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-08-08 | 78 | [8 empty] | NO COC |  | 2025-06-24 | #VALUE! | [10 empty] | Y | [8 empty] | CR9-5128, 523175 | 0 | 20.4069 | 0 | 20.4069 | 0.68632 | 52 |  | 2.4352 | 2.4352 | 0.86667 |  | NON-REV |  |  |  | FOR ISSUANCE |  |  | 0
2025-05-27 | 2025-05-28 |  | CBG | X25030793729 | EXTRA-ORDINARY PROPERTY HOLDINGS, INC. | PHASE 1 ACCESS ROAD, AMVEL COMMERCIAL COMPLEX, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing for energize |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 155.3934 | 333.21 | 1957 | NEW | 688937.77 | 197264.94 |  | 0% | 2025-05-20 15:14 | 2025-05-27 13:41 | 2025-05-28 |  |  |  | -45797.6347 | -45804.5701 | 0 | 2025-06-03 07:14 | 2025-06-10 17:54 | 2025-07-09 15:14 | -2060.8936 | 0 | 30 | 20 | 16.6667 | 21.1111 | 13.6667 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [20 empty] | 0 | -45797.6347 | 34 | -45831.6347 | -2062.4236 | 0 |  | 3.2114 | 3.2114 | 0 | 58.3653 | REV | 0-3 MONTHS
2025-06-03 | 2025-05-28 |  | HMB | X25041239297 | BARRY NEIL NOGOY TOBIAS | ZODIAC, VERAVILLE HOMES 1, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 117.52 | 313.6 | 90 | NEW | 558952.86 |  |  | #DIV/0! | 2025-05-21 15:05 | 2025-05-27 13:37 | 2025-05-28 |  | 2025-07-18 |  | 57.3715 | 51.4326 | -45856 | 2025-06-12 03:33 | 2025-06-21 16:28 | 2025-07-10 15:05 | 1.7549 | -764.2667 | 30 | 34 | 24.5192 | 31.0577 | 21.5192 | 60 | 57 | 52 | 2025-09-16 | 39 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-08-02 | #VALUE! | [18 empty] | 2025-06-03 | CV9-8094,TLN-527857 | 0 | 57.3715 | 34 | 23.3715 | 0.71489 | 13 |  | 2.1525 | 2.1525 | 0.21667 |  | REV
2025-06-03 | 2025-05-30 |  | BIZ | X25030845883 | OCEANWIDE MARITIME SERVICES CORP. | ALIMA II, ALIMA II, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 86.0247 | 191.16 | 202 | NEW | 1038571.54 | 153742.7 |  | 0% | 2025-05-21 15:25 | 2025-05-27 13:38 | 2025-05-30 |  | 2025-07-14 |  | 53.3576 | 47.4319 | -45852 | 2025-06-09 03:36 | 2025-06-17 21:14 | 2025-07-10 15:25 | 1.8607 | -764.2 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-09-12 | 43 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-07-29 | #VALUE! | [18 empty] | 2025-06-03 | CX5-8039,CX5-8038-TLN-526198 | 0 | 53.3576 | 34 | 19.3576 | 0.67504 | 17 |  | 2.4535 | 2.4535 | 0.28333 |  | REV
2025-06-03 | 2025-06-05 |  | BIZ | X24103990265 | PRIME FEATHERS CORPORATION | APITONG, CAMELLA SPV CENTRAL PH 2, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 164.2016 | 435.67 | 68 | NEW | 881351.64 | 171342.14 |  | 0% | 2025-05-22 09:59 | 2025-05-27 13:42 | 2025-06-05 |  |  |  | -45799.416 | -45804.5708 | 0 | 2025-06-13 10:43 | 2025-06-23 02:55 | 2025-07-11 09:59 | -1372.2987 | 0 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-06-05 | CS7-8140,CS7-8141,CS7-8142,CS7-0652-TLN-526192 | 0 | -45799.416 | 34 | -45833.416 | -1373.3174 | 0 |  | 2.085 | 2.085 | 0 | 56.584 | REV | 0-3 MONTHS
| 2025-05-28 |  | BIZ | X25030835417 | CHERIE ROSE COLINAYO ZHENG | ARMELA CPD-SAVVY 25, ARMELA CPD-SAVVY 25, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 68.3969 | 118.02 | 147 | NEW | 774671.36 | 84004.6 |  | 0% | 2025-05-22 14:14 | 2025-05-27 13:39 | 2025-05-28 |  | 2025-05-31 |  | 8.4069 | 3.4313 | -45808 | 2025-06-11 00:56 | 2025-06-20 00:36 | 2025-07-11 14:14 | 0.28091 | -763.4667 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-07-30 | 87 | [8 empty] | FOR AUDIT |  | 2025-06-15 | 3 | 2025-06-04 | 2025-06-18 | [8 empty] | Y | 2025-06-03 | [8 empty] | 0 | 8.4069 | 0 | 8.4069 | 0.28091 | 61 |  | 2.3191 | 2.3191 | 1.0167 |  | REV
2025-05-27 | 2025-05-27 |  | BIZ | X25041327101 | ERLINDA CRUZ RABE | WEST SERVICE, MARCELO GREEN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 3.92 | 55.14 | 47 | NEW | 114127.36 | 47377.65 |  | 0% | 2025-05-22 14:16 | 2025-05-27 | 2025-05-29 |  | 2025-07-31 |  | 69.4056 | 65 | -45869 | 2025-06-11 16:19 | 2025-06-20 20:04 | 2025-07-11 14:16 | 2.2548 | -764.4833 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-09-29 | 26 | [8 empty] | NO COC |  | 2025-08-15 | #VALUE! | [10 empty] | Y | 2025-07-30 | [8 empty] | 0 | 69.4056 | 0 | 69.4056 | 2.2548 | 0 |  | 2.2548 | 2.2548 | 0 |  | REV
2025-05-27 | 2025-05-28 |  | CBG | R23957713 | ASEANA BUSINESS PARK ESTATE ASSOCIATION, INC.,, CBG | KIUKOK, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 156.647 | 280.92 | - | RELOC | 261303.15 | 241379.84 |  | 0% | 2025-05-22 16:33 | 2025-05-27 13:41 | 2025-05-28 |  | 2025-07-13 08:12 |  | 51.6521 | 46.7715 | -45851.3417 | 2025-06-05 02:18 | 2025-06-12 11:18 | 2025-07-11 16:33 | 2.3612 | -764.189 | 28 | 20 | 16.4063 | 20.7813 | 13.4063 | 60 | 57 | 52 | 2025-09-11 08:12 | 43.6583 | [8 empty] | NO COC |  | 2025-07-28 08:12 | #VALUE! | [20 empty] | 0 | 51.6521 | 0 | 51.6521 | 2.3612 | 17.6583 |  | 3.1685 | 3.1685 | 0.29431 |  | NON-REV
2025-06-05 | 2025-06-03 |  | HMB | X25041166032 | CHARLES GAVINO | DON MANOLO, ALABANG HILLS SUBD PH 3, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 14.8428 | 19.97 | 108 | MODIFICATION | 240761.59 | 17184.83 |  | 0% | 2025-05-23 14:45 | 2025-05-30 13:39 | 2025-06-03 |  | 2025-06-13 |  | 20.3854 | 13.4313 | -45821 | 2025-06-09 22:53 | 2025-06-18 09:03 | 2025-07-12 14:45 | 0.75171 | -763.6833 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-08-12 | 74 | [8 empty] | NO COC |  | 2025-06-28 | #VALUE! | [10 empty] | Y | 2025-06-12 | [6 empty] | 2025-06-09 | CV9-0294, 530386 | 0 | 20.3854 | 0 | 20.3854 | 0.75171 | 48 |  | 2.5217 | 2.5217 | 0.8 |  | NON-REV
2025-06-02 | 2025-06-02 |  | HMB | X25041368806 | CITY GOVERNMENT OF BACOOR | GEN. EVANGELISTA, MALIKSI III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | FCOMP | Ronilo Gange Jr. | 37.7095 | 129.72 | 55 | NEW | 498354.19 | 44193.37 |  | 0% | 2025-05-23 18:02 | 2025-05-30 13:38 | 2025-06-02 |  | 2025-06-10 |  | 17.2486 | 10.4319 | -45818 | 2025-06-13 02:19 | 2025-06-22 07:43 | 2025-07-12 18:02 | 0.55414 | -763.6333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-09 | 77 | [8 empty] | NO COC |  | 2025-06-25 | #VALUE! | [10 empty] | Y | 2025-06-05 | [6 empty] | 2025-06-02 | CX5-8041,TLN-530534 | 0 | 17.2486 | 0 | 17.2486 | 0.55414 | 51 |  | 2.1926 | 2.1926 | 0.85 |  | REV
2025-06-03 | 2025-06-03 |  | HMB | X24041311265 | KENNETH IVAN TORRES | CALO, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ENERGIZE DT 8/13 |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 66.4764 | 174.23 | 82 | MODIFICATION | 469375.96 | 81261.49 |  | 0% | 2025-05-26 13:50 | 2025-05-30 13:42 | 2025-06-03 |  | 2025-08-15 |  | 80.4236 | 76.4292 | -45884 | 2025-06-15 22:07 | 2025-06-25 03:31 | 2025-07-15 13:50 | 2.5837 | -764.7333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-10-14 | 11 | [10 empty] | 2025-08-30 | #VALUE! | [10 empty] | Y | [7 empty] | 2025-06-03 | CS9-0233, CS9-0232, 521562, CS9-0211, CS9-0231 | 0 | 80.4236 | 0 | 80.4236 | 2.5837 | -15 |  | 2.1018 | 2.1018 | -0.25 |  | NON-REV
2025-06-03 | 2025-06-03 |  | HMB | X24114505637 | XERXES ULTRA GARCIA | PASEO DE LAS ACACIAS, SUSANA HEIGHTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 71.929 | 197.88 | 80 | MODIFICATION | 557269.63 | 101178.71 |  | 0% | 2025-05-26 13:53 | 2025-05-30 13:44 | 2025-06-03 |  | 2025-07-03 |  | 37.4215 | 33.4278 | -45841 | 2025-06-15 22:10 | 2025-06-25 03:34 | 2025-07-15 13:53 | 1.2022 | -764.0167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-09-01 | 54 | [8 empty] | NO COC |  | 2025-07-18 | #VALUE! | [10 empty] | Y | 2025-06-25 | [6 empty] | 2025-06-03 | DR1-2184, DR1-2198, DR1-2199, DR1-8096, DR1-2200, 526562, DR1-2201 | 0 | 37.4215 | 0 | 37.4215 | 1.2022 | 28 |  | 2.1018 | 2.1018 | 0.46667 |  | NON-REV
2025-06-12 | 2025-06-03 |  | HMB | X24104277960 | MIN MIN SEE KO | BLOCK 9, PINAGSAMA PH 1 VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | NEED JOINT SURVEY FOR STAKA WITH DRAINAGE |  | VJC | SCHED | Jenneth Madrid | 119.6419 | 377.25 | 28 | MODIFICATION | 656434.05 | 123559.51 |  | 0% | 2025-05-26 17:07 | 2025-05-30 13:47 | 2025-06-03 |  |  |  | -45803.7132 | -45807.5743 | 0 | 2025-06-18 04:26 | 2025-06-27 23:27 | 2025-07-15 17:07 | -1348.6649 | 0 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-06-17 | C8-8124, C8-8125, 526379, C8-8130 | 0 | -45803.7132 | 34 | -45837.7132 | -1349.666 | 0 |  | 1.9223 | 1.9223 | 0 | 52.2868 | NON-REV | 0-3 MONTHS
2025-06-05 | OK | Y | HMB | X25030814571 | JOSE MARIA IBANEZ LANZA | NORTH 5TH, ANGELA VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 99.4145 | 273.55 | 0 | MODIFICATION | 499907.06 | 100520.98 |  | 0% | 2025-05-26 17:07 | 2025-05-28 10:20 | 2025-05-29 | 2025-07-09 | 2025-07-09 |  | 43.2868 | 41.5694 | -45847 | 2025-06-17 13:58 | 2025-06-27 05:07 | 2025-07-15 17:07 | 1.3055 | -764.1167 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-09-07 | 48 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | FOR AUDIT |  | 2025-07-24 | 1 | 2025-07-09 | 2025-07-25 | [16 empty] | 2025-06-05 | CV8-8107,CV8-8108,TLN-527848 | 0 | 43.2868 | 34 | 9.2868 | 0.28008 | 22 |  | 1.969 | 1.969 | 0.36667 |  | NON-REV
2025-06-11 | 2025-06-03 |  | HMB | X25030863348 | FRANCIS VALDEZ BATENGA | BOMBAY, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | no tapping point sa jobsite kaya po hindi malalagyan ng DT |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 9.8533 | 11.96 | 36 | MODIFICATION | 141179.76 | 10279.23 |  | 0% | 2025-05-26 17:07 | 2025-05-30 13:45 | 2025-06-03 |  |  |  | -45803.7132 | -45807.5729 | 0 | 2025-06-14 11:42 | 2025-06-23 07:03 | 2025-07-15 17:07 | -1577.6835 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-06-11 |  | 0 | -45803.7132 | 0 | -45803.7132 | -1577.6835 | 0 |  | 2.2488 | 2.2488 | 0 | 52.2868 | NON-REV | 0-3 MONTHS
2025-06-05 | 2025-06-03 |  | BIZ | X25030895832 | FD 25 TRADING CORP. | FRUTO SANTOS, ZAPOTE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 14.5228 | 38.52 | 88 | NEW | 378411 | 33095.04 |  | 0% | 2025-05-26 17:07 | 2025-05-30 13:45 | 2025-06-03 |  | 2025-07-05 |  | 39.2868 | 35.4271 | -45843 | 2025-06-13 18:54 | 2025-06-22 09:47 | 2025-07-15 17:07 | 1.3981 | -764.05 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-09-03 | 52 | [8 empty] | FOR AUDIT |  | 2025-07-20 | -6 | 2025-07-07 | 2025-07-14 | [16 empty] | 2025-06-05 | CX6-8136,TLN-526628 | 0 | 39.2868 | 0 | 39.2868 | 1.3981 | 26 |  | 2.3234 | 2.3234 | 0.43333 |  | REV
2025-06-11 | 2025-06-03 |  | BIZ | X25010242370 | BF CHILD'S HOME EDUCATIONAL CENTER, INC. | TROPICAL, BF HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 45.3907 | 136.01 | 45 | NEW | 350273.37 | 49603.62 |  | 0% | 2025-05-26 17:07 | 2025-05-30 13:43 | 2025-06-11 |  | 2025-06-28 |  | 32.2868 | 28.4285 | -45836 | 2025-06-16 22:05 | 2025-06-26 09:00 | 2025-07-15 17:07 | 1.0003 | -763.9333 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | FOR AUDIT |  | 2025-07-13 | -10 | 2025-06-28 | 2025-07-03 | [8 empty] | Y | 2025-06-26 | [6 empty] | 2025-06-11 | CW9-8066,TLN-527169 | 0 | 32.2868 | 0 | 32.2868 | 1.0003 | 33 |  | 2.0228 | 2.0228 | 0.55 |  | REV
2025-06-05 | 2025-06-05 |  | BIZ | X25020723572 | MONICA PUBLISHING CORP, | DR. A. SANTOS, SAN ISIDRO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 105.7807 | 160.91 | - | TERMINATION | 124114.95 | 138267.27 |  | 0% | 2025-05-26 17:07 | 2025-05-30 13:41 | 2025-06-05 |  |  |  | -45803.7132 | -45807.5701 | 0 | 2025-06-08 19:54 | 2025-06-16 03:02 | 2025-07-15 17:07 | -2131.6343 | 0 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | N/A | 0 | -45803.7132 | 0 | -45803.7132 | -2131.6343 | 0 |  | 3.0383 | 3.0383 | 0 | 52.2868 | NON-REV | 0-3 MONTHS
2025-06-09 | 2025-06-09 |  | BIZ | X25041378148 | JETTI_PETROLEUM INC. | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 10.9328 | 18.82 | 35 | NEW | 199951.87 | 16170.97 |  | 0% | 2025-05-27 13:14 | 2025-06-03 10:56 | 2025-06-09 | 2025-07-08 | 2025-07-28 |  | 61.4486 | 54.5444 | -45866 | 2025-06-15 07:49 | 2025-06-24 03:10 | 2025-07-16 13:14 | 2.1166 | -764.4333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | FOR AUDIT |  | 2025-08-12 | -5 | 2025-07-08 | 2025-08-07 | [16 empty] | 2025-06-09 | TLN-530637 | 0 | 61.4486 | 0 | 61.4486 | 2.1166 | 3 |  | 2.2199 | 2.2199 | 0.05 |  | REV
2025-06-09 |  |  | BIZ | X25041378514 | PARAÑAQUE ULTRASOUND DIAGNOSTIC CENTER, INC. | AIRPORT, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 4.73 | 11.66 | 69 | NEW | 39736.69 | 10044.45 |  | 0% | 2025-05-27 13:16 | 2025-06-03 10:57 | 2025-06-09 |  | 2025-06-14 08:00 |  | 17.7806 | 10.8771 | -45822.3333 | 2025-06-14 15:03 | 2025-06-23 05:56 | 2025-07-16 13:16 | 0.63278 | -763.7056 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-08-13 08:00 | 72.6667 | [8 empty] | NO COC |  | 2025-06-29 08:00 | #VALUE! | [10 empty] | Y | 2025-06-11 | [8 empty] | 0 | 17.7806 | 0 | 17.7806 | 0.63278 | 46.6667 |  | 2.2936 | 2.2936 | 0.77778 |  | REV
2025-06-12 | OK |  | BIZ | X25051639273 | LIMCALY INDUSTRIES INCORPORATED | PASCOR, STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 4.6895 | 11.44 | 86 | MODIFICATION | 20269.74 | 9825.99 |  | 0% | 2025-05-27 17:30 | 2025-06-03 11:05 | 2025-06-17 | 2025-06-18 | 2025-06-18 |  | 21.2708 | 14.5382 | -45826 | 2025-06-14 19:17 | 2025-06-23 10:10 | 2025-07-16 17:30 | 0.75699 | -763.7667 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-08-17 | 69 | [8 empty] | FOR AUDIT |  | 2025-07-03 | 15 | 2025-06-18 | 2025-07-18 | [8 empty] | Y | 2025-06-16 | [6 empty] | N/A | B5-1178, 033595 | 0 | 21.2708 | 0 | 21.2708 | 0.75699 | 43 |  | 2.2873 | 2.2873 | 0.71667 |  | NON-REV
2025-06-05 | 2025-06-05 |  | BIZ | X25030919165 | HAMPTON PROPERTIES INC. | CASIMIRO, ZAPOTE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | sa sabado aug 16 ang digging |  | ECOM | SCHED | Ronilo Gange Jr. | 62.388 | 116.02 | 286 | NEW | 949051.31 | 82287.74 |  | 0% | 2025-05-28 10:29 | 2025-06-03 13:26 | 2025-06-05 |  |  |  | -45805.4368 | -45811.5597 | 0 | 2025-06-15 22:40 | 2025-06-24 16:18 | 2025-07-17 10:29 | -1597.3178 | 0 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-06-05 | CY6-8028,TLN-523462 | 0 | -45805.4368 | 0 | -45805.4368 | -1597.3178 | 0 |  | 2.2166 | 2.2166 | 0 | 50.5632 | REV | 0-3 MONTHS
2025-06-05 | 2025-06-05 |  | BIZ | X25030919203 | HAMPTON PROPERTIES INC. | CASIMIRO, ZAPOTE, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | sa sabado aug 16 ang digging |  | ECOM | SCHED | Ronilo Gange Jr. | 51.3726 | 92.95 | 286 | NEW | 201286.67 | 62439.3 |  | 0% | 2025-05-28 10:35 | 2025-06-03 13:26 | 2025-06-05 |  |  |  | -45805.441 | -45811.5597 | 0 | 2025-06-15 01:24 | 2025-06-23 13:21 | 2025-07-17 10:35 | -1666.2559 | 0 | 23 | 30 | 20.6175 | 26.1155 | 17.6175 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-06-05 | CY6-8027 | 0 | -45805.441 | 0 | -45805.441 | -1666.2559 | 0 |  | 2.3121 | 2.3121 | 0 | 50.559 | REV | 0-3 MONTHS
2025-06-12 |  | Y | HMB | X25041423325 | MARIFE PIMENTEL PASCUAL | PANAMUCAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 45.608 | 135.13 | 80 | MODIFICATION | 402109.55 | 48869.9 |  | 0% | 2025-05-28 10:38 | 2025-06-11 15:30 | 2025-06-12 |  | 2025-06-26 |  | 28.5569 | 14.3542 | -45834 | 2025-06-17 18:55 | 2025-06-27 00:19 | 2025-07-17 10:38 | 0.91744 | -763.9 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-25 | 61 | [8 empty] | NO COC |  | 2025-07-11 | #VALUE! | [18 empty] | 2025-06-17 | CS8-0204, CS9-8140, 530652 | 0 | 28.5569 | 0 | 28.5569 | 0.91744 | 35 |  | 2.0419 | 2.0419 | 0.58333 |  | NON-REV
2025-06-10 | 2025-06-17 |  | CBG | X24051854889 | DITO TELECOMMUNITY CORPORATION | C5 EXTENSION, PULANGLUPA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | ongoing digging makapal po ang buhos ng semento kaya po di pa tapus ang digging |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 157.8046 | 5029.47 | 31 | NEW | 4452082.21 | 188797.42 |  | 0% | 2025-05-28 13:26 | 2025-06-03 12:45 | 2025-06-17 |  |  |  | -45805.5597 | -45811.5312 | 0 | 2025-06-24 00:51 | 2025-07-04 21:30 | 2025-07-17 13:26 | -1165.497 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-06-10 | CY7-8094,CY7-8095,CY7-8096,CY7-8097,CY7-8098,TLN-518339 | 0 | -45805.5597 | 34 | -45839.5597 | -1166.3621 | 0 |  | 1.6142 | 1.6142 | 0 | 50.4403 | REV | 0-3 MONTHS
2025-06-12 | 2025-07-09 |  | HMB | X25020572839 | PHINMA PROPERTY HOLDINGS CORPORATION, | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | done energize with emc frame care of meralco meter |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 23.7233 | 75.19 | 28 | NEW | 301328.8 | 48893.24 |  | 0% | 2025-05-28 16:49 | 2025-06-03 13:11 | 2025-06-09 |  | 2025-07-03 |  | 35.2993 | 29.4507 | -45841 | 2025-06-17 18:52 | 2025-06-26 22:37 | 2025-07-17 16:49 | 1.1468 | -764.0167 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-09-01 | 54 | [8 empty] | NO COC |  | 2025-07-18 | #VALUE! | [10 empty] | Y | 2025-06-20 | [6 empty] | 2025-06-17 | DV1-5053, 520864, DV1-8037 | 0 | 35.2993 | 0 | 35.2993 | 1.1468 | 28 |  | 2.0565 | 2.0565 | 0.46667 |  | REV
2025-06-03 | 2025-06-05 |  | BIZ | X24072535997 | ALFONSO ESPINOSA LIM | NIOG II, NIOG II, BACOOR | BACOOR CITY | DASMA |  |  | C2 | FCOMP | Ian Patrick Perez | 1.73 | 3.54 | 20 | NEW | 21348.01 | 3041.67 |  | 0% | 2025-05-29 10:39 | 2025-06-03 13:08 | 2025-06-05 |  | 2025-08-08 |  | 70.5563 | 65.4528 | -45877 | 2025-06-17 05:14 | 2025-06-26 00:35 | 2025-07-18 10:39 | 2.4303 | -764.6167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-07 | 18 | [8 empty] | NO COC |  | 2025-08-23 | #VALUE! | [18 empty] | N/A | N/A | 0 | 70.5563 | 0 | 70.5563 | 2.4303 | -8 |  | 2.1547 | 2.1547 | -0.13333 |  | REV
2025-06-05 | 2025-07-09 |  | HMB | X25051742450 | AS AND T HATCH INC. | MID WEST, VICTORIAHOMES-DIAMONDPARK SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 1.75 | 5.35 | 32 | NEW | 34987.27 | 4596.82 |  | 0% | 2025-05-29 10:48 | 2025-06-03 13:07 | 2025-06-09 |  | 2025-06-20 |  | 21.55 | 16.4535 | -45828 | 2025-06-17 05:23 | 2025-06-26 00:44 | 2025-07-18 10:48 | 0.74228 | -763.8 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-19 | 67 | [8 empty] | NO COC |  | 2025-07-05 | #VALUE! | [10 empty] | Y | [7 empty] | N/A | CO9-8083, 519174 | 0 | 21.55 | 0 | 21.55 | 0.74228 | 41 |  | 2.1545 | 2.1545 | 0.68333 |  | REV
2025-06-23 | 2025-06-25 |  | HMB | X24104062252 | SIONIL BUILDERS CORPORATION | LIGAS, DOÑA MANUELA SUBD PH 4-E, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 425.9065 | 1543.28 | 88.2 | NEW | 2406705.94 | 456461.4 |  | 0% | 2025-05-29 14:11 | 2025-06-20 13:54 | 2025-06-25 |  |  |  | -45806.591 | -45828.5792 | 0 | 2025-06-23 19:10 | 2025-07-04 07:42 | 2025-07-18 14:11 | -1217.9164 | 0 | 50 | 34 | 28.208 | 35.7301 | 25.208 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-06-25 | CW7-8082, 037024, CW7-8083, CW7-8084, CW7-8085, CW7-8086, CW7-8087, CW7-8088, CW7-8089, CW7-8090, 526255, CW7-8091, CW7-8092, CW7-8093, CW7-8094 | 0 | -45806.591 | 0 | -45806.591 | -1217.9164 | 0 |  | 1.6593 | 1.6593 | 0 | 49.409 | REV | 0-3 MONTHS
2025-06-12 | 2025-06-10 |  | BIZ | X25041329837 | FILIPINAS BENSON INDUSTRIAL AND DEVELOPMENT CORPOR | DONA IRENEA, IRENEVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 69.8326 | 281.9 | 299 | NEW | 1217413.38 | 174981.58 |  | 0% | 2025-05-29 14:59 | 2025-06-03 13:28 | 2025-06-10 |  | 2025-08-01 09:30 |  | 63.7715 | 58.8347 | -45870.3958 | 2025-06-17 15:39 | 2025-06-26 12:38 | 2025-07-18 14:59 | 2.1713 | -764.5066 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 60 | 57 | 52 | 2025-09-30 09:30 | 24.6042 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-08-16 09:30 | #VALUE! | [18 empty] | 2025-06-10 | CX9-0928, DX1-8115, 527586 | 0 | 63.7715 | 34 | 29.7715 | 1.0136 | -1.3958 |  | 2.1237 | 2.1237 | -0.023264 |  | REV
2025-06-23 | 2025-06-24 |  | BIZ | X25030745369 | THE ROMAN CATHOLIC BISHOP OF PARAÑAQUE, INC | GARNET, SEVERINA DIAMOND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ONGOING NEED FINAL LOCATION FOR TASK 4 WITH PAI |  | VJC | SCHED | Jenneth Madrid | 26.9895 | 71.29 | 169 | NEW | 713706.73 | 61280.9 |  | 0% | 2025-05-29 16:35 | 2025-06-23 09:36 | 2025-06-24 |  |  |  | -45806.691 | -45831.4 | 0 | 2025-06-17 04:04 | 2025-06-25 21:32 | 2025-07-18 16:35 | -1599.4999 | 0 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-06-24 | 527885 | 0 | -45806.691 | 0 | -45806.691 | -1599.4999 | 0 |  | 2.1757 | 2.1757 | 0 | 49.309 | REV | 0-3 MONTHS
2025-06-23 | 2025-06-24 |  | BIZ | X25041445070 | THE ROMAN CATHOLIC BISHOP OF PARANAQUE, INC. | GARNET, SEVERINA DIAMOND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | CONJUNCT WO (X25030745369) |  | VJC | SCHED | Jenneth Madrid | 338.8046 | 1030.72 | 169 | NEW | 1615984.9 | 413978.95 |  | 0% | 2025-05-29 16:36 | 2025-06-23 09:35 | 2025-06-24 |  |  |  | -45806.6917 | -45831.3993 | 0 | 2025-06-22 14:20 | 2025-07-02 18:32 | 2025-07-18 16:36 | -1276.8615 | 0 | 50 | 32 | 26.9058 | 34.0807 | 23.9058 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-06-24 | DY1-1207, DY1-8098, DY1-8099, DY1-8100, 037847, DX1-8126, DX1-8127, DX1-8128, PLDT-0461, DY1-8094, DY1-0667 | 0 | -45806.6917 | 0 | -45806.6917 | -1276.8615 | 0 |  | 1.7368 | 1.7368 | 0 | 49.3083 | REV | 0-3 MONTHS
2025-06-23 | 2025-06-25 |  | BIZ | R24041284 | IFACE INC. | STA. ANA, STA. ANA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 30.8287 | 50.38 | 0 | RELOC | 77725.52 | 27579.82 |  | 0% | 2025-05-29 16:38 | 2025-06-23 09:28 | 2025-06-25 |  |  |  | -45806.6931 | -45831.3944 | 0 | 2025-06-17 11:13 | 2025-06-26 06:34 | 2025-07-18 16:38 | -1577.7861 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-06-25 | CZ9-1536, DZ1-8056 | 0 | -45806.6931 | 0 | -45806.6931 | -1577.7861 | 0 |  | 2.1461 | 2.1461 | 0 | 49.3069 | NON-REV | 0-3 MONTHS
2025-06-17 | 2025-06-18 |  | HMB | X25041307676 | CITY GOV'T OF LAS PIÑAS | LIBRA, VILLA ISABELITA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 1.79 | 7.01 | 9 | MODIFICATION | 24060.56 | 6023.01 |  | 0% | 2025-05-30 15:15 | 2025-06-17 13:21 | 2025-06-18 |  | 2025-06-27 |  | 27.3646 | 9.4437 | -45835 | 2025-06-18 09:50 | 2025-06-27 05:11 | 2025-07-19 15:15 | 0.94256 | -763.9167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-26 | 60 | [8 empty] | NO COC |  | 2025-07-12 | #VALUE! | [10 empty] | Y | [7 empty] | 2025-06-18 | 192502 | 0 | 27.3646 | 0 | 27.3646 | 0.94256 | 34 |  | 2.1137 | 2.1137 | 0.56667 |  | NON-REV
2025-06-17 | 2025-06-18 |  | HMB | X25051750601 | TARASH B. BERMUDEZ | MONIQUE, VILLA CRISTINA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | done energize with emc frame care of meralco meter |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 3.66 | 7.29 | 6 | NEW | 29846.68 | 6263.71 |  | 0% | 2025-06-02 09:11 | 2025-06-17 13:23 | 2025-06-18 |  |  |  | -45810.3826 | -45825.5576 | 0 | 2025-06-21 03:46 | 2025-06-29 23:07 | 2025-07-22 09:11 | -1577.9132 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [7 empty] | N/A | CW7-2005 | 0 | -45810.3826 | 0 | -45810.3826 | -1577.9132 | 0 |  | 2.019 | 2.019 | 0 | 45.6174 | REV | 0-3 MONTHS
2025-06-17 | 2025-06-18 |  | CBG | X25041438275 | GLOBE TELECOM INC. | E. RODRIGUEZ JR., MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done energize with emc frame care of meralco meter |  | ECOM | FCOMP | Ronilo Gange Jr. | 10.3533 | 11.51 | 3 | NEW | 147032.27 | 9892.5 |  | 0% | 2025-06-02 10:31 | 2025-06-17 13:26 | 2025-06-18 |  | 2025-06-28 |  | 25.5618 | 10.4403 | -45836 | 2025-06-21 05:06 | 2025-06-30 00:27 | 2025-07-22 10:31 | 0.88046 | -763.9333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-27 | 59 | [8 empty] | FOR AUDIT |  | 2025-07-13 | -4 | 2025-06-28 | 2025-07-09 | [8 empty] | Y | 2025-06-26 | [6 empty] | 2025-06-18 | 530762 | 0 | 25.5618 | 0 | 25.5618 | 0.88046 | 33 |  | 2.0171 | 2.0171 | 0.55 |  | REV
2025-06-17 | 2025-06-18 |  | BIZ | X25041184947 | JELLY MAHUSAY PAGUIRIGAN | MOLINO ROAD, MOLINO III, BACOOR | BACOOR CITY | DASMA |  |  | C2 | FCOMP | Ian Patrick Perez | 9.8533 | 11.75 | 19 | NEW | 139959.44 | 10098.78 |  | 0% | 2025-06-02 16:04 | 2025-06-17 13:30 | 2025-06-18 |  | 2025-08-01 12:57 |  | 59.8701 | 44.9771 | -45870.5396 | 2025-06-21 10:39 | 2025-06-30 06:00 | 2025-07-22 16:04 | 2.0622 | -764.509 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-30 12:57 | 24.4604 | [8 empty] | NO COC |  | 2025-08-16 12:57 | #VALUE! | [10 empty] | Y | [7 empty] | 2025-06-18 | CR7-6072, 530461 | 0 | 59.8701 | 0 | 59.8701 | 2.0622 | -1.5396 |  | 2.0092 | 2.0092 | -0.02566 |  | REV
2025-06-17 | 2025-06-18 |  | HMB | X25031082537 | NORELYN B AMPARADO | EVERLASTING, ZONE 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | FOR SCHED DIGGING |  | VJC | SCHED | Jenneth Madrid | 83.2274 | 203.42 | 44 | NEW | 449581.74 | 76859.46 |  | 0% | 2025-06-02 16:34 | 2025-06-17 13:28 | 2025-06-18 |  |  |  | -45810.6903 | -45825.5611 | 0 | 2025-06-24 13:25 | 2025-07-04 04:34 | 2025-07-22 16:34 | -1381.5922 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-06-18 | A8-1187, A8-8152, 530295, A8-1506 | 0 | -45810.6903 | 0 | -45810.6903 | -1381.5922 | 0 |  | 1.7585 | 1.7585 | 0 | 45.3097 | REV | 0-3 MONTHS
2025-06-25 | 2025-06-25 |  | HMB | X25020587889 | ROSANA DIMACALI ARANDA-MANALO | TRINIDAD, SAN ISIDRO SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 67.851 | 230.55 | 35 | NEW | 435025.16 | 63566.86 |  | 0% | 2025-06-03 12:18 | 2025-06-17 13:39 | 2025-06-25 |  |  |  | -45811.5125 | -45825.5687 | 0 | 2025-06-25 09:09 | 2025-07-05 00:18 | 2025-07-23 12:18 | -1381.617 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-06-25 | CX6-8149, CX6-8034, 519275 | 0 | -45811.5125 | 0 | -45811.5125 | -1381.617 | 0 |  | 1.7338 | 1.7338 | 0 | 44.4875 | REV | 0-3 MONTHS
2025-06-17 | 2025-06-18 | Y | BIZ | X25041379488 | PACIFIC RESOURCES CORPORATION | MARCOS ALVAREZ, TALON I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 11.53 | 114.42 | 224 | MODIFICATION | 269699.65 | 98338.36 |  | 0% | 2025-06-04 09:10 | 2025-06-17 13:32 | 2025-06-18 |  | 2025-07-07 |  | 32.6181 | 19.4361 | -45845 | 2025-06-22 21:21 | 2025-07-01 14:59 | 2025-07-24 09:10 | 1.1375 | -764.0833 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-09-05 | 50 | [8 empty] | FOR AUDIT |  | 2025-07-22 | -8 | 2025-07-07 | 2025-07-14 | [8 empty] | Y | [7 empty] | N/A | CV8-2064, 068870 | 0 | 32.6181 | 0 | 32.6181 | 1.1375 | 24 |  | 1.9744 | 1.9744 | 0.4 |  | NON-REV
2025-06-12 |  |  | HMB | X25051872111 | MARIA CRISTINA JOSE VENADAS | SAN JUANICO, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 2.51 | 6.4 | 18 | MODIFICATION | 24098.69 | 5499.12 |  | 0% | 2025-06-04 12:50 | 2025-06-11 14:44 | 2025-06-12 |  | 2025-06-26 |  | 21.4653 | 14.3861 | -45834 | 2025-06-23 07:25 | 2025-07-02 02:46 | 2025-07-24 12:50 | 0.73936 | -763.9 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-25 | 61 | [8 empty] | NO COC |  | 2025-07-11 | #VALUE! | [18 empty] | N/A | CT9-0478 | 0 | 21.4653 | 0 | 21.4653 | 0.73936 | 35 |  | 1.9449 | 1.9449 | 0.58333 |  | NON-REV
2025-06-23 | 2025-06-25 |  | HMB | R23808011 | MARCELINO, CRISITINA | STA. TERESITA, VILLA DONATA SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | hindi pa nahukayan as per sadang |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 535.5097 | 1589.87 | 0 | RELOC | 2393214.01 | 623353.52 |  | 0% | 2025-06-04 16:43 | 2025-06-20 13:03 | 2025-06-25 |  | 2025-07-30 |  | 55.3035 | 39.4563 | -45868 | 2025-07-01 04:08 | 2025-07-12 00:47 | 2025-07-24 16:43 | 1.4072 | -764.4667 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 2025-09-28 | 27 | [8 empty] | NO COC |  | 2025-08-14 | #VALUE! | [20 empty] | 0 | 55.3035 | 0 | 55.3035 | 1.4072 | 1 |  | 1.4326 | 1.4326 | 0.016667 |  | NON-REV
N/A | N/A |  | BIZ | X25051803052 | DIANNA MEL BUSOG LAUDENIO | PRES. E. AGUINALDO, MALACANANG VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 19.85 | 19.85 | 10 | MODIFICATION | 43763.67 |  |  | #DIV/0! | 2025-06-05 08:56 | 2025-06-11 15:43 | N/A |  | 2025-07-01 |  | 25.6278 | 19.3451 | -45839 | 2025-06-24 03:31 | 2025-07-02 22:52 | 2025-07-25 08:56 | 0.88273 | -763.9833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-30 | 56 | [8 empty] | NO COC |  | 2025-07-16 | #VALUE! | [19 empty] | CY9-2350, 122870 | 0 | 25.6278 | 0 | 25.6278 | 0.88273 | 30 |  | 1.9161 | 1.9161 | 0.5 |  | NON-REV
N/A | N/A |  | HMB | X25020395161 | JOSE CARLO CHANG MARQUEZ | UNITED NATIONS, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 122.18 | 122.18 | 57 | NEW | 338451.36 |  |  | #DIV/0! | 2025-06-05 10:53 | 2025-06-11 15:42 | N/A |  | 2025-06-25 |  | 19.5465 | 13.3458 | -45833 | 2025-06-25 19:10 | 2025-07-05 00:34 | 2025-07-25 10:53 | 0.62797 | -763.8833 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-08-24 | 62 | [8 empty] | NO COC |  | 2025-07-10 | #VALUE! | [19 empty] | CZ9-8026, CZ9-8065, 527428 | 0 | 19.5465 | 0 | 19.5465 | 0.62797 | 36 |  | 1.7845 | 1.7845 | 0.6 |  | REV
N/A | N/A | Y | HMB | X25041438549 | ROSELLER SYGENCO PIERAZ | MAHARLIKA, MARCELO GREEN VILL 5, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 31.58 | 31.58 | 76 | NEW | 228445.28 |  |  | #DIV/0! | 2025-06-05 10:55 | 2025-06-11 15:41 | N/A |  | 2025-06-22 | 2025-07-10 07:58 | 16.5451 | 10.3465 | 18.3319 | 2025-06-23 12:42 | 2025-07-02 03:35 | 2025-07-25 10:55 | 0.58881 | 0.30553 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-08-21 | 65 | [8 empty] | PAID |  | 2025-07-07 | #VALUE! | [19 empty] | DY1-5401, 530646 | 0 | 16.5451 | 0 | 16.5451 | 0.58881 | 39 |  | 1.9768 | 1.9768 | 0.65 |  | REV
N/A | N/A |  | HMB | X25041167587 | CITY GOVERNMENT OF PARAÑAQUE | STA. LUCIA, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 47.73 | 47.73 | 155 | NEW | 471898.23 |  |  | #DIV/0! | 2025-06-05 10:57 | 2025-06-11 15:40 | N/A |  | 2025-06-24 | 2025-07-10 08:02 | 18.5437 | 12.3472 | 16.3347 | 2025-06-22 19:05 | 2025-07-01 05:15 | 2025-07-25 10:57 | 0.6838 | 0.27225 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-08-23 | 63 | [8 empty] | PAID |  | 2025-07-09 | #VALUE! | [19 empty] | CX9-0110, 530503 | 0 | 18.5437 | 0 | 18.5437 | 0.6838 | 37 |  | 2.0482 | 2.0482 | 0.61667 |  | REV
2025-06-25 | 2025-06-24 |  | HMB | X25051571669 | SOLEDAD MAGDASAL ORELLANO | PENDATUN, MAHARLIKA VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 0.2 | 0.2 | 3 | NEW | 14441.33 | 171.85 |  | 0% | 2025-06-05 12:43 | 2025-06-17 13:40 | 2025-06-24 | 2025-07-09 | 2025-07-09 |  | 33.4701 | 21.4306 | -45847 | 2025-06-24 07:18 | 2025-07-03 02:39 | 2025-07-25 12:43 | 1.1529 | -764.1167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-07 | 48 | [8 empty] | FOR AUDIT |  | 2025-07-24 | 22 | 2025-07-09 | 2025-08-15 | [8 empty] | N | [7 empty] | N/A | 35014 | 0 | 33.4701 | 0 | 33.4701 | 1.1529 | 22 |  | 1.9106 | 1.9106 | 0.36667 |  | REV
N/A | N/A |  | BIZ | X25030785870 | 8TERNITY, INC. | MDC, VETERANS CENTER, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 4.17 | 4.17 | 28 | NEW | 22871.59 |  |  | #DIV/0! | 2025-06-05 14:50 | 2025-06-11 13:05 | N/A |  | 2025-06-21 |  | 15.3819 | 9.4549 | -45829 | 2025-06-24 09:25 | 2025-07-03 04:46 | 2025-07-25 14:50 | 0.52982 | -763.8167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-20 | 66 | [8 empty] | NO COC |  | 2025-07-06 | #VALUE! | [19 empty] | B7-0365, 126395 | 0 | 15.3819 | 0 | 15.3819 | 0.52982 | 40 |  | 1.9076 | 1.9076 | 0.66667 |  | REV
N/A | N/A |  | HMB | X25051592853 | CLEMENTE CAPITULO DOMINGO III | J. HULL, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 30.53 | 30.53 | 80 | MODIFICATION | 262032.82 |  |  | #DIV/0! | 2025-06-05 16:26 | 2025-06-11 15:43 | N/A |  | 2025-06-26 |  | 20.3153 | 14.3451 | -45834 | 2025-06-23 18:13 | 2025-07-02 09:06 | 2025-07-25 16:26 | 0.72298 | -763.9 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-08-25 | 61 | [8 empty] | NO COC |  | 2025-07-11 | #VALUE! | [19 empty] | CR9-0696, 530824 | 0 | 20.3153 | 0 | 20.3153 | 0.72298 | 35 |  | 1.9686 | 1.9686 | 0.58333 |  | NON-REV
2025-06-17 | 2025-06-18 |  | CBG | X25010183788 | DEPARTMENT OF HEALTH | REYVILLE I SUBD, REYVILLE I SUBD, BACOOR | BACOOR CITY | DASMA | for digging on going 8-14-25 |  | AVECO | SCHED | Ronilo Gange Jr. | 137.7473 | 374.84 | 827 | NEW | 2219583.99 | 255668.99 |  | 0% | 2025-06-09 14:05 | 2025-06-17 13:35 | 2025-06-18 |  |  |  | -45817.5868 | -45825.566 | 0 | 2025-06-25 03:15 | 2025-07-03 01:57 | 2025-07-29 14:05 | -1852.6242 | 0 | 30 | 23 | 18.5484 | 23.4946 | 15.5484 | 60 | 57 | 52 | 1900-02-28 | 45895 | Applicant holds execution | Y |  |  |  | 2025-07-02 |  |  |  |  | 1900-01-14 | 0 | [10 empty] | Y | [7 empty] | 2025-06-18 | CW5-5238, CW5-8026, 113666 | 0 | -45817.5868 | 0 | -45817.5868 | -1852.6242 | 0 |  | 2.0789 | 2.0789 | 0 | 38.4132 | REV | 0-3 MONTHS
2025-06-23 | 2025-06-25 |  | CBG | X24093626616 | MAYNILAD WATER SERVICES, INC., | BUENDIA, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 177.769 | 432.8 | 1985 | NEW | 1408047.89 | 205548.49 |  | 0% | 2025-06-09 16:09 | 2025-06-17 13:45 | 2025-06-25 |  | 2025-07-17 |  | 37.3271 | 29.4271 | -45855 | 2025-06-23 13:47 | 2025-07-01 01:57 | 2025-07-29 16:09 | 1.6564 | -764.25 | 32 | 20 | 16.9014 | 21.4085 | 13.9014 | 60 | 57 | 52 | 2025-09-15 | 40 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-08-01 | #VALUE! | [19 empty] | DR2-2043, DR1-0496, DR1-8029, PLDT 7778, DR2-8030, DR2-8031, DR1-0497, PLDT-2806, DR2-8032,523804 | 0 | 37.3271 | 34 | 3.3271 | 0.14764 | 14 |  | 2.2776 | 2.2776 | 0.23333 |  | REV
2025-06-23 | 2025-06-25 |  | HMB | X25051643547 | CITY GOVERNMENT OF TAGUIG | AREA 2 MAULING HAI, PUROK 6D, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 12.7533 | 18.05 | 132 | NEW | 238081.43 | 15511.93 |  | 0% | 2025-06-09 16:14 | 2025-06-17 13:48 | 2025-06-25 | 2025-07-29 | 2025-07-29 |  | 49.3236 | 41.425 | -45867 | 2025-06-27 00:22 | 2025-07-05 10:32 | 2025-07-29 16:14 | 1.8188 | -764.45 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-09-27 | 28 | [8 empty] | NO COC |  | 2025-08-13 | #VALUE! | [19 empty] | DZ2-8092, 530916 | 0 | 49.3236 | 0 | 49.3236 | 1.8188 | 2 |  | 1.8926 | 1.8926 | 0.033333 |  | REV
2025-06-23 | 2025-06-25 |  | HMB | X25051645744 | CITY GOVERNMENT OF TAGUIG | AREA 2 MAULING HAI, PUROK 6D, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 14.7828 | 20.84 | 105 | NEW | 242193.8 | 17504.51 |  | 0% | 2025-06-09 16:16 | 2025-06-17 13:47 | 2025-06-25 | 2025-07-29 | 2025-07-29 |  | 49.3222 | 41.4257 | -45867 | 2025-06-27 00:24 | 2025-07-05 10:34 | 2025-07-29 16:16 | 1.8188 | -764.45 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-09-27 | 28 | [8 empty] | FOR AUDIT |  | 2025-08-13 | -7 | 2025-07-30 | 2025-08-06 | [16 empty] | 2025-07-18 | DZ2-8095, 530957 | 0 | 49.3222 | 0 | 49.3222 | 1.8188 | 2 |  | 1.8925 | 1.8925 | 0.033333 |  | REV
2025-06-23 | 2025-06-25 |  | HMB | X25051638575 | CITY GOVERNMENT OF TAGUIG | AREA 1 MAULING HAI, PUROK 6D, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 12.9033 | 24.77 | 105 | NEW | 254041.17 | 21285.88 |  | 0% | 2025-06-09 16:18 | 2025-06-17 13:49 | 2025-06-25 | 2025-07-29 | 2025-07-29 |  | 49.3208 | 41.4243 | -45867 | 2025-06-27 00:26 | 2025-07-05 10:36 | 2025-07-29 16:18 | 1.8187 | -764.45 | 20 | 32 | 20.339 | 25.7627 | 17.339 | 60 | 57 | 52 | 2025-09-27 | 28 | [8 empty] | FOR AUDIT |  | 2025-08-13 | -7 | 2025-07-30 | 2025-08-06 | [16 empty] | 2025-07-18 | DZ2-8082, 530861 | 0 | 49.3208 | 0 | 49.3208 | 1.8187 | 2 |  | 1.8925 | 1.8925 | 0.033333 |  | REV
| 2025-06-25 |  | HMB | X25051641881 | CITY GOVERNMENT OF TAGUIG | AREA 2 MAULING HAI, PUROK 6D, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 19.6 | 19.6 | 72 | NEW | 203441.12 |  |  | #DIV/0! | 2025-06-09 16:33 | 2025-06-17 13:46 | 2025-06-25 | 2025-07-29 | 2025-07-29 |  | 49.3104 | 41.4264 | -45867 | 2025-06-27 18:20 | 2025-07-06 09:13 | 2025-07-29 16:33 | 1.7549 | -764.45 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-09-27 | 28 | [8 empty] | FOR AUDIT |  | 2025-08-13 | -7 | 2025-07-30 | 2025-08-06 | [16 empty] | 2025-07-18 | DZ2-8089, 530888 | 0 | 49.3104 | 0 | 49.3104 | 1.7549 | 2 |  | 1.826 | 1.826 | 0.033333 |  | REV
2025-06-17 | 2025-06-18 | Y | CBG | X24020419527 | D.M. WENCESLAO & ASSOCIATES, INC., | BRADCO, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 793.1437 | 1598.32 | 182 | NEW | 3728690.42 | 1032941.7 |  | 0% | 2025-06-09 16:54 | 2025-06-17 10:52 | 2025-06-18 |  | 2025-07-17 |  | 37.2958 | 29.5472 | -45855 | 2025-07-03 14:38 | 2025-07-13 18:50 | 2025-07-29 16:54 | 1.0396 | -764.25 | 50 | 32 | 26.9058 | 34.0807 | 23.9058 | 60 | 57 | 52 | 2025-09-15 | 40 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 | NO COC |  | 2025-08-01 | #VALUE! | [10 empty] | Y | [7 empty] | 2025-06-18 | C4-0024, C4-5286, C4-5287, C4-5288, C4-5282, 165925, C4-5283, 165994, C4-5334, C4-5335, C4-5336, C4-5337, C4-5338, C4-5339, C4-5340, C4-5341, C4-5342, C4-8018, C4-8019, C4-8020, C4-8021, C4-8022, | 0 | 37.2958 | 34 | 3.2958 | 0.091871 | 14 |  | 1.4299 | 1.4299 | 0.23333 |  | REV
2025-06-23 | 2025-06-25 |  | HMB | X24072578131 | LEONILA SINGIAN ALDEMITA | OPAL, RAYMUNDVILLE 1 CASA FILIPINA, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done energize |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 223.7728 | 741.71 | 10 | NEW | 983981.23 | 232920.47 |  | 0% | 2025-06-09 17:30 | 2025-06-20 13:48 | 2025-06-25 |  |  |  | -45817.7292 | -45828.575 | 0 | 2025-07-04 13:32 | 2025-07-14 23:41 | 2025-07-29 17:30 | -1234.5333 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-08-04 | DY1-8047, DY1-8048, DY1-8049, DY1-8050, DY1-8061, DY1-8051, 522863 | 0 | -45817.7292 | 34 | -45851.7292 | -1235.4494 | 0 |  | 1.3815 | 1.3815 | 0 | 38.2708 | REV | 0-3 MONTHS
N/A | N/A |  | CBG | X25010185964 | PHILIPPINE COUNCIL FOR HEALTH RESEARCH AND DEVELOP | SIBOL, DOST CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | For Energize |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 143.6 | 143.6 | 127 | NEW | 649332.21 |  |  | #DIV/0! | 2025-06-10 08:46 | 2025-06-17 13:53 | N/A |  | 2025-07-17 16:31 |  | 37.3229 | 30.1097 | -45855.6882 | 2025-06-29 19:28 | 2025-07-08 19:08 | 2025-07-30 08:46 | 1.2471 | -764.2615 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-09-15 16:31 | 39.3118 | [8 empty] | NO COC |  | 2025-08-01 16:31 | #VALUE! | [20 empty] | 0 | 37.3229 | 0 | 37.3229 | 1.2471 | 13.3118 |  | 1.6919 | 1.6919 | 0.22186 |  | REV
2025-06-23 | 2025-06-24 |  | HMB | X25031084163 | AMNAH BASMAN | BLOCK 141, PUROK 5, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 0.53 | 1.19 | 1.5 | NEW | 15994.32 | 1022.47 |  | 0% | 2025-06-10 08:50 | 2025-06-17 13:41 | 2025-06-24 |  | 2025-07-09 |  | 28.6319 | 21.4299 | -45847 | 2025-06-29 03:25 | 2025-07-07 22:46 | 2025-07-30 08:50 | 0.98621 | -764.1167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-07 | 48 | [8 empty] | NO COC |  | 2025-07-24 | #VALUE! | [10 empty] | N | [7 empty] | N/A | A8-0164 | 0 | 28.6319 | 0 | 28.6319 | 0.98621 | 22 |  | 1.744 | 1.744 | 0.36667 |  | REV
N/A | N/A |  | BIZ | X25051521575 | PLATINUM PETROLEUM CORP. | DR. A SANTOS, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 17.33 | 17.33 | 22 | NEW | 262559.48 |  |  | #DIV/0! | 2025-06-10 15:27 | 2025-06-17 14:00 | N/A |  | 2025-06-26 | 2025-07-23 08:27 | 15.3562 | 8.4167 | 27.3521 | 2025-06-29 10:02 | 2025-07-08 05:23 | 2025-07-30 15:27 | 0.52894 | 0.45587 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-25 | 61 | [8 empty] | PAID |  | 2025-07-11 | #VALUE! | [10 empty] | Y | [8 empty] | ALB1-1510, 530341 | 0 | 15.3562 | 0 | 15.3562 | 0.52894 | 35 |  | 1.7345 | 1.7345 | 0.58333 |  | REV
2025-06-25 | 2025-06-25 |  | HMB | X25041349231 | ELVIN HAYES VERANO GENTILES | BALLAD, STA. CECILIA VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 156.46 | 389.91 | 41.9 | MODIFICATION | 618984.53 | 134436.98 |  | 0% | 2025-06-10 16:34 | 2025-06-17 14:07 | 2025-06-25 |  |  |  | -45818.6903 | -45825.5882 | 0 | 2025-07-03 03:53 | 2025-07-12 22:54 | 2025-07-30 16:34 | -1349.1059 | 0 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-18 | CW6-0394, CW7-8110, CW7-8111, 530553, CW7-8112 | 0 | -45818.6903 | 0 | -45818.6903 | -1349.1059 | 0 |  | 1.4813 | 1.4813 | 0 | 37.3097 | NON-REV | 0-3 MONTHS
2025-06-18 | 2025-06-19 |  | CBG | X23083303906 | CIVIL AVIATION AUTHORITY OF THE PHILIPPINES | NAIA, PASAY, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 385.08 | 541.65 | 0 | MODIFICATION | 734206.72 |  |  | #DIV/0! | 2025-06-11 10:18 | 2025-06-17 14:05 | 2025-06-19 | 2025-07-18 | 2025-07-18 |  | 36.5708 | 30.4132 | -45856 | 2025-07-06 06:20 | 2025-07-16 16:29 | 2025-07-31 10:18 | 0.98538 | -764.2667 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-09-16 | 39 | [8 empty] | FOR AUDIT |  | 2025-08-02 | #VALUE! | 2025-07-18 | [17 empty] | 2025-06-18 | B5-2094, B5-8019, B5-8020, 032554 | 0 | 36.5708 | 0 | 36.5708 | 0.98538 | 13 |  | 1.3357 | 1.3357 | 0.21667 |  | NON-REV
N/A | N/A |  | CBG | X25041118209 | EFB GEOSTRUKT, INC. | BLOCK 14, BRAZILIA HEIGHTS, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 11.37 | 11.37 | 22 | NEW | 136992.52 | 138623.08 |  | 0% | 2025-06-11 12:57 | 2025-06-17 13:59 | N/A |  | 2025-07-01 | 2025-07-23 08:30 | 19.4604 | 13.4174 | 22.3542 | 2025-06-30 07:32 | 2025-07-09 02:53 | 2025-07-31 12:57 | 0.6703 | 0.37257 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-30 | 56 | [8 empty] | PAID |  | 2025-07-16 | #VALUE! | [20 empty] | 0 | 19.4604 | 0 | 19.4604 | 0.6703 | 30 |  | 1.7036 | 1.7036 | 0.5 |  | REV
2025-06-23 | 2025-06-25 |  | BIZ | X25061964589 | 101 SUPPLY CHAIN SOLUTIONS,INC | IRASAN, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | PCAN | Isan Carlo Lazaro | 20.35 | 28.78 | 0 | TERMINATION | 29818.48 | 24762.87 |  | 0% | 2025-06-13 16:09 | 2025-06-23 08:47 | 2025-06-25 |  |  |  | -45821.673 | -45831.366 | 0 | 2025-07-02 10:44 | 2025-07-11 06:05 | 2025-08-02 16:09 | -1578.3021 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | N/A | 0 | -45821.673 | 0 | -45821.673 | -1578.3021 | 0 |  | 1.6302 | 1.6302 | 0 | 34.327 | NON-REV | 0-3 MONTHS
2025-06-23 | 2025-06-25 |  | BIZ | X24104022198 | APRIL RAINE B MORALES | MON-EL, MON-EL SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done energize |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 55.0095 | 169.28 | 170 | NEW | 829725.58 | 78190.45 |  | 0% | 2025-06-13 16:02 | 2025-06-20 13:50 | 2025-06-25 |  |  |  | -45821.6679 | -45828.5764 | 0 | 2025-07-03 02:44 | 2025-07-12 02:23 | 2025-08-02 16:02 | -1531.0605 | 0 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [20 empty] | 0 | -45821.6679 | 34 | -45855.6679 | -1532.1966 | 0 |  | 1.5815 | 1.5815 | 0 | 34.3321 | REV | 0-3 MONTHS
2025-06-23 | 2025-06-25 |  | BIZ | X25041190419 | GOLDEN CHI MANAGEMENT CORP. | PERU, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For Energize |  | VJC | FCOMP | Jenneth Madrid | 80.508 | 243.39 | 226 | NEW | 1028667.62 | 141894.62 |  | 0% | 2025-06-13 15:58 | 2025-06-20 13:52 | 2025-06-25 |  | 2025-08-13 |  | 60.3345 | 53.4222 | -45882 | 2025-07-02 16:39 | 2025-07-11 13:37 | 2025-08-02 15:58 | 2.0542 | -764.7 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 60 | 57 | 52 | 2025-10-12 | 13 | Materials unavailability / With scheduled PAI | Y | Y |  |  | 2025-06-24 | 44 | 2025-08-07 |  |  | 2025-08-28 | #VALUE! | [20 empty] | 0 | 60.3345 | 44 | 16.3345 | 0.55615 | -13 |  | 1.6116 | 1.6116 | -0.21667 |  | REV
2025-07-16 | 2025-06-26 |  | CBG | X24062436530 | EDOTCO TOWERS, INC. | COLT, GATCHALIAN SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | sadang : done digging and pole erect |  | ECOM | FCOMP | Ronilo Gange Jr. | 71.39 | 91.67 | 50 | MODIFICATION | 333572.57 |  |  | #DIV/0! | 2025-06-17 07:57 | 2025-06-25 10:23 | 2025-06-26 |  | 2025-07-30 |  | 42.6689 | 34.5674 | -45868 | 2025-07-07 10:00 | 2025-07-16 13:45 | 2025-08-06 07:57 | 1.3862 | -764.4667 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-09-28 | 27 | [8 empty] | NO COC |  | 2025-08-14 | #VALUE! | [20 empty] | 0 | 42.6689 | 0 | 42.6689 | 1.3862 | 1 |  | 1.4187 | 1.4187 | 0.016667 |  | NON-REV
2025-06-30 | 2025-06-26 |  | HMB | X25030928283 | SUSANA QUINCENA AGUILAR | KABESANG SEGUNDO, FORTUNATA VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 124.91 | 281.47 | 150 | NEW | 856243.05 | 107326.76 |  | 0% | 2025-06-16 14:23 | 2025-06-25 10:24 | 2025-06-26 |  | 2025-08-09 11:22 |  | 53.8746 | 45.0403 | -45878.4736 | 2025-07-06 14:42 | 2025-07-15 18:00 | 2025-08-05 14:23 | 1.7557 | -764.6412 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 2025-10-08 11:22 | 16.5264 | [8 empty] | NO COC |  | 2025-08-24 11:22 | #VALUE! | [18 empty] | 2025-07-01 | CY9-8085, 530164, CY9-8086, 530165 | 0 | 53.8746 | 0 | 53.8746 | 1.7557 | -9.4736 |  | 1.447 | 1.447 | -0.15789 |  | REV
2025-06-26 | 2025-06-26 |  | HMB | X25041311938 | TEDDY PASCUA ALBANO | MT. SILINGAN, CAMELLA SPRINGVILLE HEIGHTS III, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 268.32 | 812.1 | 22.5 | NEW | 1282397.39 | 230146.57 |  | 0% | 2025-06-16 14:37 | 2025-06-25 10:32 | 2025-06-26 |  |  |  | -45824.6093 | -45833.4389 | 0 | 2025-07-11 10:40 | 2025-07-21 20:49 | 2025-08-05 14:37 | -1234.7186 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-18 | CS8-8099, CS8-8100, CS8-8101, CS8-8102, 530657, CS8-8103, CS8-8104, CS8-8105, CR8-0009 | 0 | -45824.6093 | 0 | -45824.6093 | -1234.7186 | 0 |  | 1.1961 | 1.1961 | 0 | 31.3907 | REV | 0-3 MONTHS
2025-06-25 | 2025-06-25 |  | CBG | R24029952 | NEW NAIA INFRA CORP., | NAIA, PASAY, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 303.46 | 946.62 | 0 | RELOC | 1474311.77 |  |  | #DIV/0! | 2025-06-13 14:58 | 2025-06-16 15:20 | 2025-06-25 |  | 2025-07-30 |  | 46.3764 | 43.3608 | -45868 | 2025-07-08 11:00 | 2025-07-18 21:09 | 2025-08-02 14:58 | 1.2496 | -764.4667 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-09-28 | 27 | [8 empty] | NO COC |  | 2025-08-14 | #VALUE! | [20 empty] | 0 | 46.3764 | 0 | 46.3764 | 1.2496 | 1 |  | 1.2765 | 1.2765 | 0.016667 |  | NON-REV
2025-06-27 | 2025-06-24 |  | HMB | X25041456660 | PRECIOUS GRACE REYES SUBIDO | M.L. QUEZON, PUROK 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 38.679 | 123.9 | 80 | NEW | 385800.5 | 39223.77 |  | 0% | 2025-06-13 14:58 | 2025-06-19 12:27 | 2025-06-24 | 2025-07-09 | 2025-07-09 |  | 25.3764 | 19.4812 | -45847 | 2025-07-03 23:15 | 2025-07-13 04:39 | 2025-08-02 14:58 | 0.81526 | -764.1167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-09-07 | 48 | [8 empty] | FOR AUDIT |  | 2025-07-24 | 22 | 2025-07-09 | 2025-08-15 | [8 empty] | Y | [7 empty] | 2025-06-24 | A8-0006, A8-8157, TLN-530720 | 0 | 25.3764 | 0 | 25.3764 | 0.81526 | 22 |  | 1.522 | 1.522 | 0.36667 |  | REV
N/A | N/A |  | HMB | X25051594622 | NICHOLAS IAN CALIMLIM DE LUNA | PRES. QUEZON, TEOVILLE SUBD WEST, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 30.21 | 30.21 | 56 | MODIFICATION | 230587.76 |  |  | #DIV/0! | 2025-06-14 00:55 | 2025-06-23 08:52 | N/A |  | 2025-07-08 |  | 23.9618 | 14.6306 | -45846 | 2025-07-02 02:42 | 2025-07-10 17:35 | 2025-08-03 00:55 | 0.85276 | -764.1 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-09-06 | 49 | [8 empty] | NO COC |  | 2025-07-23 | #VALUE! | [20 empty] | 0 | 23.9618 | 0 | 23.9618 | 0.85276 | 23 |  | 1.6713 | 1.6713 | 0.38333 |  | NON-REV
N/A | N/A |  | CBG | X24104277984 | GLOBE TELECOM, INC. | BRONZE, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 12.43 | 12.43 | 23 | MODIFICATION | 146585.7 |  |  | #DIV/0! | 2025-06-17 09:59 | 2025-06-23 08:43 | N/A |  | 2025-07-10 | 2025-08-05 09:44 | 22.5838 | 16.6368 | 26.4056 | 2025-07-06 04:34 | 2025-07-14 23:55 | 2025-08-06 09:59 | 0.77789 | 0.44009 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-08 | 47 | [8 empty] | PAID |  | 2025-07-25 | #VALUE! | [20 empty] | 0 | 22.5838 | 0 | 22.5838 | 0.77789 | 21 |  | 1.5012 | 1.5012 | 0.35 |  | NON-REV
N/A | N/A |  | CBG | X25030951328 | FILINVEST LAND, INC. | EAST SERVICE, ALABANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 5.54 | 5.54 | 11 | NEW | 20820.62 |  |  | #DIV/0! | 2025-06-16 14:05 | 2025-06-23 08:45 | N/A |  | 2025-07-04 | 2025-08-05 09:39 | 17.4133 | 10.6354 | 32.4021 | 2025-07-05 08:40 | 2025-07-14 04:01 | 2025-08-05 14:05 | 0.59979 | 0.54003 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-02 | 53 | [8 empty] | PAID |  | 2025-07-19 | #VALUE! | [20 empty] | 0 | 17.4133 | 0 | 17.4133 | 0.59979 | 27 |  | 1.5298 | 1.5298 | 0.45 |  | REV
2025-06-23 | 2025-06-24 |  | BIZ | X25041378549 | RAHUL DEVIDAS DARYANI | E. RODRIGUEZ JR., STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 7.61 | 19.61 | 0 | TERMINATION | 1005983.91 | 16849.41 |  | 0% | 2025-06-19 07:45 | 2025-06-20 13:42 | 2025-06-24 | 2025-06-30 | 2025-06-30 |  | 10.6771 | 9.4292 | -45838 | 2025-07-08 02:20 | 2025-07-16 21:41 | 2025-08-08 07:45 | 0.36777 | -763.9667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-29 | 57 | [8 empty] | FOR AUDIT |  | 2025-07-15 | 31 | 2025-06-30 | 2025-08-15 | [8 empty] | Y | [7 empty] | N/A | 514473 | 0 | 10.6771 | 0 | 10.6771 | 0.36777 | 31 |  | 1.4355 | 1.4355 | 0.51667 |  | NON-REV
2025-06-25 | 2025-06-26 |  | HMB | X25031019967 | ADONIS VERMUG | INT M.L. QUEZON, PUROK 5, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | FOR SCHED ENERGIZATION |  | VJC | SCHED | Jenneth Madrid | 110.24 | 110.24 | 4.5 | NEW | 113100.57 |  |  | #DIV/0! | 2025-06-19 12:54 | 2025-06-25 10:11 | 2025-06-26 |  |  |  | -45827.5375 | -45833.4243 | 0 | 2025-07-10 17:52 | 2025-07-20 04:47 | 2025-08-08 12:54 | -1419.8703 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [10 empty] | N | [7 empty] | 2025-07-18 | A8-1221, A8-8150, A8-1220 | 0 | -45827.5375 | 0 | -45827.5375 | -1419.8703 | 0 |  | 1.2846 | 1.2846 | 0 | 28.4625 | REV | 0-3 MONTHS
2025-06-30 | 2025-06-26 |  | BIZ | X25020699073 | ALABANG HILLS VILLAGE ASSOCIATION, INC. | DON JESUS, ALABANG HILLS SUBD PH 3, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 114.2 | 192.27 | 59 | NEW | 610937.01 |  |  | #DIV/0! | 2025-06-19 12:52 | 2025-06-25 10:34 | 2025-06-26 |  | 2025-07-16 |  | 26.4639 | 20.5597 | -45854 | 2025-07-09 21:09 | 2025-07-19 02:33 | 2025-08-08 12:52 | 0.8502 | -764.2333 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-09-14 | 41 | [8 empty] | NO COC |  | 2025-07-31 | #VALUE! | [18 empty] | 2025-07-01 | DV1-8085, 526631 | 0 | 26.4639 | 0 | 26.4639 | 0.8502 | 15 |  | 1.3321 | 1.3321 | 0.25 |  | REV
2025-06-25 | 2025-06-26 | Y | BIZ | X25061977034 | ROVIE BUGAYONG GABIOLA | BF CARNIBAL PARK, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 59.72 | 138 | 18 | NEW | 326798.64 |  |  | #DIV/0! | 2025-06-19 13:07 | 2025-06-25 10:07 | 2025-07-02 |  | 2025-07-07 |  | 17.4535 | 11.5785 | -45845 | 2025-07-10 18:05 | 2025-07-20 05:00 | 2025-08-08 13:07 | 0.54076 | -764.0833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-09-05 | 50 | [8 empty] | NO COC |  | 2025-07-22 | #VALUE! | [20 empty] | 0 | 17.4535 | 0 | 17.4535 | 0.54076 | 24 |  | 1.2843 | 1.2843 | 0.4 |  | REV
2025-06-23 | 2025-06-25 | Y | HMB | X25041097966 | ROMAN CATHOLIC BISHOP OF PARANAQUE | BARCELONA, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done digging, for pole erection :Scope of Work:Reorient Cut out Transformer /Energize 2-75KVA |  | ECOM | FCOMP | Ronilo Gange Jr. | 118.409 | 337.98 | 97 | MODIFICATION | 886605.55 | 155081.7 |  | 0% | 2025-06-19 16:24 | 2025-06-20 13:10 | 2025-06-25 |  | 2025-06-26 |  | 6.3167 | 5.4514 | -45834 | 2025-07-11 04:52 | 2025-07-20 17:47 | 2025-08-08 16:24 | 0.19322 | -763.9 | 30 | 34 | 24.5192 | 31.0577 | 21.5192 | 60 | 57 | 52 | 2025-08-25 | 61 | [8 empty] | FOR AUDIT |  | 2025-07-11 | -8 | 2025-06-26 | 2025-07-03 | [8 empty] | Y | 2025-06-25 | [8 empty] | 0 | 6.3167 | 0 | 6.3167 | 0.19322 | 35 |  | 1.2638 | 1.2638 | 0.58333 |  | NON-REV
2025-06-26 | 2025-06-26 |  | HMB | X25010133152 | TSA-TIN SHANIE ANGELO LEASING CORPORATION | MAGDIWANG, GREEN VALLEY SUBD SECT C, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 43.32 | 3.5 | 28.5 | NEW | 299225.3 | 37219.11 |  | 0% | 2025-06-19 16:32 | 2025-06-25 10:36 | 2025-06-26 |  |  |  | -45827.6889 | -45833.4417 | 0 | 2025-07-08 11:07 | 2025-07-17 06:28 | 2025-08-08 16:32 | -1578.5093 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-18 | CT8-8073, 523686 | 0 | -45827.6889 | 0 | -45827.6889 | -1578.5093 | 0 |  | 1.4229 | 1.4229 | 0 | 28.3111 | REV | 0-3 MONTHS
N/A | N/A |  | HMB | X24072781796 | HERBERT JOSEPH GO TAN | SAN CARLOS, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 387.5 | 387.5 | 231 | NEW | 1183971.14 |  |  | #DIV/0! | 2025-06-18 09:38 | 2025-06-23 08:39 | N/A |  | 2025-07-17 |  | 28.5986 | 23.6396 | -45855 | 2025-07-07 21:38 | 2025-07-16 21:38 | 2025-08-07 09:38 | 0.95329 | -764.25 | 30 | 30 | 22.5 | 28.5 | 19.5 | 60 | 57 | 52 | 2025-09-15 | 40 | [8 empty] | NO COC |  | 2025-08-01 | #VALUE! | [20 empty] | 0 | 28.5986 | 0 | 28.5986 | 0.95329 | 14 |  | 1.42 | 1.42 | 0.23333 |  | REV
N/A | N/A |  | BIZ | X25041175709 | THE ROMAN CATHOLIC BISHOP OF PARANAQUE, INC. | BLOCK 30, SOLDIERS HILLS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 47.7 | 47.7 | 99 | NEW |  |  |  | #DIV/0! | 2025-06-17 13:35 | 2025-06-23 08:54 | N/A |  | 2025-06-27 |  | 9.434 | 3.6292 | -45835 | 2025-07-05 15:22 | 2025-07-14 06:15 | 2025-08-06 13:35 | 0.33574 | -763.9167 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-08-26 | 60 | [8 empty] | NO COC |  | 2025-07-12 | #VALUE! | [20 empty] | 0 | 9.434 | 0 | 9.434 | 0.33574 | 34 |  | 1.5457 | 1.5457 | 0.56667 |  | REV
N/A | N/A |  | HMB | X25030797111 | CITY GOVERNMENT OF TAGUIG | GEN. SANTOS, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 18.64 | 18.64 | 28 | NEW |  |  |  | #DIV/0! | 2025-06-17 13:41 | 2025-06-23 08:34 | N/A |  | 2025-06-25 | 2025-07-10 08:04 | 7.4299 | 1.6431 | 15.3361 | 2025-07-06 08:16 | 2025-07-15 03:37 | 2025-08-06 13:41 | 0.25592 | 0.2556 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-24 | 62 | [8 empty] | PAID |  | 2025-07-10 | #VALUE! | [20 empty] | 0 | 7.4299 | 0 | 7.4299 | 0.25592 | 36 |  | 1.4959 | 1.4959 | 0.6 |  | REV
2025-06-30 | 2025-06-26 |  | CBG | R24098951 | CAVITEX INFRASTRUCTURE CORP., CBG | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 599.01 | 599.01 | 0 | RELOC | 829081.67 |  |  | #DIV/0! | 2025-06-20 09:46 | 2025-06-25 10:47 | 2025-06-26 |  | 2025-06-27 |  | 6.5931 | 1.5507 | -45835 | 2025-07-15 05:48 | 2025-07-25 15:57 | 2025-08-09 09:46 | 0.17765 | -763.9167 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-08-26 | 60 | [8 empty] | NO COC |  | 2025-07-12 | #VALUE! | [18 empty] | 2025-07-01 | A5-0624, A5-0623, A5-8089 | 0 | 6.5931 | 0 | 6.5931 | 0.17765 | 34 |  | 1.0938 | 1.0938 | 0.56667 |  | NON-REV
2025-07-16 | 2025-06-26 |  | CBG | R23705436 | CAVITEX INFRASTRUCTURE CORP., CBG | C5 ROAD, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 252.19 | 401.23 | 0 | RELOC | 788084.57 | 215879.29 |  | 0% | 2025-06-20 09:41 | 2025-06-25 10:48 | 2025-06-26 |  |  |  | -45828.4035 | -45833.45 | 0 | 2025-07-13 10:16 | 2025-07-23 08:49 | 2025-08-09 09:41 | -1320.7491 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-17 | CZ8-8096, CZ8-8097, CZ8-2207, CZ8-2172 | 0 | -45828.4035 | 0 | -45828.4035 | -1320.7491 | 0 |  | 1.17 | 1.17 | 0 | 27.5965 | NON-REV | 0-3 MONTHS
2025-07-01 | 2025-07-01 |  | HMB | X25010323001 | GAWARAN HEIGHTS PHASE 7 HOMEOWNERS ASSOCIATION, IN | BLOCK 3, GAWARAN HEIGHTS PH. 6 SOUTH GAWARAN, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 92.78 | 171.06 | 21 | NEW | 362747.6 | 64987.87 |  | 0% | 2025-06-23 15:37 | 2025-06-30 08:01 | 2025-07-01 |  |  |  | -45831.6507 | -45838.334 | 0 | 2025-07-14 20:35 | 2025-07-24 07:30 | 2025-08-12 15:37 | -1419.9977 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-01 | CR8-8039, 527317 | 0 | -45831.6507 | 0 | -45831.6507 | -1419.9977 | 0 |  | 1.1572 | 1.1572 | 0 | 24.3493 | REV | 0-3 MONTHS
2025-07-11 | 2025-07-01 |  | HMB | X25051611244 | ROBERTO SANTOS PANTOJA | PROSPERITY, BETTERLIVING SUBD ANNEX 29/32, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 147.73 | 304.29 | 63 | NEW | 640721.14 | 126928.96 |  | 0% | 2025-06-20 23:37 | 2025-06-30 12:58 | 2025-07-01 |  |  |  | -45828.9839 | -45838.5403 | 0 | 2025-07-12 12:04 | 2025-07-22 01:00 | 2025-08-09 23:37 | -1401.8277 | 0 | 30 | 34 | 24.5192 | 31.0577 | 21.5192 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-01 | CY9-0665, CY9-8091, CY9-8092, 530932, CY9-0861 | 0 | -45828.9839 | 0 | -45828.9839 | -1401.8277 | 0 |  | 1.224 | 1.224 | 0 | 27.0161 | REV | 0-3 MONTHS
2025-07-01 | 2025-07-01 |  | HMB | X25010341535 | CITY GOVERNMENT OF MUNTINLUPA | BUENDIA, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 120.26 | 276.82 | 10 | NEW | 543525.19 |  |  | #DIV/0! | 2025-06-24 12:26 | 2025-06-30 15:08 | 2025-07-01 |  | 2025-07-24 |  | 29.4822 | 23.3694 | -45862 | 2025-07-16 09:16 | 2025-07-26 00:26 | 2025-08-13 12:26 | 0.88915 | -764.3667 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-09-22 | 33 | [8 empty] | NO COC |  | 2025-08-08 | #VALUE! | [18 empty] | 2025-07-01 | DR2-0012, 527348, DR2-5718, DR2-8037, DR2-8038 | 0 | 29.4822 | 0 | 29.4822 | 0.88915 | 7 |  | 1.1003 | 1.1003 | 0.11667 |  | REV
2025-07-01 | 2025-07-01 |  | HMB | X25051870678 | CLAVEL BISCOCHO BENDAÑA | SAN LORENZO, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 13 | 13 | 78 | MODIFICATION | 36321.46 | 11195.76 |  | 0% | 2025-06-20 14:36 | 2025-06-30 12:54 | 2025-07-01 |  |  |  | -45828.6081 | -45838.5375 | 0 | 2025-07-08 16:23 | 2025-07-17 07:15 | 2025-08-09 14:36 | -1630.9593 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | 171685 | 0 | -45828.6081 | 0 | -45828.6081 | -1630.9593 | 0 |  | 1.4375 | 1.4375 | 0 | 27.3919 | NON-REV | 0-3 MONTHS
2025-07-01 | 2025-07-01 |  | HMB | X25051893039 | RICARDO PAAT ISLA | DARWIN, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 8.73 | 6.39 | 28 | MODIFICATION | 24261.23 |  |  | #DIV/0! | 2025-06-20 16:08 | 2025-06-30 12:55 | 2025-07-01 |  | 2025-07-16 |  | 25.3275 | 15.4618 | -45854 | 2025-07-09 10:43 | 2025-07-18 06:05 | 2025-08-09 16:08 | 0.87239 | -764.2333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-14 | 41 | [8 empty] | NO COC |  | 2025-07-31 | #VALUE! | [18 empty] | N/A | TLN 037234 | 0 | 25.3275 | 0 | 25.3275 | 0.87239 | 15 |  | 1.3891 | 1.3891 | 0.25 |  | NON-REV
2025-07-07 | 2025-07-01 |  | HMB | X25062074271 | MARIVIC LACHICA | WEST SERVICE, JOSEPH ESTRADA CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 8.38 | 8.39 | 15 | NEW | 38678.94 |  |  | #DIV/0! | 2025-06-20 16:05 | 2025-06-30 12:56 | 2025-07-01 |  | 2025-07-28 |  | 37.3299 | 27.4611 | -45866 | 2025-07-09 10:40 | 2025-07-18 06:01 | 2025-08-09 16:05 | 1.2858 | -764.4333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | NO COC |  | 2025-08-12 | #VALUE! | [18 empty] | N/A | DW1-0736-B | 0 | 37.3299 | 0 | 37.3299 | 1.2858 | 3 |  | 1.3891 | 1.3891 | 0.05 |  | REV
2025-07-14 | 2025-07-01 |  | BIZ | X25020682282 | HARD DISCOUNT PHILIPPINES, INC. | PIO FELIPE, PUROK 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | NEED JOINT SURVEY FOR STAKA WITH DRAINAGE |  | VJC | SCHED | Jenneth Madrid | 37.05 | 115.33 | 19 | NEW | 283928.98 |  |  | #DIV/0! | 2025-06-23 16:41 | 2025-06-30 13:00 | 2025-07-01 |  |  |  | -45831.695 | -45838.5417 | 0 | 2025-07-14 21:39 | 2025-07-24 08:34 | 2025-08-12 16:41 | -1419.9991 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-01 | B8-8188, 527734 | 0 | -45831.695 | 0 | -45831.695 | -1419.9991 | 0 |  | 1.1558 | 1.1558 | 0 | 24.305 | REV | 0-3 MONTHS
2025-07-01 | 2025-07-01 |  | CBG | X25061939774 | ASEANA BUSINESS PARK ESTATE ASSOCIATION, INC. | PRES. DIOSDADO MACAPAGAL, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 19.27 | 19.27 | 13 | NEW | 148300.68 |  |  | #DIV/0! | 2025-06-23 15:47 | 2025-06-30 13:02 | 2025-07-01 |  | 2025-07-18 |  | 24.3426 | 17.4569 | -45856 | 2025-07-12 10:22 | 2025-07-21 05:43 | 2025-08-12 15:47 | 0.83847 | -764.2667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-16 | 39 | [8 empty] | NO COC |  | 2025-08-02 | #VALUE! | [18 empty] | 2025-07-01 | C4-0012, 530092 | 0 | 24.3426 | 0 | 24.3426 | 0.83847 | 13 |  | 1.2862 | 1.2862 | 0.21667 |  | REV
N/A | N/A |  | HMB | X25051858121 | FRANKLIN URI SEDANO | DE SOCORRO, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | TECO | Ian Patrick Perez | 34.76 | 34.76 | 42 | NEW | 269279.91 |  |  | #DIV/0! | 2025-06-20 16:04 | 2025-06-30 12:48 | N/A |  | 2025-07-10 | 2025-08-05 09:46 | 19.3309 | 9.4667 | 26.4069 | 2025-07-09 10:38 | 2025-07-18 06:00 | 2025-08-09 16:04 | 0.66584 | 0.44012 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-08 | 47 | [8 empty] | PAID |  | 2025-07-25 | #VALUE! | [20 empty] | 0 | 19.3309 | 0 | 19.3309 | 0.66584 | 21 |  | 1.3892 | 1.3892 | 0.35 |  | REV
2025-06-26 | 2025-06-26 |  | MN | P2503184475 | MN_MAJOR (WDESIGN), Reloc of Pole affctd by Rd Widening along GSIS Rd to M.Alvarez Ext,Bacoor,Cavite | MARCOS ALVAREZ EXT GREEN VALLEY SUBD SECT A SAN NICOLAS III BACOOR CAVITE | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 56.19 | 745.63 | 0 | RELOC | 630424.09 | 48281.78 |  | 0% | 2025-05-28 18:21 | 2025-06-25 12:57 | 2025-06-26 |  |  |  | -45805.7646 | -45833.5396 | 0 | 2025-06-22 14:23 | 2025-07-03 00:32 | 2025-07-17 18:21 | -1234.2109 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-18 | CT7-0086, CT8-8013, CT7-0555, CT8-8102 |  |  |  | -45805.7646 | -1234.2109 | 0 |  | 1.7038 | 1.7038 | 0 | 50.2354 | NON-REV | 0-3 MONTHS
2025-07-07 | 2025-07-08 |  | HMB | R23330255 | NMERCADO, JOSSIE C., HMB, | MIKAS, VILLANUEVA SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 76 | 232.56 | 0 | RELOC | 349645.46 | 65297.7 |  | 0% | 2025-06-24 | 2025-07-04 14:17 | 2025-07-08 |  |  |  | -45832 | -45842.5951 | 0 | 2025-07-15 20:51 | 2025-07-25 12:00 | 2025-08-13 | -1382.2349 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-08 | CV5-8043, CV5-0680, CV5-8044 |  |  |  | -45832 | -1382.2349 | 0 |  | 1.1159 | 1.1159 | 0 | 24 | NON-REV | 0-3 MONTHS
2025-07-03 | 2025-07-03 |  | BIZ | X25062207400 | GOLDSERVE HOLDING COMPANY INC. | MIA, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | SCHED | Ronilo Gange Jr. | 7.91 | 7.91 | 0 | TERMINATION | 18658.42 | 6796.46 |  | 0% | 2025-06-25 | 2025-07-02 15:21 | 2025-07-03 |  |  |  | -45833 | -45840.6396 | 0 | 2025-07-13 18:35 | 2025-07-22 13:56 | 2025-08-14 | -1578.6922 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | 519608 |  |  |  | -45833 | -1578.6922 | 0 |  | 1.24 | 1.24 | 0 | 23 | NON-REV | 0-3 MONTHS
2025-07-18 | 2025-07-03 |  | CBG | X25051656310 | SMC SKYWAY STAGE 4 CORPORATION | ENLISTED PERSONNEL VILL PH 1, ENLISTED PERSONNEL VIL 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | COMP-CAN | Ronilo Gange Jr. | 14.85 | 14.85 | 0 | TERMINATION | 25841.11 |  |  | #DIV/0! | 2025-06-25 | 2025-07-02 15:22 | 2025-07-03 |  |  |  | -45833 | -45840.6403 | 0 | 2025-07-13 18:35 | 2025-07-22 13:56 | 2025-08-14 | -1578.6922 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | C8-5453-S |  |  |  | -45833 | -1578.6922 | 0 |  | 1.24 | 1.24 | 0 | 23 | NON-REV | 0-3 MONTHS
2025-07-14 | 2025-07-03 |  | HMB | X25030844322 | JOAN ANTONIO QUIMPO | BLOCK 19, ENLISTED PERSONNEL VIL 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 260.15 | 1124.83 | 24 | NEW | 1331234.01 | 223529.04 |  | 0% | 2025-06-25 | 2025-07-02 13:17 | 2025-07-03 |  |  |  | -45833 | -45840.5535 | 0 | 2025-07-21 11:25 | 2025-08-01 08:04 | 2025-08-14 | -1166.1952 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-03 | C8-8111, C8-8112, C8-8113, C8-8114 |  |  |  | -45833 | -1166.1952 | 0 |  | 0.916 | 0.916 | 0 | 23 | REV | 0-3 MONTHS
2025-07-14 | 2025-07-03 |  | HMB | X25041111916 | JOAN ANTONIO QUIMPO | BLOCK 19, ENLISTED PERSONNEL VIL 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 172.15 | 818.06 | 24 | NEW | 1069143.15 | 147916.01 |  | 0% | 2025-06-25 | 2025-07-02 13:16 | 2025-07-03 |  |  |  | -45833 | -45840.5528 | 0 | 2025-07-19 20:02 | 2025-07-30 06:11 | 2025-08-14 | -1234.9447 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-03 | C8-8113, C8-8114, B8-8214, B8-8215, 530324, B8-8216 |  |  |  | -45833 | -1234.9447 | 0 |  | 0.97 | 0.97 | 0 | 23 | REV | 0-3 MONTHS
2025-07-01 | 2025-07-01 |  | BIZ | X25041425641 | HARD DISCOUNT PHILIPPINES, INC. | M.L. QUEZON, PUROK 4, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | COMP | Jenneth Madrid | 3.4 | 3.4 | 19 | NEW | 20541.45 |  |  | #DIV/0! | 2025-06-24 | 2025-06-30 08:10 | 2025-07-01 | 2025-07-09 | 2025-07-09 | 2025-08-21 | 15 | 8.6597 | 43 | 2025-07-12 18:35 | 2025-07-21 13:56 | 2025-08-13 | 0.51667 | 0.71667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-07 | 48 | [8 empty] | PAID |  | 2025-07-24 | 14 | 2025-07-09 | 2025-08-07 | [16 empty] | N/A | A8-0023, 093676 |  |  |  | 15 | 0.51667 | 22 |  | 1.2744 | 1.2744 | 0.36667 |  | REV
2025-07-18 | 2025-07-04 |  | HMB | X25051535599 | JOENY WILSON BELER | A. REYES, PUROK 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 18.91 | 18.91 | 12 | NEW |  |  |  | #DIV/0! | 2025-06-25 | 2025-07-02 13:13 | 2025-07-04 |  | 2025-07-15 |  | 20 | 12.4493 | -45853 | 2025-07-13 18:35 | 2025-07-22 13:56 | 2025-08-14 | 0.68889 | -764.2167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-13 | 42 | [8 empty] | NO COC |  | 2025-07-30 | #VALUE! | [18 empty] | 2025-07-03 | A8-6034, 530804 |  |  |  | 20 | 0.68889 | 16 |  | 1.24 | 1.24 | 0.26667 |  | REV
2025-07-14 | 2025-07-08 |  | HMB | X25051838399 | JONATHAN PAJIMULA FABIAN | MAGUINDANAO EXT, PUROK 2, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 12.23 | 12.23 | 7.5 | NEW | 148408.34 |  |  | #DIV/0! | 2025-06-26 | 2025-07-03 15:01 | 2025-07-08 |  | 2025-07-24 |  | 28 | 20.3743 | -45862 | 2025-07-14 18:35 | 2025-07-23 13:56 | 2025-08-15 | 0.96444 | -764.3667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-22 | 33 | [8 empty] | NO COC |  | 2025-08-08 | #VALUE! | [18 empty] | 2025-07-08 | A8-6047, 531116 |  |  |  | 28 | 0.96444 | 7 |  | 1.2056 | 1.2056 | 0.11667 |  | REV
2025-07-02 | 2025-07-01 |  | BIZ | X25062131222 | AMBICA INTERNATIONAL CORPORATION | MERVILLE ACCESS, KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 111.02 | 114.68 | 0 | MODIFICATION |  |  |  | #DIV/0! | 2025-06-26 | 2025-07-01 06:53 | 2025-07-01 |  | 2025-07-07 |  | 11 | 5.7132 | -45845 | 2025-07-17 04:58 | 2025-07-26 15:53 | 2025-08-15 | 0.34081 | -764.0833 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-09-05 | 50 | [8 empty] | NO COC |  | 2025-07-22 | #VALUE! | [18 empty] | N/A | B7-0038, 322701, B6-0375, B6-8020, B6-0361 |  |  |  | 11 | 0.34081 | 24 |  | 1.0844 | 1.0844 | 0.4 |  | NON-REV
2025-07-14 | 2025-07-01 |  | BIZ | X25041426801 | HARD DISCOUNT PHILIPPINES, INC. | LUZON, ZONE 5, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Energize dT wala pa abang entrada ni customer for meter |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 12.13 | 12.13 | 19 | NEW |  | 10422.71 |  | 0% | 2025-06-24 | 2025-06-30 15:10 | 2025-07-01 |  |  |  | -45832 | -45838.6319 | 0 | 2025-07-12 18:35 | 2025-07-21 13:56 | 2025-08-13 | -1578.6578 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-01 | A8-0016, 530644 |  |  |  | -45832 | -1578.6578 | 0 |  | 1.2744 | 1.2744 | 0 | 24 | REV | 0-3 MONTHS
2025-07-18 | 2025-07-08 |  | BIZ | X25062155208 | HITE INC. | 2ND, TAGUIG BAGUMBAYAN INDL ASS INC, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 60.22 | 60.22 | 0 | TERMINATION | 67441.89 | 51751.2 |  | 0% | 2025-06-26 | 2025-07-03 15:03 | 2025-07-08 |  |  |  | -45834 | -45841.6271 | 0 | 2025-07-16 02:03 | 2025-07-25 05:48 | 2025-08-15 | -1489.0514 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | DY1-5917 |  |  |  | -45834 | -1489.0514 | 0 |  | 1.1371 | 1.1371 | 0 | 22 | NON-REV | 0-3 MONTHS
2025-07-18 | 2025-07-08 |  | HMB | X25041309256 | DINAH TAMONDONG YAMOMO | PRES. OSMEÑA, ZONE 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 89.73 | 168.01 | 23 | NEW | 372200.79 | 76696.67 |  | 0% | 2025-06-26 | 2025-07-03 15:06 | 2025-07-08 |  |  |  | -45834 | -45841.6292 | 0 | 2025-07-17 04:58 | 2025-07-26 15:53 | 2025-08-15 | -1420.0705 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-08 | A8-0677, A8-1246, A8-8156, 530552, A8-5971 |  |  |  | -45834 | -1420.0705 | 0 |  | 1.0844 | 1.0844 | 0 | 22 | REV | 0-3 MONTHS
N/A | N/A |  | CBG | X24114371468 | DITO TELECOMMUNITY CORPORATION | MANILA DOCTOR VILL, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Done energize with meter |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 27.7 | 27.7 | 31 | NEW | 254114.66 |  |  | #DIV/0! | 2025-06-25 | 2025-06-30 12:46 | N/A |  | 2025-07-17 12:51 |  | 22.5354 | 17.0035 | -45855.5354 | 2025-07-13 18:35 | 2025-07-22 13:56 | 2025-08-14 | 0.77622 | -764.2589 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-15 12:51 | 39.4646 | [8 empty] | NO COC |  | 2025-08-01 12:51 | #VALUE! | [23 empty] | 22.5354 | 0.77622 | 13.4646 |  | 1.24 | 1.24 | 0.22441 |  | REV
N/A | N/A |  | BIZ | X25030876602 | HARD DISCOUNT PHILIPPINES, INC. | SPINE ROAD, BELLAZONA NAVARRE, BACOOR | BACOOR CITY | DASMA |  |  | C2 | TECO | Ian Patrick Perez | 11.67 | 11.67 | 20 | NEW | 140189.34 |  |  | #DIV/0! | 2025-06-24 | 2025-06-30 07:48 | N/A |  | 2025-07-02 08:30 | 2025-07-23 12:47 | 8.3542 | 2.0292 | 21.1785 | 2025-07-12 18:35 | 2025-07-21 13:56 | 2025-08-13 | 0.28775 | 0.35297 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-08-31 08:30 | 54.6458 | [8 empty] | PAID |  | 2025-07-17 08:30 | #VALUE! | [23 empty] | 8.3542 | 0.28775 | 28.6458 |  | 1.2744 | 1.2744 | 0.47743 |  | REV
2025-07-23 | 2025-07-08 |  | BIZ | X25051521562 | GOLDSERVE HOLDING COMPANY INC. | MIA, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC / STA. ROSA | SCHED | Jenneth Madrid | 13.27 | 128.08 | 86 | NEW | 711679.97 |  |  | #DIV/0! | 2025-06-23 15:42 | 2025-07-03 15:09 | 2025-07-08 |  |  |  | -45831.6542 | -45841.6312 | 0 | 2025-07-13 23:59 | 2025-07-23 05:23 | 2025-08-12 15:42 | -1472.4197 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-08 | B5-8037, B5-0084, B5-00971, B5-5094, B5-8038, 530774 |  |  |  | -45831.6542 | -1472.4197 | 0 |  | 1.1998 | 1.1998 | 0 | 24.3458 | REV | 0-3 MONTHS
2025-07-18 | 2025-07-08 |  | HMB | X25030790337 | CITY GOVERNMENT OF BACOOR | DUPLEX SUBD, DUPLEX SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 335.49 | 726.9 | 0 | NEW | 1134646.86 | 288258.73 |  | 0% | 2025-06-27 16:36 | 2025-07-04 15:10 | 2025-07-08 |  |  |  | -45835.6917 | -45842.6319 | 0 | 2025-07-22 12:38 | 2025-08-01 22:47 | 2025-08-16 16:36 | -1235.0172 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-08 | CR7-8073, CR7-8074, CR7-8075, CR7-8076, CR7-8077, DSM1-4102, 047003 |  |  |  | -45835.6917 | -1235.0172 | 0 |  | 0.89747 | 0.89747 | 0 | 20.3083 | REV | 0-3 MONTHS
2025-07-18 | 2025-07-08 |  | HMB | X25030866480 | CITY GOVERNMENT OF BACOOR | DUPLEX SUBD, DUPLEX SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 481.05 | 949.34 | 153 | NEW | 1916746.11 | 413354.06 |  | 0% | 2025-06-27 16:42 | 2025-07-04 15:12 | 2025-07-08 | NAHUKAYAN NA,NATAYUAN NA NG POSTE. AS PER ROYO,MERON NA DAW POSTE SA SITE ON GOING DIGGING |  |  | -45835.6958 | -45842.6333 | 0 | 2025-07-20 05:28 | 2025-07-30 00:52 | 2025-08-16 16:42 | -1346.4236 | 0 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-08 | DSM1-4102, CR7-8079, CR7-8080, TLN-193341, CR7-8081, CR7-8082, 047725, CR7-0059, CR7-6122, 197086, CR7-8083, 530384, CR7-0061, CR7-8084 |  |  |  | -45835.6958 | -1346.4236 | 0 |  | 0.97831 | 0.97831 | 0 | 20.3042 | REV | 0-3 MONTHS
2025-07-15 | 2025-07-11 |  | HMB | X25010281553 | MICHELLE LUZ HILAO TAN | S. TOLENTINO, GATCHALIAN SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 105.07 | 261.64 | 30.8 | MODIFICATION | 399691.08 | 90279.44 |  | 0% | 2025-06-30 14:07 | 2025-07-08 | 2025-07-11 |  |  |  | -45838.5882 | -45846 | 0 | 2025-07-22 10:58 | 2025-08-01 02:07 | 2025-08-19 14:07 | -1382.4336 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-11 | CY8-8083, CY8-8084, 527249, CY7-0056 |  |  |  | -45838.5882 | -1382.4336 | 0 |  | 0.91718 | 0.91718 | 0 | 17.4118 | NON-REV | 0-3 MONTHS
2025-07-18 | 2025-07-08 |  | HMB | R24094970 | ROXAS, CHITO M | KALAPI, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 31.11 | 31.11 | 0 | RELOC | 52322.76 | 26327.79 |  | 0% | 2025-06-27 16:01 | 2025-07-04 14:18 | 2025-07-08 |  |  |  | -45835.6674 | -45842.5958 | 0 | 2025-07-16 10:36 | 2025-07-25 05:57 | 2025-08-16 16:01 | -1578.7841 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | DU1-8033, DU1-8034, CU9-1417 |  |  |  | -45835.6674 | -1578.7841 | 0 |  | 1.1481 | 1.1481 | 0 | 20.3326 | NON-REV | 0-3 MONTHS
2025-07-18 | 2025-07-11 |  | HMB | X25062139889 | ANGEL AMODIA CANJA | 11TH AVE EXT, HEN HEADQUARTER SUPPRT GRP, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid |  | 15 | 36 | MODIFICATION | 149190.66 |  |  | #DIV/0! | 2025-06-30 14:01 | 2025-07-08 | 2025-07-11 |  | 2025-07-24 |  | 23.416 | 16 | -45862 | 2025-07-19 08:36 | 2025-07-28 03:57 | 2025-08-19 14:01 | 0.80655 | -764.3667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-22 | 33 | [8 empty] | NO COC |  | 2025-08-08 | #VALUE! | [18 empty] | 2025-07-11 | C8-1101, 530856, C8-8170 |  |  |  | 23.416 | 0.80655 | 7 |  | 1.0477 | 1.0477 | 0.11667 |  | NON-REV
2025-07-23 | 2025-07-08 |  | BIZ | X25051640544 | S.E.A. OLYMPUS MARKETING INC | 1ST, TAGUIG BAGUMBAYAN INDL ASS INC, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | NEED PERMIT (CASH BAND) |  | VJC | SCHED | Jenneth Madrid | 157.7 | 235.99 | 120 | MODIFICATION | 699290.85 |  |  | #DIV/0! | 2025-07-01 12:40 | 2025-07-07 09:33 | 2025-07-08 |  |  |  | -45839.5278 | -45845.3979 | 0 | 2025-07-21 13:00 | 2025-07-30 16:17 | 2025-08-20 12:40 | -1493.8775 | 0 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-08 | DY2-8143, 109308 |  |  |  | -45839.5278 | -1493.8775 | 0 |  | 0.96048 | 0.96048 | 0 | 16.4722 | NON-REV | 0-3 MONTHS
N/A | N/A |  | BIZ | X25010291229 | EMERITO VER REYES | SEACOM CPD, SEACOM CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 58.26 | 58.26 | 162 | NEW | 689380.51 |  |  | #DIV/0! | 2025-06-27 15:51 | 2025-07-02 12:49 | N/A |  | 2025-07-11 |  | 13.3396 | 8.466 | -45849 | 2025-07-16 03:20 | 2025-07-24 20:48 | 2025-08-16 15:51 | 0.4658 | -764.15 | 23 | 32 | 21.4786 | 27.2062 | 18.4786 | 60 | 57 | 52 | 2025-09-09 | 46 | [8 empty] | NO COC |  | 2025-07-26 | #VALUE! | [23 empty] | 13.3396 | 0.4658 | 20 |  | 1.1642 | 1.1642 | 0.33333 |  | REV
N/A | N/A |  | HMB | X25062114606 | NICHOLAS IAN CALIMLIM DE LUNA | PRES. QUEZON, TEOVILLE SUBD WEST, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 30.51 | 30.51 | 0 | TERMINATION | 33158.88 |  |  | #DIV/0! | 2025-06-30 16:16 | 2025-07-02 12:36 | N/A |  | 2025-07-08 |  | 7.3222 | 5.475 | -45846 | 2025-07-19 10:51 | 2025-07-28 06:12 | 2025-08-19 16:16 | 0.25221 | -764.1 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-06 | 49 | [8 empty] | NO COC |  | 2025-07-23 | #VALUE! | [23 empty] | 7.3222 | 0.25221 | 23 |  | 1.0444 | 1.0444 | 0.38333 |  | NON-REV
N/A | N/A |  | HMB | X25062037709 | MONICA FE ESPIRITU LUMBA | AZUCENA, TAHANAN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 12.47 | 12.47 | 25 | MODIFICATION | 138781.8 |  |  | #DIV/0! | 2025-06-30 | 2025-07-04 07:57 | N/A |  | 2025-07-09 |  | 9 | 4.6687 | -45847 | 2025-07-18 18:35 | 2025-07-27 13:56 | 2025-08-19 | 0.31 | -764.1167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-07 | 48 | [8 empty] | NO COC |  | 2025-07-24 | #VALUE! | [23 empty] | 9 | 0.31 | 22 |  | 1.0678 | 1.0678 | 0.36667 |  | NON-REV
N/A | N/A |  | HMB | X25020561529 | SALVADOR JR. PATIGA YABES | EMERALD, POSADAS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | C2 | FCOMP | Ian Patrick Perez | 30.74 | 30.74 | 85.5 | NEW | 265833.85 |  |  | #DIV/0! | 2025-06-30 17:52 | 2025-07-02 12:53 | N/A |  | 2025-07-18 |  | 17.2556 | 15.4632 | -45856 | 2025-07-18 19:39 | 2025-07-27 10:32 | 2025-08-19 17:52 | 0.61409 | -764.2667 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-09-16 | 39 | [8 empty] | NO COC |  | 2025-08-02 | #VALUE! | [23 empty] | 17.2556 | 0.61409 | 13 |  | 1.0767 | 1.0767 | 0.21667 |  | REV
N/A | N/A |  | HMB | X25062142328 | MA. PINKY FABRA DUMANGENG | ONYX, PARANAQUE GREEN HEIGHTS, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | FCOMP | Ian Patrick Perez | 22.83 | 22.83 | 48 | NEW | 216813.62 |  |  | #DIV/0! | 2025-06-30 16:20 | 2025-07-02 12:55 | N/A |  | 2025-07-16 14:29 |  | 15.9229 | 14.0653 | -45854.6035 | 2025-07-19 10:55 | 2025-07-28 06:16 | 2025-08-19 16:20 | 0.54846 | -764.2434 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-14 14:29 | 40.3965 | [8 empty] | NO COC |  | 2025-07-31 14:29 | #VALUE! | [23 empty] | 15.9229 | 0.54846 | 14.3965 |  | 1.0443 | 1.0443 | 0.23994 |  | REV
|  |  | CBG | R23722397 | SMC NAIAX CORPORATION, | NAIA, PASAY, PASAY CITY | PASAY CITY | PARAÑAQUE |  |  |  | FCOMP | Jaron Beirnd Dimaandal |  | 850.59 | 0 | RELOC | 2093250.27 |  |  | #DIV/0! | 2025-06-20 10:36 | 2025-06-27 15:44 |  |  | 2025-06-29 |  | 8.5583 | 1.3444 | -45837 | 2025-07-15 06:38 | 2025-07-25 16:47 | 2025-08-09 10:36 | 0.2306 | -763.95 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 2025-08-28 | 58 | [8 empty] | NO COC |  | 2025-07-14 | #VALUE! | [23 empty] | 8.5583 | 0.2306 | 32 |  | 1.0928 | 1.0928 | 0.53333 |  | NON-REV
2025-05-30 | 2025-07-03 |  | BIZ | X25051726265 | A R B CONSTRUCTION COMPANY, INC. | BLOCK 3, SOLDIERS HILLS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 259.11 | 570.83 | 150 | NEW | 1414628.64 | 222656.42 |  | 0% | 2025-05-29 10:51 | 2025-05-30 08:13 | 2025-06-09 |  |  |  | -45806.4521 | -45807.3424 | 0 | 2025-06-20 23:37 | 2025-06-30 19:01 | 2025-07-18 10:51 | -1345.5645 | 0 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 1900-02-28 | 45895 | Materials unavailability | Y | Y |  |  | 2025-06-24 | 34 | 2025-07-28 |  |  | 1900-01-14 | 0 | [18 empty] | 2025-07-03 | DS1-2076, DS1-8178, DS1-1011, DS1-8177, DS1-8179, 086951, DS1-8157, 527237, DS1-8181 |  |  |  | -45840.4521 | -1346.5633 | 0 |  | 1.8373 | 1.8373 | 0 | 49.5479 | REV | 0-3 MONTHS
2025-07-08 | 2025-07-09 | Y | BIZ | X25020684097 | MANILA PRIME LAND HOLDINGS, INC. | GEN EMILIO AGUINALDO, CAMELLA HOMES PH II-A, BACOOR | BACOOR CITY | DASMA | aug 7 nag start ng digging |  | ECOM | SCHED | Ronilo Gange Jr. | 99.71 | 177.99 | 236 | NEW | 878759.98 | 85697.14 |  | 0% | 2025-07-02 13:01 | 2025-07-08 13:56 | 2025-07-09 |  |  |  | -45840.5424 | -45846.5806 | 0 | 2025-07-21 01:12 | 2025-07-29 18:50 | 2025-08-21 13:01 | -1598.542 | 0 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-09 | CV5-8064, 526900 |  |  |  | -45840.5424 | -1598.542 | 0 |  | 0.99237 | 0.99237 | 0 | 15.4576 | REV | 0-3 MONTHS
2025-07-08 | 2025-07-09 | Y | BIZ | X25051795984 | CAFEFRANCE CORP. | GEN. EMILIO AGUINALDO, CAMELLA HOMES PH II-A, BACOOR | BACOOR CITY | DASMA | aug 7 nag start ng digging |  | ECOM | SCHED | Ronilo Gange Jr. | 3.32 | 3.32 | 86 | NEW | 14987.51 |  |  | #DIV/0! | 2025-07-02 16:22 | 2025-07-08 13:57 | 2025-07-09 |  |  |  | -45840.6819 | -45846.5813 | 0 | 2025-07-20 18:09 | 2025-07-29 09:02 | 2025-08-21 16:22 | -1631.389 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | CV5-8064, 526900 |  |  |  | -45840.6819 | -1631.389 | 0 |  | 1.0078 | 1.0078 | 0 | 15.3181 | REV | 0-3 MONTHS
2025-07-08 | 2025-07-09 |  | BIZ | X25010118994 | SOUTH AVENUE HOSPITALITY INC. | L. GABRIEL, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done digging and pole erect |  | ECOM | FCOMP | Ronilo Gange Jr. | 143.41 | 221.69 | 353 | NEW | 1080773.54 | 123248.07 |  | 0% | 2025-07-03 14:22 | 2025-07-08 13:44 | 2025-07-09 |  | 2025-08-11 08:09 |  | 38.741 | 33.7674 | -45880.3396 | 2025-07-21 14:22 | 2025-07-30 04:46 | 2025-08-22 14:22 | 1.3836 | -764.6723 | 28 | 28 | 21 | 26.6 | 18 | 60 | 57 | 52 | 2025-10-10 08:09 | 14.6604 | [8 empty] | NO COC |  | 2025-08-26 08:09 | #VALUE! | [18 empty] | 2025-07-09 | C5-8188, 523922 |  |  |  | 38.741 | 1.3836 | -11.3396 |  | 0.97862 | 0.97862 | -0.18899 |  | REV
2025-07-08 | 2025-07-09 |  | BIZ | X25062317240 | SOUTH AVENUE HOSPITALITY INC. | L. GABRIEL, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done digging and pole erect |  | ECOM | FCOMP | Ronilo Gange Jr. | 15.93 | 15.93 | 28.8 | NEW | 30087.65 | 13687.42 |  | 0% | 2025-07-03 14:25 | 2025-07-08 13:45 | 2025-07-09 |  | 2025-08-11 08:14 |  | 38.7424 | 33.7701 | -45880.3431 | 2025-07-22 09:00 | 2025-07-31 04:21 | 2025-08-22 14:25 | 1.3345 | -764.6724 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-10 08:14 | 14.6569 | [8 empty] | NO COC |  | 2025-08-26 08:14 | #VALUE! | [18 empty] | N/A | 180493 |  |  |  | 38.7424 | 1.3345 | -11.3431 |  | 0.94375 | 0.94375 | -0.18905 |  | REV
2025-07-09 | 2025-07-09 |  | BIZ | X25061934243 | JMF RESTAURANT CORPORATION | GEN. SANTOS, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 141.6 | 219.88 | 204 | NEW | 982070.52 |  |  | #DIV/0! | 2025-07-02 12:29 | 2025-07-08 14:08 | 2025-07-09 | 2025-07-18 | 2025-07-18 |  | 15.4799 | 9.4111 | -45856 | 2025-07-21 13:09 | 2025-07-30 10:08 | 2025-08-21 12:29 | 0.52705 | -764.2667 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 60 | 57 | 52 | 2025-09-16 | 39 | [8 empty] | FOR AUDIT |  | 2025-08-02 | 13 | 2025-07-18 | 2025-08-15 | [16 empty] | 2025-07-09 | DZ2-5018, DZ2-8133, 531193, DZ2-0062-T, DZ2-0225 |  |  |  | 15.4799 | 0.52705 | 13 |  | 0.96967 | 0.96967 | 0.21667 |  | REV
2025-07-08 | 2025-07-09 |  | BIZ | X25062096612 | JULIE SY TORRES | R.M.T. INDUSTRIAL COMPLEX, R.M.T. INDUSTRIAL COMPLEX, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 114.36 | 114.36 | 0 | TERMINATION | 98432.74 |  |  | #DIV/0! | 2025-07-02 17:13 | 2025-07-08 14:09 | 2025-07-09 |  | 2025-08-14 |  | 42.2826 | 36.4104 | -45883 | 2025-07-23 22:11 | 2025-08-02 09:06 | 2025-08-21 17:13 | 1.31 | -764.7167 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-10-13 | 12 | [10 empty] | 2025-08-29 | #VALUE! | [18 empty] | N/A | DQ1-0206 |  |  |  | 42.2826 | 1.31 | -14 |  | 0.87628 | 0.87628 | -0.23333 |  | NON-REV
N/A | N/A |  | HMB | X25062157851 | ERNESTO C BAUTISTA JR. | BF RESORT, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | C2 | FCOMP | Ian Patrick Perez | 5.8 | 5.8 | 6 | MODIFICATION | 24865.38 |  |  | #DIV/0! | 2025-07-02 12:47 | 2025-07-04 12:45 | N/A |  | 2025-07-17 06:13 |  | 14.7264 | 12.7278 | -45855.259 | 2025-07-21 07:22 | 2025-07-30 02:43 | 2025-08-21 12:47 | 0.50724 | -764.2543 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-15 06:13 | 39.741 | [8 empty] | NO COC |  | 2025-08-01 06:13 | #VALUE! | [23 empty] | 14.7264 | 0.50724 | 13.741 |  | 0.98054 | 0.98054 | 0.22902 |  | NON-REV
N/A | N/A |  | CBG | X24104287142 | DITO TELECOMMUNITY CORPORATION | BF HOMES MARTINVILLE SUBD, BF HOMES MARTINVILLE SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 38.56 | 38.56 | 31 | NEW | 263276.54 |  |  | #DIV/0! | 2025-07-03 13:23 | 2025-07-04 12:46 | N/A |  | 2025-08-14 |  | 41.4424 | 40.4681 | -45883 | 2025-07-22 07:58 | 2025-07-31 03:19 | 2025-08-22 13:23 | 1.4275 | -764.7167 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-13 | 12 | [10 empty] | 2025-08-29 | #VALUE! | [23 empty] | 41.4424 | 1.4275 | -14 |  | 0.94524 | 0.94524 | -0.23333 |  | REV
2025-07-18 | 2025-07-11 |  | HMB | X25062239131 | EDGARDO ALFANTE LUNA | KULASI CPD, KULASI CPD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | AVECO | SCHED | Ronilo Gange Jr. | 0.59 | 0.59 | 1.5 | NEW | 15021.02 | 506.95 |  | 0% | 2025-07-03 16:18 | 2025-07-10 | 2025-07-11 |  |  |  | -45841.6792 | -45848 | 0 | 2025-07-22 10:53 | 2025-07-31 06:14 | 2025-08-22 16:18 | -1578.9912 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | CX6-0248, 158665 |  |  |  | -45841.6792 | -1578.9912 | 0 |  | 0.94105 | 0.94105 | 0 | 14.3208 | REV | 0-3 MONTHS
2025-07-18 | 2025-07-17 |  | HMB | X24083345617 | SAIMA SULTAN ABDUL | BAGONG LIPUNAN, BACLARAN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | X25020417967 |  | ECOM | SCHED | Ronilo Gange Jr. | 259.79 | 416.35 | 90 | NEW | 786924.67 |  |  | #DIV/0! | 2025-07-07 14:47 | 2025-07-14 14:53 | 2025-07-17 |  |  |  | -45845.616 | -45852.6201 | 0 | 2025-07-29 15:31 | 2025-08-08 07:43 | 2025-08-26 14:47 | -1373.683 | 0 | 32 | 34 | 25.0307 | 31.7055 | 22.0307 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-16 | D5-3396, D5-8097, D5-8098, 523552, D5-1689 |  |  |  | -45845.616 | -1373.683 | 0 |  | 0.70066 | 0.70066 | 0 | 10.384 | REV | 0-3 MONTHS
2025-07-18 | 2025-07-17 |  | HMB | X25062074037 | ERICH HERROS LINGAD | TEHERAN, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 53.97 | 132.25 | 80 | MODIFICATION | 397295.13 |  |  | #DIV/0! | 2025-07-07 23:11 | 2025-07-14 14:56 | 2025-07-17 |  | 2025-07-21 |  | 13.034 | 6.3778 | -45859 | 2025-07-28 07:28 | 2025-08-06 12:52 | 2025-08-26 23:11 | 0.41874 | -764.3167 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-09-19 | 36 | [8 empty] | NO COC |  | 2025-08-05 | #VALUE! | [18 empty] | 2025-07-16 | CZ8-0745, CZ8-8126, 531373, CZ8-2139 |  |  |  | 13.034 | 0.41874 | 10 |  | 0.74001 | 0.74001 | 0.16667 |  | NON-REV
2025-07-18 | 2025-07-16 |  | HMB | X25051639776 | REGINA OMNOS PACLIBAR | SAN JOSE, MANUYO I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 4.72 | 4.72 | 1.5 | NEW | 26372.55 |  |  | #DIV/0! | 2025-07-04 14:36 | 2025-07-11 10:36 | 2025-07-16 |  | 2025-07-28 |  | 23.3917 | 16.5583 | -45866 | 2025-07-23 09:11 | 2025-08-01 04:32 | 2025-08-23 14:36 | 0.80571 | -764.4333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | NO COC |  | 2025-08-12 | #VALUE! | [18 empty] | 2025-07-16 | CZ7-0491 |  |  |  | 23.3917 | 0.80571 | 3 |  | 0.90905 | 0.90905 | 0.05 |  | REV
2025-07-18 | 2025-07-16 |  | HMB | X25051727907 | KAINE ANTONET CHUA CORDOVA, | ONELIA JOSE, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Done energize with meter |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 125.51 | 125.51 | 77.4 | NEW | 385717.47 | 74239.76 |  | 0% | 2025-07-04 14:39 | 2025-07-11 10:26 | 2025-07-16 |  |  |  | -45842.6104 | -45849.4347 | 0 | 2025-07-24 22:56 | 2025-08-03 04:20 | 2025-08-23 14:39 | -1472.7716 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-16 | CV6-0120, 531017, CV7-8186 |  |  |  | -45842.6104 | -1472.7716 | 0 |  | 0.84781 | 0.84781 | 0 | 13.3896 | REV | 0-3 MONTHS
N/A | N/A |  | BIZ | X25030875643 | JETTI_PETROLEUM INC. | DR. A. SANTOS, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | Done energize with meter |  | C2 | FCOMP | Ian Patrick Perez | 38.06 | 38.06 | 33 | NEW | 247433.29 |  |  | #DIV/0! | 2025-07-07 14:50 | 2025-07-08 14:14 | N/A |  | 2025-07-18 |  | 10.3819 | 9.4069 | -45856 | 2025-07-26 09:25 | 2025-08-04 04:46 | 2025-08-26 14:50 | 0.3576 | -764.2667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-16 | 39 | [8 empty] | NO COC |  | 2025-08-02 | #VALUE! | [23 empty] | 10.3819 | 0.3576 | 13 |  | 0.80538 | 0.80538 | 0.21667 |  | REV
N/A | N/A | Y | BIZ | X25062023744 | YDLAZAVON PANCIT HABHAB, INC. | SAN ANTONIO, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | FCOMP | Ian Patrick Perez | 68.72 | 68.72 | 81 | NEW | 500165.57 |  |  | #DIV/0! | 2025-07-03 16:08 | 2025-07-08 14:13 | N/A |  | 2025-07-14 08:05 |  | 10.6646 | 5.7444 | -45852.3368 | 2025-07-22 23:21 | 2025-07-31 22:04 | 2025-08-22 16:08 | 0.35867 | -764.2056 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-09-12 08:05 | 42.6632 | [8 empty] | NO COC |  | 2025-07-29 08:05 | #VALUE! | [23 empty] | 10.6646 | 0.35867 | 16.6632 |  | 0.91908 | 0.91908 | 0.27772 |  | REV
N/A | N/A |  | BIZ | X24093597833 | STA CECILIA VILLAGE ASSOCIATION INC. | ARIA, STA. CECILIA VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 37.15 | 37.15 | 29 | NEW | 277878.12 |  |  | #DIV/0! | 2025-07-04 09:33 | 2025-07-08 14:21 | N/A |  | 2025-08-05 14:10 |  | 32.1924 | 27.9924 | -45874.5903 | 2025-07-23 04:08 | 2025-07-31 23:29 | 2025-08-23 09:33 | 1.1088 | -764.5765 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-04 14:10 | 20.4097 | [8 empty] | NO COC |  | 2025-08-20 14:10 | #VALUE! | [23 empty] | 32.1924 | 1.1088 | -5.5903 |  | 0.91629 | 0.91629 | -0.093171 |  | REV
N/A | N/A |  | BIZ | X25062048597 | MANILA ESPORTS ICAFE INC. | A. BONIFACIO, PUROK 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Raeven De Quiroz | 64.86 | 64.86 | 61 | NEW | 405410.08 |  |  | #DIV/0! | 2025-07-04 09:39 | 2025-07-08 14:21 | N/A |  | 2025-08-07 |  | 33.5979 | 29.4021 | -45876 | 2025-07-23 16:52 | 2025-08-01 15:35 | 2025-08-23 09:39 | 1.13 | -764.6 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 2025-10-06 | 19 | [8 empty] | NO COC |  | 2025-08-22 | #VALUE! | [23 empty] | 33.5979 | 1.13 | -7 |  | 0.89453 | 0.89453 | -0.11667 |  | REV
2025-07-17 | 2025-07-17 |  | HMB | X24093746174 | VELCOASIA DEVELOPMENT CORP. | STA. ISABEL, SUSANA HEIGHTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 9.23 | 9.23 | 0 | TERMINATION | 22600.14 | 7930.56 |  | 0% | 2025-07-09 16:39 | 2025-07-17 13:25 | 2025-07-17 |  |  |  | -45847.6937 | -45855.559 | 0 | 2025-07-28 11:14 | 2025-08-06 06:35 | 2025-08-28 16:39 | -1579.1983 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | DQ1-5771 | [5 empty] | 0 |  | 0.73388 | 0.73388 | 0 | 8.3063 | NON-REV | 0-3 MONTHS
2025-07-18 | 2025-07-17 |  | BIZ | X25041338459 | PHILIPPINE SEVEN CORPORATION | JADE HEIGHTS, VICTORIAHOMES-JADEHEIGHTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 76.27 | 155.92 | 55 | NEW | 416475.6 |  |  | #DIV/0! | 2025-07-09 12:23 | 2025-07-17 13:27 | 2025-07-17 |  | 2025-07-30 |  | 20.484 | 12.4396 | -45868 | 2025-07-29 20:40 | 2025-08-08 02:04 | 2025-08-28 12:23 | 0.65808 | -764.4667 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 2025-09-28 | 27 | [8 empty] | NO COC |  | 2025-08-14 | #VALUE! | [18 empty] | 2025-07-17 | CQ9-5742, CQ9-8091, 530723, CQ9-5741, FCO CQ9-5741 | [5 empty] | 1 |  | 0.69021 | 0.69021 | 0.016667 |  | REV
2025-07-17 | 2025-07-17 |  | HMB | X24114615817 | GLYN ROXAS PABLO | SAPPHIRE, POSADAS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | ENERGIZE 20KV AND DT 8/9; for FCOMP |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 98.3 | 254.86 | 33 | MODIFICATION | 497380.68 |  |  | #DIV/0! | 2025-07-10 15:23 | 2025-07-17 13:28 | 2025-07-17 |  | 2025-08-14 09:29 |  | 34.7542 | 27.834 | -45883.3951 | 2025-08-01 12:14 | 2025-08-11 03:23 | 2025-08-29 15:23 | 1.0481 | -764.7233 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 2025-10-13 09:29 | 11.6049 | [8 empty] | NO COC |  | 2025-08-29 09:29 | #VALUE! | [18 empty] | 2025-07-17 | DX1-0263, DX2-8020, DX2-8021, 526655, DX1-0265 | [5 empty] | -14.3951 |  | 0.614 | 0.614 | -0.23992 |  | NON-REV
2025-07-18 | 2025-07-16 |  | HMB | X25020433995 | JOHN ROMUEL DAEN ESMAS RAMIREZ | TULIP, CAMELLA TOWNHOMES SORRENTO, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 55.52 | 271.69 | 26.57 | MODIFICATION | 421014.87 | 47701.68 |  | 0% | 2025-07-08 14:20 | 2025-07-14 15:00 | 2025-07-16 |  |  |  | -45846.5972 | -45852.625 | 0 | 2025-07-30 11:11 | 2025-08-09 02:20 | 2025-08-27 14:20 | -1382.6752 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-16 | CW5-8052, 050179, CW5-8053, 527568 | [5 empty] | 0 |  | 0.67564 | 0.67564 | 0 | 9.4028 | NON-REV | 0-3 MONTHS
2025-07-18 | 2025-07-16 |  | HMB | X25031069043 | MARY ANN LIZZA M. FREKING | AGUHO, MEADOWOOD EXEC VILL PH IV-B, BACOOR | BACOOR CITY | DASMA | ( POLE DIGGING ) 9-12-25 |  | AVECO | FCOMP | Ronilo Gange Jr. | 242.65 | 477.5 | 48 | MODIFICATION | 921804.67 | 208494.48 |  | 0% | 2025-07-08 14:15 | 2025-07-14 14:58 | 2025-07-16 | 2025-08-18 06:56 | 2025-08-18 06:56 |  | 40.6951 | 34.6653 | -45887.2889 | 2025-07-31 14:50 | 2025-08-10 13:23 | 2025-08-27 14:15 | 1.1728 | -764.7881 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 2025-10-17 06:56 | 7.7111 | [8 empty] | NO COC |  | 2025-09-02 06:56 | #VALUE! | [18 empty] | 2025-07-16 | CV6-0606, CV6-0607, CV6-8062, CV6-8063, CV6-8064, 530240, CV6-0618 | [5 empty] | -18.2889 |  | 0.64574 | 0.64574 | -0.30481 |  | NON-REV
2025-07-18 | 2025-07-16 |  | HMB | R24062553 | CITY GOVERNMENT OF TAGUIG | C6 ROAD, HAGONOY, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 17.69 | 17.69 | 0 | RELOC | 44745.1 |  |  | #DIV/0! | 2025-07-01 18:26 | 2025-07-14 14:57 | 2025-07-16 |  | 2025-07-24 |  | 22.2319 | 9.3771 | -45862 | 2025-07-20 13:01 | 2025-07-29 08:22 | 2025-08-20 18:26 | 0.76577 | -764.3667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-22 | 33 | [8 empty] | NO COC |  | 2025-08-08 | #VALUE! | [18 empty] | N/A | DZ2-5885, DZ2-5842 | [5 empty] | 7 |  | 1.0069 | 1.0069 | 0.11667 |  | NON-REV
2025-07-17 | 2025-07-16 |  | HMB | X25051836146 | DIONISIO JR. GOROSPE ECHANO | 7TH , GHQ VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 4.39 | 4.39 | 1.5 | NEW | 25892.04 |  |  | #DIV/0! | 2025-07-08 15:27 | 2025-07-14 15:01 | 2025-07-16 | 2025-07-24 | 2025-07-24 |  | 15.3562 | 9.3743 | -45862 | 2025-07-27 10:02 | 2025-08-05 05:23 | 2025-08-27 15:27 | 0.52894 | -764.3667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-22 | 33 | [8 empty] | FOR AUDIT |  | 2025-08-08 | 7 | 2025-07-24 | 2025-08-15 | [16 empty] | 2025-07-16 | CY9-8094 | [5 empty] | 7 |  | 0.77005 | 0.77005 | 0.11667 |  | REV
2025-07-22 | 2025-07-22 |  | HMB | X25020561180 | DAVID ANDRE PALMA SISON | LUZON, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | POLE ERECTION / DRESSING / INSTALL DT 8/8 |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 71.44 | 91.72 | 46 | NEW | 334067.1 | 61383.98 |  | 0% | 2025-07-11 | 2025-07-21 10:17 | 2025-07-22 |  | 2025-08-09 09:11 |  | 29.3826 | 18.9542 | -45878.3826 | 2025-07-31 02:03 | 2025-08-09 05:48 | 2025-08-30 | 0.95458 | -764.6397 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 2025-10-08 09:11 | 16.6174 | [8 empty] | NO COC |  | 2025-08-24 09:11 | #VALUE! | [18 empty] | 2025-07-22 | DU1-8081, 527750 | [5 empty] | -9.3826 |  | 0.64976 | 0.64976 | -0.15638 |  | REV
2025-07-22 | 2025-07-22 |  | HMB | X25041100669 | CITY GOVERNMENT OF MUNTINLUPA | MONTILLANO, ALABANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 205.55 | 205.55 | 108.4 | NEW | 1092314.65 | 176646.77 |  | 0% | 2025-07-11 | 2025-07-21 10:19 | 2025-07-22 |  |  |  | -45849 | -45859.4299 | 0 | 2025-07-31 00:20 | 2025-08-09 03:37 | 2025-08-30 | -1494.1862 | 0 | 28 | 32 | 23.0137 | 29.1507 | 20.0137 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | 192337, DU1-6032, DU1-2195 | [5 empty] | 0 |  | 0.65179 | 0.65179 | 0 | 7 | REV | 0-3 MONTHS
2025-07-22 | 2025-07-22 |  | HMB | X25061985461 | DEBBIE BAUTISTA MACASIANO | SAN GUILLERMO, BAYANAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 24.61 | 24.61 | 3 | NEW | 180869.47 | 21147.33 |  | 0% | 2025-07-14 | 2025-07-21 10:24 | 2025-07-22 |  |  |  | -45852 | -45859.4333 | 0 | 2025-08-01 18:35 | 2025-08-10 13:56 | 2025-09-02 | -1579.3467 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | DT1-0571, 531210, DT1-0040 | [5 empty] | 0 |  | 0.58556 | 0.58556 | 0 | 4 | REV | 0-3 MONTHS
2025-07-22 | 2025-07-22 |  | BIZ | X25020540750 | LIONAPEX EQUIPMENT (PHIL.), INC. | SAN VICTORES, SEACOM CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing for ener and modify materials |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 56.86 | 77.14 | 14 | NEW | 290936.32 | 48855.55 |  | 0% | 2025-07-17 | 2025-07-22 12:56 | 2025-07-22 |  |  |  | -45855 | -45860.5389 | 0 | 2025-08-06 02:03 | 2025-08-15 05:48 | 2025-09-05 | -1489.7337 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | DX1-6120, DX1-8068, 520633 | [5 empty] | 0 |  | 0.45483 | 0.45483 | 0 | 1 | REV | 0-3 MONTHS
2025-07-22 | 2025-07-25 |  | HMB | X25051838106 | ICHAMPION APPTECH DEVELOPMENT CORPORATION | M. ROXAS, FILINVEST SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | digging only |  | ECOM | SCHED | Ronilo Gange Jr. | 289.05 | 329.61 | 169 | MODIFICATION | 1175972.96 |  |  | #DIV/0! | 2025-07-14 | 2025-07-21 10:22 | 2025-07-25 |  |  |  | -45852 | -45859.4319 | 0 | 2025-08-03 12:42 | 2025-08-12 19:18 | 2025-09-02 | -1461.5325 | 0 | 30 | 32 | 23.5294 | 29.8039 | 20.5294 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | CY8-2147, CY8-1016, 069127, CY8-1017, CY8-1127, CY8-8027, CY8-1018, CY8-1019, CY8-8089, 520472 | [5 empty] | 0 |  | 0.54187 | 0.54187 | 0 | 4 | NON-REV | 0-3 MONTHS
2025-07-22 | 2025-07-25 |  | HMB | X25062238532 | KATHY KIMBERLY S GAMBOA | WARSAW, BF HOMES, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 17.9 | 17.9 | 12 | MODIFICATION | 37198.87 |  |  | #DIV/0! | 2025-07-11 | 2025-07-21 10:15 | 2025-07-25 |  |  |  | -45849 | -45859.4271 | 0 | 2025-07-29 18:35 | 2025-08-07 13:56 | 2025-08-30 | -1579.2433 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | CW8-0420, CW8-0419 | [5 empty] | 0 |  | 0.68889 | 0.68889 | 0 | 7 | NON-REV | 0-3 MONTHS
2025-07-22 | 2025-07-23 |  | BIZ | X24072874617 | HERMAN HARRELL HORNE SCHOOL, INC. | BASA, BAHAYANG PAG-ASA PH I, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 472.66 | 472.66 | 271 | NEW | 1427142.92 | 305292.52 |  | 0% | 2025-07-17 | 2025-07-22 12:58 | 2025-07-23 |  |  |  | -45855 | -45860.5403 | 0 | 2025-08-05 22:19 | 2025-08-15 01:04 | 2025-09-05 | -1499.8406 | 0 | 32 | 30 | 22.9299 | 29.0446 | 19.9299 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | CS7-0019, CS7-8120, 137525, CS7-8121, CS7-8122, 523131, CS7-0018, FCO-CS7-0019 | [5 empty] | 0 |  | 0.45792 | 0.45792 | 0 | 1 | REV | 0-3 MONTHS
2025-07-22 | 2025-07-23 |  | HMB | X25010133147 | BELEN ALVAREZ SISON | QUEEN OF CROWN, QUEEN'S ROW AREA A SUBD, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 184.61 | 574.62 | 30.5 | NEW | 925613.28 | 157813.11 |  | 0% | 2025-07-17 | 2025-07-22 13:00 | 2025-07-23 |  |  |  | -45855 | -45860.5417 | 0 | 2025-08-10 20:02 | 2025-08-21 06:11 | 2025-09-05 | -1235.5375 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | CS7-0106, CS7-8123, CS7-0101, CS7-8124, CS7-8125, CS7-8126, CS7-8127, 523411 | [5 empty] | 0 |  | 0.37722 | 0.37722 | 0 | 1 | REV | 0-3 MONTHS
2025-07-22 | 2025-07-23 |  | HMB | X25062272902 | HARD DISCOUNT PHILIPPINES, INC. | PASO, BAGUMBAYAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | \ |  | VJC | COMP | Jenneth Madrid | 4.51 | 4.51 | 19 | NEW | 23672.39 |  |  | #DIV/0! | 2025-07-16 | 2025-07-21 10:28 | 2025-07-23 | 2025-07-28 | 2025-07-28 | 2025-08-21 | 12 | 6.5639 | 24 | 2025-08-03 18:35 | 2025-08-12 13:56 | 2025-09-04 | 0.41333 | 0.4 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | PAID |  | 2025-08-12 | -5 | 2025-07-28 | 2025-08-07 | [16 empty] | 2025-07-22 | 177754 | [5 empty] | 3 |  | 0.51667 | 0.51667 | 0.05 |  | REV
2025-07-22 | 2025-07-23 |  | HMB | X25072438368 | FEDERICO JR. PRENDOL HALOG | 1ST, BAGUMBAYAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | NJ |  | VJC | FCOMP | Jenneth Madrid | 3.2 | 3.2 | 7.5 | NEW | 23672.39 |  |  | #DIV/0! | 2025-07-16 | 2025-07-21 10:30 | 2025-07-23 | 2025-07-27 | 2025-07-28 |  | 12 | 6.5625 | -45866 | 2025-08-03 18:35 | 2025-08-12 13:56 | 2025-09-04 | 0.41333 | -764.4333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-26 | 29 | [8 empty] | FOR AUDIT |  | 2025-08-12 | 3 | 2025-07-28 | 2025-08-15 | [8 empty] | Y | 2025-07-29 | [6 empty] | N/A | DY8-8104, DY2-8104 | [5 empty] | 3 |  | 0.51667 | 0.51667 | 0.05 |  | REV
2025-07-22 | 2025-07-23 |  | HMB | X24114383822 | VICMAR D ISULAT | BLOCK 7, PUROK 13 SDH, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | FOR DIGGING (ROAD ACCESS MASIKIP MANUALLY INSTALL) |  | VJC | SCHED | Jenneth Madrid | 61.94 | 140.22 | 3 | NEW | 326113.45 |  |  | #DIV/0! | 2025-07-15 | 2025-07-21 10:25 | 2025-07-23 |  |  |  | -45853 | -45859.434 | 0 | 2025-08-05 04:58 | 2025-08-14 15:53 | 2025-09-03 | -1420.6592 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | DY2-0295, 526500, DY2-8112, DY2-8113 | [5 empty] | 0 |  | 0.49573 | 0.49573 | 0 | 3 | REV | 0-3 MONTHS
2025-07-22 | 2025-07-25 |  | BIZ | X25020431659 | A.M. ORETA & CO., INC. | GEN. SANTOS, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | ONGOING |  | VJC | SCHED | Jenneth Madrid | 270.03 | 283.63 | 460 | NEW | 1613623.68 |  |  | #DIV/0! | 2025-07-15 | 2025-07-21 10:27 | 2025-07-25 |  |  |  | -45853 | -45859.4354 | 0 | 2025-07-31 22:15 | 2025-08-09 05:47 | 2025-09-03 | -1725.786 | 0 | 28 | 26 | 19.927 | 25.2409 | 16.927 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-22 | DZ2-0085, DZ2-8130, DZ2-8131, 527483 | [5 empty] | 0 |  | 0.6022 | 0.6022 | 0 | 3 | REV | 0-3 MONTHS
N/A | N/A |  | BIZ | X24103888991 | HARD DISCOUNT PHILIPPINES, INC. | ILANG-ILANG, T.S. CRUZ SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | MAINTENANCE | SCHED | Junilo Michael Flores | 21.93 | 21.93 | 20 | NEW | 196406.01 |  |  | #DIV/0! | 2025-07-17 | 2025-07-22 12:53 | N/A |  |  |  | -45855 | -45860.5368 | 0 | 2025-08-04 18:35 | 2025-08-13 13:56 | 2025-09-05 | -1579.45 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [25 empty] | 0 |  | 0.48222 | 0.48222 | 0 | 1 | REV | 0-3 MONTHS
2025-08-05 | 2025-08-05 | Y | BIZ | X25062122012 | DISEGNO DI MILANO INC. | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 68.36 | 68.36 | 298 | NEW | 855093.42 |  |  | #DIV/0! | 2025-07-17 | 2025-07-21 15:05 | 2025-08-05 | 2025-07-31 | 2025-07-31 |  | 14 | 9.3715 | -45869 | 2025-08-03 14:49 | 2025-08-12 02:46 | 2025-09-05 | 0.50928 | -764.4833 | 23 | 30 | 20.6175 | 26.1155 | 17.6175 | 60 | 57 | 52 | 2025-09-29 | 26 | [8 empty] | FOR AUDIT |  | 2025-08-15 | 0 | 2025-07-31 | 2025-08-15 | [16 empty] | 2025-08-05 | DW1-8019, 531379 | [5 empty] | 0 |  | 0.50928 | 0.50928 | 0 |  | REV
N/A | N/A |  | BIZ | X25062317316 | SILVER LINING HOLDINGS CORP. | DOÑA SOLEDAD, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | C2 | FCOMP | Ian Patrick Perez | 12.36 | 12.36 | 18 | NEW | 855093.42 |  |  | #DIV/0! | 2025-07-17 | 2025-07-24 14:42 | N/A |  | 2025-08-06 10:10 |  | 20.4236 | 12.8111 | -45875.4236 | 2025-08-04 18:35 | 2025-08-13 13:56 | 2025-09-05 | 0.70348 | -764.5904 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-05 10:10 | 19.5764 | [8 empty] | NO COC |  | 2025-08-21 10:10 | #VALUE! | [25 empty] | -6.4236 |  | 0.48222 | 0.48222 | -0.10706 |  | REV
2025-08-05 | 2025-07-28 |  | HMB | X25041236026 | JOSE MARCO HERNANDEZ DEL PILAR | ACACIA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | digging only |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 118.03 | 274.6 | 96 | MODIFICATION | 623160.79 | 100235.56 |  | 0% | 2025-07-21 09:26 | 2025-07-28 14:51 | 2025-07-28 |  |  |  | -45859.3931 | -45866.6188 | 0 | 2025-08-11 08:28 | 2025-08-20 17:49 | 2025-09-09 09:26 | -1435.5146 | 0 | 28 | 34 | 23.9597 | 30.349 | 20.9597 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | CS9-8032, CS9-8134, CU9-1125, CS9-8135, 530454, CU9-1124 | [5 empty] | 0 |  | 0.30072 | 0.30072 | 0 | -3.3931 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-07-28 |  | HMB | X25020666216 | CITY OF LAS PIÑAS | LAZO COURT, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | digging only |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 302.7 | 537.54 | 124 | MODIFICATION | 1291179.32 | 260101.8 |  | 0% | 2025-07-18 12:47 | 2025-07-25 14:14 | 2025-07-28 |  |  |  | -45856.5326 | -45863.5931 | 0 | 2025-08-10 01:33 | 2025-08-19 20:57 | 2025-09-06 12:47 | -1347.0356 | 0 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [25 empty] | 0 |  | 0.36623 | 0.36623 | 0 | -0.53264 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-07-28 |  | HMB | X25030809834 | CITY GOVT OF LAS PIÑAS, | LAZO COURT, ALMANZA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 251.16 | 486.01 | 124 | MODIFICATION | 774554.45 | 215802.71 |  | 0% | 2025-07-18 13:14 | 2025-07-25 14:38 | 2025-07-28 |  |  |  | -45856.5514 | -45863.6097 | 0 | 2025-08-08 13:14 | 2025-08-17 22:50 | 2025-09-06 13:14 | -1433.0172 | 0 | 32 | 32 | 24 | 30.4 | 21 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [25 empty] | 0 |  | 0.38902 | 0.38902 | 0 | -0.55139 | NON-REV | 0-3 MONTHS
| 2025-07-30 |  | HMB | X25041432369 | JESSIE SALOMON VALMONTE | CUASAY, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | NEED JOINT SURVEY FOR STAKA WITH DRAINAGE |  | VJC | SCHED | Jenneth Madrid | 220.98 | 532.71 | 95.2 | NEW | 1151223.61 |  |  | #DIV/0! | 2025-07-17 12:47 | 2025-07-24 14:41 | 2025-07-30 |  |  |  | -45855.5326 | -45862.6118 | 0 | 2025-08-10 05:37 | 2025-08-20 08:31 | 2025-09-05 12:47 | -1288.001 | 0 | 40 | 34 | 26.7016 | 33.822 | 23.7016 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [25 empty] | 0 |  | 0.37827 | 0.37827 | 0 | 0.46736 | REV | 0-3 MONTHS
| 2025-07-30 |  | HMB | X25062159255 | JOHN RODNEY SANAO BRONDIAL | PRES. GARCIA, TEOVILLE SUBD EAST, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 5.08 | 5.08 | 24 | MODIFICATION | 23115.53 |  |  | #DIV/0! | 2025-07-18 17:06 | 2025-07-24 14:49 | 2025-07-30 |  | 2025-07-30 |  | 11.2875 | 5.3826 | -45868 | 2025-08-06 11:41 | 2025-08-15 07:02 | 2025-09-06 17:06 | 0.38879 | -764.4667 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-28 | 27 | [8 empty] | NO COC |  | 2025-08-14 | #VALUE! | [25 empty] | 1 |  | 0.42324 | 0.42324 | 0.016667 |  | NON-REV
2025-08-05 | 2025-08-05 | Y | BIZ | X25072495380 | DISEGNO DI MILANO INC. DOING BUSINESS UNDER THE NA | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 33.8 | 33.8 | 0 | TERMINATION | 35402.55 |  |  | #DIV/0! | 2025-07-18 11:04 | 2025-07-21 15:11 | 2025-08-05 | 2025-07-31 | 2025-07-31 |  | 12.5389 | 9.3674 | -45869 | 2025-08-06 05:39 | 2025-08-15 01:00 | 2025-09-06 11:04 | 0.4319 | -764.4833 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-09-29 | 26 | [8 empty] | FOR AUDIT |  | 2025-08-15 | 0 | 2025-07-31 | 2025-08-15 | [16 empty] | N/A | [6 empty] | 0 |  | 0.4319 | 0.4319 | 0 |  | NON-REV
N/A | N/A |  | BIZ | X25041184751 | MAXIPACIFIC FUEL GAS STATIONS INC. | DAANG-HARI RD., MOLINO IV, BACOOR | BACOOR CITY | DASMA |  |  | C2 | FCOMP | Ian Patrick Perez | 3.68 | 3.68 | 20 | NEW | 18682.3 |  |  | #DIV/0! | 2025-07-18 15:28 | 2025-07-22 12:50 | N/A |  | 2025-08-07 06:22 |  | 19.6208 | 15.7306 | -45876.2653 | 2025-08-06 10:03 | 2025-08-15 05:24 | 2025-09-06 15:28 | 0.67583 | -764.6044 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-06 06:22 | 18.7347 | [8 empty] | NO COC |  | 2025-08-22 06:22 | #VALUE! | [25 empty] | -7.2653 |  | 0.42558 | 0.42558 | -0.12109 |  | REV
2025-07-30 | 2025-07-30 |  | HMB | X25062260365 | MOHAMMAD TABAO | MARAWI, MAHARLIKA VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 0.33 | 0.33 | 2 | NEW | 14723.93 | 283.55 |  | 0% | 2025-07-21 16:23 | 2025-07-28 14:58 | 2025-07-30 |  | 2025-08-09 09:01 |  | 18.6931 | 11.7521 | -45878.3757 | 2025-08-09 10:58 | 2025-08-18 06:19 | 2025-09-09 16:23 | 0.64387 | -764.6396 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-08 09:01 | 16.6243 | [8 empty] | NO COC |  | 2025-08-24 09:01 | #VALUE! | [18 empty] | N/A | A8-0466 | [5 empty] | -9.3757 |  | 0.32093 | 0.32093 | -0.15626 |  | REV
2025-08-05 | 2025-07-30 |  | BIZ | X24104026324 | MARCELINO BELTRAN BAQUIRAN | SALAZAR, ZONE 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 6.69 | 6.69 | 0 | TERMINATION | 17701.89 |  |  | #DIV/0! | 2025-07-22 16:41 | 2025-07-28 15:05 | 2025-07-30 | 2025-08-03 | 2025-08-03 07:55 |  | 11.6347 | 5.7014 | -45872.3299 | 2025-08-10 11:16 | 2025-08-19 06:37 | 2025-09-10 16:41 | 0.40075 | -764.5388 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-02 07:55 | 22.6701 | [8 empty] | FOR AUDIT |  | 2025-08-18 07:55 | -3.3299 | 2025-08-03 | 2025-08-15 | [16 empty] | N/A | B8-1833 | [5 empty] | -3.3299 |  | 0.28606 | 0.28606 | -0.055498 |  | NON-REV
2025-07-29 | 2025-07-30 |  | HMB | X25062074364 | RICHMOND SANTOS SY | BEECHCRAFT, CONCORDE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 15.23 | 15.23 | 70 | NEW | 47339.51 |  |  | #DIV/0! | 2025-07-22 15:45 | 2025-07-28 15:00 | 2025-07-30 |  |  |  | -45860.6562 | -45866.625 | 0 | 2025-08-09 17:32 | 2025-08-18 08:25 | 2025-09-10 15:45 | -1632.0998 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | B5-2071, 180609 | [5 empty] | 0 |  | 0.29694 | 0.29694 | 0 | -4.6562 | REV | 0-3 MONTHS
2025-08-05 | 2025-07-30 |  | HMB | X24104218323 | IMELDA T. AGUILAR | ROSAL, DOÑA MANUELA SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 70.92 | 149.2 | 54.1 | MODIFICATION | 414665.83 |  |  | #DIV/0! | 2025-07-21 12:33 | 2025-07-28 14:55 | 2025-07-30 |  |  |  | -45859.5229 | -45866.6215 | 0 | 2025-08-10 20:50 | 2025-08-20 02:14 | 2025-09-09 12:33 | -1473.315 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | CW6-0581, CW7-8095, 526324, ALB1-1754 | [5 empty] | 0 |  | 0.30447 | 0.30447 | 0 | -3.5229 | NON-REV | 0-3 MONTHS
2025-07-29 | 2025-07-30 |  | HMB | X25061989906 | SUNNY ROBERT GOTAO YU | CALLE GENEROSO, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | digging 8/20 |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 68 | 146.28 | 23 | MODIFICATION | 328877.97 | 58428.66 |  | 0% | 2025-07-21 17:45 | 2025-07-28 15:10 | 2025-07-30 |  |  |  | -45859.7396 | -45866.6319 | 0 | 2025-08-11 22:43 | 2025-08-21 09:38 | 2025-09-09 17:45 | -1420.868 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | CZ9-8079, 531359 | [5 empty] | 0 |  | 0.28691 | 0.28691 | 0 | -3.7396 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-07-30 |  | BIZ | X25062208339 | RICHILL REALTY & DEVT CORP | ESPIRITU MELITON, MELITON CPD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 18.93 | 18.93 | 0 | TERMINATION | 24125.77 | 16273.72 |  | 0% | 2025-07-22 15:42 | 2025-07-28 15:04 | 2025-07-30 |  |  |  | -45860.6542 | -45866.6278 | 0 | 2025-08-10 10:17 | 2025-08-19 05:38 | 2025-09-10 15:42 | -1579.6448 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | N/A | [5 empty] | 0 |  | 0.28747 | 0.28747 | 0 | -4.6542 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-07-30 |  | BIZ | X24104300797 | RIVER OF LIFE CHRISTIAN SCHOOL INC | CAA, CAA CPD PH 1-B, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 176.64 | 486.97 | 20 | NEW | 782151.87 | 151772.08 |  | 0% | 2025-07-22 16:43 | 2025-07-28 15:08 | 2025-07-30 |  |  |  | -45860.6965 | -45866.6306 | 0 | 2025-08-14 17:18 | 2025-08-24 15:51 | 2025-09-10 16:43 | -1321.6798 | 0 | 32 | 36 | 26.0241 | 32.9639 | 23.0241 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | CX8-1682, CX8-8171, CX8-8172, ALB1-0474, CX8-8173, 523572, CX8-8174 | [5 empty] | 0 |  | 0.2393 | 0.2393 | 0 | -4.6965 | REV | 0-3 MONTHS
N/A | N/A |  | CBG | X25061974470 | DITO TELECOMMUNITY CORPORATION | ACACIA, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | on process |  | MAINTENANCE | SCHED | Junilo Michael Flores | 17.14 | 17.14 | 22 | NEW | 194170.53 |  |  | #DIV/0! | 2025-07-21 13:51 | 2025-07-28 14:53 | N/A |  |  |  | -45859.5771 | -45866.6201 | 0 | 2025-08-09 08:26 | 2025-08-18 03:47 | 2025-09-09 13:51 | -1579.6077 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [25 empty] | 0 |  | 0.32457 | 0.32457 | 0 | -3.5771 | REV | 0-3 MONTHS
N/A | N/A | Y | BIZ | X25072562347 | TRISTAN ENRIQUEZ TRINIDAD | LIGAS III, LIGAS III, BACOOR | BACOOR CITY | DASMA | on process |  | C2 | FCOMP | Ian Patrick Perez | 11.8 | 11.8 | 33 | NEW | 184304.08 |  |  | #DIV/0! | 2025-07-23 15:31 | 2025-07-25 06:53 | N/A |  | 2025-08-03 |  | 10.3535 | 8.7132 | -45872 | 2025-08-11 10:06 | 2025-08-20 05:27 | 2025-09-11 15:31 | 0.35662 | -764.5333 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-02 | 23 | [8 empty] | NO COC |  | 2025-08-18 | #VALUE! | [25 empty] | -3 |  | 0.25329 | 0.25329 | -0.05 |  | REV
2025-07-29 | 2025-07-30 | Y | CBG | X23031050954 | DEPARTMENT OF SCIENCE AND TECHNOLOGY | GEN. SANTOS, UPPER BICUTAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | on process |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 348.26 | 504.02 | 668 | MODIFICATION | 2295683.71 | 299388.1 |  | 0% | 2025-07-25 08:18 | 2025-07-25 13:57 | 2025-07-30 |  | 2025-08-09 08:52 |  | 15.0236 | 14.7882 | -45878.3694 | 2025-08-11 02:48 | 2025-08-19 09:20 | 2025-09-13 08:18 | 0.56992 | -764.6395 | 40 | 23 | 19.7708 | 25.043 | 16.7708 | 60 | 57 | 52 | 2025-10-08 08:52 | 16.6306 | [8 empty] | NO COC |  | 2025-08-24 08:52 | #VALUE! | [10 empty] | Y | 2025-08-04 | [6 empty] | 2025-07-30 | DZ1-1691, DZ2-8005, 516589 | [5 empty] | -9.3694 |  | 0.21449 | 0.21449 | -0.15616 |  | NON-REV
2025-08-05 | 2025-08-05 | Y | BIZ | X25041430567 | MEGA TRIUM FOODS CORPORATION | CELESTINO, CELESTINO SUBD, BACOOR | BACOOR CITY | DASMA | on process |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 165.83 | 186.11 | 276 | NEW | 1109918.06 | 142509.27 |  | 0% | 2025-07-24 14:55 | 2025-07-30 07:43 | 2025-08-05 |  | 2025-08-09 08:56 |  | 15.7507 | 10.0507 | -45878.3722 | 2025-08-12 03:06 | 2025-08-20 20:44 | 2025-09-12 14:55 | 0.54925 | -764.6395 | 26 | 30 | 21.5074 | 27.2426 | 18.5074 | 60 | 57 | 52 | 2025-10-08 08:56 | 16.6278 | [8 empty] | NO COC |  | 2025-08-24 08:56 | #VALUE! | [18 empty] | 2025-07-30 | CU7-2002, CU7-0670, 021906, CU7-8097, 530736 | [5 empty] | -9.3722 |  | 0.22243 | 0.22243 | -0.1562 |  | REV
2025-08-05 | 2025-08-05 |  | BIZ | X25051846574 | GOLDEN HAVEN MEMORIAL PARK, INC. | C5 EXTENSION, PULANGLUPA I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 23.45 | 23.45 | 54 | NEW | 64438.01 | 20148.81 |  | 0% | 2025-07-25 12:40 | 2025-08-01 14:52 | 2025-08-05 |  |  |  | -45863.5278 | -45870.6194 | 0 | 2025-08-12 14:27 | 2025-08-21 05:20 | 2025-09-13 12:40 | -1632.202 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | CY7-5035, 153327 | [5 empty] | 0 |  | 0.19475 | 0.19475 | 0 | -7.5278 | REV | 0-3 MONTHS
2025-08-05 | 2025-08-05 |  | HMB | X25010242053 | LAND CRIS SOMERSET DEVELOPMENT CORPORATION | LANCRIS AVENUE, LANCRIS RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | FOR SCHED DIGGING |  | VJC | SCHED | Jenneth Madrid | 364.75 | 466.16 | 474 | NEW | 1680101.75 |  |  | #DIV/0! | 2025-07-24 16:03 | 2025-08-01 14:49 | 2025-08-05 |  |  |  | -45862.6687 | -45870.6174 | 0 | 2025-08-11 07:57 | 2025-08-19 20:11 | 2025-09-12 16:03 | -1664.7267 | 0 | 32 | 26 | 20.6623 | 26.1722 | 17.6623 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | DY1-6018, DY1-6019, DY1-6017, 212418, DY1-6020, DY1-8080, DY1-8081, DY1-8082, DY1-8083, 527289, DY1-8084 | [5 empty] | 0 |  | 0.22981 | 0.22981 | 0 | -6.6687 | REV | 0-3 MONTHS
2025-08-05 | 2025-08-05 |  | HMB | X25010244921 | LAND CRIS SOMERSET DEVELOPMENT CORPORATION | LANCRIS AVENUE, LANCRIS RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | FOR SCHED DIGGING |  | VJC | SCHED | Jenneth Madrid | 225.89 | 245.37 | 740 | NEW | 1521529.47 |  |  | #DIV/0! | 2025-07-24 16:06 | 2025-08-01 14:48 | 2025-08-05 |  |  |  | -45862.6708 | -45870.6167 | 0 | 2025-08-08 21:32 | 2025-08-16 18:11 | 2025-09-12 16:06 | -1887.2062 | 0 | 28 | 23 | 18.2264 | 23.0868 | 15.2264 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | DY1-8083, DY1-8085, 527291 | [5 empty] | 0 |  | 0.26044 | 0.26044 | 0 | -6.6708 | REV | 0-3 MONTHS
2025-08-05 | 2025-08-07 |  | HMB | X25062129662 | JIGGER P CRUZ | CHESTNUT, EXECUTIVE HEIGHTS SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 48.68 | 126.96 | 56 | MODIFICATION | 340190.54 |  |  | #DIV/0! | 2025-07-24 16:08 | 2025-08-01 14:14 | 2025-08-07 |  |  |  | -45862.6722 | -45870.5931 | 0 | 2025-08-14 00:25 | 2025-08-23 05:49 | 2025-09-12 16:08 | -1473.4162 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | A7-8082, 531425 | [5 empty] | 0 |  | 0.20329 | 0.20329 | 0 | -6.6722 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-08-07 |  | HMB | R23954275 | BAUTISTA ALBERTO O, | ONYX, SEVERINA DIAMOND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 99.46 | 177.74 | 0 | RELOC | 262857.87 |  |  | #DIV/0! | 2025-07-24 14:54 | 2025-08-01 14:57 | 2025-08-07 |  |  |  | -45862.6208 | -45870.6229 | 0 | 2025-08-14 19:52 | 2025-08-24 06:47 | 2025-09-12 14:54 | -1420.9573 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | DY1-8092, 186546 | [5 empty] | 0 |  | 0.19765 | 0.19765 | 0 | -6.6208 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-08-07 |  | HMB | X25072477989 | JOSE ROSELLER JR LASCANO LATOSA | SANTOL, CAA CPD PH 1-B, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 0.6 | 0.6 | 1.5 | NEW | 15004.94 |  |  | #DIV/0! | 2025-07-24 17:26 | 2025-08-01 14:55 | 2025-08-07 |  |  |  | -45862.7264 | -45870.6215 | 0 | 2025-08-12 12:01 | 2025-08-21 07:22 | 2025-09-12 17:26 | -1579.7161 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-07-30 | CX8-1732 | [5 empty] | 0 |  | 0.21609 | 0.21609 | 0 | -6.7264 | REV | 0-3 MONTHS
2025-08-05 | 2025-08-05 |  | BIZ | X25072448988 | FIRSTAR HVAC INC. | COASTAL, LONGOS, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 2.24 | 2.24 | 0 | TERMINATION | 11569.43 | 1924.58 |  | 0% | 2025-07-25 13:29 | 2025-08-01 14:50 | 2025-08-05 |  |  |  | -45863.5618 | -45870.6181 | 0 | 2025-08-13 08:04 | 2025-08-22 03:25 | 2025-09-13 13:29 | -1579.7449 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | TLN-318840 | [5 empty] | 0 |  | 0.18732 | 0.18732 | 0 | -7.5618 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-08-05 |  | HMB | X25041311153 | NELSON ACEBO | LAGUNA BAY, SOUTH BAY GARDEN SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 49.51 | 56.71 | 82 | MODIFICATION | 322164.94 | 42564.42 |  | 0% | 2025-07-25 13:31 | 2025-08-01 14:51 | 2025-08-05 |  |  |  | -45863.5632 | -45870.6188 | 0 | 2025-08-13 20:44 | 2025-08-22 19:27 | 2025-09-13 13:31 | -1542.4702 | 0 | 23 | 34 | 22.3004 | 28.2471 | 19.3004 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | DW1-8058, 530491 | [5 empty] | 0 |  | 0.18285 | 0.18285 | 0 | -7.5632 | NON-REV | 0-3 MONTHS
| 2025-08-07 |  | HMB | X25041098276 | JOSE ANTONIO K. LEGARDA | G. CU-UNJIENG, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 107.93 | 341.38 | 33 | MODIFICATION | 585302.24 | 92334.49 |  | 0% | 2025-07-29 10:31 | 2025-08-06 15:03 | 2025-08-07 |  |  |  | -45867.4382 | -45875.6271 | 0 | 2025-08-20 21:50 | 2025-08-30 16:51 | 2025-09-17 10:31 | -1350.5412 | 0 | 30 | 36 | 25.4717 | 32.2642 | 22.4717 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | CW9-1393, CW9-8074, 035779, CW9-8075, CW9-8076, 530345, CV9-0015 | [5 empty] | 0 |  | 0.045986 | 0.045986 | 0 | -11.4382 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-08-05 |  | HMB | X25072352853 | MA AGNES SILVA | MOLAVE, MOLAVE PARK VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | NEED SURVEY FOR STAKA WITH UG ONSITE |  | VJC | SCHED | Jenneth Madrid | 351.02 | 820.71 | 42 | MODIFICATION | 1578730.37 |  |  | #DIV/0! | 2025-07-25 13:24 | 2025-08-01 14:56 | 2025-08-05 |  |  |  | -45863.5583 | -45870.6222 | 0 | 2025-08-19 09:26 | 2025-08-29 19:35 | 2025-09-13 13:24 | -1235.7681 | 0 | 40 | 36 | 27.8351 | 35.2577 | 24.8351 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | A7-8033, A7-8049, A7-8050, A7-8051, 523675, A7-8052, A7-8053, A7-8054, 523676 | [5 empty] | 0 |  | 0.14662 | 0.14662 | 0 | -7.5583 | NON-REV | 0-3 MONTHS
2025-08-05 | 2025-08-06 |  | BIZ | X25062163581 | REKADO FILIPINO CUISINE, INC | DEUTERONOMY, BF HOMES MARTINVILLE SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 100.08 | 178.36 | 139 | NEW | 872290.85 | 86015.82 |  | 0% | 2025-07-29 16:15 | 2025-07-31 07:03 | 2025-08-06 |  | 2025-08-07 |  | 8.3229 | 6.7063 | -45876 | 2025-08-18 02:57 | 2025-08-27 02:37 | 2025-09-17 16:15 | 0.2781 | -764.6 | 26 | 32 | 22.446 | 28.4317 | 19.446 | 60 | 57 | 52 | 2025-10-06 | 19 | [8 empty] | NO COC |  | 2025-08-22 | #VALUE! | [18 empty] | 2025-08-05 | CX8-6037, 531423, CX8-8207 | [5 empty] | -7 |  | 0.044203 | 0.044203 | -0.11667 |  | REV
N/A | N/A |  | BIZ | X25072495126 | ANTONIO PAOLO BACOLOD CENON | GLORIA DIAZ, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | MAINTENANCE | FCOMP | Junilo Michael Flores | 46.18 | 46.18 | 28 | NEW | 261681.61 |  |  | #DIV/0! | 2025-07-29 10:04 | 2025-08-01 15:00 | N/A |  | 2025-08-06 13:34 |  | 8.1458 | 4.9403 | -45875.5653 | 2025-08-17 04:39 | 2025-08-26 | 2025-09-17 10:04 | 0.28058 | -764.5928 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-05 13:34 | 19.4347 | [8 empty] | NO COC |  | 2025-08-21 13:34 | #VALUE! | [25 empty] | -6.5653 |  | 0.054441 | 0.054441 | -0.10942 |  | REV
2025-08-07 | 2025-08-07 |  | HMB | X23083314771 | FRANZ JOIE DEYSOLONG ARAQUE | CAIRO, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 44.69 | 122.97 | 30 | MODIFICATION | 296458.34 |  |  | #DIV/0! | 2025-07-30 18:16 | 2025-08-06 15:11 | 2025-08-07 |  |  |  | -45868.7611 | -45875.6326 | 0 | 2025-08-20 23:14 | 2025-08-30 10:09 | 2025-09-18 18:16 | -1421.1475 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | CZ8-0391, CZ8-8043, 518479, CZ8-0392 | [5 empty] | 0 |  | 0.0074015 | 0.0074015 | 0 | -12.7611 | NON-REV | 0-3 MONTHS
2025-08-07 | 2025-08-07 |  | BIZ | X25061934575 | ALFAMART TRADING PHILIPPINES, INC. | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | FCOMP | Ronilo Gange Jr. | 36.81 | 36.81 | 34.5 | NEW | 247888.96 | 31631.31 |  | 0% | 2025-07-30 10:50 | 2025-08-06 15:05 | 2025-08-07 | 2025-08-12 14:21 | 2025-08-12 14:21 |  | 13.1465 | 5.9694 | -45881.5979 | 2025-08-18 05:25 | 2025-08-27 00:46 | 2025-09-18 10:50 | 0.45282 | -764.6933 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-11 14:21 | 13.4021 | [8 empty] | NO COC |  | 2025-08-27 14:21 | #VALUE! | [18 empty] | 2025-08-05 | A5-5050, 531191 | [5 empty] | -12.5979 |  | 0.018897 | 0.018897 | -0.20997 |  | REV
2025-08-13 | 2025-08-08 |  | HMB | R23915657 | ARB CONSTRUCTION COMPANY INC., HMB | MT. APO, SOLDIER'S HILLS 4 PH I, BACOOR | BACOOR CITY | DASMA |  |  | AVECO | SCHED | Ronilo Gange Jr. | 37.83 | 191.59 | 0 | RELOC | 229981.27 | 32504.12 |  | 0% | 2025-07-31 17:18 | 2025-08-12 15:09 | 2025-08-08 |  |  |  | -45869.7208 | -45881.6312 | 0 | 2025-08-21 22:16 | 2025-08-31 09:11 | 2025-09-19 17:18 | -1421.1772 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | CT7-8141, CT7-8140, CV7-0096 | [5 empty] | 0 |  | -0.022334 | -0.022334 | 0 | -13.7208 | NON-REV | 0-3 MONTHS
| 2025-08-07 |  | HMB | X25072598830 | BARANGAY TALON KUATRO | SAMPAGUITA, SAN ANTONIO VALLEY 17, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 25.91 | 25.91 | 40 | NEW | 217753.95 | 22263.84 |  | 0% | 2025-07-31 17:00 | 2025-08-06 15:13 | 2025-08-07 |  |  |  | -45869.7083 | -45875.634 | 0 | 2025-08-19 11:35 | 2025-08-28 06:56 | 2025-09-19 17:00 | -1579.9566 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-05 | CV7-0039, 531950 | [5 empty] | 0 |  | -0.024398 | -0.024398 | 0 | -13.7083 | REV | 0-3 MONTHS
| 2025-08-07 |  | HMB | X25010076510 | THEODORE REYES LEONIN | CHAMPACA, TAHANAN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | DIGGING 8/13; POLE ERECTION / DRESSING 8/18; ENERGIZATION, FOR FCOMP 8/19 |  | CHALLENGER | FCOMP | Isan Carlo Lazaro | 148.27 | 188.83 | 42 | NEW | 527240.99 | 127393.09 |  | 0% | 2025-07-31 13:20 | 2025-08-06 15:14 | 2025-08-07 |  | 2025-08-20 14:16 |  | 20.0389 | 13.9597 | -45889.5944 | 2025-08-21 18:18 | 2025-08-31 05:13 | 2025-09-19 13:20 | 0.62086 | -764.8266 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 2025-10-19 14:16 | 5.4056 | [8 empty] | NO COC |  | 2025-09-04 14:16 | #VALUE! | [18 empty] | 2025-08-05 | CW9-0498, DW1-8051, DW1-8052, CW9-0456, DW1-8052, 527047 | [5 empty] | -20.5944 |  | -0.017213 | -0.017213 | -0.34324 |  | REV
| N/A |  | HMB | X25061951229 | GLADYS ROMUALDEZ JOHNSON | BLOCK 1, BRAZILIA HEIGHTS, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | C2 | FCOMP | Ian Patrick Perez | 26.83 | 26.83 | 53 | MODIFICATION | 218940.69 | 18979.17 |  | 0% | 2025-07-31 10:07 | 2025-08-04 08:42 | 2025-08-07 |  | 2025-08-08 |  | 7.5785 | 3.6375 | -45877 | 2025-08-18 11:54 | 2025-08-27 02:47 | 2025-09-19 10:07 | 0.2697 | -764.6167 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 2025-10-07 | 18 | [8 empty] | NO COC |  | 2025-08-23 | #VALUE! | [25 empty] | -8 |  | -0.015001 | -0.015001 | -0.13333 |  | NON-REV
2025-08-19 | 2025-08-07 |  | CBG | X24093538960 | RIZAL COMMERCIAL BANKING CORPORATION | BF RESORT, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 5.26 | 5.26 | 26 | NEW | 32944.83 | 4519.49 |  | 0% | 2025-08-04 12:19 | 2025-08-12 15:15 | 2025-08-07 |  |  |  | -45873.5132 | -45881.6354 | 0 | 2025-08-23 06:54 | 2025-09-01 02:15 | 2025-09-23 12:19 | -1580.0877 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | N/A | TLN-052429 | [5 empty] | 0 |  | -0.15545 | -0.15545 | 0 | -17.5132 | REV | 0-3 MONTHS
2025-08-13 | 2025-08-07 |  | HMB | X25072684723 | CIPRIANO JR T. SISON | DON JUAN, GAT MENDOZA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | on process |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 17.88 | 17.88 | 40 | NEW | 54051.77 | 15365.98 |  | 0% | 2025-08-01 16:58 | 2025-08-12 15:15 | 2025-08-07 |  |  |  | -45870.7069 | -45881.6354 | 0 | 2025-08-20 11:33 | 2025-08-29 06:54 | 2025-09-20 16:58 | -1579.991 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-07 | B5-0376, 167886 | [5 empty] | 0 |  | -0.058795 | -0.058795 | 0 | -14.7069 | REV | 0-3 MONTHS
2025-08-19 | 2025-08-07 |  | HMB | X25051644653 | MARIA ANTONIETTE PECKSON NAGAI | 6TH, GOLDEN GATE SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | POLE ERECTION / INSTALL DT ( 1 - 50 KVA) 8/15; |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 68.99 | 147.27 | 75 | NEW | 397281.96 | 59273.77 |  | 0% | 2025-08-04 12:08 | 2025-08-12 15:16 | 2025-08-07 |  |  |  | -45873.5056 | -45881.6361 | 0 | 2025-08-24 20:25 | 2025-09-03 01:49 | 2025-09-23 12:08 | -1473.7642 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-07 | CV8-1389, CV9-5949, TLN-520568 | [5 empty] | 0 |  | -0.14475 | -0.14475 | 0 | -17.5056 | REV | 0-3 MONTHS
2025-08-13 | 2025-08-07 |  | CBG | X24103907761 | DITO TELECOMMUNITY CORPORATION | AREA 2 SAN AGUSTIN, SAN AGUSTIN VILLAGE AREA 2, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | POLE ERECTION ¦ POLE DRESSING ¦ WIRE STRINGING ¦ INSTALL DT (1- 50 KVA ) 8/20 |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 76.22 | 96.5 | 23 | NEW | 336387.87 | 65492.61 |  | 0% | 2025-08-05 12:53 | 2025-08-12 15:17 | 2025-08-07 |  |  |  | -45874.5368 | -45881.6368 | 0 | 2025-08-25 14:56 | 2025-09-03 18:41 | 2025-09-24 12:53 | -1490.3684 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-07 | CZ9-8051, CW9-8055, 526112, CZ9-8052 | [5 empty] | 0 |  | -0.17988 | -0.17988 | 0 | -18.5368 | REV | 0-3 MONTHS
2025-08-13 | 2025-08-08 |  | BIZ | X25072477127 | MARICEL G. SARMIENTO | M.L. QUEZON, PUROK 6, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | WITH CONJUNCT WO TAPPING POINT (WALA LANG SA SITE) |  | VJC | SCHED | Jenneth Madrid | 85.77 | 164.05 | 63 | NEW | 580376.35 |  |  | #DIV/0! | 2025-08-04 14:49 | 2025-08-12 15:22 | 2025-08-08 |  |  |  | -45873.6174 | -45881.6403 | 0 | 2025-08-24 23:06 | 2025-09-03 04:30 | 2025-09-23 14:49 | -1473.7678 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-07 | DZ2-8033, DZ2-8134, 531796, DZ2-0101 | [5 empty] | 0 |  | -0.14834 | -0.14834 | 0 | -17.6174 | REV | 0-3 MONTHS
2025-08-13 | 2025-08-08 |  | HMB | X25062037196 | MANUEL SARIANA BOLON | MAGSAYSAY, PUROK 2A, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | FCOMP | Jenneth Madrid | 0.73 | 0.73 | 1.5 | NEW | 15258.91 | 627.25 |  | 0% | 2025-08-05 12:16 | 2025-08-12 09:50 | 2025-08-08 |  | 2025-08-12 09:50 |  | 6.8986 | 0 | -45881.4097 | 2025-08-24 06:51 | 2025-09-02 02:12 | 2025-09-24 12:16 | 0.23762 | -764.6902 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-11 09:50 | 13.5903 | [8 empty] | NO COC |  | 2025-08-27 09:50 | #VALUE! | [18 empty] | 2025-08-07 | A8-1442 | [5 empty] | -12.4097 |  | -0.18983 | -0.18983 | -0.20683 |  | REV
2025-08-19 | 2025-08-08 |  | CBG | X25041244029 | ISON TOWER LTD. INC. | MILLARES, PUROK 4B, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | WO DONE (FCOMP) |  | VJC | FCOMP | Jenneth Madrid | 11.3 | 11.3 | 22 | NEW | 146931.81 |  |  | #DIV/0! | 2025-08-05 16:53 | 2025-08-12 15:18 | 2025-08-08 |  | 2025-08-13 |  | 7.2965 | 0.3625 | -45882 | 2025-08-24 11:28 | 2025-09-02 06:49 | 2025-09-24 16:53 | 0.25132 | -764.7 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-12 | 13 | [8 empty] | NO COC |  | 2025-08-28 | #VALUE! | [18 empty] | 2025-08-07 | A8-0834, 215369 | [5 empty] | -13 |  | -0.19645 | -0.19645 | -0.21667 |  | REV
2025-08-13 | 2025-08-13 |  | HMB | X25072557290 | IGNACIO L. LEDESMA | PRES. GARCIA, SOUTH ADMIRAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 79.49 | 157.77 | 46 | MODIFICATION | 408580.46 |  |  | #DIV/0! | 2025-08-05 07:41 | 2025-08-12 15:21 | 2025-08-13 |  |  |  | -45874.3201 | -45881.6396 | 0 | 2025-08-26 12:39 | 2025-09-04 23:34 | 2025-09-24 07:41 | -1421.3197 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-07 | A7-0748, A7-8087, TLN-531815, A7-0749 | [5 empty] | 0 |  | -0.16483 | -0.16483 | 0 | -18.3201 | NON-REV | 0-3 MONTHS
| 2025-08-13 |  | BIZ | R24106120 | DON BOSCO CENTER OF STUDIES, INC., | MICHAEL RUA, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 59.26 | 210.63 | 0 | RELOC | 267327.02 |  |  | #DIV/0! | 2025-08-04 14:50 | 2025-08-20 08:49 | 2025-08-13 |  |  |  | -45873.6181 | -45889.3674 | 0 | 2025-08-26 11:41 | 2025-09-05 02:50 | 2025-09-23 14:50 | -1383.4901 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-07 | CY9-8077, CY9-8079 | [5 empty] | 0 |  | -0.13927 | -0.13927 | 0 | -17.6181 | NON-REV | 0-3 MONTHS
| 2025-08-13 |  | BIZ | X25072438725 | ALFAMART TRADING PHILIPPINES, INC. | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | hindi pa tapos sa digging : Sir itong manila prime ng cavite , tatlong palapag daw puro semento 😅, pa advice ndin Po sa nag follow up nxt week pa tlga matatapos, sumuko na bareta at shovel nong digger eh.. Hndi pa boss tapos hukay eh tatlong patong ng concrete |  | ECOM | FCOMP | Ronilo Gange Jr. | 1.91 | 1.91 | 4.5 | NEW | 12949.55 | 1641.1 |  | 0% | 2025-08-08 14:42 | 2025-08-08 14:56 | 2025-08-13 |  | 2025-08-12 14:22 |  | 3.9861 | 3.9764 | -45881.5986 | 2025-08-27 09:17 | 2025-09-05 04:38 | 2025-09-27 14:42 | 0.1373 | -764.6933 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 2025-10-11 14:22 | 13.4014 | [8 empty] | NO COC |  | 2025-08-27 14:22 | #VALUE! | [18 empty] | N/A | A5-5050
| 2025-08-15 |  | CBG | X25051900761 | AYALA LAND, INC., | DUHAT RD. COR. DBP AVE., ARCA SOUTH, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE |  |  | VJC | SCHED | Jenneth Madrid |  | 115.19 | 4250 | NEW | 240487.38 |  |  | #DIV/0! | 2025-08-08 09:33 | 2025-08-20 08:51 | 2025-08-15 |  |  |  | -45877.3979 | -45889.3688 | 0 | 2025-08-21 12:20 | 2025-08-28 19:28 | 2025-09-27 09:33 | -2135.0635 | 0 | 26 | 20 | 16.1157 | 20.4132 | 13.1157 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | B8-6213, B8-8225
| 2025-08-15 |  | HMB | X25062074195 | ARTHUR J. LEDESMA | VIENNA, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | SCHED | Jenneth Madrid |  | 706.06 | 102 | MODIFICATION | 1263037.77 |  |  | #DIV/0! | 2025-08-08 15:58 | 2025-08-20 08:50 | 2025-08-15 |  |  |  | -45877.6653 | -45889.3681 | 0 | 2025-08-31 04:44 | 2025-09-10 00:08 | 2025-09-27 15:58 | -1347.6564 | 0 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | A6-8079, 034298, A6-8080, A6-8081, A6-8082, A6-8083, 531369
| 2025-08-13 |  | CBG | X24041436603 | DITO TELECOMMUNITY CORPORATION | C. ARELLANO, KATARUNGAN VILLAGE, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | DIGGING 8/15; |  | CHALLENGER | SCHED | Isan Carlo Lazaro |  | 89.35 | 22 | NEW | 419897.84 | 59352.45 |  | 0% | 2025-08-11 11:03 | 2025-08-20 08:55 | 2025-08-13 |  |  |  | -45880.4604 | -45889.3715 | 0 | 2025-08-31 13:06 | 2025-09-09 16:51 | 2025-09-30 11:03 | -1490.5609 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | CS9-0279, 050858
| 2025-08-13 |  | BIZ | X24104021997 | ROSA NISMAL ABANGON | AGUIRRE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro |  | 129.12 | 45 | NEW | 359556.01 | 43707.46 |  | 0% | 2025-08-11 16:44 | 2025-08-20 08:54 | 2025-08-13 |  |  |  | -45880.6972 | -45889.3708 | 0 | 2025-09-01 21:42 | 2025-09-11 08:37 | 2025-09-30 16:44 | -1421.5173 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | CW9-0278, CW9-8057, 526180
| 2025-08-14 |  | HMB | X25062260009 | RAYMOND CANARIA ALMAZAN | HUMILITY, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | SCHED | Isan Carlo Lazaro |  | 13.04 | 23 | MODIFICATION | 142685.55 | 11207.18 |  | 0% | 2025-08-12 16:43 | 2025-08-20 08:56 | 2025-08-14 |  |  |  | -45881.6965 | -45889.3722 | 0 | 2025-08-31 11:18 | 2025-09-09 06:39 | 2025-10-01 16:43 | -1580.3695 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | CZ8-1249, 531636
| 2025-08-15 |  | HMB | X25061989891 | DE FENG CORPORATION | PHILIP, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 526.61 | 1165.95 | 42 | MODIFICATION | 2087885.05 |  |  | #DIV/0! | 2025-08-12 15:08 | 2025-08-20 08:58 | 2025-08-15 |  |  |  | -45881.6306 | -45889.3736 | 0 | 2025-09-08 02:33 | 2025-09-18 23:12 | 2025-10-01 15:08 | -1167.4326 | 0 | 50 | 36 | 29.476 | 37.3362 | 26.476 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | CZ8-0271, CZ8-8118, CZ8-8119, CZ8-8120, 003090, CZ8-8121, 847640, CZ8-8122, CZ8-8123, CZ8-8124, 531290, CZ8-8125
2025-08-15 | OK |  | BIZ | X24114527619 | LEGADO CAR SALES BACOOR, INC. | MOLINO BLVD., BAYANAN, BACOOR | BACOOR CITY | DASMA |  |  | ECOM | SCHED | Ronilo Gange Jr. | 21.88 | 21.88 | 64 | NEW | 240537.18 |  |  | #DIV/0! | 2025-08-06 13:45 | 2025-08-13 08:55 | 2025-08-11 |  |  |  | -45875.5729 | -45882.3715 | 0 | 2025-08-24 15:32 | 2025-09-02 06:25 | 2025-09-25 13:45 | -1632.6307 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 60 | 57 | 52 | 1900-02-28 | 45895 | [10 empty] | 1900-01-14 | 0 | [18 empty] | 2025-08-13 | CU6-5491, 526658
| 2025-08-19 |  | SME | X25020685549 | MAXIPACIFIC FUEL GAS STATIONS INC. | MOLINO, NIOG III, BACOOR | BACOOR CITY | DASMA |  |  | POWERHOUSE | SCHED | Isan Carlo Lazaro | 81.79 | 160.07 | 20 | NEW | 377857.81 | 70278.4 |  | 0% | 2025-08-13 16:27 | 2025-08-20 09:03 | 2025-08-19 |  |  |  | -45882.6854 | -45889.3771 | 0 | 2025-09-03 21:25 | 2025-09-13 08:20 | 2025-10-02 16:27 | -1421.5789 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 61 | 57.95 | 52.95 | 1900-03-01 | 45895 | [30 empty] | 2025-08-19 | CW6-6107, CW6-8118, 527869
| 2025-08-19 |  | HMB | X25072367339 | JOCELYN OROLA PEÑALOSA | LEMON, CAA CPD PH 2A, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | POWERHOUSE | SCHED | Isan Carlo Lazaro |  | 4.78 | 1.5 | NEW | 26126.5 | 4107.1 |  | 0% | 2025-08-14 09:58 | 2025-08-20 09:20 | 2025-08-19 |  |  |  | -45883.4153 | -45889.3889 | 0 | 2025-09-02 04:33 | 2025-09-10 23:54 | 2025-10-03 09:58 | -1580.4287 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 62 | 58.9 | 53.9 | 1900-03-02 | 45895 | [30 empty] | 2025-08-19 | CX8-1274, 148282
| 2025-08-20 |  | HMB | X25072479965 | MAELYN GARNACE MANAGBANAG | CHALLENGER, MOONWALK VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. |  | 6.49 | 1.5 | NEW | 19743.25 | 5576.37 |  | 0% | 2025-08-14 12:21 | 2025-08-20 09:18 | 2025-08-20 |  |  |  | -45883.5146 | -45889.3875 | 0 | 2025-09-02 06:56 | 2025-09-11 02:17 | 2025-10-03 12:21 | -1580.4322 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 63 | 59.85 | 54.85 | 1900-03-03 | 45895 | [30 empty] | N/A | CU7-0217
| 2025-08-20 |  | SME | X25072437371 | MID-FIL FOODS, INC. | DAANG HARI, ALABANG WEST, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE |  |  | ECOM | SCHED | Ronilo Gange Jr. | 12.95 | 12.95 | 18 | NEW | 143520.03 | 11127.28 |  | 0% | 2025-08-14 15:52 | 2025-08-20 09:16 | 2025-08-20 |  |  |  | -45883.6611 | -45889.3861 | 0 | 2025-09-02 10:27 | 2025-09-11 05:48 | 2025-10-03 15:52 | -1580.4372 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 64 | 60.8 | 55.8 | 1900-03-04 | 45895 | [30 empty] | 2025-08-19 | CT9-8090, 531659
| 2025-08-19 |  | SME | X25041103834 | IMDS SUPPLY CHAIN SOLUTIONS CORP | VILLONGCO RD, SUCAT, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | digging 8/20; digging 8/21; digging 8/22 |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 151.73 | 230.01 | 216 | NEW | 1033789.72 | 130379.52 |  | 0% | 2025-08-13 16:32 | 2025-08-20 09:12 | 2025-08-19 |  |  |  | -45882.6889 | -45889.3833 | 0 | 2025-09-01 17:12 | 2025-09-10 14:11 | 2025-10-02 16:32 | -1562.1963 | 0 | 28 | 30 | 22.028 | 27.9021 | 19.028 | 65 | 61.75 | 56.75 | 1900-03-05 | 45895 | [30 empty] | 2025-08-19 | DW1-8057, 319251
| 2025-08-19 |  | SME | X25041467872 | FIRST AMBASSADOR LOGISTICS SOLUTIONS, INC. | WEST SERVICE, PHILCREST CPD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 46.13 | 46.13 | 43 | NEW | 71566.32 | 39635.92 |  | 0% | 2025-08-14 12:18 | 2025-08-20 09:17 | 2025-08-19 |  |  |  | -45883.5125 | -45889.3868 | 0 | 2025-09-02 06:53 | 2025-09-11 02:14 | 2025-10-03 12:18 | -1580.4321 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 66 | 62.7 | 57.7 | 1900-03-06 | 45895 | [30 empty] | N/A | DV1-1143, 271890
| 2025-08-19 |  | HMB | X25051611068 | ANGELINA GOYENA BATACAN | LOTUS, SUN VALLEY SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | digging 8/21; digging 08/22 |  | CHALLENGER | SCHED | Isan Carlo Lazaro | 273.52 | 664.93 | 110 | MODIFICATION | 1198142.95 | 234234.72 |  | 0% | 2025-08-14 16:54 | 2025-08-20 09:16 | 2025-08-19 |  |  |  | -45883.7042 | -45889.3861 | 0 | 2025-09-06 05:40 | 2025-09-16 01:04 | 2025-10-03 16:54 | -1347.8338 | 0 | 40 | 32 | 25.5319 | 32.3404 | 22.5319 | 67 | 63.65 | 58.65 | 1900-03-07 | 45895 | [30 empty] | 2025-08-19 | DZ1-8061,DZ1-2824, DZ1-8062, DZ1-8063, DZ1-8064, DZ1-8065, DZ1-0372, 530890
| 2025-08-19 |  | CBG | R24257880 | CAVITEX INFRASTRUCTURE CORP., | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | SCHED | Jenneth Madrid | 76.08 | 83.61 | 0 | RELOC | 152509.65 |  |  | #DIV/0! | 2025-08-13 11:49 | 2025-08-20 09:14 | 2025-08-19 |  |  |  | -45882.4924 | -45889.3847 | 0 | 2025-09-02 13:52 | 2025-09-11 17:37 | 2025-10-02 11:49 | -1490.6269 | 0 | 23 | 36 | 23.0855 | 29.2416 | 20.0855 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-19 | A5-8069, A5-8070, A5-8093
| 2025-08-19 |  | HMB | X25041438528 | JERON L RAMOS | GUILLERMO, PARKVIEW HOMES PH 3, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | SCHED | Jenneth Madrid | 47.17 | 125.45 | 42 | MODIFICATION | 364226 |  |  | #DIV/0! | 2025-08-14 16:50 | 2025-08-20 09:15 | 2025-08-19 |  |  |  | -45883.7014 | -45889.3854 | 0 | 2025-09-04 21:48 | 2025-09-14 08:43 | 2025-10-03 16:50 | -1421.6104 | 0 | 26 | 36 | 24.2069 | 30.6621 | 21.2069 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-19 | A7-1455, 530744, A7-8078
| 2025-08-22 |  | CBG | X24083431547 | DITO TELECOMMUNITY CORPORATION | NATIONAL, ALABANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | WMTRL | Isan Carlo Lazaro | 36.37 | 36.37 | 31 | NEW | 263703.95 |  |  | #DIV/0! | 2025-08-15 08:41 |  | 2025-08-22 |  |  |  | -45884.3618 | 0 | 0 | 2025-09-03 03:16 | 2025-09-11 22:37 | 2025-10-04 08:41 | -1580.4614 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | N/A | DT1-0578, 086259
| 2025-08-22 |  | HMB | X25072801458 | GLADYS MAIDA BORINAGA DOLINA | BATULAO, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE |  |  | CHALLENGER | WMTRL | Isan Carlo Lazaro | 41.44 | 41.44 | 80 | MODIFICATION | 288094.92 |  |  | #DIV/0! | 2025-08-19 08:27 |  | 2025-08-22 |  |  |  | -45888.3521 | 0 | 0 | 2025-09-06 10:14 | 2025-09-15 01:07 | 2025-10-08 08:27 | -1633.0855 | 0 | 20 | 34 | 21.0744 | 26.6942 | 18.0744 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-22 | CS8-0175, 536096
| 2025-08-22 |  | BIZ | X25010246348 | STARR PROPERTIES & DEVELOPMENT CORPORATION | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | POWERHOUSE | WMTRL | Isan Carlo Lazaro | 27.46 | 105.75 | 72 | NEW | 156666.36 |  |  | #DIV/0! | 2025-08-18 12:09 |  | 2025-08-22 |  |  |  | -45887.5062 | 0 | 0 | 2025-09-07 20:26 | 2025-09-17 01:50 | 2025-10-07 12:09 | -1474.214 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-22 | CZ8-0172, CZ8-8108
| N/A |  | BIZ | X25020368377 | STARR PROPERTIES & DEVELOPMENT CORPORATION, | MULTINATIONAL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | UG | WMTRL | Jayson Ramores |  | 186.48 | 72 | NEW | 892024.52 |  |  | #DIV/0! | 2025-08-18 12:11 |  | N/A |  |  |  | -45887.5076 | 0 | 0 | 2025-09-07 20:28 | 2025-09-17 01:52 | 2025-10-07 12:11 | -1474.214 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | N/A | CZ8-8108, 527236
| 2025-08-22 |  | HMB | X25030995991 | CITY GOVERNMENT OF PARANAQUE | MIA, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | WMTRL | Jenneth Madrid | 86.41 | 164.69 | 80 | NEW | 570005.56 |  |  | #DIV/0! | 2025-08-18 16:14 |  | 2025-08-22 |  |  |  | -45887.6764 | 0 | 0 | 2025-09-08 00:31 | 2025-09-17 05:55 | 2025-10-07 16:14 | -1474.2195 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-22 | B5-1593, B5-8151, 530192, B5-5160
| 2025-08-22 |  | HMB | X25062223204 | EDOUARD ANTHONY L. DE CASTRO | FORT MAX RESORT, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | VJC | WMTRL | Jenneth Madrid | 91.34 | 247.91 | 44 | NEW | 519550.13 |  |  | #DIV/0! | 2025-08-16 08:27 |  | 2025-08-22 |  |  |  | -45885.3521 | 0 | 0 | 2025-09-07 05:18 | 2025-09-16 20:27 | 2025-10-05 08:27 | -1383.844 | 0 | 28 | 36 | 24.8684 | 31.5 | 21.8684 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-22 | A6-5094, A6-8084, A6-8085, 531479
| OK |  | HMB | X25062332546 | SAMSON TAN RIVERO | DON RUFINO, TAHANAN VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE |  |  | ECOM | WMTRL | Ronilo Gange Jr. | 90.92 | 111.2 | 90 | NEW | 397607.89 |  |  | #DIV/0! | 2025-08-18 15:22 | [5 empty] | -45887.6403 | 0 | 0 | 2025-09-07 23:39 | 2025-09-17 05:03 | 2025-10-07 15:22 | -1474.2183 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-22 | DW1-8060, 531650
| OK |  | HMB | X25062131943 | LENA LONGSON SANTOS | GEN. EMILIO AGUINALDO, PANAPAAN VI, BACOOR | BACOOR CITY | DASMA |  |  | ECOM | WMTRL | Ronilo Gange Jr. | 58.18 | 137.27 | 65 | NEW | 428434.7 |  |  | #DIV/0! | 2025-08-15 16:14 | [5 empty] | -45884.6764 | 0 | 0 | 2025-09-05 00:31 | 2025-09-14 05:55 | 2025-10-04 16:14 | -1474.1231 | 0 | 26 | 34 | 23.3451 | 29.5704 | 20.3451 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895 | [30 empty] | 2025-08-22 | CW5-8062, 531376
[28 empty] | 0 | 0 | 0 | 1900-01-17 18:35 | 1900-01-26 13:56 | 1900-02-18 | 0 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895
[28 empty] | 0 | 0 | 0 | 1900-01-17 18:35 | 1900-01-26 13:56 | 1900-02-18 | 0 | 0 | 20 | 36 | 21.7742 | 27.5806 | 18.7742 | 68 | 64.6 | 59.6 | 1900-03-08 | 45895
Formulas:
NEW KPI (Starting October 2021) = [DATE WMTRL]+50
DATE NEEDED TO COMP = [DATE FCOMP]+[SPT(M) for comp]
AGEING DAYS SINCE FCOMP = IFERROR(TODAY()-[DATE FCOMP],"")
CERTIFICATE OF COMPLETION = [DATE FCOMP]+15
RUNNING DAYS = IF(AND([DATE RECEIVED BY CONTRACTOR]=0,[DATE COMPLETED NTC]=0), "0",IF([DATE COMPLETED NTC],([DATE COMPLETED NTC]-[DATE RECEIVED BY CONTRACTOR]),TODAY()-[DATE RECEIVED BY CONTRACTOR]))
DATE WMTRL = VLOOKUP([WO NO],'[3]List of Work Orders'!$A:$P,7,FALSE)
Note on E93: Zyreen S. Cruz (Miescor Logistics, Inc.): Conjuct to wo# X23114409472 CITY GOVT OF TAGUIG
Note on E136: DIGGING C/O POWERHOUSE WITH SUBMITTED COC 11/09/24
Note on E183: Zyreen S. Cruz (Miescor Logistics, Inc.): ECOM TO VJC

## PCA SUMMARY
hide cells -> | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01
2024-01-01 | 2025-01-01: from; 2025-02-01: 2025-01-01
PCA COMPLETION INDEX | 2025-01-01: to; 2025-02-01: 2025-06-30; 2025-10-01: PCA COMPLETION INDEX; 2025-11-01: WEIGHT; 2025-12-01: TARGET; 2026-01-01: STRETCH
YTD ENERGIZED | 359 | PCA COUNT INDEX |  | CONVERSION RATE |  | PERFORMANCE COMPLETION INDEX |  | TARGET | STRETCH |  | 5% | 98.6% | 100%
CARRY-OVER FROM 2024 | 112 | Completed vs Goal |  | Completed vs Released |  |  |  | 606 | 622 | PCA COUNT | 2% | 98% | 100%
FOR CANCELLATION/CANCELLED | 22 | 117.3% |  | 75.42% |  | 92.18% |  |  |  | PCA CONVERSION RATE | 3% | 99% | 100%
WMTRL 2025 | 2025-01-01: 386; 2025-02-01: ^adjust month for target |  | For weekly update |  | (edit here)
Carry-over includes PCAN & PCAN3 / OH and UG | 2025-01-01: <-- refer to list of WOs below |  | COUNT | Start date | 2025-08-01 | [18 empty] | 254
[15 empty] | REVENUE ONLY | End date | 2025-08-16 |  |  | WITH EXCLUSION | [14 empty] | PRDI | 205 | 49 | <--- WO COUNT | edit CF1 cell first
PCA COUNT | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL |  | CREW | TOTAL PCA COMPLETED | COMPLETED (AUGUST 1-15, 2025) | CCTI (FCOMP) | CCTI (less than FCOMP) | CCTI (FCOMP) | CCTI (less than FCOMP) | Count of beyond SPT | YTD APT | APT |  |  | SUPV | TOTAL PCA COMPLETED | COMPLETED THIS WEEK | CCTI (FCOMP) | CCTI (less than FCOMP) | APT | WEEKLY APT |  | CREW | PRDI (not yet COMP, beyond SPT) | PRDI (COMP) | COMP WORK ORDERS
Monthly Stretch | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 624 |  | AVECO | 54 | 1 | 1.7796 | 2.725 | 1.7466 | 2.725 | 24 | 73.749 | 106.7965 |  |  | Ronilo Gange | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! |  | AVECO | 1.8266 | 3.11 | 5
Monthly Target | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 612 |  | CHALLENGER | 76 | 3 | 1.155 | 2.5001 | 1.0833 | 1.5449 | 6 | 43.8051 | 63.7715 |  |  | Isan Carlo Lazaro | 84 | 4 | 1.3495 | 2.3705 | 46.8814 | 70.2757 |  | CHALLENGER | 1.8985 | 2.9303 | 11
COMPLETED 2024 | 35 | 50 | 33 | 23 | 45 | 45 | 55 | 40 | 40 | 54 | 20 | 35 | 475 |  | ECOM | 42 | 7 | 1.2241 | 2.8457 | 1.3146 | 2.8457 | 16 | 51.6568 | 69.4397 |  |  | Jenneth Madrid | 130 | 7 | 1.6147 | 2.1002 | 67.593 | 126.3446 |  | ECOM | 2.3345 | 2.5944 | 3
COMPLETED (Revenue) | 43 | 42 | 54 | 32 | 55 | 45 | 51 | 31 | 0 | 0 | 0 | 0 | 353 | 359 | POWERHOUSE | 52 | 1 | 2.1821 | 2.3247 | 2.107 | 2.3247 | 17 | 75.5228 | 76.7799 |  |  | Jemuel Peralta | 5 | 0 | 0.38729 | 0 | 29.5984 | #DIV/0! |  | POWERHOUSE | 2.1699 | 3.3833 | 1
COMPLETED UG/SLEM PCA TAGGED UNDER PQS | 1 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  | VJC | 87 | 7 | 1.4764 | 2.1695 | 1.343 | 1.8961 | 13 | 62.564 | 126.3446 |  |  | Ian Patrick Perez | 23 | 5 | 0.65486 | 5.6617 | 21.4796 | 65.2132 |  | VJC | 1.984 | 1.9863 | 13
COMPLETED (released 2024 & prior) | 34 | 12 | 15 | 6 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 78 |  | C2 | 24 | 5 | 0.64974 | 5.6617 | 0.6599 | 0 | 1 | 21.1024 | 65.2132 |  |  | UG | 3 | 0 | 1.6799 | 0 | 102.8572 | #DIV/0! |  | C2 | 0 | 1.5485 | 15
COMPLETED (Non-Revenue) | 20 | 19 | 28 | 32 | 27 | 30 | 27 | 14 | 0 | 0 | 0 | 0 |  |  | MAINTENANCE | 16 | 4 | 1.2229 | 0.48222 | 1.2857 | 0.48222 | 1 | 41.3162 | #DIV/0! |  |  | SLEM | 3 | 0 | 0 | 0 | 98.6667 | #DIV/0! |  | MAINTENANCE | 1.8208 | 1.4333 | 1
RECEIVED | 57 | 53 | 44 | 51 | 52 | 57 | 47 | 25 | 0 | 0 | 0 | 0 | 386 |  | STA. ROSA | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 198.6505 | #DIV/0! |  |  |  | 248 | 16 | [5 empty] | TOTAL | 2.001 | 2.2333 | 49
YTD STRETCH | 52 | 104 | 156 | 208 | 260 | 312 | 364 | 416 | 468 | 520 | 572 | 624 | 4056 |  | TOTAL | 353 | 28 | 1.4014 | 2.5443 | 1.3665 | 2.3551 | 79 | 59.1234 | 92.912 | [11 empty] | 2.0458
YTD TARGET | 51 | 102 | 153 | 204 | 255 | 306 | 357 | 408 | 459 | 510 | 561 | 612 | 3978 |  |  |  |  | 1.6104 |  | 1.5473
YTD ACTUAL | 44 | 87 | 143 | 175 | 231 | 277 | 328 | 359 | 359 | 359 | 359 | 359 | 359 | ^ must be equal | [20 empty] | PRDI
CANCELLED 2024 (CAN/CLOSED-CAN) | JAN: 1; FEB: 4; MAR: 4; APR: 3; MAY: 0; JUN: 0; TOTAL: 12 | < manual encode | TOTAL MHRS | [19 empty] | Target | 1
REMAINING 2024 AGEING PCA | JAN: 77; FEB: 61; MAR: 42; APR: 33; MAY: 25; JUN: 22; JUL: 22 |  | REVENUE ONLY | [19 empty] | Stretch | 0.95
VARIANCE FROM TARGET | JAN: 7; FEB: 15; MAR: 10; APR: 29; MAY: 24; JUN: 29; JUL: 29 |  | CREW | TOTAL MNHRS COMPLETED | COMPLETED (JULY 1-31, 2025) | [17 empty] | *SPT: 60 Days
Completion of Ageing | 31.25% | 45.54% | 62.5% | 70.54% | 77.68% | 80.36% | 80.36% | [5 empty] | 80.36% |  | AVECO | 18333.94 | 548.67
PCA MHRS (REVENUE) | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL |  | CHALLENGER | 11903.89 | 559.73
COMPLETED | 6054.2343 | 5553.3542 | 5014.9138 | 1772.017 | 5261.7842 | 2590.2478 | 3668.4127 | 2179.0792 | 0 | 0 | 0 | 0 | 32094.0432 |  | ECOM | 4016.29 | 748.39
RECEIVED | 6211.1129 | 3877.2951 | 3129.8109 | 4351.0504 | 4312.7796 | 5310.3337 | 4222.21 | 973.22 | 0 | 0 | 0 | 0 | 32387.8126 |  | POWERHOUSE | 6524.39 | 3.52
[15 empty] | VJC | 21088.77 | 974.3
PCA MHRS (NON-REVENUE) | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL |  | C2 | 555.24 | 43.13
COMPLETED | 2004.4837 | 1492.7078 | 2510.7689 | 4141.7967 | 2288.5399 | 2477.6258 | 2456.1935 | 1318.2867 | 0 | 0 | 0 | 0 | 18690.403 |  | MAINTENANCE | 1111.41 | 186.75
RECEIVED | 1198.9238 | 1952.878 | 2481.8007 | 1943.7781 | 4684.8494 | 3027.4187 | 3053.93 | 138.75 | 0 | 0 | 0 | 0 | 18482.3287 |  | STA. ROSA | 725.83 | 0
RECEIVED COUNT | 18 | 24 | 30 | 33 | 25 | 29 | 30 | 2 | 0 | 0 | 0 | 0 |  |  | TOTAL | 64259.76 | 3064.49
[15 empty] | PENDING PCA (REV AND NON-REV) |  | USING C1 MANHOURS |  |  | REVENUE |  | NON-REVENUE
[15 empty] | PENDING PER SEGMENT | WO COUNT | MANHOURS | APPLIED LOAD |  | WO COUNT | MHRS | WO COUNT | MNHRS | [7 empty] | COMPLETED PER SEGMENT | WO COUNT | TOTAL MNHRS | APPLIED LOAD
[15 empty] | HMB | 162 | 20542.0692 | 9002.85 |  | 71 | 11682.0048 | 91 | 8860.0643 | [7 empty] | HMB | 27 | 4807.27 | 3066.8
[15 empty] | BIZ | 52 | 4455.6996 | 4833 |  | 32 | 3450.8336 | 20 | 1004.866 | [7 empty] | BIZ | 18 | 1763.02 | 1613
[15 empty] | CBG | 37 | 4456.5152 | 7686 |  | 24 | 2256.0043 | 13 | 2200.5109 | [7 empty] | CBG | 17 | 5810.31 | 4210
[15 empty] | MN | 44 | 4953.7997 | 0 |  | 0 | 0 | 44 | 4953.7997 | [7 empty] | MN | 1 | 45.82 | 0
[15 empty] | REL | 2 | 1850.9444 | 0 |  | 0 | 0 | 2 | 1850.9444 | [7 empty] | TOTAL | 63 | 12426.42 | 8889.8
[15 empty] | TOTAL | 253 | 31305.2284 | 21521.85 |  | 127 | 17388.8427 | 126 | 13916.3856
TOTAL COMPLETED PER PROJECT TYPE
[31 empty] | CREW | REV | NON-REV | TOTAL
[31 empty] | AVECO | 54 | 31 | 85
[15 empty] | 2025 PENDING (REV ONLY) | USING C1 MANHOURS |  |  | PCA REV > 500MH |  | PCA REV 100 - 500MH |  | PCA REV < 100MH | [7 empty] | CHALLENGER | 76 | 44 | 120
[15 empty] | CREW | TOTAL |  |  | DIFFICULT |  | AVERAGE |  | EASY | [7 empty] | ECOM | 42 | 35 | 77
[16 empty] | Count | Manhrs |  | Count | Manhrs | Count | Manhrs | Count | Manhrs | for checking purposes | [5 empty] | POWERHOUSE | 52 | 26 | 78
[15 empty] | AVECO | 29 | 5020.2846 |  | 1 | 717.2996 | 13 | 3475.8676 | 15 | 827.1174 | 29 | 5020.2846 |  |  |  |  | VJC | 87 | 44 | 131
[15 empty] | CHALLENGER | 11 | 1277.2703 |  | 0 | 0 | 4 | 957.6483 | 7 | 319.622 | 11 | 1277.2703 |  |  |  |  | C2 | 24 | 5 | 29
[15 empty] | ECOM | 23 | 4140.9135 |  | 2 | 1476.4864 | 9 | 2184.7025 | 12 | 479.7246 | 23 | 4140.9135 |  |  |  |  | MAINTENANCE | 16 | 9 | 25
[15 empty] | POWERHOUSE | 23 | 2351.3728 |  | 0 | 0 | 11 | 1923.8538 | 12 | 427.519 | 23 | 2351.3728 |  |  |  |  | STA. ROSA | 2 | 0 | 2
[15 empty] | VJC | 19 | 2847.6326 |  | 0 | 0 | 11 | 2395.3641 | 8 | 452.2685 | 19 | 2847.6326 |  |  |  |  | TOTAL | 353 | 194 | 547
[15 empty] | C2 | 1 | 76.36 |  | 0 | 0 | 0 | 0 | 1 | 76.36 | 1 | 76.36
[15 empty] | MAINTENANCE | 2 | 39.07 |  | 0 | 0 | 0 | 0 | 2 | 39.07 | 2 | 39.07 |  |  |  |  | TOTAL COMPLETED PER PROJECT TYPE |  | USING TOTAL MANHOURS
[15 empty] | STA. ROSA | 5 | 1210.109 |  | 0 | 0 | 4 | 1126.0013 | 1 | 84.1077 | 5 | 1210.109 |  |  |  |  | CREW | REV | NON-REV | TOTAL | AVE. MNHRS
[15 empty] | TOTAL | 113 | 16963.0127 |  | 3 | 2193.786 | 52 | 12063.4376 | 58 | 2705.7892 | 113 | 16963.0127 |  |  |  |  | AVECO | 18333.94 | 7114.49 | 25448.43 | 299.3933
2024 & PRIOR | [30 empty] | CHALLENGER | 11903.89 | 9501.59 | 21405.48 | 178.379
FOR CANCELLATION | [30 empty] | ECOM | 4016.29 | 6761.27 | 10777.56 | 139.9683
WO | JAN: DESCRIPTION; FEB: SUPERVISOR; MAR: CREW; APR: WMTRL DATE; MAY: EAM STATUS; JUL: Date Cancelled | [17 empty] | POWERHOUSE | 6524.39 | 2676.17 | 9200.56 | 117.9559
X21104486609 | JAN: JEFFREY SAGUN CHAN; FEB: Jenneth Madrid; MAR: VJC; APR: 2021-11-18 16:50; MAY: PCAN3; JUN: pending; AUG: MODIFICATION |  | CATEGORY |  | MHRS |  | SPT | - Total performance to be indexed based on actual WO count % contribution - Scope: 2025 received and completed - Exclusions will be considered/validated including transfer of delays to other milestone/office | [10 empty] | VJC | 21088.77 | 5213.71 | 26302.48 | 200.7823
X21030949643 | JAN: ROBERTO DE MESA BUNYI; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2021-11-24 11:52; MAY: PCAN; JUN: pending; AUG: MODIFICATION | using Total Mhrs | EASY | < 100MH | 0 | 100 | 30 | [11 empty] | C2 | 555.24 | 70.38 | 625.62 | 21.5731
X22052042329 | JAN: MARIA IMELDA BUYOC SANDWEG; FEB: Jemuel Peralta; MAR: VJC; APR: 2022-08-23 11:15; MAY: PCAN3; JUN: pending; AUG: MODIFICATION | Column "P" | AVERAGE | 101 - 500MH | 101 | 500 | 60 | [11 empty] | MAINTENANCE | 1111.41 | 306.3 | 1417.71 | 56.7084
R21956925 | JAN: MACAGGA DANICA RUTH RABENA; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2022-12-09; MAY: PCAN4; JUN: pending; AUG: RELOC |  | DIFFICULT | > 500MH | 501 | 5000 | 90 | [11 empty] | STA. ROSA | 725.83 | 0 | 725.83 | 1.3269
X22125127907 | JAN: MEGAWIDE CONSTRUCTION CORPORATION; FEB: Ronilo Gange Jr.; MAR: AVECO; APR: 2022-12-21 12:42; MAY: PCAN; JUN: pending; AUG: TERMINATION | [17 empty] | TOTAL | 64259.76 | 31643.91 | 95903.67 | 175.3266
X22104175107 | JAN: MARK KENNETH VITUG FLORES; FEB: Ronilo Gange Jr.; MAR: AVECO; APR: 2023-04-03; MAY: PCAN3; JUN: pending; AUG: NEW |  | EASY | 2025 COMPLETED WITHIN SPT | 2025 TOTAL COMPLETED | 2025 RECEIVED | SPT OF FCOMP ONLY | 2025 PERF
X23072866920 | JAN: GLOBE TELECOM, INC.; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2023-08-10 10:40; MAY: PCAN; JUN: pending; AUG: MODIFICATION |  | AVECO | 4 | 16 | 19 | 25% | 21.05%
X23072873118 | JAN: JOSEPH T. CHUA; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2023-09-26 09:10; MAY: PCAN3; JUN: pending; AUG: NEW |  | CHALLENGER | 19 | 39 | 43 | 48.72% | 44.19%
X23010135604 | JAN: DANILO CASPE SEPTIMO; FEB: Ronilo Gange Jr.; MAR: AVECO; APR: 2023-11-23 16:24; MAY: PCAN3; JUN: pending; AUG: NEW |  | ECOM | 8 | 24 | 29 | 33.33% | 27.59%
X23010135483 | JAN: ELENA SALAZAR BOÑAGA; FEB: Ronilo Gange Jr.; MAR: AVECO; APR: 2023-11-23 16:26; MAY: PCAN3; JUN: pending; AUG: NEW |  | POWERHOUSE | 5 | 23 | 31 | 21.74% | 16.13%
X22114994258 | JAN: MAYNILAD WATER SERVICES, INC.; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2023-11-29 16:05; MAY: PCAN3; JUN: pending; AUG: NEW |  | VJC | 14 | 36 | 37 | 38.89% | 37.84%
X23114600974 | JAN: BP WATERWORKS, INC.; FEB: Ronilo Gange Jr.; MAR: AVECO; APR: 2024-05-09 15:24; MAY: PCAN; JUN: pending; AUG: NEW |  | C2 | 14 | 24 | 25 | 58.33% | 56%
X24051549285 | JAN: DITO TELECOMMUNITY CORPORATION; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2024-05-30 09:53; MAY: PCAN3; JUN: pending; AUG: NEW |  | MAINTENANCE | 3 | 13 | 15 | 23.08% | 20%
X23104092125 | JAN: PHILIP SIGFRID ALFARO FORTUN; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2024-08-30 14:29; MAY: CLOSED-CAN; JUN: ü; AUG: NEW |  | STA. ROSA | 0 | 0 | 0 | #DIV/0! | #DIV/0!
X24051828444 | JAN: DITO TELECOMMUNITY CORPORATION; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2024-10-02 08:35; MAY: CLOSED-CAN; JUN: ü; AUG: NEW |  |  | 67 | 175 | 199 | 38.29% | 33.67%
X24083159101 | JAN: CHONA RODRIGUEZ GAN; FEB: Isan Carlo Lazaro; MAR: CHALLENGER; APR: 2024-10-03 16:53; MAY: PCAN3; JUN: pending; AUG: MODIFICATION
R23605089 | JAN: CHAN JULIE TANG,; FEB: Ronilo Gange Jr.; MAR: ECOM; APR: 2024-11-12 16:32; MAY: CLOSED-CAN; JUN: ü; AUG: RELOC
X24062437670 | JAN: DITO TELECOMMUNITY CORPORATION; FEB: Isan Carlo Lazaro; MAR: POWERHOUSE; APR: 2024-12-13; MAY: PCAN3; JUN: pending; AUG: NEW |  | AVERAGE | 2025 COMPLETED WITHIN SPT | 2025 TOTAL COMPLETED | 2025 RECEIVED | SPT OF FCOMP ONLY | 2025 PERF
X22125058629 | JAN: CITY GOVERNMENT OF MUNTINLUPA; FEB: Isan Carlo Lazaro; MAR: MAINTENANCE; APR: 2025-02-10 14:37; MAY: PCAN; JUN: pending; AUG: MODIFICATION |  | AVECO | 5 | 16 | 31 | 31.25% | 16.13%
X25061964589 | JAN: 101 SUPPLY CHAIN SOLUTIONS,INC; FEB: Isan Carlo Lazaro; MAR: POWERHOUSE; APR: 2025-06-13 16:09; MAY: PCAN; JUN: pending; AUG: TERMINATION |  | CHALLENGER | 11 | 22 | 24 | 50% | 45.83%
X23093634405 | JESUS, THE GOOD SHEPHERD CHURCH OF MUNTINLUPA, INC | Jemuel Peralta | CHALLENGER | 2024-03-08 09:36 | CAN | ü | 2025-01-14 | NEW | [6 empty] | ECOM | 2 | 10 | 16 | 20% | 12.5%
X24052001012 | VILLA LIGHT NEIGHBORHOOD ASSOCIATION INC. | Jenneth Madrid | VJC | 2024-06-20 22:04 | CLOSED-CAN | ü | 2025-03-21 | NEW | [6 empty] | POWERHOUSE | 0 | 5 | 15 | 0% | 0%
X24062342140 | JOAN ANTONIO QUIMPO | Jemuel Peralta | CHALLENGER | 2024-07-11 08:38 | CAN | ü | 2025-04-21 | NEW | [6 empty] | VJC | 10 | 29 | 40 | 34.48% | 25%
X24051926078 | DITO TELECOMMUNITY CORPORATION | Jenneth Madrid | VJC | 2024-07-23 15:44 | CLOSED-CAN | ü | 2025-02-22 | NEW | [6 empty] | C2 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
X24072565971 | DITO TELECOMMUNITY CORPORATION | Jenneth Madrid | VJC | 2024-08-07 09:01 | CLOSED-CAN | ü | 2025-04-30 | NEW | [6 empty] | MAINTENANCE | 2 | 3 | 3 | 66.67% | 66.67%
X24041115574 | DITO TELECOMMUNITY CORPORATION | Jenneth Madrid | VJC | 2024-09-02 10:05 | CLOSED-CAN | ü | 2025-02-06 | NEW | [6 empty] | STA. ROSA | 0 | 0 | 0 | #DIV/0! | #DIV/0!
X24062428692 | GREENLAND NEW LOWER BICUTAN NEIGHBORHOOD ASSOCIATI | Jenneth Madrid | VJC | 2024-09-30 14:58 | CLOSED-CAN | ü | 2025-03-14 | NEW | [7 empty] | 30 | 85 | 129 | 35.29% | 23.26%
X24083439704 | DITO TELECOMMUNITY CORPORATION | Jenneth Madrid | VJC | 2024-10-02 07:46 | CLOSED-CAN | ü | 2025-02-06 | NEW
X24093787030 | CONVERGE INFORMATION AND COMMUNICATIONS TECHNOLOGY | Jenneth Madrid | VJC | 2024-10-15 15:03 | CLOSED-CAN | ü | 2025-02-06 | NEW | [6 empty] | DIFFICULT | 2025 COMPLETED WITHIN SPT | 2025 TOTAL COMPLETED | 2025 RECEIVED | SPT OF FCOMP ONLY | 2025 PERF
X24104029330 | NOEMI A SUMINISTRADO | Jenneth Madrid | VJC | 2024-11-20 10:38 | CLOSED-CAN | ü | 2025-04-02 | NEW | [6 empty] | AVECO | 1 | 4 | 11 | 25% | 9.091%
X24114645437 | SM DEVELOPMENT CORPORATION, | Jenneth Madrid | VJC | 2024-12-02 15:31 | CLOSED-CAN | ü | 2025-03-21 | NEW | [6 empty] | CHALLENGER | 0 | 2 | 4 | 0% | 0%
X24114498829 | VILLA LIGHT NEIGHBORHOOD ASSOCIATION INC. | Jenneth Madrid | VJC | 2024-12-11 16:03 | CLOSED-CAN | ü | 2025-03-21 | NEW | [6 empty] | ECOM | 0 | 0 | 7 | #DIV/0! | 0%
[15 empty] | POWERHOUSE | 0 | 2 | 6 | 0% | 0%
[15 empty] | VJC | 1 | 7 | 12 | 14.29% | 8.333%
[15 empty] | C2 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
[15 empty] | MAINTENANCE | 0 | 0 | 0 | #DIV/0! | #DIV/0!
[15 empty] | STA. ROSA | 0 | 0 | 0 | #DIV/0! | #DIV/0!
[16 empty] | 2 | 15 | 40 | 13.33% | 5%
[15 empty] | TOTAL | 99 | 275 | 368 | 36% | 26.9%
PENDING
2024
| MONTH FCOMP | WO COUNT | APP. LOAD | TOTAL MHRS
| (blank) | 321 | 24351.415 | 35753.4352
| BIZ | 64 | 4436 | 3795.9808
| MODIFICATION | 5 | 752 | 945.496
| NEW | 43 | 3684 | 1983.581
| PCA RELOC | 2 | 0 | 275.7503
| RELOC | 1 | 0 | 81.4201
| TERMINATION | 13 | 0 | 509.7334
| CBG | 54 | 11732 | 8070.7595
| MODIFICATION | 5 | 105 | 318.8777
| NEW | 32 | 11627 | 3930.3896
| PCA RELOC | 2 | 0 | 314.6535
| POLE RELOC | 2 | 0 | 1442.0948
| RELOC | 7 | 0 | 1360.9625
| TERMINATION | 6 | 0 | 703.7814
| HMB | 151 | 8161.415 | 18729.5403
| MODIFICATION | 57 | 3510.375 | 5276.5132
| NEW | 65 | 4651.04 | 11830.0784
| PCA RELOC | 7 | 0 | 390.9168
| POLE RELOC | 1 | 0 | 261.8848
| RELOC | 21 | 0 | 970.1471
| MN | 47 | 0 | 2060.2748
| OLDT | 19 | 0 | 934.8568
| RETIREMENT OF IDLE FACILITES | 5 | 0 | 117.6528
| RTA | 22 | 0 | 996.9331
| SUPPLEMENTAL MN FOR PCA | 1 | 0 | 10.8321
| REL | 4 | 0 | 3059.2637
| POLE RELOC | 4 | 0 | 3059.2637
(blank)
(blank)
| GCB | 1 | 22 | 37.6161
| NEW | 1 | 22 | 37.6161
| 2025-01-10 16:30 | 1 | 0 | 37.03
| HMB | 1 | 0 | 37.03
| PCA RELOC | 1 | 0 | 37.03
| 2025-01-06 13:08 | 1 | 32 | 14.8103
| HMB | 1 | 32 | 14.8103
| MODIFICATION | 1 | 32 | 14.8103
| 2025-01-10 17:04 | 1 | 4.5 | 262.641
| HMB | 1 | 4.5 | 262.641
| NEW | 1 | 4.5 | 262.641
| 2025-01-10 17:37 | 1 | 295.5 | 954.8506
| HMB | 1 | 295.5 | 954.8506
| NEW | 1 | 295.5 | 954.8506
| 2025-01-14 09:49 | 1 | 54 | 10.35
| HMB | 1 | 54 | 10.35
| MODIFICATION | 1 | 54 | 10.35
| 2025-01-11 11:14 | 1 | 80 | 47.4355
| HMB | 1 | 80 | 47.4355
| MODIFICATION | 1 | 80 | 47.4355
| 2025-01-08 07:22 | 1 | 44 | 109.024
| HMB | 1 | 44 | 109.024
| NEW | 1 | 44 | 109.024
| 2025-01-11 | 4 | 214 | 201.2736
| BIZ | 2 | 86 | 77.7149
| NEW | 2 | 86 | 77.7149
| HMB | 2 | 128 | 123.5587
| MODIFICATION | 2 | 128 | 123.5587
| 2025-01-02 14:27 | 1 | 127.5 | 421.59
| HMB | 1 | 127.5 | 421.59
| NEW | 1 | 127.5 | 421.59
| 2025-01-09 11:54 | 1 | 120 | 93.062
| BIZ | 1 | 120 | 93.062
| NEW | 1 | 120 | 93.062
| 2025-01-06 15:36 | 1 | 44 | 45.667
| BIZ | 1 | 44 | 45.667
| NEW | 1 | 44 | 45.667
| 2025-01-09 14:41 | 1 | 31.5 | 61.1395
| HMB | 1 | 31.5 | 61.1395
| NEW | 1 | 31.5 | 61.1395
| 2025-01-06 15:35 | 1 | 624 | 341.1727
| BIZ | 1 | 624 | 341.1727
| NEW | 1 | 624 | 341.1727
| 2025-01-11 11:12 | 1 | 131.5 | 167.3971
| HMB | 1 | 131.5 | 167.3971
| NEW | 1 | 131.5 | 167.3971
| 2025-01-09 09:36 | 1 | 890.5 | 283.2732
| HMB | 1 | 890.5 | 283.2732
| NEW | 1 | 890.5 | 283.2732
| 2025-01-15 | 6 | 420.5 | 264.1417
| BIZ | 1 | 60 | 14.2433
| NEW | 1 | 60 | 14.2433
| CBG | 1 | 117 | 46.2
| NEW | 1 | 117 | 46.2
| HMB | 3 | 243.5 | 192.0206
| NEW | 3 | 243.5 | 192.0206
| MN | 1 | 0 | 11.6778
| OLDT | 1 | 0 | 11.6778
| 2025-01-11 10:06 | 1 | 115 | 6.79
| BIZ | 1 | 115 | 6.79
| NEW | 1 | 115 | 6.79
| 2025-01-18 | 2 | 68 | 244.1598
| CBG | 2 | 68 | 244.1598
| ECP | 1 | 68 | 200.2298
| MODIFICATION | 1 | 0 | 43.93
| 2024-12-13 | 5 | 80 | 2594.5538
| CBG | 2 | 0 | 156.33
| MODIFICATION | 1 | 0 | 139.95
| TERMINATION | 1 | 0 | 16.38
| HMB | 2 | 80 | 90.5947
| MODIFICATION | 1 | 80 | 71.4526
| RELOC | 1 | 0 | 19.1421
| REL | 1 | 0 | 2347.6291
| POLE RELOC | 1 | 0 | 2347.6291
| 2024-12-20 | 1 | 0 | 9.1265
| HMB | 1 | 0 | 9.1265
| RELOC | 1 | 0 | 9.1265
| 2025-01-24 | 3 | 77 | 101.9701
| BIZ | 3 | 77 | 101.9701
| NEW | 3 | 77 | 101.9701
| 2025-01-20 | 4 | 1038 | 607.6694
| BIZ | 2 | 139 | 174.4817
| NEW | 1 | 139 | 29.505
| TERMINATION | 1 | 0 | 144.9767
| CBG | 1 | 730 | 209.1735
| NEW | 1 | 730 | 209.1735
| HMB | 1 | 169 | 224.0142
| NEW | 1 | 169 | 224.0142
| 2025-01-21 | 1 | 87 | 0
| HMB | 1 | 87 | 0
| MODIFICATION | 1 | 87 | 0
| 2025-01-10 | 1 | 200 | 428.8492
| HMB | 1 | 200 | 428.8492
| NEW | 1 | 200 | 428.8492
| 2025-01-31 | 8 | 192 | 954.282
| BIZ | 1 | 0 | 176.7701
| TERMINATION | 1 | 0 | 176.7701
| CBG | 6 | 163 | 774.7819
| NEW | 4 | 163 | 492.7771
| TERMINATION | 2 | 0 | 282.0048
| HMB | 1 | 29 | 2.73
| NEW | 1 | 29 | 2.73
| 2025-01-14 | 2 | 276 | 109.1904
| BIZ | 1 | 196 | 27.4528
| NEW | 1 | 196 | 27.4528
| HMB | 1 | 80 | 81.7376
| NEW | 1 | 80 | 81.7376
| 2025-01-12 | 1 | 49 | 68.0405
| BIZ | 1 | 49 | 68.0405
| NEW | 1 | 49 | 68.0405
| 2025-01-26 | 2 | 178 | 123.7743
| BIZ | 1 | 21 | 39.92
| MODIFICATION | 1 | 21 | 39.92
| HMB | 1 | 157 | 83.8543
| NEW | 1 | 157 | 83.8543
| 2025-01-27 | 1 | 66 | 83.1652
| BIZ | 1 | 66 | 83.1652
| NEW | 1 | 66 | 83.1652
| 2025-01-30 | 8 | 3162.3 | 1536.1634
| BIZ | 1 | 16 | 1.73
| NEW | 1 | 16 | 1.73
| CBG | 5 | 3101 | 1052.7509
| MODIFICATION | 1 | 23 | 36.0138
| NEW | 3 | 3078 | 937.0615
| POLE RELOC | 1 | 0 | 79.6756
| HMB | 2 | 45.3 | 481.6825
| MODIFICATION | 1 | 41.5 | 358.343
| NEW | 1 | 3.8 | 123.3395
| 2025-01-04 | 1 | 82 | 25.0823
| HMB | 1 | 82 | 25.0823
| NEW | 1 | 82 | 25.0823
| 2025-01-25 | 1 | 31 | 12.3128
| CBG | 1 | 31 | 12.3128
| NEW | 1 | 31 | 12.3128
| 2025-01-27 14:12 | 1 | 155 | 16.0428
| HMB | 1 | 155 | 16.0428
| NEW | 1 | 155 | 16.0428
| 2025-01-28 | 2 | 0 | 206.7552
| CBG | 1 | 0 | 205.7057
| PCA RELOC | 1 | 0 | 205.7057
| HMB | 1 | 0 | 1.0495
| RELOC | 1 | 0 | 1.0495
| 2025-02-06 | 2 | 595 | 1918.0138
| BIZ | 1 | 247 | 144.6317
| NEW | 1 | 247 | 144.6317
| HMB | 1 | 348 | 1773.3821
| NEW | 1 | 348 | 1773.3821
| 2025-02-01 | 5 | 1963 | 615.437
| BIZ | 4 | 1963 | 418.9304
| NEW | 3 | 1963 | 383.387
| TERMINATION | 1 | 0 | 35.5434
| CBG | 1 | 0 | 196.5066
| TERMINATION | 1 | 0 | 196.5066
| 2025-02-07 | 7 | 280 | 307.5848
| BIZ | 2 | 126 | 111.5488
| NEW | 2 | 126 | 111.5488
| CBG | 2 | 59 | 44.7893
| MODIFICATION | 1 | 39 | 3.58
| NEW | 1 | 20 | 41.2093
| HMB | 3 | 95 | 151.2467
| NEW | 3 | 95 | 151.2467
| 2025-02-05 | 5 | 325 | 373.6859
| BIZ | 2 | 151 | 313.847
| NEW | 2 | 151 | 313.847
| CBG | 1 | 0 | 29.5181
| RELOC | 1 | 0 | 29.5181
| HMB | 2 | 174 | 30.3208
| MODIFICATION | 1 | 60 | 11.4428
| NEW | 1 | 114 | 18.878
| 2025-02-04 | 1 | 0 | 54.72
| BIZ | 1 | 0 | 54.72
| TERMINATION | 1 | 0 | 54.72
| 2025-02-15 | 6 | 303.1 | 330.5976
| HMB | 6 | 303.1 | 330.5976
| MODIFICATION | 1 | 44 | 138.4457
| NEW | 5 | 259.1 | 192.1519
| 2025-02-11 | 7 | 521.5 | 306.1724
| BIZ | 3 | 77 | 37.6395
| NEW | 2 | 77 | 37.6395
| TERMINATION | 1 |  | 0
| HMB | 4 | 444.5 | 268.5329
| MODIFICATION | 1 | 100 | 92.7618
| NEW | 3 | 344.5 | 175.7711
| 2025-02-14 | 3 | 52.6 | 441.9204
| BIZ | 2 | 48 | 394.1397
| NEW | 2 | 48 | 394.1397
| HMB | 1 | 4.6 | 47.7807
| NEW | 1 | 4.6 | 47.7807
| 2025-02-08 | 3 | 208.9 | 134.0051
| HMB | 3 | 208.9 | 134.0051
| MODIFICATION | 2 | 204 | 112.5648
| RECONTRACT OF SERVICE | 1 | 4.9 | 21.4403
| 2025-02-12 | 1 | 70.5 | 34.5195
| HMB | 1 | 70.5 | 34.5195
| NEW | 1 | 70.5 | 34.5195
| 2025-02-10 | 4 | 144 | 109.6198
| BIZ | 2 | 62 | 0
| NEW | 2 | 62 | 0
| HMB | 2 | 82 | 109.6198
| MODIFICATION | 1 | 67 | 109.6198
| NEW | 1 | 15 | 0
| 2025-02-09 | 2 | 115 | 45.709
| BIZ | 1 | 30 | 3.92
| NEW | 1 | 30 | 3.92
| HMB | 1 | 85 | 41.789
| NEW | 1 | 85 | 41.789
| 2025-02-22 | 4 | 395 | 665.796
| BIZ | 1 | 220 | 183.2653
| MODIFICATION | 1 | 220 | 183.2653
| CBG | 2 | 35 | 349.6593
| NEW | 1 | 35 | 207.1843
| RELOC | 1 | 0 | 142.475
| HMB | 1 | 140 | 132.8714
| MODIFICATION | 1 | 140 | 132.8714
| 2025-02-28 | 2 | 110 | 2.198
| BIZ | 1 | 0 | 2.198
| TERMINATION | 1 | 0 | 2.198
| HMB | 1 | 110 | 0
| NEW | 1 | 110 | 0
| 2025-02-18 | 1 | 52 | 48.755
| BIZ | 1 | 52 | 48.755
| NEW | 1 | 52 | 48.755
| 2025-02-24 | 3 | 95.5 | 330.9884
| CBG | 1 | 31 | 273.9374
| NEW | 1 | 31 | 273.9374
| HMB | 2 | 64.5 | 57.051
| NEW | 2 | 64.5 | 57.051
| 2025-02-25 | 2 | 83 | 298.8791
| BIZ | 1 | 10 | 2.58
| NEW | 1 | 10 | 2.58
| HMB | 1 | 73 | 296.2991
| NEW | 1 | 73 | 296.2991
| 2025-02-27 | 2 | 57 | 274.0698
| BIZ | 1 | 42 | 214.8948
| MODIFICATION | 1 | 42 | 214.8948
| HMB | 1 | 15 | 59.175
| NEW | 1 | 15 | 59.175
| 2025-02-26 15:17 | 1 | 78 | 666.3304
| BIZ | 1 | 78 | 666.3304
| NEW | 1 | 78 | 666.3304
| Grand Total | 451 | 38770.315 | 53155.2231
Scope: At least WTMRL as of January 1, 2025
Category: NEW (CC-type)
EAM Status: FCOMP 2025 and consider in computation that all on-going projects (less than FCOMP and beyond SPT)
Scope:
- FCOMP Date and COMP Date are in the current year
- FCOMP Date is in the current year, not yet COMP and is already beyond the SPT
Category: NEW (CC-type)

## PRIORITY
Based on the following categories: |  |  |  |  | AVECO | COMPLETED THIS MONTH | 1958.5569 |  |  | REMAINING (MNHRS) | 891.5431 | CCBC | COMPLETED THIS MONTH | 2319.5445 |  |  |  | REMAINING (MNHRS) | 986.5655 | ECOM | COMPLETED THIS MONTH |  |  |  | REMAINING (MNHRS) |  | POWERHOUSE | COMPLETED THIS MONTH | 1213.7617 |  |  |  | REMAINING (MNHRS) | 2092.3496 | 2394.0806 | VJC | COMPLETED THIS MONTH | 1443.0291 |  |  |  | REMAINING (MNHRS) | 280.1827 | <- UPDATE MONTHLY
1 | tagged VIP |  |  |  |  | MONTHLY CAPABILITY | 2850.1 | [5 empty] | MONTHLY CAPABILITY | 3306.11 | [6 empty] | MONTHLY CAPABILITY | 2394.08 | [5 empty] | MONTHLY CAPABILITY | 3306.1113 | [5 empty] | 1180.3189 |  | MONTHLY CAPABILITY | 1723.2118
2 | PCA: New and Temporary (newly released; within 30 days) |  |  |  |  | WEEKLY | 712.525 |  |  |  | 6011.75 |  | WEEKLY | 826.5275 |  |  |  | TOTAL REQUIRED MHRS | 1457.7135 |  | WEEKLY |  |  |  | TOTAL REQUIRED MHRS | 1943.9718 |  | WEEKLY | 826.5278 |  |  |  | TOTAL REQUIRED MHRS | 2813.1477 |  |  | WEEKLY REQUIREMENT | 430.803 |  |  |  | TOTAL REQUIRED MHRS | #N/A
| a | Telco |  |  | NO | WO | DESC | LOC | WMTRL DATE | TYPE | MNHRS | NO | WO | DESC | LOC | WMTRL DATE | WMTRL TO FCOMP | TYPE | MNHRS | NO | WO | DESC | LOC | WMTRL DATE | TYPE | MNHRS | NO | WO | DESC | LOC | WMTRL DATE | WMTRL TO FCOMP | TYPE | MNHRS |  | NO | WO | DESC | LOC | WMTRL DATE | WMTRL TO FCOMP | TYPE | MNHRS
| b | Refer to CBG, BIZ & HMB list |  |  | 1 | P2502183604 | Relocation of Pole along Molino Rd.SM Molino-Zapote Bacoor, Cavite -Segment 13 | ALONG MOLINO RD. FROM BRGY MOLINO 1 TO BRGY BRGY LIGAS 1, BACOOR CAVITE | 2025-05-07 | PCA RELOC | 975.48 | 1 | X24030854536 | DITO TELECOMMUNITY CORPORATION | ESTEHONOR CPD, ESTEHONOR CPD, MUNTINLUPA | 2025-03-07 12:38 | 69.4736 | NEW | 98.4871 | 1 | [6 empty] | 1 | X25020551884 | VAS SOLUTIONS INC. | PHASE 2 ACCESS ROAD, AMVEL COMMERCIAL COMPLEX, PARANAQUE | 2025-04-02 12:59 | 43.459 | NEW | 14.3228 |  | 1 |  |  |  | #N/A | #N/A | #N/A | #N/A
| b1 | CBG - |  |  | 2 | P2502183605 | Relocation of Pole along Molino Rd.SM Molino-Zapote Bacoor, Cavite -Segment 14 | ALONG MOLINO RD. FROM BRGY SAN NICOLAS 2 TO ANIBA 2,BACOOR CAVITE | 2025-05-06 | PCA RELOC | 1756.02 | 2 | X24072535895 | DITO TELECOMMUNITY CORPORATION | SINIGUELAS, ZONE 1, TAGUIG CITY | 2025-02-04 14:03 | 100.4146 | NEW | 49.4332 | 2 | R22419641 | ONOFRE, CORAZON VILLA, | GLORIA DIAZ, BF RESORT VILL, LAS PINAS CITY | 2024-08-22 14:49 | RELOC | 153.4688 | 2 | X23083154356 | CITY GOVERNMENT OF PARAÑAQUE | MANGGA, MASVILLE, PARANAQUE | 2025-02-13 13:55 | 91.4201 | NEW | 308.1928 |  | 2 |  |  |  | #N/A | #N/A | #N/A | #N/A
| b2 | BIZ - | Sir Art Macalinao |  | 3 | R19291776 | CITY GOVERNMENT OF BACOOR | GEN. TIRONA, HABAY I, BACOOR | 2021-12-03 | PCA RELOC | 1071.65 | 3 | X23114515533 | DITO TELECOMMUNITY CORPORATION | R. AVANCEÑA, KATARUNGAN VILLAGE, MUNTINLUPA | 2025-04-28 13:22 | 17.4431 | NEW | 22.84 | 3 | X25020594777 | CITY GOVERNMENT OF MUNTINLUPA | FILINVEST SOCIALIZED HOUSING, FILINVEST SOCIALIZED HOUSING, MUNTINLUPA | 2025-03-11 | MODIFICATION | 57.3666 | 3 | X24104087935 | FIRSTAR HVAC INC. | COASTAL, LONGOS, BACOOR | 2025-03-03 16:41 | 73.3049 | NEW | 144.3689 |  | 3 |  |  |  | #N/A | #N/A | #N/A | #N/A
| b3 | HMB - |  |  | 4 | R19617176 | OFFICE OF CONGRESSMAN STRIKE B. REVILLA | BLOCK 2, PRINCETON HEIGHTS PH 3, BACOOR | 2021-10-06 | PCA RELOC | 1133.23 | 4 | X23072870847 | DITO TELECOMMUNITY CORPORATION | BANABA, AYALA-ALABANG VILL, MUNTINLUPA | 2025-04-22 16:01 | 23.3326 | NEW | 35.1818 | 4 | X24083258065 | KENNETH NGO CHUA | DOÑA INES, ALABANG HILLS SUBD PH 1, MUNTINLUPA | 2025-01-24 14:01 | MODIFICATION | 37.5495 | 4 | X24103967581 | VIRGILIO BRILLIANTES SY | LAPU-LAPU, BACLARAN, PARANAQUE | 2025-01-16 16:44 | 119.3028 | NEW | 33.7385 |  | 4 |  |  |  | #N/A | #N/A | #N/A | #N/A
3 | Ageing |  |  |  | 5 | X25010176215 | MARY GRACE MESINA MANDAP | BASILIO ESTANISLAO, BF RESORT VILL, LAS PINAS CITY | 2025-02-24 | NEW | 219.82 | 5 | X24072722048 | DITO TELECOMMUNITY CORPORATION | C. ARELLANO, KATARUNGAN VILLAGE, MUNTINLUPA | 2025-04-23 08:24 | 22.65 | NEW | 18.1028 | 5 | R24098951 | CAVITE INFRASTRUCTURE CORP (SUMAPA-MULTI) | MULTINATIONAL VILLAGE< BRGY MOONWALK , PARANAQUE | AWOE MANUAL | RELOC | 50.68 | 5 | R23611939 | DPWH DEO LAS PINAS-MUNTI, | MARCOS ALVAREZ, TALON V, LAS PINAS CITY | 2024-11-14 16:10 | 182.3266 | RELOC | 80.4941 |  | 5 |  |  |  | #N/A | #N/A | #N/A | #N/A
| a | Rev |  |  | 6 | X25041368806 | CITY GOVERNMENT OF BACOOR | MALIKSI SUPER HEALTH CENTER GEN. EVANGELISTA, MALIKSI III, BACOOR, CAVITE | 2025-05-23 | NEW | 129.72 | 6 | X23072739849 | DITO TELECOMMUNITY CORPORATION | MEDEL, ZONE 3, TAGUIG CITY | 2025-05-07 07:28 |  | NEW | 154.5843 | 6 | X25030835417 | CHERIE ROSE COLINAYO ZHENG | 8004 ARMELA CPD.-SAVVY 25, MARCELO GREEN,PARANAQUE | 2025-05-22 | NEW | 97.74 | 6 | X24062437670 | DITO TELECOMMUNITY CORPORATION | BETTERLIVING SUBD ANNEX 45, PARANAQUE | 2024-12-13 | 154 | NEW | 134.781 |  | 6 |  |  |  | #N/A | #N/A | #N/A | #N/A
| b | Non-Rev (check applied load, if "Modification") |  |  | 7 | X24062164559 | EDWARD VINCENT SANTOS DAUIGOY | DAHLIA ST . TOPMAN VILLAGE NRGY BF NTERNATIONAL ,LAS PINAS | 2024-12-10 | MODIFICATION | 220.04 | 7 | X24062083547 | DITO TELECOMMUNITY CORPORATION | M.L. QUEZON, PUROK 3, TAGUIG CITY | 2025-05-08 13:59 |  | NEW | 40.2713 | 7 | X25041327101 | ERLINDA CRUZ RABE | ALONG WEST SERVICE RD , MARCELO GREEN,PARANAQUE | 2025-05-22 | NEW | 55.14 | 7 | X24041002556 | STA. LUCIA REALTY & DEVELOPMENT, INC. | VISTA VERDE SOUTH EXEC PH4, BACOOR | 2024-12-20 | 147 | NEW | 125.0909 |  | 7 |  |  |  | #N/A | #N/A | #N/A | #N/A
4 | Reloc |  |  |  | 8 | X25020687798 | TWIN KARAT REALTY CORPORATION | QUIRINO COR. PELAEZ ST., BRGY. SAN DIONISIO, PARANAQUE CITY, METRO | 2025-04-28 | NEW | 255.02 | 8 | X23072871198 | DITO TELECOMMUNITY CORPORATION | SAN JUANICO, AYALA-ALABANG VILL, MUNTINLUPA | 2025-05-09 08:33 |  | NEW | 17.3228 | 8 | X25010271342 | ALVEO LAND CORP., | ALABANG-ZAPOTE, ALMANZA I, LAS PINAS CITY | 2025-02-18 15:59 | NEW | 31.3685 | 8 | X24051849062 | DITO TELECOMMUNITY CORPORATION | BETTER LIVING SUBD, PARANAQUE | 2025-02-04 | 101 | NEW | 37.6161 |  | 8 |  |  |  | #N/A | #N/A | #N/A | #N/A
2025-01-01 |  |  |  |  | 9 | R23806071 | EL GRANDE DEVELOPMENT CORPORATION,, HMB | BAGTIKAN, BF EL GRANDE, BACOOR | 2024-12-03 | PCA RELOC | 44.73 | 9 | X25010021411 | FRANCES CHRISTINE RAMIREZ AGUIRRE | DAO, MAYWOOD VILL, PARANAQUE | 2025-04-28 15:59 | 17.334 | MODIFICATION | 135.691 | 9 | X24041057959 | GLOBE TELECOM, INC. | WEST SERVICE, MARCELO GREEN VILL, PARANAQUE | 2025-03-07 12:28 | NEW | 72.0884 | 9 | X24103988119 | DITO TELECOMMUNITY CORPORATION | ARIAS CPD, TAMBO, PARANAQUE | 2025-04-11 09:29 | 34.6049 | NEW | 3.3295 |  | 9 |  |  |  | #N/A | #N/A | #N/A | #N/A
[5 empty] | 10 | X24072779669 | MA FATIMA FESTIN PERDIDO | TALIM, TIERRA NUEVA SUBD, MUNTINLUPA | 2024-08-01 | MODIFICATION | 53.59 | 10 | X24114614743 | PTR PREMIER HOLDINGS INC. | ST. JOSEPH, ST. JOSEPH SUBD, LAS PINAS CITY | 2025-03-20 15:14 | 56.3653 | NEW | 42.4455 | 10 | X24114468464 | CITY GOVT OF LAS PIÑAS | PILI, GOLDEN ACRES SUBD, LAS PINAS CITY | 2025-03-06 16:36 | MODIFICATION | 89.3826 | 10 | X24072847895 | DITO TELECOMMUNITY CORPORATION | DR. J. GABRIEL, BACLARAN, PARANAQUE | 2025-04-24 12:46 | 21.4681 | NEW | 55.94 |  | 10 |  |  |  | #N/A | #N/A | #N/A | #N/A
| KPI CALCULATOR |  |  |  | 11 | X24093485481 | ANIELYN OCAMPO BALICUDIONG | HABAY I, HABAY I, BACOOR | 2025-01-16 | NEW | 152.45 | 11 | X24093717312 | MARIA PERLA G DATINGALING | J. DIAZ, KATARUNGAN VILLAGE, MUNTINLUPA | 2024-12-11 17:03 | 155.2898 | MODIFICATION | 222.6366 | 11 | X25020477740 | ECEAS CORPORATION | FRANCE, BETTER LIVING SUBD, PARANAQUE | 2025-03-10 17:04 | NEW | 36.5095 | 11 | X24103963394 | HERSTAL SECURITY AGENCY, INC. | DOÑA SOLEDAD, BETTER LIVING SUBD, PARANAQUE | 2025-01-09 18:06 | 126.2458 | NEW | 50.1975 |  | 11 |  |  |  | #N/A | #N/A | #N/A | #N/A
| ASSUME FCOMP DATE |  | 2025-05-16 |  | 12 | [6 empty] | 12 | X24062492521 | DOMINIC CONSTRUCTION, INC. | DR. A. SANTOS, SN ANTONIO, PARANAQUE | 2024-10-11 15:44 | 216.3446 | TERMINATION | 8.93 | 12 | X24083217792 | L.T. SOUTHVILLE SCHOOL, INC. | LUXEMBOURG, BF HOMES, LAS PINAS CITY | 2025-03-10 12:00 | MODIFICATION | 151.474 | 12 | X22104473949 | CELEDONIA C. UTANES | KYOTO COR JERUSALEM ST., BF HOMES, PARAÑAQUE | 2023-04-27 | 750 | MODIFICATION | 64.7485 |  | 12 |  |  |  | #N/A | #N/A | #N/A | #N/A
[5 empty] | 13 | [6 empty] | 13 | X25030955124 | TIN PHO LIM | CADENA DE AMOR, AYALA-ALABANG VILL, MUNTINLUPA | 2025-03-28 | 49 | MODIFICATION | 104.55 | 13 | R23462615 | UNIOIL PETROLEUM INC | DONA SOLEDAD EXTN, BETTER LIVING SUBD, PARANAQUE | 2025-03-13 13:33 | RELOC | 49.6652 | 13 | X24030740806 | REGIDOR HOOD OFRIN | MAIN, MERVILLE SUBD, PARANAQUE | 2024-07-10 16:33 | 309.3104 | MODIFICATION | 68.4635 |  | 13 |  |  |  | #N/A | #N/A | #N/A | #N/A
[5 empty] | 14 | [6 empty] | 14 | X25010271934 | DANILO FLORES TARRIELA | BATANGAS SOUTH, AYALA-ALABANG VILL, MUNTINLUPA | 2025-03-28 | 49 | MODIFICATION | 74.99 | 14 | X25020594777 | CITY GOVERNMENT OF MUNTINLUPA | FILINVEST SOCIALIZED HOUSING, FILINVEST SOCIALIZED HOUSING, MUNTINLUPA | 2025-03-11 13:54 | MODIFICATION | 57.3666 | 14 | R23301679 | JAVIER, ROSALINA | GENESIS, VILLANUEVA SUBD, BACOOR | 2024-09-03 09:42 | 254.5958 | RELOC | 16.9341 |  | 14 |  |  |  | #N/A | #N/A | #N/A | #N/A
| CCTI | AVECO |  |  | 15 | [6 empty] | 15 | X25010341987 | THE PLASTIC FLAMINGO PHILIPPINES INC. | R.M.T. INDUSTRIAL COMPLEX, R.M.T. INDUSTRIAL COMPLEX, MUNTINLUPA | 2025-03-31 14:52 | 45.3806 | MODIFICATION | 123.1366 | 15 | X25020478582 | NESTOR R LLORCA | PINAGKAISA, PUROK 1A, TAGUIG CITY | 2025-03-14 16:11 | NEW | 950.7477 | 15 | R23445427 | ARCEO, ELIZABETH | BLOCK 1, LA CHARINA SUBD, MUNTINLUPA | 2024-10-11 15:15 | 216.3643 | RELOC | 35.9652 |  | 15 |  |  |  | #N/A | #N/A | #N/A | #N/A
|  | CCBC |  |  | 16 | [6 empty] | 16 | X24083159101 | CHONA RODRIGUEZ GAN | DOÑA AURORA, TAHANAN VILL, PARANAQUE | 2024-10-03 16:53 | 224.2963 | MODIFICATION | 91.2262 | 16 | X25030933327 | JHOY MEDINA MATILLA | ROSAL, T.S. CRUZ SUBD, LAS PINAS CITY | 2025-03-28 | TERMINATION | 18.52 | 16 | X24114520845 | ERIC GERARD TURLA OLIVA | WALING-WALING, TAHANAN VILL, PARANAQUE | 2025-02-19 15:53 | 85.3382 | NEW | 37.0495 |  | 16 |  |  |  | #N/A | #N/A | #N/A | #N/A
|  | ECOM |  |  | 17 | [6 empty] | 17 | X25030779048 | A R B CONSTRUCTION COMPANY, INC. | BLOCK 3, SOLDIERS HILLS SUBD, MUNTINLUPA | 2025-05-15 10:20 |  | NEW | 86.9895 | [7 empty] | 17 | X24124701777 | NELLY YAP RAÑOLA | JUAN ALEGRE, BF HOMES, PARANAQUE | 2025-02-21 15:51 | 83.3396 | NEW | 79.9595 |  | 17 |  |  |  | #N/A | #N/A | #N/A | #N/A
|  | POWERHOUSE |  |  | 18 | [6 empty] | 18 | X25010310869 | CAT COMICS LAND INC. | ROSE OF HEAVEN, TALON VILL, LAS PINAS CITY | 2025-05-13 13:02 |  | NEW | 93.2287 |  | R22633190 | CANDIE CHUA CO. | BLK 8, PALM COAST MARINA, PARANAQUE | 2023-08-31 12:27 | RELOC | 85.5844 | 18 | X24114480257 | CITY GOV'T OF LAS PIÑAS | ALABANG-ZAPOTE, PAMPLONA I, LAS PINAS CITY | 2025-03-06 17:05 | 70.2882 | NEW | 10.9328 |  | 18 |  |  |  | #N/A | #N/A | #N/A | #N/A
|  | VJC |  |  | 19 | [6 empty] | 19 | X25031010090 | LILIA T. AMADOR | PRES. QUIRINO AVE, ZONE 6, TAGUIG CITY | 2025-04-21 15:27 |  | NEW | 12.2133 | [7 empty] | 19 | X25010318012 | REBACE REAL ESTATE AND DEVELOPMENT (REBACE) CORP. | REBACE BACOOR RESIDENCES, BACOOR | 2025-03-07 16:48 | 69.3 | NEW | 202.2694
[5 empty] | 20 | [6 empty] | 20 | X25010121042 | MODISSOL PROPERTY MANAGEMENT CORPORATION | EL GRANDE, BF HOMES, PARANAQUE | 2025-04-28 16:03 |  | NEW | 25.4528 | [7 empty] | 20 | X25010330816 | GOLDILOCKS BAKESHOP, INC. | ST. FRANCIS, SAN AGUSTIN VILL, PARANAQUE | 2025-03-25 15:43 | 51.3451 | NEW | 1.73
[5 empty] | 21 | [6 empty] | 21 | [14 empty] | 21 | X24010242621 | MICHELLE MARTELINO YU | OXFORD, HILLSBOROUGH SUBD, MUNTINLUPA | 2025-03-27 | 50 | NEW | 127.88
| APT | AVECO |  |  | 22 | [6 empty] | 22 | [14 empty] | 22 | X24104306412 | DON ANTONIO ROXAS CHUA FOUNDATION. INC. | A.R. CHUA, PACIFIC VILL, MUNTINLUPA | 2025-04-02 14:21 | 43.4021 | NEW | 43.4902
|  | CCBC |  | 80.4865 | 23 | X24093863040 | AIRA NAVARRO JUBILADO | A. MABINI, TUAZON SUBD, LAS PINAS CITY | 2024-11-29 | NEW | 113.71 | 23 | [14 empty] | 23 | X25010249268 | SITIO SUNRISE NEIGHBORHOOD ASS | GALAXY, BRICKTOWN PH 3 SUBD, PARANAQUE | 2025-04-04 17:53 | 41.2549 | NEW | 114.5162
|  | ECOM |  |  | 24 | X24030696318 | ALY PLACE PROPERTIES INC. | BOUGAINVILLA, T.S. CRUZ SUBD, LAS PINAS CITY | 2025-04-24 | NEW | 173.68 | 24 | [14 empty] | 24 | X24020419372 | CITY GOVERNMENT OF LAS PINAS | MALUNGGAY, CAA CPD PH 3, LAS PINAS CITY | 2025-04-11 15:42 | 34.3458 | NEW | 440.682
|  | POWERHOUSE |  | 119.0386 | 25 | [6 empty] | 25 | [14 empty] | 25 | X25020460575 | LINAHEIM CORPORATE SERVICES, INC. | KAINGIN RD., KAINGIN, PARANAQUE | 2025-04-15 13:57 | 30.4187 | NEW | 103.6063
|  | VJC |  | #N/A | [7 empty] | 26 | [14 empty] | 26 | X25020681892 | HARD DISCOUNT PHILIPPINES, INC. | DAANG HARI, PERPETUAL VILLAGE, TAGUIG CITY | 2025-04-21 15:18 | 24.3625 | NEW | 11.2928
[12 empty] | 27 | [14 empty] | 27 | X25020573238 | REIGNWOOD DEVELOPMENT CORPORATION | BLOCK 1B, BENEDETTO RESIDENCES, LAS PINAS CITY | 2025-04-30 12:34 | 15.4764 | NEW | 38.2185
[27 empty] | 28 | X24051781334 | MARIA NATALIA ORIG PALMA | BELMONT, ALABANG 400 VILLAGE, MUNTINLUPA | 2024-11-25 08:38 | 171.6405 | MODIFICATION | 56.18
| AGEING | AVECO | [24 empty] | 29 | X24062388683 | MARC MEDALLA O'CONNOR | ARAGONA, CITADELLA EXEC VILL, LAS PINAS CITY | 2024-12-09 15:08 | 157.3694 | MODIFICATION | 4.2367
|  | CCBC |  | 0 | [22 empty] | 30 | X24114453678 | JENNIFER GALANG UY | KATARUNGAN VILLAGE, MUNTINLUPA | 2024-12-16 | 151 | MODIFICATION | 193.6015
|  | ECOM | [24 empty] | 31 | X24114563541 | MONOCRETE CONSTRUCTION PHILIPPINES, INC. | PRES. DIOSDADO MACAPAGAL, ASIAWORLD CITY, PARANAQUE | 2025-01-02 16:09 | 133.3271 | TERMINATION | 20.65
|  | POWERHOUSE |  | 2 | [22 empty] | 32 | R23771915 | SALITA, HERMIE | ST. MARK, PARKDALE II SUBD, BACOOR | 2025-02-13 14:03 | 91.4146 | RELOC | 52.9761
|  | VJC |  | 0 | [22 empty] | 33 | X25020514312 | CITY GOV'T OF LAS PIÑAS | PULO, SITIO PULO, LAS PINAS CITY | 2025-03-06 17:05 | 70.2882 | MODIFICATION | 10.4428
[27 empty] | 34 | X25030941835 | YIQUN YANG | MANILA DOCTOR VILL, ALMANZA I, LAS PINAS CITY | 2025-03-28 | 49 | TERMINATION | 89.25
| PCA COUNT | AVECO |  | 6
|  | CCBC |  | 13
|  | ECOM |  | 6
|  | POWERHOUSE |  | 22
|  | VJC |  | 0
Formulas:
WMTRL DATE = VLOOKUP([WO],'C1'!$E:$W,19,FALSE)

## VIP
VIP | SEGMENT | WO NO | DESCRIPTION | LOCATION | MUNICIPALITY | AREA OF RESPONSIBILITY | VENDOR REMARKS (free text) | C1 REMARKS (with or without issue) | CREW | EAM STATUS | SUPV | Vendor MHRS | TOTAL MHRS | APPLIED LOAD | TYPE | TOTAL PLANNED PROJECT COST | TOTAL ESTIMATED COST (SERVICES) | BILLED / PARTIALLY BILLED COST | % BILLED | DATE WMTRL | DATE SCHED | DATE RECEIVED BY VC | ACTUAL DATE COMPLETED ON SITE | DATE FCOMP | RELATED VIP | SITE STATUS | REMARKS (additional info/cause of delay)
Y | REL | R19617176 | OFFICE OF CONGRESSMAN STRIKE B. REVILLA, | GEN. EMILIO AGUINALDO, PANAPAAN VI, BACOOR | BACOOR CITY | DASMA | Job 3 for SSP/liveline, Job 4 with telco for email to FA, Job 5 for survey live line, Task 10 with issue on hukay, request assistance bacoor, job 7 for PAI sched; | W/ ISSUE | AVECO | SCHED | Ronilo Gange Jr. | 1133.2284 | 1795.22 | 0 | RELOC | 1921072.21 | 821316.27 | 0 | 0 | 2021-10-06 19:29 | 2021-10-12 | 2021-10-13 | 0 | 0 | LGU Mayor Strike Revilla | Pending | R/ Way Probelm
Y | CBG | R21631238 | CAVITEX INFRASTRUCTURE CORP. | N. ARMSTRONG, MOONWALK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | awaiting clearance from CAVITEX on completion of project, task 11 modification | W/ ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 382.9296 | 638.83 | 0 | PCA RELOC | 1414835.62 | 433240.12 | 0 | 0 | 2022-03-01 14:24 | 2022-03-03 12:33 | 2022-03-03 | 0 | 2025-06-10 | PMO
Y | CBG | R21662615 | FOOD TERMINAL, INC. | LANGKA, FTI CPD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | for completion May 2022 | W/O ISSUE | VJC | DPRG-PCR | Raeven De Quiroz | 102.0535 | #N/A | 0 | RELOC | 160444.02 | 92012.91 | 83552.45 | 0.90805 | 2022-04-22 07:47 | 2022-04-28 | 2022-04-27 | 0 | 0
Y | REL | R20609999 | CAVITEX INFRASTRUCTURE CORP. | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | PENDING MPTS | W/ ISSUE | ECOM | SCHED | Ronilo Gange Jr. | 717.716 | 1361.61 | 0 | RELOC | 1575766.41 | 923509.73 | 0 | 0 | 2022-04-26 13:29 | 2022-04-29 15:17 | 2022-04-29 | 0 | 0 | PMO | Pending | R/ Way Probelm Along C5 South Link
Y | HMB | X22052042329 | MARIA IMELDA BUYOC SANDWEG | JOY, DREAMLAND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | with issue, 1/11-with cash bond | W/ ISSUE | VJC | PCAN3 | Jemuel Peralta | 162.5766 | #N/A | 45 | MODIFICATION | 803861.8 | 139773.08 | 0 | 0 | 2022-08-23 11:15 | 2022-08-31 | 2022-08-31 | 0 | 0
Y | REL | R21135764 | CAVITEX INFRASTRUCTURE CORP. | MULTINATIONAL VILL, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for completion within October; on going digging, tasks 5 and 7(90 ft), 11; asking for assistance w/ MPTS | W/ ISSUE | ECOM | FCOMP | Ronilo Gange Jr. | 812.4623 | 1110.82 | 0 | RELOC | 2403133.25 | 809631.02 | 175011.86 | 0.21616 | 2022-09-07 07:53 | 2022-09-09 | 2022-09-12 | 2025-04-11 | 2025-04-22 | PMO | Pending
Y | CBG | X22031018462 | GLOBE TELECOM, INC. | BLOCK 13, BERNABE CPD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | with digging issue; w/ ROW issue (03-16-23); for digging (03-23-23); follow up to BC Pole location issue (with drainage) - resolved (with revised plan / new pole location and tapping point - revised last 05/16/2023) 09192023 ROW issue - MIDC and GLOBE has on-going negotiation for the neighbor's concent as per CRS TSE 11242023 ROW issue - waiting for update from Globe for the neighbor's concent as per TSE | W/ ISSUE | AVECO | CAN | Ronilo Gange Jr. | 76.2585 | #N/A | 23 | MODIFICATION | 359981.35 | 63350.41 | 0 | 0 | 2022-11-16 09:07 | 2022-11-21 | 2022-11-18 | 0 | CAN | CANCEL | CANCEL | CANCEL
Y | CBG | R21631694 | CAVITEX INFRASTRUCTURE CORP., | KAINGIN, STO. NIÑO, PARAÑAQUE | PARAÑAQUE CITY | PARAÑAQUE | ongoing (03-16-23); c/o MPTS | W/ ISSUE | ECOM | INPRG | Ronilo Gange Jr. | 1059.1652 | 1865.53 | 0 | RELOC | 3525946.4 | 1241706.01 | 0 | 0 | 2023-03-07 | 2023-03-08 | 2023-03-14 | 0 | 0 | PMO | On -Going / Pending | R/ Way Probelm Along C5 South Link
Y | HMB | R22633190 | CANDIE CHUA CO. | BLK 8, PALM COAST MARINA, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | For Sched September 26, 2023 survey/digging; pole location issue Update as of October 28. Issue on HOA and Customer not yet conduct meeting to resolve the issue | W/ ISSUE | ECOM | INPRG | Ronilo Gange Jr. | 85.5844 | 185.89 | 0 | RELOC | 258760.27 | 91241.75 | 0 | 0 | 2023-08-31 12:27 | 2023-09-05 | 2023-09-05 | 0 | 0 | Boss Tsops | Completed on-site | R/ Wau Problem / Hold by Customer for 5 timer already . Issue with HOA adn Customer Affected.
Y | BIZ | X24010310203 | HSL - BRAILLE COLLEGE, INC., | DURIAN, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 7/11/24 - Joint Survey; resolved pole location but need additional phase/leg; only one phase is existing - pending release of conjunctive project | (R) W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 193.1311 | 206.16 | 136 | MODIFICATION | 846143.09 | 155556.72 | 0 | 0 | 2024-06-03 17:23 | 2024-06-07 09:31 | 2024-06-04 | 0 | 2025-03-31 10:02 | Atty. Pamintuan thru Parañaque BC |  | Created new supplemetary WO for the modification of service drop (X24114538494)
Y | HMB | R23354122 | MANAHAN, MELANIE V., | SAPLUNGAN, MEADOWOOD EXEC. VILLAGE PHASE 3B, BACOOR | BACOOR CITY | DASMA | Hold Execution as per BC Mam Grace Alarcon due wrong polcaation as per developer | W/ ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 21.84 | 85.64 | 0 | RELOC | 114511.06 | 17587.5 | 0 | 0 | 2024-08-14 09:32 | 2024-08-20 08:32 | 2024-08-20 | 0 | 2025-05-22 | ERC /Terence Jay Gonzales (G3-Bacoor) | On -going/ Completion 2nd Week o May
Y | HMB | R22419641 | ONOFRE, CORAZON VILLA, | GLORIA DIAZ, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | For Schedule PAI :sadang:done digging and pole erection | Drainage Diversion | ECOM | FCOMP | Ronilo Gange Jr. | 153.4688 | 236.63 | 0 | RELOC | 418004.67 | 123585.18 | 0 | 0 | 2024-08-22 14:49 | 2024-08-30 13:25 | 2024-08-28 | 2025-07-31 | 2025-07-31 | Joe Zaldarriaga | For Schedule PAI | Drainage Diversion
Y | HMB | X24052000269 | CITY GOVERNMENT OF TAGUIG | MAULING CREEK, PUROK 6D, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | On Going Execution | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 831.7975 | 2323.61 | 45 | NEW | 3487719.57 | 668695.04 | 0 | 0 | 2024-08-30 16:13 | 2024-09-06 12:33 | 2024-09-04 | 0 | 2025-05-09 | LGU Congresman Adeng / Mayor Cayetano | On Going
Y | BIZ | X24072692499 | HSL - BRAILLE COLLEGE, INC., | DURIAN, ZONE 1, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | pole location / with existing drainage | W/ ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 550.2171 | 550.22 | 136 | MODIFICATION | 2501537.66 | 443077.47 | 0 | 0 | 2024-09-11 10:50 | 2024-09-16 14:35 | 2024-09-13 | 0 | 2025-03-31 10:12 | Cong. Sonny Lagon | Scheduled for pole digging 1st week of December 2024 | Conducted a rejoint survey for bunot tayo operations on tasks 18 and 19; Assigned crew diverted to NAIA Reliability Wos
Y | HMB | X24020641632 | HENRY LAO LIM | BUKIDNON, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | FOLLOW UP FROM ATTY KIM HENARES | W/O ISSUE | POWERHOUSE | FCOMP | Jenneth Madrid | 224.0142 | 224.01 | 169 | NEW | 1042085.27 | 180394.18 | 0 | 0 | 2024-09-18 16:38 | 2024-09-24 14:23 | 2024-09-20 | 2025-01-20 | 2025-01-20 | Boss Joey Alonzo thru boss Jojit Galan
Y | HMB | X22125062389 | SONNY L LAGON | ACACIA, MULTINATIONAL VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | for completion 2nd week of Nov | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 428.8492 | 49.95 | 200 | NEW | 1862458.44 | 345375.27 | 0 | 0 | 2024-09-26 11:26 | 2024-10-01 09:31 | 2024-09-28 | 0 | 2025-01-10 | Paranaque BC - Ron Bernardo
Y | HMB | X24083444242 | JEIKA PROPERTIES CORPORATION | BLOCK 6, KATHLEEN PLACE 5 SUBD, BACOOR | BACOOR CITY | DASMA | for scheduling | W/O ISSUE | CHALLENGER | FCOMP | Isan Carlo Lazaro | 1773.3821 | 1716.66 | 348 | NEW | 8506182.51 | 1428065.65 | 0 | 0 | 2024-10-10 10:11 | 2024-10-17 12:32 | 2024-10-16 | 0 | 2025-02-06 | Boss Joey Alonzo
Y | HMB | X24073033797 | CELSO T DIMARUCUT | DOÑA CONCHA CRUZ, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | VIP, PRESIDENT & CEO OF ROXAS HOLDING. MVP GROUP | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 47.4355 | 47.44 | 80 | MODIFICATION | 392547.56 | 38222.75 | 0 | 0 | 2024-10-22 17:03 | 2024-10-28 15:06 | 2024-10-28 | 0 | 2025-01-11 | Joe R. Zaldarriaga
Y | HMB | X24083323243 | NICOLE TRINIDAD LOTILLA | DAFFODIL, PILAR VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | with follow up from Raul Reyes of Corp Com | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 196.5603 | 431.23 | 42.36 | MODIFICATION | 807326.91 | 158286.09 | 0 | 0 | 2024-11-04 15:21 | 2024-11-11 14:56 | 2024-11-06 | 2025-03-03 | 2025-03-05 | Former staff and consultant of MVP | Scheduled for pole digging 1st week of December 2024
Y | HMB | X24083277607 | JONATHAN KEE AGABIN | SAMAR, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | FOLLOW UP FROM ATTY KIM HENARES | W/O ISSUE | VJC | FCOMP | Jenneth Madrid | 81.7376 | 160.02 | 80 | NEW | 454689.41 | 65090.91 | 0 | 0 | 2024-11-08 16:13 | 2024-11-13 14:55 | 2024-11-12 | 0 | 2025-01-14 | Boss Dion Cruz
Y | HMB | X24072802372 | JOSE MARTIN GRUBA NOEL | QUINTIN PAREDES, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | VIP, OWNER IS RET. GENERAL MANNY IDQUIVAL | For Schedule of Digging 1/8/2024 | ECOM | FCOMP | Ronilo Gange Jr. | 119.9787 | 120.71 | 86 | MODIFICATION | 588535.37 | 96616.31 | 26531.14 | 0.2746 | 2024-11-08 16:14 | 2024-11-13 14:53 | 2024-11-21 | 2025-01-10 | 2025-01-11 | ROLA | Completed
Y | HMB | R23611939 | DPWH DEO LAS PINAS-MUNTI, | MARCOS ALVAREZ, TALON V, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Done pole erection retirement nalang po ng poste hindi po maretire ang poste kasi may gumagawa po ng kalsada | 0 | POWERHOUSE | SCHED | Isan Carlo Lazaro | 80.4941 | 158.78 | 0 | RELOC | 246953.97 | 64820.26 | 0 | 0 | 2024-11-14 16:10 | 2024-11-20 10:02 | 2024-11-20 | 0 | 0 | John Y. Salamero, former LP Officer | For referral to UAM to proceed with pole retirement | ROW issues
Y | HMB | X23020656225 | JENNIFER AUSTRIA BARZAGA | LAUAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | SSP Dec 26 | W/O ISSUE | CHALLENGER | FCOMP | Jemuel Peralta | 421.59 | 813 | 127.5 | NEW | 1822047.68 | 338008.24 | 0 | 0 | 2024-11-15 | 2024-11-25 | 2024-12-05 | 0 | 2025-01-02 | Boss Benjie Cusi
Y | BIZ | X24020649090 | MICHAEL CHRISTIAN R. PICHEL | M.L. QUEZON, PUROK 3, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | Completed, for re-trigger of PO and route to FCOMP | 0 | VJC | TECO | Jenneth Madrid | 68.0405 | 339.78 | 49 | NEW | 525931.28 | 54791.3 | 138590.65 | 2.5294 | 2024-11-22 15:22 | 2024-11-28 08:28 | 2024-11-27 | 2025-01-12 | 2025-01-12 | Boss FJS
Y | BIZ | X24062171822 | M.H. BURTON REPAIR SERVICES, INC. | BLOCK 5, MAGDIWANG SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 240.5183 | 240.52 | 120 | NEW | 1126618.35 | 193724.47 | 0 | 0 | 2024-11-22 15:24 | 2024-11-28 08:31 | 2024-11-27 | 0 | 2025-03-26 | BIZ Partners
Y | HMB | X24093863040 | AIRA NAVARRO JUBILADO | A. MABINI, TUAZON SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | Pending problem with R/Way | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 113.706 | 347.15 | 20 | NEW | 622295.41 | 91565.09 | 0 | 0 | 2024-11-29 09:41 | 2024-12-04 09:44 | 2024-12-03 | 0 | 2025-06-24 | Noel Dizon | Pending | Hold by a 3rd party at Task 2 as Vendor initiate Pole erection * Already Coordinate with LAs Pinas Business Center -Sir Robbie 5/13/25
Y | HMB | X24093725089 | RUBEN LEYVA TERRADO | PILAR, ST. JOSEPH SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 167.3971 | 167.4 | 131.5 | NEW | 833252.11 | 134801.61 | 0 | 0 | 2024-12-06 12:56 | 2024-12-12 10:48 | 2024-12-17 | 0 | 2025-01-11 | Boss RoLA
Y | BIZ | X24103956559 | LILY REAL ESTATE DEVELOPMENT CORPORATION | QUIRINO, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | W/O ISSUE | AVECO | FCOMP | Ronilo Gange Jr. | 187.6016 | 228.97 | 395 | NEW | 1391926.53 | 151199.6 | 0 | 0 | 2024-12-11 13:24 | 2024-12-16 14:14 | 2024-12-17 | 2025-04-04 | 2025-04-04 | Taguig LGU thru Taguig BC | Completed
Y | BIZ | X24104044893 | SONAK HOLDINGS CORPORATION | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 55.05 | 55.05 | 177 | NEW | 141821.41 | 44330.4 | 4026.35 | 0.090826 | 2024-12-11 14:30 | 2024-12-13 09:47 | 2024-12-16 | 2025-03-19 | 2025-03-19 09:27 | COM Sison -office of Corp Comm. | Completed
Y | HMB | X24124692677 | CITY GOVERNMENT OF BACOOR | MOLINO HOMES I SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 299.6567 | 447.14 | 250 | NEW | 1901958.33 | 354962.15 | 0 | 0 | 2024-12-26 12:54 | 2025-01-03 12:26 | 2025-01-02 | 0 | 2025-03-12 14:39 | Boss FJS
Y | HMB | X24093778968 | CITY GOVERNMENT OF TAGUIG | M.L. QUEZON, LOWER BICUTAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 296.2991 | 1116.82 | 73 | NEW | 2732739.46 | 648325.44 | 0 | 0 | 2025-01-08 16:28 | 2025-01-14 14:50 | 2025-01-10 | 0 | 2025-02-25 | Villar Group
Y | HMB | X24124906791 | VILLA LIGHT NEIGHBORHOOD ASSOCIATION INC. | BLOCK 10, VILLA LIGHT SUBD, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 459.0968 | 3541.54 | 225 | NEW | 4039465.57 | 439590.53 | 0 | 0 | 2025-01-17 14:32 | 2025-01-27 14:02 | 2025-01-21 | 0 | 2025-06-28 | Taguig BC | On-going construction | Sevaral locations with diverson of water pipes
Y | CBG | X25010079615 | CMSTAR MANAGEMENT INC. | DAANG-HARI RD., MOLINO IV, BACOOR | BACOOR CITY | DASMA | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 1155.0618 | 1160.74 | 45 | NEW | 3660384.15 | 992062.56 | 0 | 0 | 2025-01-17 15:21 | 2025-01-23 12:32 | 2025-01-21 | 0 | 2025-03-10 | Boss Choi/Boss Dion
Y | CBG | R23797676 | CAVITEX INFRASTRUCTURE CORP., | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 123.7648 | 196.43 | 0 | RELOC | 584843.86 | 158179.17 | 62538.81 | 0.39537 | 2025-01-20 09:07 | 2025-01-21 12:18 | 2025-01-21 | 2025-03-13 | 2025-03-17 08:43 | Obet Galang | Completed
Y | BIZ | X25010119305 | VICENTE P PEREZ | EL GRANDE, BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 33.4983 | 33.5 | 35 | NEW | 241637.84 | 26975.31 | 6007.35 | 0.2227 | 2025-01-22 17:00 | 2025-01-28 08:26 | 2025-01-24 | 2025-03-04 04:21 | 2025-03-04 | Boss Erwin
Y | BIZ | X24093766158 | ALFAMART TRADING PHILIPPINES, INC. | QUEEN'S MAIN, QUEEN'S ROW AREA A SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 36.5195 | 39.53 | 28 | NEW | 281351.55 | 33962.66 | 0 | 0 | 2025-01-24 14:08 | 2025-01-31 15:08 | 2025-01-30 | 0 | 2025-03-31 | Boss Erwin
Y | BIZ | X24072540238 | HARD DISCOUNT PHILIPPINES, INC. | GOV. P.F. ESPIRITU, PANAPAAN II, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 9.9328 | 13.29 | 20 | NEW | 145240.66 | 11416.91 | 0 | 0 | 2025-01-27 12:16 | 2025-02-03 | 2025-01-30 | 2025-04-29 | 2025-04-30 | EOC/BIZ | Completed
Y | BIZ | X25010059547 | ALFAMETRO MARKETING INC. (CORCUERRA - BANNER 4TH ESTATE) | BANNER, 4TH ESTATE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | TECO | Isan Carlo Lazaro | 10.8028 | 19.97 | 31 | NEW | 202246.77 | 17159.97 | 0 | 0 | 2025-01-28 15:26 | 2025-02-03 13:38 | 2025-01-31 | 2025-03-04 04:21 | 2025-03-04 | Ma'am Cecilia Domingo thru Boss RRA and Boss EOC
Y | BIZ | X24093683073 | ELECTRO-SYSTEMS INDUSTRIES CORPORATION | BAES, PERPETUAL VILLAGE, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 214.8948 | 257.28 | 42 | MODIFICATION | 589728.55 | 173057.12 | 96239.21 | 0.55611 | 2025-01-31 | 2025-02-05 08:13 | 2025-02-04 | 0 | 2025-02-27 | ROLA
Y | BIZ | X25010120302 | CDC REALTY INC. | DOVE LOFTS, LION'S PARK RESIDENCES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | with follow up from Ma'am Cecille, Head Enterprise & National Government | VJC | FCOMP | Jenneth Madrid | 70.6731 | 120.1 | 193 | NEW | 813015.11 | 97030.13 | 47759.31 | 0.49221 | 2025-02-06 13:14 | 2025-02-12 10:32 | 2025-02-10 | 2025-03-03 | 2025-03-03 | Boss Dion Cruz
Y | BIZ | X24030689569 | PILIPINAS SHELL PETROLEUM CORPORATION | SAMPAGUITA, CAMP SAMPAGUITA, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | AVECO | TECO | Ronilo Gange Jr. | 666.3304 | 2874.93 | 78 | NEW | 3575972.05 | 828522.98 | 1303521.46 | 1.5733 | 2025-02-08 20:10 | 2025-02-11 12:55 | 2025-02-21 | 2025-02-26 | 2025-02-26 | PMO | Completed
Y | CBG | X24124769477 | CMSTAR MANAGEMENT INC. | DAANG-HARI RD., MOLINO IV, BACOOR | BACOOR CITY | DASMA | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 18.5428 | 24.46 | 45 | NEW | 364258.38 | 21017.78 | 0 | 0 | 2025-02-11 13:39 | 2025-02-18 14:45 | 2025-02-17 | 0 | 2025-03-11 07:21 | Boss Choi/Boss Dion
Y | BIZ | X24093492216 | ALFAMART TRADING PHILIPPINES, INC. | SUMMIT CIRCLE SUBD, SUMMIT CIRCLE SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 9.9328 | 13.04 | 28 | NEW | 186146.6 | 11202.05 | 0 | 0 | 2025-02-18 16:09 | 2025-02-24 09:23 | 2025-02-21 | 2025-03-04 04:21 | 2025-03-04 | Boss Erwin
Y | HMB | X24010064473 | ALEXANDER SANTOS ISIP | LANCASTER, HILLSBOROUGH SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 38.0585 | 48.2 | 110 | MODIFICATION | 391390.73 | 41443.2 | 0 | 0 | 2025-02-18 16:27 | 2025-02-24 07:05 | 2025-02-21 | 0 | 2025-03-25 08:10 | Rocky D. Bacani
Y | HMB | X25010176215 | MARY GRACE MESINA MANDAP | BASILIO ESTANISLAO, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 119.7629 | 308.41 | 33 | NEW | 601808.84 | 130472.59 | 0 | 0 | 2025-02-18 17:43 | 2025-02-24 10:39 | 2025-02-21 | 0 | 2025-07-26 | Carlo Topacio | Pending | Work load
Y | CBG | R23926303 | CAVITEX INFRASTRUCTURE CORP., CBG | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 365.078 | 633.77 | 0 | RELOC | 1683427.63 | 498912.29 | 0 | 0 | 2025-02-19 08:19 | 2025-02-25 12:43 | 2025-02-21 | 0 | 2025-03-20 | Boss Choi | Digging CompletEe
Y | CBG | R23926307 | CAVITEX INFRASTRUCTURE CORP., CBG | KAINGIN RD., KAINGIN, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 79.5357 | 202.88 | 0 | RELOC | 216676.78 | 173073.31 | 0 | 0 | 2025-02-19 08:25 | 2025-02-25 12:44 | 2025-02-21 | 0 | 2025-04-04 | Boss Choi | Completed
Y | BIZ | X25010136657 | COFFEE MASTERS, INC. | MOLINO BLVD, MOLINO III, BACOOR | BACOOR CITY | DASMA | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 15.6428 | 48.36 | 142 | NEW | 472661.66 | 41560.12 | 0 | 0 | 2025-02-24 16:50 | 2025-03-01 04:21 | 2025-02-28 | 2025-03-04 04:21 | 2025-03-04 | Boss Erwin
Y | HMB | X25010341636 | TERESITA G MANAHAN | BOEING, CONCORDE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | sadang:Pag uusapan padaw sa clubhouse mam Jen, puro usap na Sila haha! Extension of facilities na to sa Dami ng hukay ,Good am Po, hndi pa Po nahuhukay yong gustong location ni customer, approval pa Po sa HOA…Hndi pa boss, hndi ko pa Po alam kung nag ka sundo na sa club house pra sa final relocation ng transformer pole.. pahuhukayan ko sana | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 51.0195 | 75.67 | 80 | NEW | 439221.4 | 65045.18 | 0 | 0 | 2025-02-25 17:05 | 2025-03-11 08:05 | 2025-02-28 | 0 | 2025-04-24 | Boss Pao Cruz | Completed
Y | CBG | X24093485695 | POSH PROPERTIES DEVELOPMENT CORPORATION | BELLE, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | VJC | TECO | Jenneth Madrid | 35.6185 | 72 | 1062 | NEW | 149903.73 | 41002.37 | 0 | 0 | 2025-03-10 16:59 | 2025-03-17 08:24 | 2025-03-12 | 2025-04-12 | 2025-04-12 | Ma'am Bernice Rama |  | Pending work permit from ABPEA
Y | BIZ | X24114614743 | PTR PREMIER HOLDINGS INC. | ST. JOSEPH, ST. JOSEPH SUBD, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 42.4455 | 134.28 | 77 | NEW | 395516.39 | 48111.19 | 0 | 0 | 2025-03-20 15:14 | 2025-03-28 10:34 | 2025-03-26 | 2025-06-11 | 2025-06-11 | Kim Verlie/Mike Agbay | Completed
Y | HMB | X25020466847 | NADINE G ABELA | LUZON, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | For execution 3/26/25 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 13.1828 | 29.57 | 46 | MODIFICATION | 222665.25 | 25003.23 | 0 | 0 | 2025-03-25 11:06 | 2025-03-25 12:32 | 2025-03-26 | 0 | 2025-04-04 | Boss Erwin
Y | HMB | X25010329960 | RODRIGO SANGALANG LA TORRE | TOPAZ, SEVERINA DIAMOND SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 36.03 | 63.43 | 66 | NEW | 359972.84 | 54526.82 | 0 | 0 | 2025-03-25 23:02 | 2025-03-28 10:51 | 2025-03-28 | 0 | 2025-04-22 | Boss Jerry Lao | Completed
Y | HMB | X25010249951 | ALEX JUSTINIANO CLAVERIA | SANTIAGO LOOP, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 56.1126 | 69.62 | 110 | NEW | 417348.14 | 59036.1 | 0 | 0 | 2025-03-26 10:00 | 2025-03-28 10:46 | 2025-03-27 | 0 | 2025-04-15 14:12 | Anthony Almeda, NGCP President
Y | HMB | X24083316199 | ADEL MUNDAN BALOGO | SAUDI ARABIA, BETTER LIVING SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | VJC | COMP | Jenneth Madrid | 37.9685 | 138.31 | 60 | NEW | 391146.94 | 43717.18 | 0 | 0 | 2025-03-26 16:23 | 2025-03-31 12:32 | 2025-03-28 | 0 | 2025-04-29 | George Salinas
Y | BIZ | X24062169287 | ALFAMART TRADING PHILIPPINES, INC. | MADRID, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 10.9328 | 34.7 | 28 | NEW | 229386.46 | 29815.7 | 0 | 0 | 2025-03-27 12:42 | 2025-04-03 14:52 | 2025-03-28 | 2025-04-29 | 2025-04-30 | Boss Obet Galang | Completed
Y | BIZ | X25010350650 | ICE & WATER STOP, INC. | SAN ANTONIO VALLEY 1, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 120.88 | 225.66 | 456 | MODIFICATION | 1392661.74 | 194181.44 | 0 | 0 | 2025-03-28 | 2025-04-02 10:21 | 2025-04-01 | 0 | 2025-04-16 09:45 | Boss Obet Galang
Y | BIZ | X25010222514 | PHILIPPINE SEVEN CORPORATION | MAHOGANY, VICTORIA HOMES-PEARL HTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 11.6428 | 24.54 | 38 | NEW | 216246.34 | 21087.55 | 0 | 0 | 2025-03-31 14:45 | 2025-04-10 06:41 | 2025-04-04 | 0 | 2025-04-14 | Boss Jonald Sampol
Y | BIZ | X25020551884 | VAS SOLUTIONS INC. | PHASE 2 ACCESS ROAD, AMVEL COMMERCIAL COMPLEX, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | POWERHOUSE | FCOMP | Jenneth Madrid | 14.3228 | 32.8 | 42 | NEW | 364286.5 | 28180.26 | 0 | 0 | 2025-04-02 12:59 | 2025-04-08 15:50 | 2025-04-04 | 0 | 2025-05-12 09:03 | Roberto Galang | Pending approval of schedule | Road access problem
Y | HMB | X25030992057 | ANTONITA MOYNIHAN DAYRIT | YELLOW STONE, SOUTH GREEN PARK SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 160.5779 | 440.47 | 85 | NEW | 873159.92 | 175896.21 | 0 | 0 | 2025-04-03 23:29 | 2025-04-08 17:36 | 2025-04-10 | 0 | 2025-04-30 | Paranaque BC - Ron Bernardo; from Maritoni Fernandez
Y | CBG | X24104075973 | TOTAL GAMEZONE XTREME INCORPORATED | WEST SERVICE, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 83.7633 | 133.31 | 2530 | MODIFICATION | 1070121.16 | 112876.91 | 0 | 0 | 2025-04-04 15:13 | 2025-04-04 15:13 | 2025-04-08 | 0 | 2025-04-11 | Ma'am Bernice Rama
Y | HMB | X25030863021 | S3A UNITED INC. | PACIFIC AVE, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 14.3728 | 50.27 | 133.5 | NEW | 395842.01 | 43192.67 | 0 | 0 | 2025-04-04 17:54 | 2025-04-14 | 2025-04-10 | 2025-05-05 | 2025-05-05 | Doy Yang of EGIP | Completed
Y | HMB | X25030881259 | HEIDELBERG BORJA CRUZ | HERRERA ST., TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 77.1231 | 169.2 | 15 | NEW | 375527.67 | 77719.68 | 0 | 0 | 2025-04-07 09:18 | 2025-04-15 13:00 | 2025-04-10 | 0 | 2025-06-28 | Bacoor BC Head, TJ Gonzales | Pending | Work load
Y | HMB | X25030992093 | MARCO ANGELO FELIX LIM LOPEZ | YELLOW STONE, SOUTH GREEN PARK SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 1.73 | 4.31 | 31 | MODIFICATION | 20761.28 | 3703.32 | 0 | 0 | 2025-04-07 13:43 | 2025-04-08 17:38 | 2025-04-10 | 0 | 2025-04-30 | Paranaque BC - Ron Bernardo; from Chief Justice Mario Lopez
Y | HMB | X25030752071 | MICHAEL G. DAVID | BLOCK 7, DOÑA ROSARIO HEIGHTS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 100.0143 | 141.59 | 60 | MODIFICATION | 555158.87 | 129417.11 | 0 | 0 | 2025-04-10 16:48 | 2025-04-15 13:15 | 2025-04-15 | 2025-06-13 | 2025-06-13 | Boss Rensy Robles | Energization 6/10/2025
Y | HMB | X25030872408 | CITY GOVERNMENT OF TAGUIG | BLOCK 27, PINAGSAMA PH 2 VILL, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 53.5395 | 164.6 | 173 | NEW | 840107.52 | 73792.22 | 48164.88 | 0.65271 | 2025-04-11 07:43 | 2025-04-18 11:00 | 2025-04-19 | 2025-04-28 | 2025-04-28 10:46 | Boss FOG
Y | HMB | X25030884434 | RONALD CARANAY CALINGAY | GREEN GRASS, GREEN VALLEY SUBD SECT A, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 18.3928 | 20.28 | 2 | NEW | 197328.6 | 60293.5 | 0 | 0 | 2025-04-14 10:38 | 2025-04-23 14:42 | 2025-04-24 | 0 | 2025-05-22 | Joe Zaldarriaga
Y | BIZ | X25010118641 | HIJO GREENS, INC. | EDISON, EDISON INDUSTRIAL COMPLEX, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 80.9174 | 216.64 | 183 | NEW | 911302.13 | 118917.61 | 0 | 0 | 2025-04-15 10:51 | 2025-04-23 14:45 | 2025-04-24 | 0 | 2025-05-16 | Boss RoLA and Boss FJS | On Going / Schedule on May 10-11 | Approval of Permit of Brgy mobilzation the will for possible of road obtruction /road Closure
Y | HMB | X25031019727 | CITY GOVERNMENT OF TAGUIG | CHAMPACA, STO. NINO, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 171.3066 | 415.57 | 896 | NEW | 2903581.15 | 323053.56 | 0 | 0 | 2025-04-21 15:58 | 2025-04-22 06:55 | 2025-04-23 | 2025-04-28 | 2025-04-28 10:39 | Boss FOG
Y | HMB | X25010318160 | METRO SOUTH PROPERTIES CORPORATION | RAVENGA, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 236.4671 | 712.49 | 100 | NEW | 1276315.37 | 275877.53 | 0 | 0 | 2025-04-22 13:18 | 2025-04-28 14:49 | 2025-04-28 14:44 | 0 | 2025-07-10 | Bacoor BC Head, TJ Gonzales | Pending | Work load
Y | BIZ | X23031056287 | ALFAMART TRADING PHILIPPINES, INC | GEN. TIRONA, MABOLO I, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 48.5935 | 131.89 | 28 | NEW | 293996.61 | 46063.97 | 0 | 0 | 2025-04-22 16:44 | 2025-04-30 13:02 | 2025-05-02 | 0 | 2025-05-24 | Roberto Galang | On going Excution
Y | BIZ | X25030864022 | RAHUL DAVE DARYANI | E. RODRIGUEZ JR., STO. NINO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | VJC | COMP | Jenneth Madrid | 33.928 | 70.21 | 135 | NEW | 736986.61 | 60355.24 | 31342.96 | 0.51931 | 2025-04-24 16:09 | 2025-04-30 13:34 | 2025-05-02 | 2025-06-19 | 2025-06-19 | Boss Jason Calsas | SSP schedule on June 18 | with scheduled PAI
Y | HMB | X25010021411 | FRANCES CHRISTINE RAMIREZ AGUIRRE | DAO, MAYWOOD VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 135.691 | 159.18 | 64 | MODIFICATION | 813670.22 | 136773.92 | 0 | 0 | 2025-04-28 15:59 | 2025-05-06 13:08 | 2025-05-06 | 2025-06-03 | 2025-06-03 | Boss Erville
Y | BIZ | X25020687798 | TWIN KARAT REALTY CORPORATION | QUIRINO, SAN DIONISIO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | POLE DRESSING | 0 | AVECO | SCHED | Ronilo Gange Jr. | 117.5349 | 275.3 | 526 | NEW | 1305014.67 | 219118.06 | 0 | 0 | 2025-04-28 16:01 | 2025-05-06 13:10 | 2025-05-06 | 0 | 0 | Betty Sy
Y | HMB | X25041129915 | ROSE ANNE A. AGUIRRE | C. PALANCA SR., BF HOMES, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 115.2395 | 387.15 | 42 | MODIFICATION | 733089.1 | 131663.28 | 0 | 0 | 2025-04-29 16:12 | 2025-05-06 13:13 | 2025-05-06 | 0 | 2025-07-04 | Wife of Mulanay Quezon Mayor Aris Aguirre, Son of DOJ Sec. Aguirre III | For execution on June 12 | Work load concern
Y | HMB | X25041129547 | S3A UNTIED INC. | PACIFIC AVE, MARINA SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 7.61 | 15.61 | - | TERMINATION | 23102.58 | 13412.51 | 0 | 0 | 2025-04-30 08:20 | 2025-04-14 | 2025-05-06 | 2025-05-05 | 2025-05-05 | Doy Yang of EGIP
Y | BIZ | X25041173300 | ALBERT TIONGSON LORENZO | BACOOR, MAMBOG IV, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 43.4047 | 85.69 | 25 | NEW | 479294.17 | 73631.56 | 0 | 0 | 2025-04-30 08:47 | 2025-05-06 13:17 | 2025-05-06 | 0 | 2025-05-27 | Mr. Mark Richmund De Leon, Executive from MPTC
y | BIZ | X24104298635 | ANKONG HOLDINGS, INC. | JAIME, AIRPORT VILL, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | POLE ERECTION & DRESSING 8-6-25 | 0 | AVECO | SCHED | Ronilo Gange Jr. | 717.2996 | 883.64 | 358 | NEW | 2507240.06 | 774008.21 | 0 | 0 | 2025-04-30 18:17 | 2025-05-06 13:22 | 2025-05-06 | 0 | 0 | Boss Ferdie Geluz | On -Going / Pending | Problem with Task 20 with Underground Facilites fro Customer Side (Resolve as of 7-18-25)
Y | BIZ | X25030757040 | AMBICA INTERNATIONAL CORPORATION | MERVILLE ACCESS, KALAYAAN VILL/BALAGBAG, PASAY CITY | PASAY CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 153.192 | 402.96 | 378.94 | MODIFICATION | 1682589.76 | 212028.41 | 0 | 0 | 2025-05-02 16:44 | 2025-05-09 14:42 | 2025-05-09 | 0 | 2025-05-28 10:13 | Roberto Galang | For Energization July 2, 2025
Y | HMB | X25010252654 | ENRIQUE JOSE NUGUID LIM | BURGOS, TOWN AND COUNTRY WEST SUBD, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 160.3052 | 451.25 | 25 | NEW | 802915.53 | 185129.56 | 0 | 0 | 2025-05-05 14:49 | 2025-05-14 12:28 | 2025-05-14 | 0 | 2025-07-04 | Bacoor BC Head, TJ Gonzales
Y | BIZ | X25020524644 | TIERRA BELLA PROPERTIES INC. | PRES. M. ROXAS, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 27.5028 | 53.43 | 131 | NEW | 676674.86 | 45931.94 | 0 | 0 | 2025-05-05 14:52 | 2025-05-07 13:20 | 2025-05-08 | 2025-05-15 | 2025-05-15 | Bernard Castro
Y | BIZ | X25020630582 | TIERRA BELLA PROPERTIES INC. | PRES. M. ROXAS, TAMBO, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 79.0485 | 172.85 | 131 | NEW | 482774.42 | 148527.48 | 0 | 0 | 2025-05-05 14:54 | 2025-05-07 13:21 | 2025-05-08 | 2025-05-15 | 2025-05-15 | Bernard Castro
Y | CBG | X25020582768 | MIESCOR INFRASTRUCTURE DEVELOPMENT CORPORATION | BAGONG SILANG INTERIOR, QUEEN'S ROW EAST , BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 18.6528 | 31.3 | 31 | NEW | 263217.11 | 26892.84 | 0 | 0 | 2025-05-06 09:31 | 2025-05-07 13:22 | 2025-05-08 | 0 | 2025-05-22 | Boss Choi
Y | BIZ | X25020415616 | SOUTH METRO ICE PLANT CORP. | NATIONAL, TUNASAN, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 64.2368 | 141.79 | 280 | NEW | 955389.18 | 104026.12 | 0 | 0 | 2025-05-06 14:09 | 2025-05-09 14:24 | 2025-05-09 | 0 | 2025-06-21 | Boss FOG and Administrator of Muntinlupa LGU
Y | BIZ | X25030926983 | PANCITERIA LIDO CHINESE CUISINE CORP. | MOLINO BLVD., MAMBOG IV, BACOOR | BACOOR CITY | DASMA | 0 | 0 | AVECO | FCOMP | Ronilo Gange Jr. | 111.5933 | 340.66 | 106 | NEW | 961200.12 | 158218.3 | 0 | 0 | 2025-05-09 17:23 | 2025-05-12 13:28 | 2025-05-13 | 0 | 2025-05-22 | Chi Padua
Y | HMB | X25010310869 | CAT COMICS LAND INC. | ROSE OF HEAVEN, TALON VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 93.2287 | 122.65 | 78 | NEW | 585320.96 | 105380.41 | 0 | 0 | 2025-05-13 13:02 | 2025-05-21 13:14 | 2025-05-23 | 2025-06-13 | 2025-06-13 | Gerald San Pedro
Y | BIZ | X25030779048 | A R B CONSTRUCTION COMPANY, INC. | BLOCK 3, SOLDIERS HILLS SUBD, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 86.9895 | 138.92 | 150 | NEW | 962706.76 | 118986.45 | 0 | 0 | 2025-05-15 10:20 | 2025-05-16 15:23 | 2025-05-19 | 0 | 2025-05-31 | Robinsons and Ms. Robina Gokongwei-Pe
Y | HMB | X25030814571 | JOSE MARIA IBANEZ LANZA | NORTH 5TH, ANGELA VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | POWERHOUSE | FCOMP | Isan Carlo Lazaro | 99.4145 | 273.55 | 0 | MODIFICATION | 499907.06 | 100520.98 | 0 | 0 | 2025-05-26 17:07 | 2025-05-28 10:20 | 2025-05-29 | 2025-07-09 | 2025-07-09 | Ma'am Lani Anastacio and Rocky Bacani
Y | HMB | X25041423325 | MARIFE PIMENTEL PASCUAL | PANAMUCAN, AYALA-ALABANG VILL, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | MAINTENANCE | FCOMP | Junilo Michael Flores | 45.608 | 135.13 | 80 | MODIFICATION | 402109.55 | 48869.9 | 0 | 0 | 2025-05-28 10:38 | 2025-06-11 15:30 | 2025-06-12 | 0 | 2025-06-26 | Paolo Cruz | Hold last June 28 fpor Re-schedule on July 11
Y | BIZ | X25041379488 | PACIFIC RESOURCES CORPORATION | MARCOS ALVAREZ, TALON I, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 11.53 | 114.42 | 224 | MODIFICATION | 269699.65 | 98338.36 | 0 | 0 | 2025-06-04 09:10 | 2025-06-17 13:32 | 2025-06-18 | 0 | 2025-07-07 | Boss Jerry Lao
Y | HMB | X25041438549 | ROSELLER SYGENCO PIERAZ | MAHARLIKA, MARCELO GREEN VILL 5, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | C2 | TECO | Ian Patrick Perez | 31.58 | 31.58 | 76 | NEW | 228445.28 | 0 | 0 | #DIV/0! | 2025-06-05 10:55 | 2025-06-11 15:41 | N/A | 0 | 2025-06-22 | Carlo Topacio
Y | CBG | X24020419527 | D.M. WENCESLAO & ASSOCIATES, INC., | BRADCO, ASEANA BUSINESS PARK, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 793.1437 | 1598.32 | 182 | NEW | 3728690.42 | 1032941.7 | 0 | 0 | 2025-06-09 16:54 | 2025-06-17 10:52 | 2025-06-18 | 0 | 2025-07-17 | Related to ASEANA Substation permit approval; Ma'am Bernice
Y | BIZ | X25061977034 | ROVIE BUGAYONG GABIOLA | BF CARNIBAL PARK, BF RESORT VILL, LAS PINAS CITY | LAS PIÑAS CITY | PARAÑAQUE | 0 | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 59.72 | 138 | 18 | NEW | 326798.64 | 0 | 0 | #DIV/0! | 2025-06-19 13:07 | 2025-06-25 10:07 | 2025-07-02 | 0 | 2025-07-07 | BIZ Partners: with escalation from the Office of the President and ERC
Y | HMB | X25041097966 | ROMAN CATHOLIC BISHOP OF PARANAQUE | BARCELONA, MERVILLE SUBD, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | done digging, for pole erection :Scope of Work:Reorient Cut out Transformer /Energize 2-75KVA | 0 | ECOM | FCOMP | Ronilo Gange Jr. | 118.409 | 337.98 | 97 | MODIFICATION | 886605.55 | 155081.7 | 0 | 0 | 2025-06-19 16:24 | 2025-06-20 13:10 | 2025-06-25 | 0 | 2025-06-26 | Boss RoLA
Y | BIZ | X25020684097 | MANILA PRIME LAND HOLDINGS, INC. | GEN EMILIO AGUINALDO, CAMELLA HOMES PH II-A, BACOOR | BACOOR CITY | DASMA | aug 7 nag start ng digging | 0 | ECOM | SCHED | Ronilo Gange Jr. | 99.71 | 177.99 | 236 | NEW | 878759.98 | 85697.14 | 0 | 0 | 2025-07-02 13:01 | 2025-07-08 13:56 | 2025-07-09 | 0 | 0 | Mam Chi
Y | BIZ | X25051795984 | CAFEFRANCE CORP. | GEN. EMILIO AGUINALDO, CAMELLA HOMES PH II-A, BACOOR | BACOOR CITY | DASMA | aug 7 nag start ng digging | 0 | ECOM | SCHED | Ronilo Gange Jr. | 3.32 | 3.32 | 86 | NEW | 14987.51 | 0 | 0 | #DIV/0! | 2025-07-02 16:22 | 2025-07-08 13:57 | 2025-07-09 | 0 | 0
Y | BIZ | X25062023744 | YDLAZAVON PANCIT HABHAB, INC. | SAN ANTONIO, SAN ANTONIO VALLEY 1, PARANAQUE | PARAÑAQUE CITY | PARAÑAQUE | 0 | 0 | C2 | FCOMP | Ian Patrick Perez | 68.72 | 68.72 | 81 | NEW | 500165.57 | 0 | 0 | #DIV/0! | 2025-07-03 16:08 | 2025-07-08 14:13 | N/A | 0 | 2025-07-14 08:05
Y | BIZ | X25062122012 | DISEGNO DI MILANO INC. | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 68.36 | 68.36 | 298 | NEW | 855093.42 | 0 | 0 | #DIV/0! | 2025-07-17 | 2025-07-21 15:05 | 2025-08-05 | 2025-07-31 | 2025-07-31
Y | BIZ | X25072495380 | DISEGNO DI MILANO INC. DOING BUSINESS UNDER THE NA | WEST SERVICE, CUPANG, MUNTINLUPA | MUNTINLUPA CITY | PARAÑAQUE | 0 | 0 | VJC | FCOMP | Jenneth Madrid | 33.8 | 33.8 | 0 | TERMINATION | 35402.55 | 0 | 0 | #DIV/0! | 2025-07-18 11:04 | 2025-07-21 15:11 | 2025-08-05 | 2025-07-31 | 2025-07-31
Y | BIZ | X25072562347 | TRISTAN ENRIQUEZ TRINIDAD | LIGAS III, LIGAS III, BACOOR | BACOOR CITY | DASMA | on process | 0 | C2 | FCOMP | Ian Patrick Perez | 11.8 | 11.8 | 33 | NEW | 184304.08 | 0 | 0 | #DIV/0! | 2025-07-23 15:31 | 2025-07-25 06:53 | N/A | 0 | 2025-08-03
Y | CBG | X23031050954 | DEPARTMENT OF SCIENCE AND TECHNOLOGY | GEN. SANTOS, UPPER BICUTAN, TAGUIG CITY | TAGUIG CITY | PARAÑAQUE | on process | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 348.26 | 504.02 | 668 | MODIFICATION | 2295683.71 | 299388.1 | 0 | 0 | 2025-07-25 08:18 | 2025-07-25 13:57 | 2025-07-30 | 0 | 2025-08-09 08:52
Y | BIZ | X25041430567 | MEGA TRIUM FOODS CORPORATION | CELESTINO, CELESTINO SUBD, BACOOR | BACOOR CITY | DASMA | on process | 0 | CHALLENGER | FCOMP | Isan Carlo Lazaro | 165.83 | 186.11 | 276 | NEW | 1109918.06 | 142509.27 | 0 | 0 | 2025-07-24 14:55 | 2025-07-30 07:43 | 2025-08-05 | 0 | 2025-08-09 08:56
Note on Z1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: #N/A appears if not updated in the other source file

## AGEING
as of | 2025-07-18 | <- reference: as of CJ1 cell |  |  | PER SUPERVISOR |  | RRG |  |  |  | IGL |  |  |  | JMM
BASED ON PCA TYPE |  |  |  |  | and ASSIGNED CREW |  | AVECO |  | ECOM |  | CHALLENGER |  | POWERHOUSE |  | VJC |  | C2 |  | MAINTENANCE |  | STA. ROSA |  | TOTAL
REV |  | WO COUNT | MNHRS |  | REV |  | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS
| 0-3 MONTHS | 71 | 9415.5777 |  |  | 0-3 MONTHS | 18 | 3497.1396 | 12 | 1399.2366 | 6 | 789.0643 | 18 | 1453.5541 | 14 | 2224.2431 | 0 | 0 | 2 | 39.07 | 0 | 0 | 70 | 9402.3077
| 4-6 MONTHS | 22 | 3469.8942 |  |  | 4-6 MONTHS | 7 | 905.3816 | 5 | 1324.2761 | 2 | 51.1632 | 4 | 763.0377 | 3 | 349.6756 | 1 | 76.36 | 0 | 0 | 0 | 0 | 22 | 3469.8942
| 7-9 MONTHS | 11 | 2665.8152 |  |  | 7-9 MONTHS | 0 | 0 | 3 | 929.0793 | 2 | 378.6753 | 1 | 134.781 | 2 | 273.7139 | 0 | 0 | 0 | 0 | 3 | 949.5657 | 11 | 2665.8152
| 10 MONTHS AND ABOVE | 10 | 1424.9957 |  |  | 10 MONTHS AND ABOVE | 4 | 617.7634 | 3 | 488.3215 | 1 | 58.3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 260.5433 | 10 | 1424.9957
|  | 114 | 16976.2827 |  |  |  | 29 | 5020.2846 | 23 | 4140.9135 | 11 | 1277.2703 | 23 | 2351.3728 | 19 | 2847.6326 | 1 | 76.36 | 2 | 39.07 | 5 | 1210.109 | 113 | 16963.0127
NON-REV |  | WO COUNT | MNHRS |  | NON-REV |  | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS | WO COUNT | MNHRS
| 0-3 MONTHS | 40 | 3635.5243 |  |  | 0-3 MONTHS | 6 | 331.71 | 14 | 1299.2794 | 8 | 743.64 | 7 | 835.0505 | 5 | 835.0505 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 4044.7304
| 4-6 MONTHS | 25 | 2473.1155 |  |  | 4-6 MONTHS | 11 | 690.6472 | 4 | 296.9261 | 0 | 0 | 8 | 35.1895 | 1 | 35.1895 | 0 | 0 | 1 | 30.6 | 0 | 0 | 25 | 1088.5523
| 7-9 MONTHS | 17 | 1257.9634 |  |  | 7-9 MONTHS | 7 | 685.8684 | 5 | 307.8358 | 0 | 0 | 3 | 32.8803 | 1 | 32.8803 | 1 | 6.77 | 0 | 0 | 0 | 0 | 17 | 1066.2348
| 10 MONTHS AND ABOVE | 37 | 5584.9624 |  |  | 10 MONTHS AND ABOVE | 8 | 1570.0639 | 14 | 2755.6892 | 5 | 470.3986 | 4 | 340.8146 | 5 | 340.8146 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 5477.7809
|  | 119 | 12951.5656 |  |  |  | 32 | 3278.2895 | 37 | 4659.7305 | 13 | 1214.0386 | 22 | 1243.9349 | 12 | 1243.9349 | 0 | 0 | 1 | 30.6 | 0 | 0 | 117 | 11670.5284
TOTAL |  | 233 | 29927.8484 |  |  |  | 61 | 8298.574 | 60 | 8800.644 | 24 | 2491.3089 | 45 | 3595.3077 | 31 | 4091.5675 | 2 | 83.13 | 3 | 69.67 | 5 | 1210.109 | 231 | 28640.3112
2025-01-01
PER SEGMENT (COUNT) | [7 empty] | Note: 4 WOs released on 2023 are included in the Ageing count (Rev)
REV | [5 empty] | SUMMARY: PENDING OH |  | 'C1'!$D:$D,"<>MN",'C1'!$L:$L,"<>OPS"
| CBG | BIZ | HMB |  |  | CLEAN-UP AGEING WOs
0-3 MONTHS | 10 | 24 | 37
4-6 MONTHS | 5 | 2 | 15 |  |  |  | COUNT | AGEING (2024 & PRIOR) | RELEASED 2025 |  |  |  | TOTAL |  | COUNT | AGEING (2024 & PRIOR) | RELEASED 2025 |  | TOTAL
7-9 MONTHS | 4 | 0 | 7 | [5 empty] | 10 MONTHS AND ABOVE | 7-9 MONTHS | 4-6 MONTHS | 0-3 MONTHS |  |  |  |  | > 90 DAYS | 0-90 DAYS
10 MONTHS AND ABOVE | 2 | 2 | 6 |  |  |  | REVENUE | 20 | 0 | 1 | 22 | 71 | 114 |  | REVENUE | 20 | 23 | 71 | 114
| 21 | 28 | 65 |  |  |  | NON-REVENUE | 49 | 0 | 5 | 25 | 40 | 119 |  | NON-REVENUE | 49 | 30 | 40 | 119
NON-REV | [6 empty] | TOTAL | 69 | 0 | 6 | 47 | 111 | 233 |  | TOTAL | 69 | 53 | 111 | 233
| CBG | BIZ | HMB
0-3 MONTHS | 2 | 10 | 28 |  |  |  | MHRS | AGEING (2024 & PRIOR) | RELEASED 2025 |  |  |  | TOTAL |  | MHRS | AGEING (2024 & PRIOR) | RELEASED 2025 |  | TOTAL
4-6 MONTHS | 3 | 5 | 17 | [5 empty] | 10 MONTHS AND ABOVE | 7-9 MONTHS | 4-6 MONTHS | 0-3 MONTHS |  |  |  |  | > 90 DAYS | 0-90 DAYS
7-9 MONTHS | 3 | 3 | 11 |  |  |  | REVENUE | 3943.0523 | 0 | 147.7586 | 3469.8942 | 9415.5777 | 16976.2827 |  | REVENUE | 3943.0523 | 3617.6528 | 9415.5777 | 16976.2827
10 MONTHS AND ABOVE | 4 | 2 | 29 |  |  |  | NON-REVENUE | 6620.9111 | 0 | 222.0147 | 2473.1155 | 3635.5243 | 12951.5656 |  | NON-REVENUE | 6620.9111 | 2695.1302 | 3635.5243 | 12951.5656
| 12 | 20 | 85 |  |  |  | TOTAL | 10563.9634 | 0 | 369.7733 | 5943.0097 | 13051.102 | 29927.8484 |  | TOTAL | 10563.9634 | 6312.783 | 13051.102 | 29927.8484
TOTAL | 33 | 48 | 150
PER SEGMENT (MHRS)
REV | [5 empty] | SUMMARY: PENDING UG
| CBG | BIZ | HMB |  |  |  | COUNT | AGEING (2024 & PRIOR) | RELEASED 2025 |  |  |  | TOTAL
0-3 MONTHS | 895.1899 | 3190.8676 | 5329.5202 | [5 empty] | 10 MONTHS AND ABOVE | 7-9 MONTHS | 4-6 MONTHS | 0-3 MONTHS
4-6 MONTHS | 442.0081 | 78.09 | 2949.7961 |  |  |  | REVENUE | 0 | 0 | 0 | 0 | 0 | 0
7-9 MONTHS | 657.0781 | 0 | 2008.7371 |  |  |  | NON-REVENUE | 2 | 0 | 0 | 0 | 0 | 2
10 MONTHS AND ABOVE | 225.3582 | 132.536 | 1067.1015 |  |  |  | TOTAL | 2 | 0 | 0 | 0 | 0 | 2
| 2219.6343 | 3401.4936 | 11355.1548
NON-REV | [6 empty] | MHRS | AGEING (2024 & PRIOR) | RELEASED 2025 |  |  |  | TOTAL
| CBG | BIZ | HMB | [5 empty] | 10 MONTHS AND ABOVE | 7-9 MONTHS | 4-6 MONTHS | 0-3 MONTHS
0-3 MONTHS | 267.04 | 466.8794 | 2901.6049 |  |  |  | REVENUE | 0 | 0 | 0 | 0 | 0 | 0
4-6 MONTHS | 371.8948 | 282.744 | 1818.4767 |  |  |  | NON-REVENUE | 299.23 | 0 | 0 | 0 | 0 | 299.23
7-9 MONTHS | 256.1858 | 45.47 | 956.3076 |  |  |  | TOTAL | 299.23 | 0 | 0 | 0 | 0 | 299.23
10 MONTHS AND ABOVE | 1229.3103 | 209.7726 | 2294.9351
| 2124.4309 | 1004.866 | 7971.3243
TOTAL | 4344.0652 | 4406.3596 | 19326.4792
| 2021-01-01 | 2022-01-01
| 2023-01-01 | 2024-01-01 | 2025-01-01
| >=& | <&
YTD ENERGIZED | 359
CARRY-OVER from 2024 | 112 | -12 [PENDING FOR CANCELLATION] = 96
WMTRL this year | 386 | baseline ä _
Carry-over includes PCAN & PCAN3
REV + NON-REV | 2021 | 2022 | 2023 | 2024 | 2025 | TOTAL
CAN | 2 | 1 | 0 | 2 | 0 | 5
CLOSED-CAN | 1 | 0 | 0 | 13 | 0 | 14
COMP-CAN | 0 | 0 | 0 | 0 | 1 | 1
PCAN | 1 | 1 | 1 | 1 | 2 | 6
PCAN3 | 2 | 1 | 5 | 3 | 0 | 11
COMPLETION OF PENDING FOR CANCELLATION |  | 55.88%
REV ONLY | 2021 | 2022 | 2023 | 2024 | 2025 | TOTAL
CAN | 0 | 0 | 0 | 2 | 0 | 2
CLOSED-CAN | 0 | 0 | 0 | 12 | 0 | 12
COMP-CAN | 0 | 0 | 0 | 0 | 0 | 0
PCAN | 0 | 0 | 0 | 1 | 0 | 1
PCAN3 | 0 | 0 | 5 | 2 | 0 | 7
COMPLETION OF PENDING FOR CANCELLATION |  | 82.35%

## VENDOR PRODUCTIVITY
| 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01
| 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
CONTRACTOR | YTD ACCOMPLISHMENT | YTD CAPABILITY | JULY ACCOMPLISHMENT | JUNE CAPABILITY | CAPABILITY (BASED ON DECLARED T.O) | % ACTUAL CAP | % PRODUCTIVITY (JUNE) | % TOTAL PRODUCTIVITY
AVECO | 10028.3207 | 17761.2131 | 776.1279 | 301.8414 | 2850.0959 | 10.59% | 257.1% | 56.46%
CHALLENGER | 12090.241 | 16703.0237 | 1985.441 | 465.2092 | 2394.0806 | 19.43% | 426.8% | 72.38% | 11 | < current day of the month when checking monthly capability
ECOM | 6310.888 | 14966.6575 | 373.921 | 441.871 | 2394.0806 | 18.46% | 84.62% | 42.17%
POWERHOUSE | 6606.5308 | 15831.9174 | 598.5838 | 329.8473 | 2394.0806 | 13.78% | 181.5% | 41.73%
VJC | 9849.2646 | 14101.3976 | 1438.5125 | 455.8739 | 1938.0652 | 23.52% | 315.6% | 69.85%
TOTAL | 44885.2452 | 79364.2094 | 5172.5862 | 1994.6428 | 11970.4029 | 16.66% | 259.3% | 56.56%
as of July 11
MONTHLY ACCOMPLISHMENT
CONTRACTOR | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL ACCOMPLISHMENT
AVECO | JAN: 2672.9692; FEB: 905.1005; MAR: 919.9805; APR: 2151.1123; MAY: 1958.5569; JUN: 644.4734; JUL: 776.1279 | 10028.3207
CHALLENGER | JAN: 956.8503; FEB: 2956.0097; MAR: 1840.0379; APR: 765.767; MAY: 2319.5445; JUN: 1266.5906; JUL: 1985.441 | 12090.241
ECOM | JAN: 1268.1719; FEB: 603.6743; MAR: 1357.4366; APR: 1361.4626; MAY: 331.8655; JUN: 1014.3561; JUL: 373.921 | 6310.888
POWERHOUSE | JAN: 1488.6252; FEB: 648.8167; MAR: 2110.1769; APR: 388.5596; MAY: 1213.7617; JUN: 158.0069; JUL: 598.5838 | 6606.5308
VJC | JAN: 1621.0814; FEB: 1845.4007; MAR: 1171.6608; APR: 983.0122; MAY: 1443.0291; JUN: 1346.5679; JUL: 1438.5125 | 9849.2646
C2 | JAN: 28.61; FEB: 66.92; MAR: 77.35; APR: 0; MAY: 0; JUN: 115.28; JUL: 241.92
MAINTENANCE | JAN: 22.41; FEB: 20.14; MAR: 49.04; APR: 20.78; MAY: 13.95; JUN: 299.838; JUL: 710.1
STA. ROSA | JAN: 0; FEB: 0; MAR: 0; APR: 0; MAY: 269.6164; JUN: 222.7607; JUL: 0
TOTAL | JAN: 8058.718; FEB: 7046.062; MAR: 7525.6827; APR: 5670.6937; MAY: 7550.3241; JUN: 5067.8736; JUL: 6124.6062 | 44885.2452
MONTHLY CAPABILITY | JAN: based on declared crew complement; MAY: May 22-30 based on actual sign on count; JUN: based on actual sign on count; JUL: based on actual sign on count
CONTRACTOR | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
AVECO | 2850.0959 | 2850.0959 | 2850.0959 | 2850.0959 | 2630.8578 | 850.644 | 1289.1203 | 1590.2074
CHALLENGER | 2394.0806 | 2394.0806 | 2394.0806 | 2394.0806 | 2468.6215 | 1311.0441 | 1565.3604 | 1781.6753
ECOM | 2394.0806 | 2394.0806 | 2394.0806 | 1938.0652 | 2284.4615 | 1245.2727 | 855.0288 | 1461.5876
POWERHOUSE | 2394.0806 | 2394.0806 | 2394.0806 | 2394.0806 | 2008.2214 | 929.5697 | 1753.9052 | 1563.8988
VJC | 1938.0652 | 1938.0652 | 1938.0652 | 1938.0652 | 1723.2118 | 1284.7355 | 1753.9052 | 1587.2842
TOTAL | 11970.4029 | 11970.4029 | 11970.4029 | 11514.3875 | 11115.3741 | 5621.2661 | 7217.3198 | 7984.6533
MONTHLY PRODUCTIVITY
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
| 67.32% | 58.86% | 62.87% | 49.25% | 67.93% | 90.16%
for monthly updating | FEB: shared with C2
JANUARY | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane
AVECO | JAN: 3; FEB: 1; MAR: 1; APR: 1; MAY: 25; JUN: 2850.0959
CHALLENGER | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
ECOM | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
POWERHOUSE | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
VJC | JAN: 2; FEB: 1; APR: 1; MAY: 17; JUN: 1938.0652
TOTAL | JAN: 11; FEB: 5; MAR: 4; APR: 5; MAY: 105; JUN: 11970.4029
FEBRUARY | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane
AVECO | JAN: 3; FEB: 1; MAR: 1; APR: 1; MAY: 25; JUN: 2850.0959
CHALLENGER | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
ECOM | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
POWERHOUSE | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
VJC | JAN: 2; FEB: 1; APR: 1; MAY: 17; JUN: 1938.0652
TOTAL | JAN: 11; FEB: 5; MAR: 4; APR: 5; MAY: 105; JUN: 11970.4029
REFERENCE FOR VC MEETINGS
MARCH | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability; OCT: MARCH; NOV: Count of Crew |  |  | Effective Personnel Count | Effective Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane; OCT: CONTRACTOR; NOV: Basket; DEC: Stake | Trucco | Crane
AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959 |  |  |  | AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959
CHALLENGER | 2 | 1 | 1 | 1 | 21 | 2394.0806 |  |  |  | CHALLENGER | 4 | 1 | 1 | 1 | 29 | 3306.1113
ECOM | 2 | 1 | 1 | 1 | 21 | 2394.0806 |  |  |  | ECOM | 2 | 1 | 1 | 1 | 21 | 2394.0806
POWERHOUSE | 2 | 1 | 1 | 1 | 21 | 2394.0806 |  |  |  | POWERHOUSE | 4 | 1 | 1 | 1 | 29 | 3306.1113
VJC | 2 | 1 |  | 1 | 17 | 1938.0652 |  |  |  | VJC | 2 | 1 | 0 | 0 | 14 | 1596.0537
TOTAL | 11 | 5 | 4 | 5 | 105 | 11970.4029 |  |  |  | TOTAL | 15 | 5 | 4 | 5 | 118 | 13452.4527
APRIL | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability; OCT: APRIL; NOV: Count of Crew |  |  | Effective Personnel Count | Effective Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane; OCT: CONTRACTOR; NOV: Basket; DEC: Stake | Trucco | Crane
AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959 |  |  |  | AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959
CHALLENGER | 2 | 1 | 1 | 1 | 21 | 2394.0806 |  |  |  | CHALLENGER | 4 | 1 | 1 | 1 | 29 | 3306.1113
ECOM | 1 | 1 | 1 | 1 | 17 | 1938.0652 |  |  |  | ECOM | 1 | 1 | 1 | 1 | 17 | 1938.0652
POWERHOUSE | 2 | 1 | 1 | 1 | 21 | 2394.0806 |  |  |  | POWERHOUSE | 4 | 1 | 1 | 1 | 29 | 3306.1113
VJC | 2 | 1 |  | 1 | 17 | 1938.0652 |  |  |  | VJC | 2 | 1 | 0 | 0 | 14 | 1596.0537
TOTAL | 10 | 5 | 4 | 5 | 101 | 11514.3875 |  |  |  | TOTAL | 15 | 5 | 4 | 5 | 114 | 12996.4374
MAY | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability; JUL: Actual Monthly Capability; OCT: MAY; NOV: Count of Crew |  |  | Effective Personnel Count | Effective Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane; OCT: CONTRACTOR; NOV: Basket; DEC: Stake | Trucco | Crane
AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959 | 2630.8578 |  |  | AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959
CHALLENGER | 2 | 1 | 1 | 1 | 21 | 2394.0806 | 2468.6215 |  |  | CHALLENGER | 4 | 1 | 1 | 1 | 29 | 3306.1113
ECOM | 2 | 1 | 1 | 1 | 21 | 2394.0806 | 2284.4615 |  |  | ECOM | 2 | 1 | 1 | 1 | 21 | 2394.0806
POWERHOUSE | 2 | 1 | 1 | 1 | 21 | 2394.0806 | 2008.2214 |  |  | POWERHOUSE | 4 | 1 | 1 | 1 | 29 | 3306.1113
VJC | 2 | 1 |  | 1 | 17 | 1938.0652 | 1723.2118 |  |  | VJC | 2 | 1 | 0 | 0 | 14 | 1596.0537
TOTAL | 11 | 5 | 4 | 5 | 105 | 11970.4029 | 11115.3741 |  |  | TOTAL | 15 | 5 | 4 | 5 | 118 | 13452.4527
92.86%
JUNE | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability; JUL: Actual Monthly Capability; OCT: JUNE; NOV: Count of Crew |  |  | Effective Personnel Count | Effective Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane; OCT: CONTRACTOR; NOV: Basket; DEC: Stake | Trucco | Crane
AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959 | 850.644 |  |  | AVECO | 3 | 1 | 1 | 1 | 25 | 2850.0959
CHALLENGER | 2 | 1 | 1 | 1 | 21 | 2394.0806 | 1372.4308 |  |  | CHALLENGER | 4 | 1 | 1 | 1 | 29 | 3306.1113
ECOM | 2 | 1 | 1 | 1 | 21 | 2394.0806 | 1319.8136 |  |  | ECOM | 2 | 1 | 1 | 1 | 21 | 2394.0806
POWERHOUSE | 2 | 1 | 1 | 1 | 21 | 2394.0806 | 1021.6498 |  |  | POWERHOUSE | 4 | 1 | 1 | 1 | 29 | 3306.1113
VJC | 2 | 1 |  | 1 | 17 | 1938.0652 | 1302.2746 |  |  | VJC | 2 | 1 | 0 | 0 | 14 | 1596.0537
MN | 4 | 1 |  |  | 22 | 2508.0844 | 59.626 |  |  | TOTAL | 15 | 5 | 4 | 5 | 118 | 13452.4527
C2 | JAN: 1; MAY: 4; JUN: 456.0153; JUL: 1582.903
TOTAL | JAN: 16; FEB: 6; MAR: 4; APR: 5; MAY: 127; JUN: 14478.4873; JUL: 7509.3418
51.87%
JULY | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability; JUL: Actual Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane
AVECO | JAN: 3; FEB: 1; MAR: 1; APR: 1; MAY: 25; JUN: 2850.0959; JUL: 1289.1203
CHALLENGER | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806; JUL: 1565.3604
ECOM | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806; JUL: 855.0288
POWERHOUSE | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806; JUL: 1753.9052
VJC | JAN: 2; FEB: 1; APR: 1; MAY: 17; JUN: 1938.0652; JUL: 1753.9052
MN | JAN: 4; FEB: 1; MAY: 22; JUN: 2508.0844; JUL: 710.1
C2 | JAN: 1; MAY: 4; JUN: 456.0153; JUL: 241.92
TOTAL | JAN: 16; FEB: 6; MAR: 4; APR: 5; MAY: 127; JUN: 14478.4873; JUL: 8169.3398
56.42%
AUGUST | JAN: Count of Crew; MAY: Effective Personnel Count; JUN: Effective Monthly Capability; JUL: Actual Monthly Capability
CONTRACTOR | JAN: Basket; FEB: Stake; MAR: Trucco; APR: Crane
AVECO | JAN: 3; FEB: 1; MAR: 1; APR: 1; MAY: 25; JUN: 2850.0959
CHALLENGER | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
ECOM | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
POWERHOUSE | JAN: 2; FEB: 1; MAR: 1; APR: 1; MAY: 21; JUN: 2394.0806
VJC | JAN: 2; FEB: 1; APR: 1; MAY: 17; JUN: 1938.0652
MN | JAN: 4; FEB: 1; MAY: 22; JUN: 2508.0844
C2 | JAN: 1; MAY: 4; JUN: 456.0153
TOTAL | JAN: 16; FEB: 6; MAR: 4; APR: 5; MAY: 127; JUN: 14478.4873
0%