## Parañaque
Billing Process
Process Flow Chart | Description | Responsible | Accountable | Support | Consulted | Informed
| Vendor route Work Order to FCOMP status Node D - Completed C2 ECP-SR WOs with partial billing | Vendor Coordinator | Vendor Team Leader | Vendor Clerk | Vendor Owner | Implem Team
| Vendor performs Quality Inspection. | Vendor QI | Vendor Team Leader | Vendor Clerk | Vendor Owner | Implem Team
| Vendor Coordinator prepare all required documents and submits them. 1. COC* 2. As Built Sketch 3. As Built Form 4. Vendor QI Checklist 5. STF 6. Before and After Pictures* 7. Work Order/Location Specifications 8. FALLAWMA Checklist *C2 requirements for partial billing of ECP-SR projects (refer to page 3) | Vendor Coordinator | Vendor Team Leader | Vendor Clerk | Vendor Owner | Implem Team
| Clerks reviews submittal—are all docs complete and acceptable? | Clerks | WO Supervisor | Vendor Coordinator | Team Leader | Implem Team
| Does the vendor require SI modification? If Yes, Vendor shall submit Modification Request Form If No, proceed to next step | Vendor | Vendor Owner | Vendor Coordinator | Team Leader | Implem Team
| WO Supervisor reviews and approves SI modification request then encode it to EAM | WO Supervisor | Team Leader | Clerks | Sector Head | Implem Team
| WO Supervisor tags modified SI as “COMP” Is WO Energized? Not Energized - e.g. Installation, retirement, or relocation of guy wire Energized - e.g. Extension of facilities, installation of DT If yes, proceed to partial billing If No, proceed to QI | WO Supervisor | Team Leader | Clerks | Sector Head | Implem Team
| WO Supervisor conducts table audit and inspect the SI quantities and accuracy for billing. | WO Supervisor | Team Leader | Clerks | Sector Head | Implem Team
| An audit (table or field) is performed to double check the quality of field work. | Quality Inspector | Team Leader | Engineering Aide | Sector Head | Implem Team
| Does the audit pass? If No → node A (Rework path) If Yes → Check Material Variance | Quality Inspector | Team Leader | Engineering Aide | Sector Head | Implem Team
| Audit Team flags any over‐ or under‐consumption of materials. | Quality Inspector | Team Leader | Engineering Aide | Sector Head | Implem Team
| Was material usage exactly as prescribed? If No → node C (NTC path) If Yes → Inspect SI for Billing | Quality Inspector | Team Leader | Engineering Aide | Sector Head | Implem Team
| WO Supervisor inspect the SI quantities and accuracy for billing. | WO Supervisor | Team Leader | Clerks | Sector Head | Implem Team
| Clerk sends the certificate of acceptance and email to notify the Vendor. | Clerks | WO Supervisor | Engineering Aide | Team Leader | Implem Team
Process Flow Chart | Description | Responsible | Accountable | Support | Consulted | Informed
| QI tags the SI as needing rework. | Quality Inspector | WO Supervisor | Engineering Aide | Team Leader | Implem Team
| Vendor Coordinator notifies their crew lead that rework is required | Vendor Coordinator | Vendor Team Leader | Vendor Clerk | Vendor Owner | Implem Team
| Vendor Crew executes rework. | Vendor Crew | Vendor Crew Lead | Vendor Coordinator | Vendor Team Leader | Implem Team
| WO Supervisor checks if Vendor met the SLA for turnaround on rework. if Yes → node B (Conduct QI) If No → WO Supervisor issues a Notice to Contractor (NTC) for material variance or late rework. | WO Supervisor | Team Leader | Engineering Aide | Sector Head | Implem Team
| Does the Contractor respond to the NTC within the contractual timeframe? if Yes → Acknowledge Reply If No → Send NOV to Contractor | WO Supervisor | Team Leader | Engineering Aide | Sector Head | Implem Team
| WO Supervisor logs the reply and confirms acceptance | WO Supervisor | Team Leader | Engineering Aide | Sector Head | Implem Team
| WO Supervisor tallies days beyond SLA for reporting and possible debit. | WO Supervisor | Team Leader | Engineering Aide | Sector Head | Implem Team
| Did the Contractor finish remediation before the NOV cutoff? If No → Send NOV to Contractor If Yes → node B (Conduct QI) | WO Supervisor | Team Leader | Engineering Aide | Sector Head | Implem Team
| WO Supervisor issues a debit memo to recover costs for non‑compliance. | WO Supervisor | Team Leader | Engineering Aide | Sector Head | Implem Team
Process Flow Chart | Description | Responsible | Accountable | Support | Consulted | Informed
| Vendor tags completed services in EAM for ECP-SR projects only | Vendor Coordinator | Vendor Team Leader | Vendor Clerk | Vendor Owner | C2 Team
| Vendor Coordinator prepare all required documents and submits them. 1. Partial COC with modification form (if any) 2. Before and After Pictures | Vendor Coordinator | Vendor Team Leader | Vendor Clerk | Vendor Owner | C2 Team
| Clerks reviews submittal—are all docs complete and acceptable? | Clerks | WO Supervisor | Vendor Coordinator | Team Leader | C2 Team
| Does the vendor require SI modification? If Yes, Vendor shall submit Modification Request Form If No, proceed to next step | Vendor | Vendor Owner | Vendor Coordinator | Team Leader | C2 Team
| WO Supervisor reviews and approves SI modification request then encode it to EAM | WO Supervisor | Team Leader | Clerks | Sector Head | C2 Team
| WO Supervisor tags modified SI as “COMP” Scope of work includes HDE and pole dressing. | WO Supervisor | Team Leader | Clerks | Sector Head | C2 Team
| WO Supervisor conducts table audit and inspect the SI quantities and accuracy for billing. | WO Supervisor | Team Leader | Clerks | Sector Head | C2 Team
START
Actual Field Completion
Perform Vendor QI
Modify SI?
Tag SI Complete
Complete Requirements & Submit COC
Requirements Complete?
Conduct Table Audit or Field Audit
QI Ok?
Check Material Variance
Inspect SI for Billing
End
Submit Modification Form to Supervisor
Encode Modificaion in EAM
Tag SI as Rework
A
Confirm to Vendor
Perform Rework
Done within __ days?
B
Send NTC to Contractor
Contractor Reply within 5 days?
Acknowledge Receipt of Reply
Count Day/s of Delay until Completed
Send NOV to Contractor
Proceed to Debit Memo
Done within __ days?
B
A
End
Yes
No
Yes
No
Yes
Yes
No
Without Variance?
C
No
Yes
Notify Vendor
B
Inspect SI for Partial Billing
Is WO Energized?
Yes
No
No
Yes
Yes
No
No
Page 2
Page 1
Page 3
COMP SI
Modify SI?
Tag SI Complete
Complete Requirements & Submit Partial COC
Requirements Complete?
Submit Modification Form to Supervisor
Encode Modification in EAM
Yes
No
Yes
No
D
Inspect SI for Partial Billing
D